## PM&Sales
Category | Issue | owner | status | due date | Progress
PM | DVT3 sample qty for ALT/SKB | ALT | close | 2021-03-15 | [Fii] Nominally ALT has 176pcs left for DVT3 (320-36-108) but will need to calculate the actual qty left with increased BOM cost after design change. [Fii 0317] If the qty is not informed by 3/18 the schedule will be delayed for another week because the factoy load the demand once a week. [ALT] Will provide on 3/17
PM | R&R discussion | Fii/ALT | close | 3/23=>3/26=>4/9 | [Fii] Fii will update the R&R list and ALT needs to check if additional items needed. [ALT 0319] Will provide the detailed items about HW development for discussion. [Fii 0326] Fii will review and reply by 3/29 [ALT 0329] We add some feedback on your comment in "AMP Board R&R" Tab. [ALT 0401] R&R for AMP board PCB artwork for MP still needs to be discussed. [Fii 0408] Fii willdo the EMC test and provide the solutions for EMC issue. [ALT 0408] MP artwork will be owned by ALT.
Sales | pre-MP+MP PO for 1K | ALT | close | 3/26=>4/8 | [Fii] will evaluate the BOM bassed on final ME design by 3/19 first. The final PO should be provided by 3/26. [Fii 0319] Before 3/24 Fii will evaluate the BOM cost based on the design as of 3/19. If there are design changes after then the price will be updated again. Also the E&O will be handled by ALT. [Fii 0325] ALT needs to provide the UP for amplifier [ALT 0326] will provide it today for Fii to update the quote. [Fii 0401] Will provide the quotation within this week. [Fii 0412] Those LT greater than 90 days are not prepared. Need ALT to provide the PO ASAP to lead the demand based on current design.
Sales | E&O amount for DVT and 1K (pre MP+MP) after design change | Fii/ALT | pending | 4/7=>4/29=>8/31 | [Fii 0901] Fii will summarize all E&O once BOM fix. [Fii 0826] ALT consigned P/N for TMI3252S will be ready on 8/26.=> Released on 8/27. [ALT 0825] AMP design: HW is final. But there are 4pcs 1K resistance that need Fii to issue ECR to remove. [Fii 0823]Need ALT to confirm a) whether AMP design is final b) whether ALT will consign TMI3252S in further (close) ALT commented that TMI3252S will be consigned part in forther on 8/23 meeting. [Fii 0504] BOM is not finalized yet. [Fii 0415] ALT updated BOM again on 4/13 and the EC process is still ongoing. [Fii 0409] Will provide the 1st version but will update again before MP due to possible design change after the verification of DVT3. [Fii 0325] HW Tom will isse EC by 3/26 and the list will be updated later. [ALT] Final ME Design will be derivered by 3/19. We can deliver Speaker cable data by 3/19 Speaker data will be ready by 4/9 [Fii] Will evaluate when receiving the final ME drawing together with HW design
PM | Fii will scrap all the ALT provided parts such as hosuing sub-assembly, speakers and speaker cables after DVT2 | Fii | close | 2021-04-09 | [ALT 0317] Fii provide the list for ALT to review first. [Fii 0325] List provided to ALT [Fii 0326] Received the reply from ALT and will scrap based on the confirmation column.
PM | DVT3 material preparation | Fii/ALT | open | 4/29=>5/19 | [Fii 0520] to check SD report [ALT 0513] reworked housing and speaker cable ETA TBC by ALT [ALT 0512] 5/13 ETA Fii factory by ALT/Inkel [ALT 0511] Inkel to reowork housing, target to be finished on 5/12. [Fii 0510] Housing sample can't perfect match, under checking by ALT SH when receiving. [Fii 0428] The most gating is Inkel housing. Fii controlled parts will be ready by 5/4. [ALT 0423] Inkel finished T0 tooling. DVT3 ETD 4/28. SOP should be provided no later than 4/27 to keep the DVT3 schedule. [Fii 0420] The shortage will be updated on 4/21.=>4/26 [Fii 0416] Plz prepare the documents needed for ECAP PN application. Need the PO for DVT3 ASAP. The schedule will be delayed if not provided by 4/19. [ALT 0413] We will send AMP and ECAP by this Friday. We are checking on Mechanical part delivery schedule. We will inform Mechanical part delivery schedule when we get feedback from INKEL. [Fii 0412] Need check ALT provided parts schedule. Need amplifier & ECAP ETA factory 4/21. ME parts & speaker sets ETA factory 4/23. [Fii 0409] Fii QVL don't have stock ready for ECAP with spec requested by ALT and need ALT to check the originally designated vendor for DVT3 sample build demand. Fii will change to QVL part for MP. Mantis #0001143~0006640 [Fii 0406] Need the PO to place the order for extra parts from the design change for DVT3 ASAP. [ALT 0401] Already talked to AML Korea BD and got the reply in need of PO. [ALT 0326] ALT talked to AML and will check with AML BD for the preparation of A113X. [Fii 0324] Fii will prepare materials for AMP board for DVT3 and MP based on ALT provided BOM on 3/19 on Mantis 1143. The 1st EC will be released by 3/26 by HW Tom. [Fii 0319] -A113X was kicked off by ALT with AML and ALT has the power to push AML BD Demian to book MP 1K demand. Fii will place the order to AML when receiving the PO from ALT later. -ALT helps to check the Wellang amplifier LT and start the preparation of DVT3 first. [Fii 0317] -A113X LT*32WK. Will need ALT to have AML Demian book the materials for DVT3 and MP. Fii will also check with vendor. [Fii] Fii will finalize the AMP BOM for production and place order for DVT3 by 3/17.(Sean)
PM | New speaker sets data sheet for application of new PNs | ALT | close | 4/7=>4/13 | [ALT 0401] will reply by 4/5 if the data sheet could be released as planned. [Fii 0406] Need apply for PN immediately. Plz provide it no later than 4/12. [Fii 0412] Got the data sheet for cables. Need the speaker's ASAP. [ALT 0413] Dreamus answered that they will send their datasheet by tomorrow morning.
PM | Philips business trip visa documents | Fii-Dennis | close | 2021/4/12=>4/28 | [Fii 0325] 1. 外國法人指派文件Travel Order_ALT_revised更新上傳法務系統。(3/24,done) 2. 待孫律師核簽 (3/25,done) [0326] 1. 用印簽核。(3/29,done)=> 目前核簽到鄭總 2. 3/25 和人事怡廷及Call Philips 查詢, 簽證申請以韓國辦事處規定為準 , 簽證需有邀請函及工作許可才核發簽證。 [0330] 1. 3/29送虎躍廠用印。 2. 3/30 文件送勞動部開案審查。 [0331] 已送勞動局 , 編號: 1100565962 ( 勞動局回覆,申請需要12個工作天) [0401] 1. 詢問勞動局加急需求 ,勞動局回覆,目前沒有這項申請管道,也沒有加費用申請加急的作法。 2. 可到網站:http://www.wda.gov.tw , 查詢申請進度,已經提供 ALT Philip 了解目前進度及查詢訊息。 [0406-0408] 查詢勞動局網站:http://www.wda.gov.tw , 進度為審查中。 [0409] 所附的合約是新加坡的公司和韓國ALT Co,.Ltd兩家外國公司簽約，不符合規定。需要補件。 note : 需提供買賣訂單或合約 , 是新加坡公司台灣分公司和 ALT 之間有關的文件。 [0412] ALT 提供訂單 , 先用原用印申請單,將ALT 訂單送虎躍廠用印。 [0415] 1. ALT 訂單用印已重新送勞動局審核,依辦理周小姐回覆依3/31收件, 4/1開始計算12個工作天為 (4/20完成) 。 note : 1. 4/20 勞動局核可後會將公文郵寄出 , 4/23可收到公文。 2. ALT 再依公文申請簽證,韓國台灣辦事處回覆需5個工作天 , 預計4/28完成。 [0421] 1. 4/16 下午收到勞動局核可公文 , 4/17郵寄到韓國。 2. 4/21 Tracking number : EE940708313TW , ALT Philips 已經收到文件。 [防疫規定 : 人事周怡廷 ) 1. 依據國內防疫規定 , 客戶來台之後 => 先隔離 14天 => 再自主健康管理 7天 2. 鴻海公司內部規定 , 再自主健康管理 7天期間 , 如果要進公司開會...等等 , 需持有核酸檢驗核格報告才可到公司。 3. 完成自主健康管理 7天者 , 鴻海公司內部規定不需提供核酸檢驗核格報告。
PM | Wellang AMP designation letter & vendor contact to register vendor code and PN =>changed to B&S | ALT | close | 2021-06-30 | [Fii 0507] ALT request change to be consign. [Fii 0428] Sales Tiffanie is checking with ALT the buy and sell part list. [Fii 0326] Vendor code registration is in process and expected to complete by end of June. Will notify ALT once the process is done and before then will need ALT to support buy and sell. [Fii 0325] Documents are submitted in the system for DVT3 PN application and will finish by 4/9. [Fii 0317] Need to apply for PN with B&S mode and direct trading mode at the same time. Need ALT to provide the needed documents and reply email.
PM | AMP eMMC 4G changed to NAND flash | ALT/Fii | close | 2021-04-07 | [ALT 0402] Could you check NAND Flash that Mr. Lonnie KIM informed in e-mail ? [Fii 0406] Fii buyer is checking the supply and will reply by 4/7 [Fii 0409] Will change to NAND flash starting from DVT3.
PM | Package final artwork for MP version | ALT | close | 2021/6/22 =>8/10 | [ALT 0810] Energy label : ALT checked and there is no issue, so please proceeds with MP. [Fii 0802] energy efficiency label sample built ( due date : 8/10) [ALT 0729] I'm sending the final artwork of the energy efficiency label for SWAN. Please share the schedule of the sample photo. [Fii 0728] The printing provide by 7/27. [Fii 0721] Label L/T 20 day , sample bulit L/T 10 day , artwork due date : 7/22. [Fii 0719] The printing will be confirmed on the 7/15->7/27 of the Giftbox production. [Fii 0621] Suppliers are unwilling to do giftbox new printing, so purchase assistance helps. (A total of seven samples have been made so far) [Fii 0617] 1. new QSG sample ETD 6/19. (new vender) 2. Please take a picture of giftbox sample badly logo printed. In addition,a good logo printing sample picture, will be provided for vender evaluation and comparison. 3. The ALT confirms EPE on 6/8. [Fii 0603] (1) QSG new sample ETD 6/4 (2) Vendor will print again gift box to check printing quality (3) EPE foam sample ETD 6/4.(4) KC label artwork to be provided. [Fii 0601] (1) wrong QSG sample with previous artwork, vendor is remaking right now, sample ETD by 6/4 (2) Gift box sample has printing quality issue, ALT/SKB has conditional approval for this sample (3) EPE Foam can't fit into gift box perfectly. [Fii 0520] ALT provide artwork of giftbox and QSG, but artwork of KC label to be confirmed. [Fii 0514] ALT request to update artwork again, sample preparation is stopped and pending now. [Fii 0513] to provide sample by 5/31 for ALT's approval [ALT 0511] To keep current artowrk to meet schedule [ALT0507] ALT to update artwork [Fii 0428] The vendor agreed to ship out 5pcs to Korea(shipped on 4/27) and need ALT to advise FEDEX account for the rest samples. [Fii 0423] The vendor feedback they can support samples but the delivery cost needs to be born by customer. Plz advise [Fii 0412] sample ETD no later than 4/23. [Fii 0409] Need to check with vendor for the sample qty and schedule by 4/13. [Fii 0406] ALT approves to use up old stock for DVT3. Need ALT to provide the updated artwork for MP version and check the sample qty.
PM | ALT advised FFC cable + bushing vendor HWASUNG | Fii | close |  | [Fii 0406] Notified the vendor to prepare the sample for verification. EMI performance is worse than P Two
PM | Sub-boards PCB hold production as ALT requested | ALT/Fii | close | 2021-04-14 | [Fii 0413] ALT notifed to hold production on 4/13 and update the gerber of AMP board. The gerber out date from Fii to PCB vendor will be on 4/14. Total delay of 5 days will impact the DVT3 build schedule. [Fii 0414] There will be cost for PCB as the old one cannot be used and need to scrap. The DVT3 start date changed to 5/3.
Sales | PO for acoustic chamber modification | ALT/Fii | close | 2021-04-16 | [Fii 0415] Will provide the breakdown list for SW within 4/15 and need the PO by 4/16 as the SW modification is still needed for DVT3. [Fii 0416] The PO should be provided by 4/19.
PM | 2nd source list to be introduced after MP | Fii | close | 2021-08-30 | [Fii 0901] RD to provide the proposal today. [Fii 0820] Since there is no difference between 24CH or 36CH (L/T:392), RD to survey whehter there is any other solution to improve L/T issue. [ALT 0505] Please confirm if Sunlord's inductor should be pass BMT [Fii 0423] The introduction process follows Eagle. [Fii 0421] Including ECAP from NICHICON
PM | LS communication inductor OPO cancel(Mantis 0001131~0006674) | ALT | close | 2021-05-07 | [Fii 0513] ALT confirm the running change plan. [Fii 0512] Fii issued PO to LS communication, Fii double confirm Sunlord's L/T, ALT confirm running change after 30K. [Fii 0511] Fii will release 30K PO to LS commnunication. [ALT 0510] Sunlord's contact window and L/T. and need to decide how many pcs to issue PO to LS communication. [ALT 0507] Will try to provide it on 5/7 [Fii 0505] IND-Sunlord Fii checks if QVL again. And Philip will help check the change reason and more information (how the IND affects the acoustic performance, FR? THD?) [Fii 0428] Plz check if will continue to use the inductor SPH10040-100M for MP and onward. This will impact the 100pcs material preparation and the heatspreader design. | 1131
PM | 30pcs heatspreader allocated to ALT for urgent request to BMT | Fii | close | 2021-05-14 | [Fii 0428] N.W.E shipped out 30pcs AMP heatspreader top and bottom to ALT on 4/27 from 195sets demand for DVT3. Need to push to re-make 30 sets for DVT3
PM | Final design of heatspreader *25pcs sample | Fii | close | 2021-06-07 | [Fii0615] New Heatspreader 6/15 ETA (VN) [Fii 0601] 25pcs samples ETA 6/10 , haven't get ALT's PO [Fii 0524] Under tooling modification due to T1 housing design change and request vendor to ETD 5/31 [ALT 0521] ALT to confirm if final heatspreader sampe Korea. [ALT 0520] ALT inform to hold tooling kick off due to top case of housing is going to change, heatspreader sample will need to be modified again. [ALT 0513] Fii updated final design, need ALT to confirm then Fii will kick off tooling [Fii 0511] Quotation provided to ALT Steve, wait for PO. [Fii 0507] ALT agree on tooling kick off.
PM | ALT designation letter for BQB lab | ALT | close | 2021-05-04 | [ALT 0430] Will reply by 5/4.
PM | DREAMUS REACH (SVHC 211 items) Compliance Declaration | ALT | close | 2021-06-04 | [ALT 0705] ALT provide by 7/5. (Fii QC team inspection document) [Fii 0617] REACH_符合性宣告(FK3N00002007_I).xls => need to fill in and company's seal. [ALT 0527] target to provide by 6/4 [Fii 0510] Fii QC team sent requirement to ALT for confirmation [ALT 0507] Provide the documents within WK 5/10. [Fii 0430] Plz check with DREAMUS for the declaration with general format for REACH.
PM | Final version of FFC cable/Heatspreader/Housing Assembly | Fii | close | 2021-05-20 | [0623]supplier has sent to Korea (TRK# 774034212546) [Fii 0617] 5 set new FFC cable : The supplier now has five sets of FFC (Enhanced shielding) cable sample to provide ALT. Please agree to use the ALT Fedex account to send FFC (Enhanced shielding) cable sample. [Fii 0601] To confirm schedule for 2 gaskets samples in order to add into final version of 25 pcs sample for KC/BMT [Fii 0520] ALT request to assembly 30pcs(20pcs for ALT, 5 for Fii) advanced FFC cable with shielding , final heatspreader of mainboard, current top heatspreader and T0 housing in VN factory. (20pcs final top heatspreader to be sent to Korea) Fii to check with factory about work order, and ETA schedule of FFC cable and heatspreader. ALT to check the T1 housing ETA schedule.
PM | VN factory lock down issue | Fii | close | 2021-06-15 | [Fii 0527] Guang Chau site is under application to VN government for unblock.
PM | T1 housing sample qty | Fii | close | 2021-06-02 | [ALT 0624] T1 sample will be ready by 6/26. [Fii 0615] provide 4 more T1 housing samples =>T1 housing samples (4pcs) will be used in DVT3 production and assembly four groups to provide housing reliability test . Note : Test Item :T1 Housing => Free Fail Drop Test/Operational Random Vibretion/Operational Shock Test [Fii 0603] Fii to update T1 housing sample purpose. [Fii 0602] Fii to confirm required T1 housing sample to be shipped on 18th June.
PM | Extra acoustic equipment purchaising | Fii | close | 2021-06-10 | [Fii 0621] New acoustic equipment order can be confirmed and provided on 7/1. [Fii 0617] New acoustic equipment L/T : 8week ~ 10week. [ALT 0603] ALT to provide extra acoustic equipment PO.
PM | 5 set DVT3 PCBA send to Korea | Fii | close | 2021-06-30 | [ALT 0702] sample have been received. [Fii 0630] 5 set DVT3 PCBA ETD 6/30 =>(TRK# 774112265640) [Fii 0627] 5 set DVT3 PCBA ETD 6/30 (Vietnam) [ALT 0624 ] SW version => secure [Fii 0623] SWAN five sets of DVT3 PCBA sample : 1. SW version ( secure or non secure ?). 2. DVT3 MP will reduce " New 25pcs sample for KC version" 5 unit shipped to Korea. 3. The application can be sent on 6/30 => Please agree to use tht ALT Fedex account to send the PCBA sample.
PM | Dolby MS11 certification | ALT | close | 7/20=>8/31 | [Fii 0901] Provided Dolby certification on 9/1. [Fii 0820]Under Fii internal legal process. [Fii 0728]Our legal team received MS11 exception letter agreement from Dolby today which describes the following points. 1. Licensee will have until August 30th, 2021 to certify the new STB(model name: BFX-UA300). 2. The sell-off period for this specific STB will be extended until June 30th, 2024. 3. Licensee shall not manufacture or Sell any products incorporating MS11 Technology that are not approved by August 30, 2021 However, ALT team told us that we don't need to sign any extension agreement, and only resubmit the new test result with modifying documentation to Dolby certification engineer Steve, and the royalty paid by ALT. But Dolby US asked us to sign this letter/agreement before we get the MS11 certification by Aug. 30 We think it needs to discuss this critical issue with ALT team for how to deal with it in tomorrow's daily call. [Fii 0707] First priority - Option A : Submit based on MS11 w/o HE-AAC (to confirm by end of this week) 1) Synaptics to provide the patch which turn off MS11 AAC , and keep Synaptics in-house AAC, 2) Fii Brent and ALT will test IPTV all channels in Korea by this week (owner: ALT/Fii ) 3) SPTek to modify IPTV player instead of Synaptics SDK (owner: ALT-Mr. Yoon) 4) Fii to double check if Synaptics has experience of " in-house AAC only" (Owner: Fii-Jacky) 5) Extend due date issue: ALT will negotiate with Dolby Korea to sign amendment for extension. (owner: ALT- JW) 6) ALT will submit the MS11 w/o HE-AAC certification and pay to Dolby. Option B: Submit based on MS11 w/ HE-AAC (ALT will check if optionA isn't work) - Submit based on current SW - ALT to get Dolby's MS11 w/ HE-AAC or MS12 w/ HE-AAC (owner: ALT- JW) - Suggest to find the discussion record btw Dolby and ALT last year to see what proposal Dolby provided. If they didn't mention that ALT should get Via Licensing's AAC before sign MS12 w/ HE-AAC with Dolby, then ALT can strongly request Dolby to find solution for it. (No matter it's a waiver for this project only or to grant ALT : MS12 w/ HE-AAC, it's Dolby's call) - ALT to submit the MS11 w/ HE-AAC certification and pay to Dolby according to our supply agreement. [Fii 0706] In summary of Jacky and my comment, there are two options: Option A : Submit based on MS11 w/o HE-AAC - Precondition: 1) Synaptics to provide the library which turn off all AAC (owner: Fii-Jacky) 2) SPTek to modify IPTV player instead of Synaptics SDK (owner: ALT-Mr. Yoon) - ALT to submit the MS11 w/o HE-AAC certification and pay to Dolby according to our supply agreement. Option B: Submit based on MS11 w/ HE-AAC - Submit based on current SW - ALT to get Dolby's MS11 w/ HE-AAC or MS12 w/ HE-AAC (owner: ALT- JW) - Suggest to find the discussion record btw Dolby and ALT last year to see what proposal Dolby provided. If they didn't mention that ALT should get Via Licensing's AAC before sign MS12 w/ HE-AAC with Dolby, then ALT can strongly request Dolby to find solution for it. (No matter it's a waiver for this project only or to grant ALT : MS12 w/ HE-AAC, it's Dolby's call) - ALT to submit the MS11 w/ HE-AAC certification and pay to Dolby according to our supply agreement. Extend due date issue: - Synaptics will negotiate with Dolby USA and provide the documents for ALT to sign in order to extend.
PM | AMP Board E cap SAMYOUNG 100uF/35V (FII not verder code) | ALT | close | 2021-07-20 | [Fii 0715] The order has been completed. [Fii 0713] 1.7/13 first places an order for 30 sets of 120K capacitors to the agent, and the agent and the capacitor agent (三瑩) discuss the delivery process. 2. The establishment of agent (三瑩) Vender Code is expected to be completed in three months. [Fii 0712] Can it be changed to ALT buy & sell material ?
PM | Pre-MP buy & sell 1K materials | ALT | close | 2021-07-25 | [ALT 0722] Provide a schedule list of buy & sell materials . [Fii 0715]When will the materials arrive at the factroy?
PM | September 4K order | ALT | close | 2021-07-25 | [Fii 0803] start 12k materials prepare [Fii 0802]As per our weekly review meeting minutes, ALT will confirm AMP/Main board solution on next Monday (08/02). => In order to reduce th risk, the materials production of 12k will also be suspended. ( Main PCB/FFC Cable/Heatsink..) [ALT 0723] ALT agrees to 12K order risk buy. [Fii 0721] Provide a list of risk buy materials. [Fii 0715] Need to risk buy ?
PM | Pre-MP SPOT 1K materials and 2nd source part list | ALT/FII | close | 2021-07-25 | [Fii 0721] Provide a list of 2nd part materials. ( for sopt list) [Fii 0719] Some materials cannot be found in the spot market (TI LP5036RJVR).
PM | BFX-AT100 (T99X171.00) DIODES & 3peak 2nd source reliability test | ALT/FII | close | 2021-08-31 | [Fii 0825] 1. Diodes 40pcs control run done; 3PEAK 100pcs control run on 8/25--> will provide control run report before next week. 2. CFT will deliver out 20pcs to Taiwan RD team by 8/28. [Fii 0821] Reliability is completed based on Fii testing rule. [Fii 0819]provide the control run report. [ALT 0818] I asked test items on attached e-mail. In our test conditions, we asked as follows : 4) 20 sets AC power on/off 100 times 5) 20 sets Passive standby on/off 100 time (We don’t support this function) 6) DUT full load & 45℃ Condition 20 sets minimum 72h aging test In your report, 1. You used 2 samples. We asked 20 samples. 2. There are “RED LED” in your picture. So we need to check your test environment. . Did you connect HDMI / Ethernet cable ? . Did you connect USB for Full load condition ? . What is the iperf test spec ? In your test condition, it looks DUT didn’t connect nothing except Adaptor. So this picture cannot use for test report. We cannot accept this test condition.
PM | SWAN reliability test | ALT | close | 2021-08-23 | [ALT 0823] ALT comment to waive single unit test. (with package is necessary) [Fii 0819] Free Fall Drop Test (Single unit test) (fail / please check test report) Need ALT to check how to fix this issue.
PM | KC certification BMT schedule | ALT | close | KC:9/20->10/5 BMT:close | [Fii 1008] Did KC complete on schedule? [ALT 1001] KC postpone to 10/5. [Fii 1001] How about the progress? [ALT 0901] KC: testing is completed. Target to obtained KC is 9/20. BMT: Target to complete BMT is 9/30. [Fii 0901] Please comment when will ALT complete KC certification and BMT so that Fii could start pre-MP.
PM | The datasheet for B&S, consign materials | ALT | close | 2021-09-09 | [Fii 0910] Need to confirm L-CH, R-CH speaker cable MPN with ALT. [Fii 0901] To prepare IQC for MP, please double-check whehter all datasheet is the latest version. If ALT has any update, please provide to us by 9/9 to prevent IQC failure.
PM | RoHS | Fii | open | 2021-10-01 | [Fii 0915] Need ALT to upload RoHS information for ALT's B&S/consign/designated materials. https://supplier-gp.ambit.com.tw/supplier/Login.aspx [ALT 0903] Need Fii to try to pull in one week. [Fii 0903] Kicked off document collection with QA team based on ALT confirmed declaration format.
PKRD | Package improved solution | Fii | close | 2021-09-14 | [Fii 0915] Giftbox: The bursting strength is limitation in B flute. Vendor comment there is no way to imporve. Carton: PK RD is working with vendor to have improved sample based on BC flute. Will be cost up.
PM | Alternative parts approval from ALT/SKB Eagle's Ethernet: Realtek -> Motocom Swan's LED: TI -> Awinic | ALT/SKB | Open | 2022-06-01 | [Fii 03/29 ] Arrange the alternative sample to ALT - Eagle 03/29 / Swan 04/2
PM | Eagle LED 21496870012022011126732 / 21496870012022011126654 | ALT | Closed | TBD | [Fii 04/19 ] Canon Provide the test log reports to SH [ALT 04/20] SH feedback the concerns in test log report [Fii 04/21] Canon co-work with internal team to figure out the abnormal syndrom in log file [Fii 04/22] Canon would like to know whether SH will hand carry the defected units to VN facility during the audit visit
PM | 2nd Source | Fii/ALT | Open | TBD | [Fii 05/20 ] Eagle BT Module Cypress (L/T=378 days = 54 weeks) Have to get the Q4 P.O ASAP since long L/T
PM | Supply of Components | Fii/ALT | Open | TBD | [ALT/Fii 05/25 ] Biz meeting: ALT-Steve will update the decision about the risk buy on 05/27 ALT/Fii weekly meeting [Fii 05/20 ] SWAN AWINIC Risk Buy 20K due to the long L/T of testing
PM | Eagle RMA 13K | Fii | Close | TBD | [0202] ALT paid 1st&2nd RMA cost by 1/31. [0113] Foxconn informed cost by 1/12 [0106] Foxconn will inform the cost. [1223] Foxconnn is checking with Factory the list that uploaded on Mantis May 6th by ALT. [1202] Foxconn will update RMA data about no. of STBs out of warranty and components for repair. [1125] There are differences between no. of NON-LED defect for 2nd RMA. Foxconn reported that it was 1,112, but finally it was 585 exclude 105 units that need to scrap. Foxconn informed that the 1st q'ty is based on no. of units before repair. But the 2nd q'ty is exact no. after repair. ALT asked Foxconn to leave a comment when there is some changes about no. or status on Mantis. [1118] ALT asked Foxconn to provide RMA 2 Report. RMA units almost all repaired. It is not provided yet. There is no scrap units in RMA 2. Foxconn will check it about no. of scrap unit. RMA 2 report wil be provide by 11/25. [1028] It already discussed with Mr. Steve Lee and Mr. Vincent yesterday. It will followed their discussion. [1021]Fii is still checking RMA cost with VN. VN will ship out 1st RMA1594pcs next time(include scrap 76pcs) Foxconn Factory needs more discussion. So Foxconn TW will ask ALT to have meeting after their internal discussion. [1014] Foxconn asked ALT to have a meeting for RMA cost discussion. It is about cost for Out of warrent units except LED issue. Foxconn will provide the details about it by 10/17. ALT will review the details and make a schedule to discuss. [1007] FII asked to change the RMA Label contents from "Made in Vietnam" to "assembled in Vietnam". Foxconn will send an e-mail about it. There are some wrong information on Serial no. of 2nd Batch RMA. ALT will check the information that Foxconn think wrong after receiving the information. There is no invoice packing list in 8.4K shipping document. Foxconn will provide it by today. [9/30] Foxconn VN will ship out 8.4K pcs of 1st RMA on 10/3 and ETD VN is 10/5. 2nd RMA batch will arrive today(9/30). [0923] The rest of 1st RMA(9.3K) will ship out on 9/26, 2nd RMA is on the way to VN. ETA VN is 9/28. Foxconn will inform exact no. of q'ty not to ship to Korea after meeting. [0908] If RMA unit shipped from VN to Korea directly, then it may cause customs clearance. For this ALT need some additional discusstion to reduce Tax. Foxconn will support it. So ALT donexn't need to worry about it. [901] Shipping schedule: Foxconn Factory will ship 2.9 K 1st RMA return batch. It will ship on 9/6 with 2K shipment of SWAN at the same time. 2 batch RMA : ALT shipped already and it arrived in HK 8/31 [0826] Foxconn will ship 1st RMA return batch(1.9K) next week. Detail schedule will be updated by this afternoon. 2nd batch of RMA will be shipped out on 8/27, not 8/16. And ETA HK is 8/30. 1 day delay for shipping schedule. Q'ty is 12,732. [ALT 0819] Foxconn VN can ship first 3K RMA units. Foxconn VN will update when they can ship to Korea. Based on RMA repair schedule, Foxconn VN factory repaired about 340 units per day. But Foxconn VN keep their daily repair capacity to 1200 units. To achieve it, Foxconn VN Factory will increase man power after Eagle MP. [ALT 08/12] Foxconn Factory will update RMA Status. Currently Foxconn cannot meet schedule. It will update by this week. [Fii 07/14] Leave Hong Kong to Vietnam on 07/19. Logistics& Custom 7~10 days. RMA will start from 7/31. [Fii 05/25] Screen the devices SN: 98.2% is related to old issue LED Diode Est total L/T 35days+ = Logistics (HK to VN) 7 days + Custom 7 days + In house repair at least 7 days + Logistics (HK to VN) 7 days + Custom 7 days
PM | License and Royalty for exFAT/NTFS (1540) | FII | Open |  | [1111] Other manufacturer support exFAT/NTFS R/W function. So we should provide Read funtion at least. [1104] ALT wants to know whether Foxconn can support it or not. ALT heard from SKB that other manufacturers will support R/W function from A12. ALT cannot know whether other manufacturers have File system license and their STB can support it. [1028] Foxconn think that there is no issue to support Read function for exFAT/NTFS. ALT already asked to support it from next build. ALT already asked it to Mr. Jacky Chiang. [1021] exFAT/NTFS will be free on A13. ALT asked Foxconn which File system can support for A12. Can Foxconn support exFAT Read function ? ALT needs Foxconn's opinion about File system. [1014] ALT doesn't have any information for other vendors. SKB would like to make a specification on File system for A 12 version. [1007] ALT asked Foxconn to update it on Mantis. Foxconn updated. [0930] Foxconn doesn't have license for exFAT and NTFS. ALT asked to provide about this answer by e-mail. [0923] Foxconn Support exFAT/NTFS File system for Android 12. Is there any issue on Royalty and License ? Foxconn is checking on it with legal team ALT asked FII to update Foxconn internal discussion status and result on mantis.
| EOL DDR4 4G | FII/ALT | Close |  | [1021]Fii booked the DDR4 4G base on ALT forecast. But as Hynix DDR4 4G has already been EOL, second source is still indeed. ALT will ask Foxconn to start 2nd source introduction when it need. Foxconn estimate DDR 2nd source introduction will take for 4 month. [1014] ALT provide the forecast about SWAN 2023. If Foxconn didn't have enough Hynix DDR, then Foxconn can order based on the forecast. ALT doesn't want to release ECO this time. If ECO will be needed, then it will be done by next year. ALT asked to Foxconn when ALT start to ECO decision. [1007] Eagle already has 2nd source for Samsung. So ALT asked Foxconn to use Hynix DDR for SWAN. Foxconn need PO for DDR for Eagle . [0930] ALT asked to Foxconn to go on and asked to provide the schedule for this ECO. ALT informed that it need 40 samples for BMT(20), QA(10) and ALT(10). But it may change after discussion with SKB. [0923] Hynix DDR4 4G EOL. ALT will check it and update on mantis.
| [SWAN]Synnex_Hynix DDR4 8Gb C-die EOL | FII | Close |  | [1104] SKB accepted it. Foxconn wants to get an e-mail about it. ALT will send e-mail early of next week. [1028] ALT will update about any feedback from SKB. [1021] Has upload Hynix DDR4 8Gb D-die report on mantis #0001547. Need ALT to review and approve it. ALT will inform to SKB and come back soon [1014] Hynix DDR4 8Gb die already EOL. ALT is checking which documents are needed for ECO request for SKB. Foxconn will provide their DDR Test report by 10/17. But customers always don't want this kinds of mistakes. ALT will discuss it with SKB, but ALT asked Foxconn not to happen it again strongly.
| Idle Stock | Fii | Open | 2022-10-30 | [1202] ALT complain about idle stock information. ALT asked Foxconn to provide exact idle stock information. ALT and Foxconn will dicuss based on this information more. [1118] Foxconn will discuss with JW Kim of ALT. [1028] It is dicussed yesterday. It will handle based on yesterday discussion. [1021] Fii booked materials based on SWAN forecast. But the needs is put off by 2023. There are too many idle in VN/BT. Fii is asking ALT to buy the idle stock.
| ATV12 NRE&AMAZON Prime Video NRE | Fii | Close | 2022-10-30 | [1028] NRE was discussed yesterday. ALT asked Foxconn to provide Amazon Prime Video test plan. SKB hopes it will finish within month. [1021] Fii asked ALT/SKB to pay NRE about ATB12&AMAZON Prime Video.
| PCR(Post Consumer Materials) use - Portion/cost | FII | Open |  | [1223] Foxconn is checking internally about Fail items on PCR-ABS reliability test. Foxconn keep checking it by next week. If there is no progress, then ALT will close it. [1209] ALT asked Foxconn to provide the test items, test criteria and its result, not test report for other vendor. [1118] Question about cost for PCR-ABS : SKB asked ALT about cost for Mechanical parts using PCR-ABS. ALT knew alreay that Foxconn isn't inform about cost about component. But it is request from SKB, not ALT. ALT asked Foxconn to support about it. ALT think that there is no requirement to use LG Chemical product only. ALT thinks that Foxconn can suggest other vendor that already has GRS Certification. [1111] PCR-PC can use 50% and cost will increase about $0.1. And PCR-ABS cannot be use for IR issue. [1104] Foxconn will feedback it after check internally and comeback soon. [1102] SKB asked ALT to check the following items. It was FII's reply 2 years ago. How much portion that PCR material can use for mechanical parts : 50% Cost increase when we use PCR material : US$ 0.1
| BI |  |  |  | [ALT_0515] Please update the milestone. For more detail, need to discuss this item on 'Eagle' part. [ALT_0508] According to the updated milestone, 'Sample delivery to ALT and TW' will be on "5/18~5/23". There is some gap between those days, and it looks like it does not fit the following milestones, which are ALT confirmation and Fii starts reliability test. Please recheck your specific target day. --> Need to discuss this item in the 'Eagle' Part; there is the same question in row 20. [0504] Schedule update: Mold trial will be 5/10-11 in Dongguan, Sample build will be 5/15-16 in Nanning. Sample will be sent to ALT after silk print. [0427] SKB approved for Apr and May MP for housing on the short-term solution. Mold trial will be 5/4 in Dongguan, Sample build will be 5/10 in Nanning. [ALT_0425] ALT will request the customer to confirm for April MP for housing on the short-term solution after receiving Fii's formal notice, including completed 8D and two kinds of test reports. [0421] ALT is waiting for an e-mail about it. [0421]Fii will send 8D report/test report mentioned on Mantis/E-mail to Daniel to ALT on 4/24.reliability test items will be discussed by RD of both sides. [0414] ALT will provide the reliability test requirement to Fii on 4/17, factory will send sample on 4/16 before 24:00, samples will arrival ALT on 4/19, in the morning. Foxconn will provide new sample(old mold + ABS) through DHL. ETD 4/16, ETD 4/19. ALT need tracking no. for new samples. [0413]Fii ask ALT to check with SKB if Apr&May's MP can use old mold+ABS. schedule has been sent on 4/13. Also need ALT to inform biz trip schedule. [0331] Please provide tracking# on mantis when Foxconn ship out the samples. [0330]Fii will make T9 sample and quantity would be based on Old mold+ABS. Samles(上,中,下, and Old mold+ABS)would be sent on 4/4. [0324] Please follow ALT's requirement on the 3/23 email Emma sent, and it must be provided by 3/27. After reviewing the relevant data, it is possible to deliver the limit sample production standards for the next MP. [3/23]Eagle housing's MP might be finished on Mar 26 and will start next sample after discussed with ALT. Fii is checking all status requested by ALT and will update ASAP. [3/17] T8 sample have some issues and need ALT to give feedback of T8 housing conditional approval for production or stop the production [3/16] Fii's housing dep. said they are trying to refix the gas mark and wild lines, so they changed some conditions before MP. Gas mark and surface have been improved. Fii will update the report of T8 version on Mantis(#1557). and Sample will be sent by 3/17. [0313]ALT approve T7's housing for Mar's MP conditionally. Fii will make T8 sample after Mar's MP. and thermal test result will be updated by 3/13. [0303] Ms. Miya Wang is out of office today. ALT and Foxconn will have meeting next monday(3/6). Reliability test with T4 will be finished by next week. Foxconn may provide test result by 3/8. [0224] No update yet. [0223] FII will provide the updated milestone by 2/23.FII need to provide the housing that made at the VN site as a final sample. [0217]FII will provide the updated milestone by 2/18 and the vendor will ship out T6 by 2/18. [0202] 1)T4 Sample sent by 2/1.Supplier is preparing status of modify history. will be sent by 2/8(Miya) 2)Package spec will be sent by 2/7.(Miya) [0119]Will send goldon sample to ALT on Feb 1. [0112] Schedule updated as below. [1223] It is on track, but Covid-19 is getting worse in China. So plan may impact. Based on current plan, Foxconn will provide golden sample by 1/6. Role : CN - design, VN - manufacturing, TW - testing. Foxconn will provide 20 golden samples to ALT. [1209] It is on track so far. [1118] ALT needs new Housing sample to check Housing and marks. And ALT will need samples with PCBA. ALT will check and comeback about no. of samples. ALT wants to know how Foxconn will test IR transmissivity. Foxconn will provide drawing abot test by 11/21. [1111] Foxconn can keep BI change schedule that provided in this week. [1104] ALT asked Foxconn to provide BI change schedule.
| SWAN Last order |  | Open |  | [Fii_0620] OK. Hope we can have the final conclusion soon. [ALT_0614] Sophie will review idle materials and JW will discuss NRE with Miya [Fii_0613] Miya is working with Sophie to review the idle materials and NRE. [Fii_0606] We have a draft version for the idle materials list and will send to ALT for review next week. [ALT_0531] Please update us the production status and send us the idle materials list when ready for review. [ALT_0524] After we review the idle materials list and finalize the amount of payment then can arrange shipment. [Fii_0523] Base on the plan as picture, we will send out the idle materilas list by 6/3. [ALT_0517] After finising the SMT, please send out the idle material list for review. [Fii_0516] Latest plan is to start SMT on 5/21. [ALT_0510] Noted, please update the progress in time, thank you. [Fii_0509] No problem. We will start the build in mid of May then ship with idle materials together by June. [ALT_0503] We would like you to ship out the PCBAs with idle materials together, so the best delivery date will be around June. Please help to arrange it, thank you. [Fii_0502] The delivery date of PCB is ETA Fii VN by 5/15, so we can ship the PCBA in the end of May. Any issue with this delivery schedule? [ALT_0426] Please check if Fii can ship out PCBAs after June ( Dolby license issue ) confirm the PCBA delivery schedule with the vendor and reply to Sophie's email which was sent yesterday. [Fii_0425] PCB vendor didn't feedback the delivery date yet. Keep pushing and will update the delivery schedule later. [Fii_0418] We are waiting for the feedback of vendors. Will update the production plan and delivery schedule next week. [ALT_0412] Please update the production and delivery schedule and idle materials list to us , thank you. [Fii_0411] 100pcs LTB PCBA PO was received. Factory is preparing the materials with the vendors now. Will inform ALT if any issue. [Fii_0328] Noted. We will start to prepare the materials after receiving your PO next week. [ALT_0328] We decided to do the full test instead of skipping the test procedure, about the PO, we will discuss the price internally and feedback to you by next week. [Fii_0325] Factory feedback there will be not full verified if jump any step for the SWAN test. [ALT_0315] Please check if the test procedure that we want to use for the main board can proceed in your testing line, and if need extra jigs or fixtures list it out via mail, also any risk that ALT needs to be bear pointed out. [Fii_0314] Miya will provide the quote of SWAN PCBA for last order this week. [ALT_0308] We received the EOL mail, after internal discussion JW will reply later. Also, we would like to provide deliverable list which Fii can provide to ALT once we pay the NRE. [ALT_0223] Noted, when receive the EOL letter will inform SKB. [Fii_0222] Miya will issue the official EOL letter next week. [ALT_0216] We will discuss this with SKB and feedback to you later. [Fii_0215] As Snaptics IC had been EOL in the end of Jan., Fii can't produce SWAN to ALT anymore. If ALT didn't feedback us the final decision of SWAN last order, Fii will send the EOL letter within Feb.. [ALT_0202] Noted, after receiving the file, we will discuss it internally and give feedback to you later. [Fii_0201] We received evaluation request to produce 70 or 100pcs more SWAN PCBA from ALT. Miya will reply the quotation by 2/2 and we need ALT's final confirmation for the build Q'ty. For the excess charge, it will be provided after the build. [ALT_0126] Will discuss RMA Q'ty first, still waiting for SKB's answer. [ALT_0119] Try to reply this issue by next week. [ALT_0112] ALT is working on it. We'll update it soon. [Fii_0111]As synaptics will EOL by end of Jan, if ALT do not have any demand, Fii will start EOL process. [ALT_1222] ALT will inform Fii as soon as SKB finalizes the demand for next year [Fii_1221] Till now, we still didn't receive any feedback for SWAN last order yet. [ALT_1215] We will have meeting with SKB and will let you know the result next week. [Fii_1214]Please let us know when SKB will feedback. [ALT_1208] Still wait for SKB's feedback. When we get feedback from SKB will share it with you ASAP. [ALT_1124] Still wait for SKB's feedback. Try to reply it by next week. [Fii_1123]Still not received the FCST and PO yet. Please reply ASAP. [ALT_1117] SKB will have a meeting next week and come out with the results no later than Nov. and we will share the results by then. [Fii_1116]Please let us know the status ASAP. Factory is pushing us for the long lead time materials. [ALT_1110] ALT will update by early next week. [Fii_1109]Please update [ALT_1020] The decision will come out around early Nov, will inform you the result by then. [ALT_1013] Will check with SKB & Synaptics then give the feedback. [Fii_1012]Fii is still waiting for 2024's PO. And please help to advise Dolby license status by mail. [ALT_0721] ALT will discuss with SKB and reply this last order Q'ty in early of Aug. [Fii_0720]according to Mr JW's e-mail, Fii will purchas MPQ firstly. but please keep pushing SKB about the 2024's FCST. Some components' L/T is over 1 year. [ALT_0630] Noted, will do the internal discussion and feedback later [Fii 0629]Normally, Model which is not EOL, our minimum order quantity for materials is MPQ. After receiving notification of EOL from the customer, we will conduct an inventory check and provide a detailed list to the customer. We kindly request the customer to proceed with the purchase. [ALT_0616] Noted, will do the internal discussion and feedback later [Fii_0615]Fii add some materials this week, and get approval to order MPQ. The condition is after EOL, before ALT buying idle materials, Fii will provide details of idle materials. [ALT_0425] ALT is under checking with customer. We'll keep you updated. [0421]MR. JW saild ALT will arrange a meeting with SKB next week to talk about this issue. [0414] ALT will discuss internally and get back you soon. [0413] Due to materials' L/T, please reply before 4/20. [0331] ALT is waiting for SKB confirmation. [0330]Fii updated materials price to ALT and is waiting for confirmation. [0323]ALT asked Fii to check materials from spot market, which amout is above USD300. Fii will update by 3/26. [0317] Foxconn provide the cost for the remaining materials is $7,500 when all the material is purchased by MOQ. ALT asked to check the cost difference when purchasing parts for 22K production from spot market. [03/16] About unique parts of SWAN. After checked with our supplier, Fii could only order by MOQ. Fii also checked with spot market if we can buy the balance q'ty, the price is too high. According to L/T, some of materials need to be ordered ASAP.
| SWAN DDR 2nd Source Cost |  | Close |  | [ALT_0424] It is same situation about HW &ME item 68, DDR 2nd source for AMP. ALT will handle it with same policy of DDR for AMP. [0414] ALT will have internal discuss and reply. [0413]Please check if SWAN will be EOL. [0331] ALT will discuss with SKB and feedback later. [0324] under internal discuss and will feedback later [0323] Fii already sent E-mail for approval E-mail. [0317] ALT already sent e-mail about test that ALT wants. If Foxconn need any other approval e-mail, then they will ask to ALT. [03/16] Need ALT's approval email for remove 4 tests.
| KC Label |  | Close |  | [Fii_0706]There are 14.5k old version in stock. [ALT_0616] Please let us know whether the new Eagle KC label will be applied for July MP and how many will be covered. [ALT_0515] Okay. Please keep us update. [0512] New Label will be use from MP in Aug. And FII will announce when they start to use. [Fii_0511]Fii ordered 26k for MP already. will change to new version after using all stocks. New version has been approved on 5/10. [ALT_0508] Please follow up on our previous question about 67K stocks, and let us know the status regarding our request for an Atv label update (5/4 email by Emma). [ALT_0424] ALT think that RMA didn't use new label. Anyway Foxconn can use old label for MP. After using all old labels, Foxconn can use new label. If you have any difficulties for it, it is up to you. Please check the Emma's email on 4/25. [0421] T99X171 and K18X001's labels have been approved via photo. May's MP will use new label. but there are 67k Eagle's label in stock. these will be used in RMA. [0414] Foxconn will send picture by 4/17 and send the samples to ALT office. ALT asked to check and feedback about the label q'ty for UHD4(Eagle AOSP). [0413] Label sample and photo will be sent next week. Please confirm via photo. [0331] ALT will release the new artwork soon. [0330] Will change to new label from May's MP. Fii is waiting for the new artwork.If artwork delayed, Fii will revise this schedule. [0324] New Artwork will share with Fii in early April. When implementing the new materials we request by running change. ( should consume all the old materials first ) [0323]About new label, Fii's normal process is as below. When ALT provide new label's spec, Fii will check if these process can be shorter. receive artwork→make proposal(2-3 days)→ALT/SKB confirm(1 days)→make sample(3weeks)→send sample for confirmation(1week)→request EC on system(1week)→order new label(L/T 3weeks)→ start MP with new label
| Gift Box |  | Done |  | [ALT_0421]Sample has been approved. As there will be 2k old version in stock, ALT approved Fii to usd old box for 2k MP in May. [0413]Sample has beed delayed and will be ready on 4/19(Photo).
| Questionnaire for SONY |  | Close |  | [ALT_0616] Noted, ALT will help to push AML [Fii_0615]Sorry it takes some time for me to get permission for sending e-mail to AML. Fii sent E-mail to AML on 6/15, ALT will got the e-mail after it was approved. [ALT_0609] ALT will help to push AML, but please write an email to AML first and loop ALT members in it. [Fii_0608] Please help to push AML. [ALT_0602] FYI, Synaptics wants to discuss contents provider directly after signing NDA. We'll keep update. [ALT0526] Please keep push AML and Synaptics, if still no feedback from them, ALT will help to push. [Fii_0525] Fii sent request to AML and Synaptics, is still waiting for their feedback. [ALT_0519] ALT sent Foxconn's feedback to SKB. SKB returned additional questions of WB. ALT sent it to FII. [Fii_0518]Fii's email is in SPAM. please check mailbox and get feedback from SKB. [ALT_0512] Foxconn already provide it. There is no update from Synaptics after that. Sony's additional question was placed when ALT sent the doc. first. ALT will check it and come back soon. [Fii_0511]Please check Jason's reply. If SKB/ALT has any comment, please let us know. [ALT_0508] ALT would like to know what Foxconn and Synaptics want. AML already provided it even though they didn't ask anything related to NDA. ALT sent this document on 4/4, and AML provided their feedback on 4/11. If Synaptics has any special reason to delay than other SoC, then please let ALT know. [0504] SWRD replied on 5/2 via Wechat. Mr. Kail will foward Synaptics China FAE's request to ALT. Synaptics said that some questions are too detailed (e.g. related to chipset security implementation) NDA probably required. [4/24] ALT asked to provide it, but there is no feedback from Foxconn SW side. Foxconn will check it with SW team and come back soon. [4/18] Foxconn is waiting for Synaptics's Feedback. [4/4] SKB asked to fill it a document that is set-top box security specification for SONY(One of overseas content company content supplier).
| Samyoung's E-cap (B&S parts) |  | Close |  | [Fii_8/17]Arrived. [ALT_0811] ALT sent 5000pcs on 9th Aug, please check it with Factory and let us know if you have any question. After then, this item will be closed. [ALT_0721] will send 5000pcs first to Fii, if have any problems, let us know ASAP. [Fii_0720]Got quotation and delivery from Mr JW. [ALT_0714] It will change to B&S part and ALT will update the quote to Fii [Fii_0629]Fii do not have Samyoung's vendor code, Samyoung refused to deal via agent. Fii is finding other way to solve this issue. Please wait. [ALT_0616] Please check if Fii can get a quote for Samyoung materials through an agent, and if so, please let us know the price.
| FFC Cable order |  | Close | 2023-07-14 | [ALT_0728] ALT replied ask to proceed with ordering the new FFC 11K. New FFC cable will be applied from 1K in the next MP 5K. And ALT will reply regarding the FCST next week. [ALT_0721] will reply before 7/25 [Fii_0720]Please feed us back ASAP. [ALT_0714] The bottom line is new FFC cables can be ordered above the MOQ(10K), and a delivery date notice is required for new cable orders. ALT will provide the feedback by next week, considering the L/T.
| R/C regarding deleting NUGU mark |  | Close |  | [ALT_0811] We'll get back to you when SKB decides it and I'll reopen it. [Fii_0810]ALT replied that SKB will not delet NUGU this time. [ALT_0728] Try to reply before 8/4 [ALT_0721] will check with SKB when can get the confirmation to ALT, then will notify to Fii immediately. [Fii_0720]considering process of running change(need 1 month), Fii suggest to change items from Sep.please let us know if SKB could accept this schedule. we need to stop materials' open PO ASAP. [ALT_0714] SKB plans to delete the 'NUGU inside' mark on all items (Housing, QSG, Box). Please let us know the current stocks and when R/C.
| Eagle Sampple |  | close |  | [ALT_0721] After checking with SKB, they reply us it is difficult to send defected samples back to ALT (ref 7/18's mail from JW) [Fii_0720]sample will be sent on 7/31. Free samples need quite long process. According to Steve's e-mail, please help to check what are the defected samples used for. [ALT_0714] Foxconn need to return Eagle samples with new PHY. But ALT cannot collect all Eagle samples with new PHY. ALT will informed that no. of collected samples first and send back it. Foxconn will check the delivery schedule of new 20 samples(Non-secured 10, secured 10) Foxconn will use ALT Fedex account to deliver new samples.
| SWAN new PHY samples |  | Close |  | [Fii_0914]Sent on 9/9. [Fii_0907] Will reply by 9/11. [ALT_0901] Based on the current production plan and test standard, please confirm when is the target date that can ship out these samples. [Fii_0831]Before we ship out these samples, we need to do all of the test. As LED has some problems, these sample could not pass the test. [ALT_0825] Can you explain why the main board need to be test LED issue? There is no LED board on the main board. [Fii_0824] before shipping these PCBAs, Fii need to test them. the test is related to LED. So we will ship PCBAs until LED issue been solved. [ALT_0818] Please check if factory can send some main b'd to ALT. Due to main board is not relative to LED issue. [Fii_0817]LED in stock is under analysis, Fii will produce these samples after LED quality confirmed. [ALT_0811] Please check the target date again with the factory. [Fii_0804]Samples will be sent by 8/21 via Fedex. [Fii_0727]Fii is checking the materials' stock and reply by 7/31. [ALT_0721] OK, will send e-mail to VN factory PM [Fii_0720]Please send e-mail to Fii include VN factory PM. thanks. [ALT_0714] ALT will return Main b'd that use new PHY. But ALT cannot collect all Eagle samples with new PHY. Currently we have 10 pcs from BMT. Foxconn cannot use those b'd after rework because it use new PCB. But FII need to return it. ALT will informed that no. of collected samples first and send back it.
| Eagle Memory 2nd Source |  | close |  | [ALT_0308] ALT already purchased 600K memory for the Eagle project, so currently no need for Samsung memory. [Fii_0307] Fii prefer not to introduce Samsung new die memory for Eagle. [Fii_0229] This topic was a topic for Vincent and Daniel when they met in MWC. Will discuss with Vincent once he come back from business trip. [ALT_0223] We need price information to decide whether to let Fii buy it, please ask sourcer to provide price to us, thank you. [Fii_0222] Our sourcer would not like to update the pricing if no actual demand with it. Samsung new die verification was pending as well. Let's keep the BS continuously. [ALT_0216] Please feedback the current Samsung memory's price by monthy first, and about the ALT do the BS continuously this issue, we will feedback this after internally discussion. [Fii_0215] Fii buyer suggests ALT to do the BS continuously. [ALT_0202] 1. Please provide the current Samsung memory's price by monthly to us. 2. Please ask the factory to provide the SN# list to indicate which devices use Samsung memory. [Fii_0201] Normally Samsung memory is always cheaper than Hynix one. If ALT decide to use Samsung memory, Fii will charge the PPV base on the pricing of shipping date. Need ALT's final decision for it. Fii will purchase Samsung parts as early as possible for lower cost. [ALT_0126] Memory die change doesn't need BMT, but once the Samsung memory is cheaper than Hynix then will use Samsung's memory. If decide to use Samsung memory then will proceed reliability test. [Fii_0125] Any decision for the memory policy? [ALT_0119] Will discuss internally and feedback by next week. [Fii_0118] We need ALT's long term decision for memory policy. If there is no Samsung demand anymore, it's unnecessary to spent time and monry to verify Samsung new die. [ALT_0105] We only need 10pcs samples from control run, not 20pcs ( shipping date 2/27 ) [Fii_1228] The samples with Samsung new die were shipped from VN factory. We will start the verification test from next week. [ALT_1222] Please share a milestone or status if there is any update. And will provide the SN for control run as AN requested by this week. [ALT_1219] Fii has old Samsung Memory (D1x) of about 900 pcs and will use it first for Eagle Jan Demend. After that, Fii will use ALT B&S memory. Fii will provide SKB S/N information, which applies Samsumg and ALT B&S memory. [ALT_1215] Will feedback on our sample Q'ty via mail before 1/5. [Fii_1214]Please see attached. [ALT_1208] Samsung's new die is confirmed, please share the Samsung new die test schedule with us. Hynix confirmation will be sent via mail by today. [ALT_1201] This will be discussed while ALT travel to TW (12/4~12/5) [ALT_1124] We will feedback our comment by end of Nov. [Fii_1123]2nd source test would take saveral months. based on ALT's FCST, 100k will be used up before Mar., Please reply this by 11/24. [ALT_1117]Due to Fii can't buy the 100K memory set, so ALT will do the B&S 100K first, but not decide from 2024 will transfer to B&S. Need to discuss this issue with Fii later. ALT will notify the 2nd source introduction by end of Nov. [Fii_1116]Fii has started internal process on system. If there is any necessory doc.or procedures, Fii will ask ALT for assist. If memory is going to be B&S from 2024, please help to close 2nd source issue and creat a new one for B&S status. Thanks. [ALT_1110] Mr. HS Kim already emailed that ALT will handle the memory as B&S. Please proceed accordingly and inform us if there are any necessary documents or procedures. [Fii_1109]Now there is no stock, so we can't book the memories.Please check Fii's mail [ALT_1103] We will reply the FCST by next Tue. Please check with the payment date issue. [Fii_1102]For 100k additional PO, it will be used for 2024 demand. please reply these 100k's shipping plan. [ALT_1027] Please inform us what kinds of momery( old or new ) on our released PO. [Fii_1026]Sent quotation to ALT Daniel and Steve. [ALT_1020] Please check 200K set(4G*2+8G*2) delivery schedule & Price to us first. [ALT_1013] Please provide the current Hynix P/N & Samsung P/N ( for SWAN ) to us by next Monday. Will discuss this issue at next Friday's meeting. [Fii_1012]Samsung announced that D4 die version will transfer from D1x to D1z, Samsung D1x production will be reduced next year around 50%. PN (D1x) Samsung PN(D1z) Project K4A4G165WF-BCTD K4A4G165WG-BCTD K4A8G165WC-BCTD K4A8G165WG-BCTD To avoid delivery and price pressure, we recommend introducing D1z, which has the same unit price as D1x now and offers a more guranteed delivery time. If ALT/SKB is ok with this, Fii will send reliability test plan to ALT. and please also let us know how many samples SKB will need as well. sample and test cost will discuss with ALT's biz team later.
| Eagle Mold Transfer |  | Closed |  | [ALT_1229] OK. It need to keep to track this version with no issue until complete the SKB inspection. ALT will close this agenda when we complete the SKB inspection. [Fii_1228] Our VN Factory received the golden samples already. Will use them for IQC inspection. Thanks! [ALT_1222] ALT provided the feedback on 12/20 and also sent the golden sample (上, 中 status) on 12/21. [ALT_1215] Will feedback on our opinion after checking the sample. [Fii_1214] Fedex tracking # 7744 3984 3990. samples will arrive by 12/15. [ALT_1208] If send out the golden sample, please provide the tracking # to us. [ALT_1201] Please send the golden sample with w/o NUGU (上/中/下) to ALT ASAP, and the 8D report of this month's issue. [ALT_1124] We check the sample and will feedback via mail by today. [ALT_1117] We will check the sample status and feedback our comment via mail. [Fii_1116]Sample has been sent on 11/15 via Fedex#7740 9604 9774. bottoms have already been produced. Please help to distinguish VN&CN ver with SN no this time. From 2024, bottom will be updated. [ALT_1110] This agenda can be cleared only in case the housing made in VN is manufactured and delivered as scheduled, and then is passed on the SKB inspection without issue. As we have already provided feedback on the first sample, we cannot approve those housings to proceed with MP. So please provide improved samples as soon as possible to ensure that the MP schedule stays on track. [F11_1109]Done. [ALT_1103] Miya will check with Vincent about the prevention action & responsibility and reply it. Also please reply Emma's email as well. [ALT_1027] We only received 2 weeks ahead notice wording, but there is no prevention action & responsibility for the incident in that mail. [ALT_1020] Regarding the incident of moving the mold early without ALT's confirmation, Fii should take responsibility. To prevent such actions in the future, Fii needs to send an official mail with prevention action plan and responsibility of this incident (If there are issues with new housing and impact the December delivery schedule, Fii should accept full responsibility). Golden Samples Q'ty will inform you later. [Fii_1019]I'm sorry that it was too late for us to issue the PO and request the factory not to move the mold. Therefore, for the December order, 10k will be produced in Nanning, and another 10k will be produced in Vietnam. The mold has already reached Vietnam, and the factory has started the sampling process. Please let us know how many samples are needed for confirmation. Furthermore, because there have been no changes in the mechanism, mold, or materials, only an appearance confirmation is required. [ALT_1013] Please provide the Nov production plan with Q'ty allocation by next Monday ( need to indicate how many Q'ty housing is in stock, and how many Q'ty will be produced in VN ) [Fii_1012]Eagle's mold will be transferred to VN by Nov.Fii will provide schedule to ALT and send samples for approval.
| NUGU Logo delete |  | Close |  | [ALT_1229] Got it. Thanks. / Closed [Fii_1228] Well noted. Our factory will scrap the housing with NUGO logo. [ALT_1222] We're afraid those cannot be used for 2024Y MP. As we requested last Oct, the new version must be introduced from the 1st MP demand. SKB finalized the introducing time after ALT checked with Fii. [Fii_1221] After checking, there are top housing 8552 pcs, BOX GIFT 668 pcs, MANUAL 1000 pcs with NUGU logo in the factory. [ALT_1215] In 2024 need to ship without NUGU logo devices. Please share with us how many Q'ty housings with NUGU logo are left in the warehouse first. [Fii_1214] Received confirmation by 12/8. [ALT_1208] Will send out the confirmation letter by today. [ALT_1201] Please check if ALT can give feedback on this on 12/8. [ALT_1124] We will confirm QSG & Gift box together, so please send gift box to us ASAP. [Fii_1123]QSG samples: Sent. Gift box: might be delayed. Fii will keep pushing supplier and feedback by 11/24. [ALT_1117] Please keep us updated on the progress. [Fii_1116]Samlples will be sent by 11/21. [ALT_1110] The original schedule we requested was yesterday (9th Nov). Please provide the sample schedule by today. [Fii_1109]Sample schedule is under checking [ALT_1103] Please reply the artwork file status and sample status by today. [ALT_1027] Please update artwork file to us. [ALT_1020] Please update the stock status of NUGU materials. please review the 2024 production plan for items without the NUGU logo to ensure there are no issues and provide feedback by today, 10/20.
| Eagle/SWAN human resorce |  | Close |  | [Fii_1214]Yes. [ALT_1208] We received the contact list, so from now on about MP factory issue will contact AN to control the issue, weekly tracking issue will contact Cato for overall control? [ALT_1201] Please provide feedback on Mr. Yoon's mail questions which were sent on 11/10. [ALT_1124] We didn't get any email until now, please send the MM resource allocation to us ASAP. [Fii_1116]will reply via mail by 11/17. [ALT_1110] It's not 'Done'. Please check ALT's further inquiries which Mr. Yoon emailed, and provide Fii's feedback. [Fii_1109]Done [ALT_1103] Please reply it by next Monday. (HW/SW/PM) [ALT_1027] Please share the Eagle/SWAN headcount resource and R&R with us.
| Google test environment |  | Open |  | [Fii_0620] May we have the latest progress of Google test environment in ALT? [Fii_0606] Thanks for the update. Please keep us posted once you have any progress. [ALT_0531] ALT took over Eagle OS. 12 on 5/24. Eagle OS. 10 will start preparing the testing environment from next week. [Fii_0530] OK. ALT take over Eagle OS. 12 from June first. And take over SWAN OS.10 and Eagle OS.10 later. [ALT_0524] After Fii helps to solve issues on Mantis, ALT can take over Google Test but only Eagle OS. 12. Eagle/SWAN OS. 10 will start to set up the Google test environment after Eagle OS. 12 is finished. [Fii_0523] Fii suggest ALT to take over Google test for Eagle from June. Fii help to resolve issues via Mantis. [ALT_0517] Google test issues will be discussed and managed via Mantis [Fii_0516] Google Test requires the accumulation of experience. The speed of testing mainly depends on proficiency and the speed of troubleshooting. The assistance we can provide on Mantis should mainly focus on solving problems that will cause the test stuck. [ALT_0510] We didn't get any feedback from Fii, we fix all the issues by ourself, so please check our issues immediately and feedback quickly in next time. [Fii_0509] After checking, Fii had resolved all Mantis issues [ALT_0503] We will ask to help for some test fails from today. Please keep supporting us. After fixing all the issues we can estimate when we can take over the google test. [Fii_0502] The test key was provided to ALT. Kinbay and Kerwin are supporting to resolve GTS related issues. Any target date that ALT can take over the test? [ALT_0426] ALT has some test issues, please feedback the issues immediately, Cato will check these issues and feedback. [Fii_0418] No problem. Once ALT can take over the Google test, please inform us immediately. Thanks! [ALT_0412] We will start testing on our side but still need your support until end of April. [Fii_0411] The 20pcs were shipped to ALT already. Thanks! [ALT_0329] We sent the mail on 3/26, please check again, thanks. [Fii_0328] After checking with Miya, we didn't receive PO for 20pcs Eagle yet. Please help to double check. [ALT_0328] Already released the PO and feedback FedEx account # to the factory. Please share the shipping information with us once ships out. [Fii_0325] Please help to release PO for the test samples, then we can arrange the shipment from our factory. [ALT_0315] Please inform us of the Google test sample 20pcs delivery schedule. We need to receive it by the end of March. [Fii_0314] Let's keep tracking the schedule for Eagle test environment first. [ALT_0308] Mr. Yoon mail replied " if Eagle & SWAN do the test at the same time, it will cause Eagle test delay", so we prefer to seperate the test of Eagle & SWAN. [Fii_0307] We have received the plan from Mr. YOON. Wish the schedule for SWAN can be pull in to 4/15 as well. [Fii_0229] We are waiting for the plan of the FW build and Google test from Mr. YOON. Before they are took over by ALT, Jacky's team will help continuously. [ALT_0223] We will reply mail to you by 2/27. [Fii_0222] Mr. YOON feedback he will share the plan of the FW build & Google test by this week. Fii will provide our support if needed. [ALT_0216] Noted, we are currnetly making a plan of the FW build & Google test and will share it to you once finished, if we need this support will let you know when will travel to Taipei for FW build/ Google test training. Before we finished the testing plan & build plan, please keep supporting us. [Fii_0215] If ALT team needed, we sincerely invite ALT engineers to come to Taipei for 1 week training including FW build, Google test. It will be more efficiency. [ALT_0202] We are still trying to setup the Google test environment, but still we have some issues that need to be solved first. After that, we will know if we can build the code by ourselves. [Fii_0201] May we know when ALT could setup ready for the build code and Google test environment? [ALT_0126] We are preparing the test environment and doing the fine tuning, if there are any issues will let you know. [Fii_0125] The test tools were sent to ALT by 1/19. [Fii_0118] The test tools will be sent to ALT by next week.Just waiting for our top manager's signature for this. [ALT_0112] 1. We would like to ask again the Fii for proceed with smoothly the technical support without any other issues mixed up, which is not related. 2. ALT already paid 2024Y NRE, which include the Google test tool, set-up envinorment, and build key. 3. Please help to Fii support technical side immediately. [Fii_0111]As RMA cost is overdue, Fii team locked this process. Fii need to explain to FI team. [ALT_0105] Fii will provide the test tool to ALT later [ALT_1215] Still under discussion, will feedback on what kinds of support that need from Fii [ALT_1208] ALT is under internal discussion, will feedback later once the conclusion comes out [ALT_1201] Will discuss this while ALT travel to TW (12/4~12/5) [ALT_1124] SKB ask us to prepare the one day Google test environment, Please provide us the test configuration ASAP.
| Eagle 600K PO |  | Close |  | [ALT_1222] Closed. [Fii_1221] We received Eagle 600K PO already. Thanks! [ALT_1215] We will give feedback to you on this issue by next Monday. [Fii_1214] ALT didn't place Eagle 600K PO to Fii for Everlight LED preparation by 12/12.
| 2nd source implementation |  | Open |  | [Fii_0620] Any update for BMT schedule? [ALT_0614] We are checking the BMT schedule with SKB, once we have confirmed the schedule will inform you ASAP. [Fii_0613] Any update for BMT schedule? We have to make an EC and purcument plan for the 2nd source materials. [ALT_0607] We get the samples today, will check the BMT schedule with SKB, and once have clear information will share it with you. [Fii_0606] Fedex tracking number: 776683161799. Had sent to SH by email and wechat. [ALT_0531] Please share the tracking# with us when 38pcs ship out. Please send us the LDO additional test report ASAP. [Fii_0530] The control run of 2nd source was completed. The 38pcs will be ship to SH on 6/4. [ALT_0524] Please update the ship out schedule of 38pcs samples and also provide the updated first test report when the vendor is ready, also the final test report should be provided on 5/24. [Fii_0523] We are processing the control run now and will inform SH once we ship put the 38 pcs samples for BMT. [ALT_0517] We will feedback on 5/10 test report comments by 5/17. [Fii_0516] Cooper had uploaded RD test report in Mantis 1176 on 5/10. As HWQA test will be completed on 5/17, the test report should be uploaded on 5/24. [ALT_0510] Please let us know when you can release the test report to us, thank you. [Fii_0509] Our HWQA will completed test by 5/17. Cooper will release an final 2nd source list for control run. Then we will ship 38 units to ALT for BMT test. [ALT_0503] We already test EMI/EMC in Korea, the result is OK. [Fii_0502] So far, Cooper had sent EMI/EMC report to ALT. They are reviewing the other test report now and will send to ALT one by one. [ALT_0426] Please send us the test report once comes out. [Fii_0425] Fii is applying with Fedex shipment for 2pcs EMI/EMC device. Will send tracking number once we get it. [Fii_0418] EMI/EMC was pass. The 2pcs device will ship to ALT by next week. HWQA verification is on going. The schedule is arranged on the early of May so far. We are trying to pull in now. Will keep ALT posted. [ALT_0412] Please update the verification progress and result and update the tracking# to us about the 2pcs device for EMI. [Fii_0411] Fii RD received 18 pcs samples and start the verification. Will keep updated. [ALT_0329] Once the schedule changes, please notify us immediately and mark the change point from the previous schedule. [Fii_0328] Sorry that we forget our factory can't arrange any SMT during quarter end inventory check. Our SMT of 2nd source will be postpone to 4/1~4/3. Please find the updated schedule as attached. [ALT_0328] Noted, please use our MP stock for this 2nd source sample build. [Fii_0325] We will build 18 units for RD and 100 units as a control run to make sure the yield of production. So total is 118pcs for the Hynix memory. [ALT_0315] Please inform us how many sets of memory that will be used for 2nd source build. We need to manage this B&S material to make sure the Q'ty on both parts in the same page. [Fii_0314] The 2nd source build was postponed from 3/15 to 3/18 as delay of new IR receiver, but Fii would like to catch up the full schedule on time. [ALT_0308] Please proceed with 2nd source test without Samsung memory, about the sample Q'ty, we will double-check with SKB and inform you later. Also, please double-confirm of delivery date if any changes ( attached picture ). By the way, please inform us how many sets of DDR4, memory you need from MP materials to build the 2nd source samples, we will check if we need to send extra materials to you. [Fii_0307] Yes. It's SI test for DDR. Our RD can't test it by ourselves. Have to test by outsoucing. [ALT_0304] Let us know what kinds of test for DDR 2nd source from your Agent. If you mean SI test, can you test it yourself ? If you can, then it is OK. We just want to review and compare your test result. We have some issue when we develop eagle first. So we would like to compare test result original one and new one. [Fii_0229] One critical issue for Samsung new die verification. The agent feedback us the DDR test is arranged to Q3 already. The schedule is not accetable. Fii profer not to implement memory for 2nd source. [ALT_0223] Please update the test report to us according to your schedule. [Fii_0222] Please find the estimated schedule of 2nd source implementation as attached. [ALT_0216] Please share the test plan and schedule with us. [Fii_0215] Understood. We are asking for samples from vendors to verify 2nd sources without RJ45 cable. Will keep ALT posted once we have any test report for them. [ALT_0202] SKB don't want to change RJ45 cable. [Fii_0201] We have replied Lonnie's questions and provide the complete datasheet for 2nd source of RJ45 cable. At meanwhile, we are asking test samples from the vendors for all of the 2nd source. Will start the verification after CNY. [ALT_0126] Mr. Lonnie asked three questions via WeChat, only one question got the answer, and the remaining 2 questions still waiting for answers. Please reply it ASAP. [Fii_0125] We just recieved latest feedback from Loonie by 1/25. Cooper will reply at soonest. [ALT_0119] Mr. Lonnie already send the BOM just now, please double check and feedback to us ASAP. [Fii_0118] We need Lonnie's help to send us the BOM ALT on hand now. Then we can double check if any mistake between yours and ours. Our RD will check and feedback as soon as possible. For the cost downinformation, I think this topic should be belong to Vincent & Steve. We just follow the instruction to do the 2nd source implementation. [ALT_0112] ALT is still under discussion, will get back to you. But as we requested before, please provide the cost down information. Also, please provide Fii feedback about ALT technical part review on the mantis. [Fii-0111] Cost reduction is for 2024's special support, it is discussed with Andy and Steve. Because now Eagle's profit is negative, so Fii ask ALT's help for check if these components be used in Eagle project. [ALT_0105] We will review it and feedback our comments. Please provide the unit price information to us. [Fii_0104] Fii has uploaded the 2nd source list and comparison table to case 0001176 to kick-off the verification. Plz have your engineering team to review and have your comments.
| Eagle IR Receiver Shortage |  | Close |  | [Fii_0222] There is no further shortage issue for IR receiver. Agree to close this topic. [ALT_0216] If there is no more shortage issue, can we close this issue? [Fii_0215] Roisy had provided Feb. production plan. So far, there is no shortage for IR receiver. [ALT_0202] Please provide Feb. production plan to us ASAP. [Fii_0201] The vendor will ship IR receiver particially. Before CNY, we can get 16K first. We will keep monitoring vendor's shipment after CYN holidays. [ALT_0126] Thanks for update, please keep us posted. thanks. [Fii_0125] IR receiver for Jan. was arrived on 1/24. There is no issue for the shipment on Jan. The current delivery schedule of Feb. is 2/20 from the vendor, we are pull in with buyer continuously. [ALT_0119] Please double check with Factory about the production schedule. Please keep us posted about the Jan & Feb material arrival status. [Fii_0118] Currently, the delivery schedule for IR receivers this month is January 25th, but we anticipate shipping on January 26th. Our buyer is still pushing for this schedule. But about Feb’s schedule, the wafer’s delivery schedule for IR receiver has been updated, and currently, all 60,000 units are at risk. We are keeping pushing pour supplier and expect to receive specific production scheduling details by next Monday. [ALT_0112] Please provide the exact status information including the delivery schedule on the demand for Jan and Fed.
| Eagle & SWAN Mantis Issue List Tracking |  | Open |  | [Fii_0523] We follow ALT's proposal that ALT update the list using Google Docs every Wednesday and Fii feedback every Thursday. [Fii_0516] The latest Mantis issue list was updated and sent. Need ALT's help to feedback. [Fii_0509] We sent Eagle and SWAN Issue List Tracking by today. Need ALT's help to feedback. In the future, it will be updated by weekly. We also can discuss this in weekly meeting if necessary.

## Eagle
Category | Issue | owner | status | due date | Progress
PM | Eagle additional sample (w/ DIODES, 3PEAK 2nd source) | FII | close | 2021-08-26 | [Fii 0901] VN will ship out 20pcs DUT to Taiwan on 9/1. ETA date will be 9/9 because VN is in holiday during 9/2~9/5. Reliability schedule is under checking with HWQA. [Fii 0827] ALT require to run 100% aging test (100pcs) on control run. However, ALT also require CFT to ship out 25K by 8/31. =>CFT will ship out the shipment first and go back to run aging test. Expect to run aging test from 8/31. After CFT complete the againg thest test, will deliver 20pcs to Taiwan. [Fii 0825] CFT will deliver out 20pcs to Taiwan RD team by 8/28. [Fii 0820] According to the requirement from ALT RD, the sample that ALT required is 20pcs. MFG is checking when they can ship out 20pcs because normal shipment is the first priority.
HWQA | Reliability testing for 20pcs (w/ DIODES, 3PEAK 2nd source) | FII | close | 2021/9/24 -->10/15 | [ALT 1013] Approved for 2nd source Diodes+3Peak phase in. [ALT 1001] Will feedback next week. (mantis#1321) [Fii 0924] Reliability test report provided on Mantis, need ALT to agree to phase in. [Fii 0903] Target testing period: 9/18 ~ 9/21. Target to provide the testing report: 9/24.
Sales | Eagle RMA carton | ALT | close | TBD | [Fii 0305] Factory provided RMA report for ALT review. [Fii 0224] Factory team is handling RMA. Traget to complete RMA by 2/25 and provide FA report on 2/28. [Fii 0119] Factory PM provided RMA schedule. 1/26 ETA VN factory, target to finish RMA and ship to Korea around 2/15. [Fii 0113] Factory PM William will handle the following process. Currently waiting for logistics team to confirm the vessel schedule. [ALT 1224] ALT shipped 1st carton of RMA DUT. [Fii 1215] Factory provided the RMA rules. [Fii 1210] Factory is checking the RMA shipping requirement internally, will update ASAP. [Fii 1123] Provided judgement from package RD. [ALT 1118] ALT provided another solution from Korea--> Fii will check with package RD for suggestion based on the information provided. [Fii 1104] Due to custom policy, need ALT to purchase directly from YUTO(package vendor). [Fii 1022] Checking the final cost and process(customs policy) at factory side, will feedback ASAP. [ALT 1020] confirmed to issue PO for Fii to purchase the carton from VN(by vessel) [Fii 1012] Provided solutions and need ALT to finalize the decision and execute ASAP. Please be aware of the warranty period. [ALT 1008] ALT feedback the cost and spec form korean vendor. [ALT 1001] Will feedback next week. [Fii 0909] Fii provided shipping cost (sea/air) from VN to ALT. Wait for ALT's decision. [Fii 0903] After checking with Fii sourcer and logistics members: Shipping cost from VN to Korea is much higher than Carton cost. --> Fii provide drawings and ALT will check with suppliers in Korea [ALT 0901] RMA >6000pcs, will check exact quantity after the meeting--> Till 9/3 Total 3107pcs [Fii 0825] Fii will disucss the expense internally and propose to ALT. Package test estimates to be finished on 9/10; [Fii 0820] Under packing reliability testing at Fii site.
HW/PM | New RCU (Mantis #1344) | ALT/FII | close | 2021-09-24 | [Fii 0930] As the old/new RCU will both exists, need ALT to clearly instruct which batch to ship with new RCU in the future. [Fii 0922] New RCU PN provided (Mantis #1344) [ALT 0915] Update datasheet for new RCU [Fii 0908] Fii will apply for new PN and check how factory can control it. CE team asked to provide high resolution datasheet. [ALT 0908] ALT informed to introduce new RCU for Eagle adding Smart TV control function.
PM | EPD certification | ALT | close | TBD | [Fii 0117]Factory PM An already feedback the factory visit question. [ALT 1123] Request to provide more details of pallet packaging info. --> provided [Fii 1118] Electricity consumption data provided to ALT. [Fii 1111] Factory will check internally and collect data. (Target to provide next week) [Fii 1110] Factory requested ALT to provide english template form for them to fill in the electricity consumption data required. [Fii 1104] Need Steve to send out an official request mail for EPD certification. And please list the information and document needed with template to fill in.
HW/PM | 2nd source (Eth PHY/BT/IC) (Mantis #1353) | ALT/FII | close | TBD | [0324] ALT is closed it due not to apply 2nd source. Motorcomm PHY has issue when Ethernet cable plug and unplug repeatedly. [Fii 0421] The CRC and autonegotiation test report has been provided to mantis #1459 on 4/19. [Fii 0414] Fii QA team is working on the CRC test now. And the report can be provided by next Tuesday (4/19) [Fii 0408] 1. Motorcomm YT8531C: waiting for BMT. [Fii 0331] 1. Motorcomm YT8531C - Samples already shipped out. - Need ALT to confirm BMT schedule. Fii would like to introduce this materail from 5/1. [Fii 0324] 1. Motorcomm YT8531C: Will ship out on 3/25. 2. Ampak W511: stop the development due to SKB reject to use Ampak W511. [Fii 0317] 1. Motorcomm YT8531C : VN is running control run. Will ship out the samples by 3/23. 2. Ampak W511 - SW progress for BT compatibility: Samples arrived at AML China office. However, due to China government policy for COVID19, they cannot enter into their office for analysis. - SKB comment: SKB reject to use Ampak W511. Cypress still in critical shortage isse. [Fii 1216] As Movon is not Fii QVL, Fii will introduce Ampak as 2nd source. [ALT 1215] Foxconn can decide to use Ampak or Movon for BT 2nd source. [Fii 1119] ALT feedback to make decisions on BT module by next Monday.(11/22-->12/7) [Fii 1111] Have reviewed the MOVON's datasheet. The module size is about 1mm wider than AMPAK module but the current space can still be placed in. We don't have questions to using this module in Eagle. [ALT 1110] ALT suggested BT 2nd source (Movon(MD-BRC101)) [Fii 1104] EFUSE 2nd source Toshiba cannot provide samples for verification. [Fii 1022] Fii provided cost to Steve, wait for update. [ALT 1015] ALT will discuss internally if accept Fii rule for test samples. (4pcs for reliability test and 100pcs control run) [Fii 1014] Tiffanie will discussed about the cost with Steve. According to Fii's rule, we need 4pcs for reliability test and 100pcs control run in the factory. For the phase in plan, we will arrange 2 rounds introduction. 1st round (pin to pin): IC 3peak TPV809S-3TR ETH PHY Motorcomm YT8531C 2nd round (re-layout): EFUSE Toshiba TCKE712BNL BT Ampak W511 [ALT 1008] Need Fii to provide the phase in plan and cost liability. [Fii 1007] Need ALT to agree with the 2nd source introduction ASAP (except for BT module) [Fii 1001] For ETH PHY Motorcomm, as it is not QVL material, Fii will need ALT to designated Motorcomm as 2nd source via email if the reliability and control run passed in order to apply for Fii PN. [ALT 0924] Please check who will pay the new certification fee and test. [Fii 0917] Update comparison datasheet on Mantis. Need ALT to check and officially confirm to start the phase in process. [Fii 0915] Due to the long LT of current materials, please check below suggested 2nd source.
SW/PM | SW upgrade | ALT/FII | close | 2022-03-01 | [Fii 0223] RD applied EC to introduce new FW based on parties conclusion. [Fii 0214] Eagle: control run from 2/15. providing report by 2/18. SWAN: control run from 2/16. providing report by 2/19. [Fii 0210] Factory will do control run after MP shipment on 2/14. Target to introduce the new SW from March.
HW/Sales | BT module issue | ALT/FII | Pending | 2022-03-28 | [Fii 0331] Pending due to parties biz team have not reach the conclusion. [Fii 0324] 1. We heard from Sales team that ALT will going to propose Movon's BT solution to SKB and move it to B/S if SKB accept it. Need ALT to update the current status. [Fii 0317] 1. ALT inform Fii that SKB doesn't agree to use AMPAK W511 module since SKB concern about BT change, and would like to keep BT chipset as it is. 2. Need to find another way to solve it.
Quality | CS materials for out of warranty | FII | close | 2022-07-06 | [Fii 0714] Fii has provided on 7/14. [Fii 0707] There are 3 material which need sourcer to maintain price, due date:7/11 [ALT 0630] SKB is request the CS parts below for out of warranty STB . Please let us know the quotataion and lead time and MOQ. - Each part can be requested separately - LD1301, U301, U302, U303, U30, U307, L1001, T801, J801, U1402, D901, U1401, U801, U306, Q1001, Q1002, Q1103
Quality | FA report | FII | Close | 2022-07-06 | [Fii 0707] Factoy will check and reply. Keep updated. [ALT 0630] Issue up the BFX-AT100 defected units from incomming inspection end customer on 4/19, but Only the initial analysis was reported. https://mantis.cnsbg.foxconn.com/vaas/view.php?id=1484
HW | Test plan of shielding removal | FII | close | 2022-08-12 | [0331] According to FII Thermal test result of Android 12, it almost reach the higher limit of SKB Specification with Shield CAN. So if we removal Shield CAN, then thermal test result will be failed. So ALT decided to keep applying Shield CAN. [0303] SKB asked additional test for thermal issue. It needs test environment. So ALT is looking for Labs that can test Thermal issue for more than a week. ALT will decide whether ALT will keep trying to remove shield can or not after reviewing the cost and effort. [0224] It is very complicate situation. Current new housing has similar test result with thermal test without shield CAN. We should understand why new housing test has bad thermal test result before report it to SKB. ALT asked FII to explain the relation between Test result and Regin / SW change. [0217] SKB asked ALT to provide more test results. SKB request Data : Teperature of Top/bottom and SoC during below test condition. Log and failure analysis(ANR/Tombstone/Error etc) for each unit and test period. SKB Test condition : Multiview menu / PIP menu / Monkey Test / Stand by On/Off aging SKB requested Q'ty : above 10 pcs for with/without shield can SKB requested test time : more than a week ALT is checking the test cost. ALT will evaluate the effectiveness of cost reduction, includeing testing cost. ALT will inform both SKB and Foxconn after evaluation. [0210] SKB needs more time to decide. SKB concerned about SoC temperature. They think it may connect to VOC. So Foxconn should prepare Shield can for quantity on April. ALT will check SKB's status and update if they have any changes. [0203] Foxconn informed that it should be decided quickly for material preparation. But currently SKB needs time to investigate about the relationship SoC temperature and VoC rate. SKB is reviewing SoC temperature for both ours and INTEK's STB. SKB will update their decision or request about test. ALT thinks that SKB needs more time. Foxconn should keep using shield CAN before SKB makes a decision. [Fii 0202] ALT confirmed that it's no need to prepare the thermal test result for first MP SW version. SKB still concern about thermal increase after shielding can removal. They asked to provide thermal measuement during aging test. They will compare it wih INTEK STB. So, we need more time to get SKB's decision whether they accept the shielding can removal or not. [ALT 0120] SKB is in discussion internally. ALT will contact today afternoon. After contact, ALT will update when ALT get any update from SKB. [0113] ALT made supplementary document and submit to SKB. SKB will review and feedback to us. [0106] Thermal test with 15.502.43 can be tested on 1/30. Its CPU load is similar with 15.520.8. Foxconn provided its thermal test result for discussion with SKB without thermal test result. ALT will discuss with SKB based on it next week. But currently SKB didn't accept to apply no Shield CAN yet. [1223] Foxconn will CPU Load test with SW version 15.502.43 and feedback to ALT soon. INTEK SoC temperature is lower than ours. Foxconn will check with SW part the reason why INTEK SoC is not busy. ALT asked Foxconn to check that Foxconn disable the unused part(ADC, Audio DAC and Video DAC) [Fii 1222] 1. Have uploaded the CPU loading comparison report to ALT and it looks the CPU loading is still havey (90%) after VPN set and login SKB server. 2. INTEL housing has a lower temperature of the top/bottom case than Fii. We are reviewing the INTEK encloures with our thermal team and will provide our thoughts for ALT reference. [1209] Foxconn tested CPU load difference between DVT SW and the latest SW. It will be provided when it summarized soon. The DVT SW needs more CPU Load than the latest one. [Fii 1208] 1. Will use the FW provided by ALT to perform the thermal test for INTEK box. The test will be started from next Thursday (12/15). 2. Will prepare a comparison list to show the CPU loading between DVT S/W and the MP S/W. [1202] ALT asked to Foxconn about 2 things. 1. Why DVT Thermal test is not same as 2nd source Thermal test ? Please check it and explain why. 2. Thermal test result with INTEK with same test condition of Foxconn. Foxconn informed that they can test with INTEK STB last week. But currently Foxconn cannot test because Foxconn doesn't know where INTEK STB is. Foxconn use INTEK STB for mechanical review. After that Foxconn doesn't know where INTEK STB is. ALT ask to find it and inform the result by next weekly meeting. [Fii 1201] 1. The thermal chamber are full occupied by other projects until mid. Dec. Have asked QA team to pull-in the schedule and will keep ALT informed abuot the confirmed schedule. 2. The old software version that will be used for testing is 15.502.13 [1125] ALT asked to provide the plan for thermal test with INTEK STB. ALT will provide old SW version that DVT thermal test used. Link is as follows. https://drive.google.com/file/d/1xz1jR9QQMqmpp_52kYvz864BdFm6Q2eh/view?usp=share_link [Fii 1124] According to the vmstat result provided by ALT. It seems the result is different from what I expected because the CPU load of A10 (v15.522.9) is higher than A9 (v15.502.39), and it means the temperature of A10 should be higher than A9 but our thermal test result is just opposite. [1118] ALT asked the cost difference between with and without shield can. Foxconn's explanation is not enough. So ALT asked to provide the cost for Shield CAN components and thermal pads each. Foxconn will provide it to ALT Biz side. ALT provided test result to SKB in this week. Once ALT receive the review result from SKB, then ALT will feedback to Foxconn ASAP. [Fii 1110] The reliability test report has been provided to ALT on 11/7. Need ALT/SKB to approve for the change, and then Fii will arrange the control run & EC to implement the change. [1104] Foxconn can provide test report by next week. [Fii 1103] The test is in progress without any issues. It can be finished by 11/4. [Fii 1027] The reliability test of HFC & TIANMAI 1.5W Thermal pad has been started from 10/26, and will be finished by 11/4 [1021] ALT needs reliability test result. Foxconn will share test plan by today. If ALT has any question or request, then let Foxconn know. ALT didn't receive mechanical dimension information for 1.5W yet. ALT needs update cost information with final spec. Foxconn will inform it later.
SW/HW | Passive Standby | FII | Close | 2022-08-26 | [ALT 812] Eagle. Current SW has issues related to wakeup. It caused by ramdom timer in BL3.bin. Foxconn already received new patch from AML. It will test today. The boot issueis no ethernet after passive standby. ALT need test SW to measure Passive standby power consumption. Foxconn can provide after apply BL3.bin patch. SWAN - Wake lock, Currently Foxconn have SW issue on passive Standby. If LED is on, then Power consumption will be increase. ALT needs test SW. ALT will measure passive standby power consumption. Foxconn will let ALT know when Foxconn can provide test SW. [Fii 0811] Will need SW team update the status in weekly meeting
SW | Motorocom Eth disconnection issue | FII | Close | 2022-08-26 | [1028] ALT suggested to close this issue. If Foxconn asked to review Motorcomm issue again in Eagle, then it will reopen. [1021] Foxconn will not investigate anymore for eagle. Foxconn will use Motocomm PHY for next gen. eagle. [1014] ALT can reproduce this issue with ECO that FII proposed. ALT shared the video clip on mantis how ALT can reproduce it. [1007] ALT is trying to reproduce this issue with auto test environment. But ALT cannot reproduce it for a week. ALT is trying to find the sequence of reproduction. Test condition (connection/disconnection time, minute) : 5/10, 5/3, 1/1 with 3 units. [0930] ALT tested again without rework and reproduce the issue after 5 days test. ALT set up auto test environment today. ALT will start test from today. But ALT cannot sure Foxconn's solution even though the issue cannot reproduce during the teset. To confirm the solution, ALT needs technical explanation why Foxconn's solution can solve the issue and what the root cause is. [Fii 0929] Any update from ALT about the test result of rework solutions provided by Fii? [0923] The rework guide is not the same as before Foxconn asked ALT to test. ALT will check the guide and try to test it. If ALT has some question on your test and rework guide, then ALT will leave some comments on Mantis. [Fii 0922] We will provide hardware rework to ALT reference. Can ALT check to see if the reproduction rate can be improved? [0916] Foxconn didn't finish the review of this issue yet. But ALT cannot apply 2nd source when 2nd source Eth PHY has some issue. ALT tested with SWAN but ALT cannot reproduce with SWAN. So ALT will check SWAN after enagle debugging result again. [ALT 0812] Foxconn add some log and released test SW. And Foxconn tried to reproduce this issue, but failed. ALT thought that Foxconn didn't test it enough. It need to test more than 3 hours. ALT tested with different 3 STBs. but ALT can saw the issue. Foxconn should increase test time. ALT will test with new SW and feedback it by 8/16. [Fii 0811] Will need SW team update the status in weekly meeting
| GPIO Setting voltage |  | Close | 2022-11-25 | [Fii 1124] 1. Fii has provided GPIO value of Eagle/SWAN via e-mail. Please kindly review it. [1118] ALT provide an e-mail to check the GPIO setting voltage. Please check and support us with your HW/SW for both SWAN and Eagle
HW | Thermal test(component level) for Android 12 | FII | Close | 2023-02-28 | [0428] ALT will check it whether it can be closed or not later. [0331] SKB informed that they will check the final status of new housing in MP Stage. They will check it mid of April when ALT will deliver first MP units that use ABS housing. [0324] ALT submitted Test report to SKB. SKB is reviewing it. [Fii 0323] The comparison table and formal reliability reports has been updated on mantis 1617 on 3/21. [0317] Foxconn will provide Thermal test result as follow. A10+PC(3/17), A12+PC(3/20) And Foxconn will provide test report by 3/21. [Fii 0316] Fii will arrange additional two thermal test PC+ATV10 & PC+ATV12 and provide the report for ALT review by 3/21. [Fii 0309] Fii have updated some thermal test result on mantis, and will continue to discuss this issue with ALT on mantis 1557. [0303] Based on FII comments, A12 spend 7% CPU load more. But according to FII test result, CPU with A10 temperature is lower than A12. It is not make sense. We should explain why A12 and ABS temperature is higher than A10 and PC-ABS. So please provide your test report and your analysis result. There is no error log during test for A10 and A12 SW version. So we don't need to check the CPU abnormal load due to network connection error. [0224] ALT asked Foxconn to explain test result based on resin and OS changes. But there is no feedback from FII by 2/24. [Fii 0223] The report has been uploaded on mantis on 2/20. Need ALT/SKB to confirm whether the ABS material change with ATV12 is acceptable or not. [0217] ALT informted that SW for test is v. 15.537.8 before. And test schedule will be update on Mantis toady by Foxconn. [0210] SKB asked all manufacturers to test thermal test with Android 12. So ALT should provide it to SKB. Foxconn will conduct Thermal test with Android 12. ALT already provide new SW version information(v15.537.6) for test on mantis#1577. DUT should have Shield can.
ME | BI Change | FII | close | 2023-02-28 | [0512] Foxconn VN received it on 5/5. [0508] ALT sent it via fedex, 7720 4010 5290 on 5/4. 中, 下 are only approved. [0428] Foxconn will provide exact address for recipient. ALT will send approved samples to recipient. [ALT_0425] ALT will provide feedback about 上, 中, 下samples after checking it with the customer. [0331] ALT will review FII's 上, 中, 下samples for tolerence check. [0224] ALT is reviewing the document. But there are some attached documents in the last page. We cannot see it. [0217] Miya will check and reply next week. [0210] ALT asked Foxconn to provide change list for ABS mechancal design for ABS.(mantis#1557) Foxconn will provide the cost difference information by e-mail. Foxconnn will check ALT's other requests and feedback by 2/14 or 15
HW | LED lifetime | FII | close | 2023-04-28 | [0428] SKB is discussing internally. There is over 70K defected units include LED defects in SKB ware house. ALT will check that those defected unit is LED defect or not. And if there are LED defected units and other defected units in warranty, then ALT will send it via RMA process. [0414] ALT met SKB engineers on 4/13. ALT submitted the data for LED Life time. SKB will review and they will make questionnaire if they have. ALT will forware it once ALT receive. [Fii 0413] 1. According to ALT Mr.Yoon, there are some LED defected units return from the field and the LED color change to pink color while user watch IPTV and the R/G/B turns on in the same time. Fii have replied ALT that the LED life prediction report is based on physical characteristics, and it can not be improved unless the brightness time and box temperature are reduced. As LED is almost always on, if color deviate occurs after about two years, the only solution is to replace the LED. 2. For the type of chip LED used in Eagle is the higher grade of life time type. For normal chip LED component, the L50 life time is about 2-3 years.
HW | Reliability test of short term solution about PC mold with ABS | FII | Close | 2023-05-05 | [Fii 0518] The reliability test report has uploaded to mantis 1708 on 5/16. The report has reviewed and confirmed by SH. [Fii 0511] * Pancil hardness test - pass * Logo/print abrasion test -pass * Drop test - pass * Vibration test random (Op) - pass * Shock test (Op) - on-going The reliability test report can be released by 5/16 0508] Reliability test report release date ? [Fii 0504] Update reliability test plan as attachment. The whole test will be completed by 5/12. [0428] ALT asked Foxconn to keep update reliability test status. [Fii 0427] ALT confirmed the reliability test items on 4/26. Fii will arrange 6pcs housing samples from NWE to RD office. The samples ETD is 4/27 and ETA is about 5/2. Will update the schedule to ALT once received the housing samples. [ALT 0424] Reliability Test items : ALT will feedback by 4/25 [Fii 0421] 1. For the IR test and chassis static load test report, ALT has sent 4pcs top case samples to Fii RD office on 4/21. If we receive the samplpes by 4/24, we will perform the test and prepare the report to ALT on 4/25 Fii will update the following status to ALT when we get a confirmed delivery schedule from the supplier NWE. 2. For the reliability test items required by ALT, Fii think some of the test items can be waived. Fii will provide the comment to Sales Miya, and then Miya will discuss with ALT Biz team about the test items first before starting the reliability test. [0418] PC mold with ABS. - Reliability test: 4/24(Mon) ~ 5/5(Fri) - Target date for providing the reliability test report: 5/11(Thu) - Remarks: We need to submit at least the report for the IR test and Chassis Static Load, so please provide those reports by 4/24(Mon) for approval.
HW | Reliability test of long term solution about New mold for ABS + ABS material | FII | close | 2023-05-26 | [ALT_0615] OK. There is no issue on the reliability test report. [Fii 0615] Fii have provided the RDT report on mantis 1617. [Fii 0608] The three RDT test items are passed. Fii can provide the report by 6/12. [ALT_0602] Ok, please let us know the test schedule. [Fii 0601] ALT just received the new housing samples o 6/1. We are checking with the QA team to schedule the 3 RDT testing(logo printing abrasion, pancil hardness, chassis static load). Will update Fii's test plan when received QA team's feedback. [ALT0526] Please send 上 中 下sample to ALT ASAP. [Fii_0525] 0524 inject sample: over glossy,texture is similar as golden sample. but there are some scratches on the high-light side. 0525 inject sample: improved scratches. silk print will be finished on 0526 and sample will be sent on 0526. Miya will share tracking no. later. [ALT_0519] Based on the Fii's update, there are some issue(Gas mark, over glossy) on the trial sample at NN. Factory are working on it for improvement and will update the status. [Fii_0518] 5/18's sample still has issue. Miya will summary the issues and send to ALT on 5/19. If schedule would be delayed, Mr JW is also check with SKB if old mold could be used for Jun's MP. [0512] There was some issue on Trial injection in Dongguan. There were Gas mark, weld line(side) and the high glossy on top. So Vendor will have another trial today. ALT asked that Foxconn should make new reliable schedule for sample trial and MP first, and then ask ALT to make a plan for biz trip. [0508] According to FII plan, which one is correct ? And what is the ETA of samples in Korea ? - The new tooling schedule: 4/13~5/9. - The new tooling deliver to NN: 5/11-5/13 - Sample build: 5/14-5/16 - Housing sample printing & assembly: 5/17-5/18 - Housing deliver to ALT&TW: 5/18~5/23 - Reliabilty Test: 5/23~5/31 - ALT Confirm New Tooling housing: 5/23~5/24 [Fii 0504] Updated schedule as below, - The new tooling schedule: 4/13~5/9. - The new tooling deliver to NN: 5/10-5/11 - Sample build: 5/12-5/16 - Housing sample printing & assembly: 5/17-5/18 - Housing deliver to ALT&TW: 5/19 [0428] ALT informed that they cannot dispatch their engineer to approve the sample due to VISA process time. So Foxconn will send it to ALT via express service. [Fii 0427] ALT confirmed the reliability test items on 4/26. - The new tooling schedule: 4/13~5/5. - The new tooling deliver to NN: 5/7-5/8 - Sample build: 5/9-5/10 - Housing sample printing and deliver to ALT&TW: 5/11 [ALT 0424] Reliability Test items : ALT will feedback by 4/25 [Fii 0420] For the reliability test items required by ALT, Fii think some of the test items can be waived. Fii will provide the comment to Sales Miya, and then Miya will discuss with ALT Biz team about the test items first before starting the reliability test. [0418] New mold for ABS + ABS material - Reliability test: 5/16(Tue) ~ 5/26(Fri) - Target date for providing the reliability test report: 6/1(Thu) - Remarks: We need to submit at least the report for the IR test and Chassis Static Load, so please provide those reports by 5/16(Tue) for approval.
HW | LED DATASHEET | FII | close | 2023-05-05 | [ALT0526] Please don't make the same mistake again. Fii should follow the standard procedure to prevent the mistake occurred. [Fii 0525] Fii have sent RD report for LED symbol mismatch issue on mantis1129. [0519] ALT wants to get 8D report for the issue on wrong LED Lib. use for schematic diagram. [Fii 0518] Fii will update the Fii formal 8D report on mantis 1129 on 5/18. [ALT_0515] ALT will check the material on mantis and get back to you if there is any question or so. [0508] Foxconn will provide revised circuit diagram and 8D report by 5/12. [Fii 0504] Fii have replied it on mantis 1129 on 5/4. [0428] LED pin assign is mismatch with schematic and datasheet. - in schemetic, LED VCC is Pin 4. but LED datasheet LED VCC is Pin 1 https://mantis.cnsbg.foxconn.com/vaas/view.php?id=1129#c13028 ALT asked Foxconn to check, and Foxconn will check it and come back soon.
HW | Request for cooperation to reduce cost of Eagle | FII | close | 2023-05-11 | [ALT_0105] this topic will discuss in PM&Sales (2nd source implementation) [ALT_1215] Will arrange another meeting to discuss it. [ALT_1201] Will discuss this topic while ALT travel to TW (12/4~12/5) [ALT_1124] We will reply the TP by next week. [Fii_1123]Please let us know the target price first. [ALT_1117] Please provide the cost down solution of 2024 to meet ALT's target price. [Fii_1116]Fii is keeping cost down for one year. 2024 will keep doing that. [ALT_1110] Fii-ALT have to improve competitiveness on the unit price of next year. Thus, please consider and propose other suggestions(except for cables). ALT thinks we can't see the last proposal to have much effect. [Fii_1109]Please update [ALT_1013] Will feedback by next week. [ALT_1006] Will do the internal review then feedback on our opinion. [Fii_1005] Done [ALT_0922] Fii reply that they will send it out by next week. [ALT_0908] We will reply it by early next week. [Fii_0824]According to discussion with ALT's sales, will reply by 8/31. [ALT_0818] When can we get the Non QVL materials cost? Please feedback to us ASAP. [Fii_0817]Fii will check the total cost and talk to ALT's Biz team. [ALT_0811] Please check again whether Fii can provide cost information, even grouped costs. And it would be appreciated if you understand the purpose of our request is for Fii-ALT to win the next bidding. [ALT_0804]We are currently in the process of reviewing the parts, and once we receive feedback from SKB, we will promptly inform Fii. [Fii_0804]Fii provided data sheet to ALT. please let Fii know when will get prove from SKB. [ALT_0714] ALT will send e-mail about technical information share policy. ALT cannot accept any components change without any information related to new components. SKB asked that the data sheet compare for the ECO and its evidence. ALT cannot confirm to SKB about the performance of any HW changes. [Fii_0706]According to Miya's mail, sample fee or certification fee is NOT included. Mr JW said ALT wants to test all of these second source(Fii recomend and ALT recomend) together. [ALT_0630] If can't share the datasheet to ALT, ALT can't feedback any comments on cost down issue. If only cost down $0.3 please check if sample fee or certification fee is included. [Fii_0629]Replied by 6/28. [Fii_0615]E-mail has been sent by 6/13. Fii will reply Mr Yoon's e-mail about 2nd source which are recommended by Fii. [ALT_0609] Add additional proposal in the cost reduction part list from FII. Please provide the total cost reduction plan to ALT review by 6/9. What if cost reduction plan has some risks on the ALT side, need to share the information with ALT first then can discuss it later. [Fii 0608] 1. Fii have surveyed RJ45 2nd source based on Fii QVL vendor list(CZT, LIYANG, YUQIU, Powerway) one month ago but couldn't find a suitble part yet. 2. Miya will provide the cost gap information to ALT biz team directly. [ALT_0602] 1. Please check and suggest other candidates of RJ45 on your side. 2. Please provide the cost gap nformation except for RJ45. [Fii 0601] Have updated the review result of connectors on mantis1717. They are ok to use except RJ45 connector. Need ALT to provide more comment on RJ45 if any. [ALT0526] ALT uploaded 3D data on Mantis(#1717) [Fii 0525] Have updated Fii comment and feedback to Lonnie on 5/22. Need ALT to upload the 3D file of connectors(RJ45, USB3.0, HDMI) to Mantis directly since our ME is unable to open the file from PPT. [Fii 0518] Have received the feedback from Loonie. Fii is reviewing the comment and document, and will reply ALT by 5/22. [Fii 0511] ALT provides components change doc. of Egale for Fii reference. Fii will review the document and provide the preliminary feedback to ALT by 5/12. Fii will provide which component can be changed or not and the reason to ALT if it can not be used.
ME | Mold Transfer | FII | close |  | [Fii_0629]After checking with supplier, we decided not to keep making housing in NN. [ALT_0616] when you have the conclusion of the mold transfer date, please share it ALT first [Fii_0615]Fii is still checking the feasibility of mold transfer, and will reply after internal discussion. [ALT_0609] It is not decided whether FII will move mechanical part production site. Foxconn will share the decision whether they will move ME parts production site and the schedule if FII decide to move the site by 6/14. [Fii_0608]Fii is checking schedule and process of mold transfer to VN. Miya will reply by mail on 6/14. [ALT_0602] Please provide the milestone about mold transfer to VN.
HW | Introduce new LED component | FII | OPEN | 2023-10-20 | [ALT_0426] Before LED EOL, We may have some extra orders. Will discuss this issue before the end of this year. [Fii_0425] So far, base on last meeting conclusion with Everlight. The deadline for LED PO is 12/31/2024. I think maybe our buyer will negotiate with Everlight in Q4 again if 2025 Eagle demand from ALT is much clear. [ALT_0419] About 2025 Eagle production, what is the deadline for placing LED PO? Please advise. [Fii_0418] Yes. Everlight postpone the EOL date to the end of 2024. ALT can purchase extra LEDs with MPQ 2K at least. [ALT_0412] Please check with Everlight if possible to purchase extra LEDs, and the possible MOQ Q'ty. Please tell us about 2025 Ealge production plan with LED issue. How do you want to prepare the LED for Eagle? Please advise. [Fii_0411] 298K LEDs were shipped to ALT by 4/2. [Fii_0328] LED just arrived HK today, will check the shipping information and update to ALT by Wechat once we confirm the schedule. [ALT_0328] Please share the shipping information to us, thank you. [Fii_0325] After checking with Everlight, their ETA HK date is 3/28. We will arrange to ship to ALT once we receive them. [ALT_0315] The delivery ETD was 3/25, if there is any change please let us know. [Fii_0314] Fii will pay for the logistic cost. Will inform ALT once the shipment is arranged. [Fii_0229] The logistic cost is around US$200. Will discuss with our FI for it internally. [Fii_0222] Everlight only agree to ship the LED to HK. We are evaluating the logistic cost now. [Fii_0215] Our buyer is negotiating with Everlight now. [ALT_0202] The rest 298K shipping cost should be borne by Fii or Everlight. Please figure it out, thanks. [Fii_0201] 2K LED has been shipped to ALT on 1/31 by ALT Fedex account. We have one more question is how to ship the rest 298K from HK to ALT on Mar.? May ALT help to handle the logistic from HK to KR? [ALT_0126] We will provide FedEx account for this 1 reel LEDs delivery only. will reply via email. [Fii_0125] After checking with Factory, we can ship 1 reel LEDs to ALT. Please help to provide your Fedex or DHL account, then we can arrange the delivery through it. [ALT_0119] Please ship 1~2 reels LEDs ASAP, if we receive the 1~2 reels first then the 3/25 shipping schedule is fine with us. [Fii_0118] The shipping schedule feedback from Everlight is 3/25. Their feedback is with Chinese. For the 1 or 2 reals LEDs, we will feedback later. [ALT_0112] As far as Fii shared via WeChat, estimated shipping schedule would be on the end of Mar. Please provide that information officially. And could you please check if you could provide the 1 or 2 reals of Everlight LEDs first in order to set up the RMA line in Korea? [ALT_0105] Please check with Everlight when can ship out 300K LEDs(RMA) ASAP, we can accept the partial shipment as well. [Fii_0104] Everlight didn't feedback yet. Our buyer is checking the LED delivery date as well. Will feedback to ALT once we get any response from Everlight. [ALT_1229] Please feedback to us about 300K LEDs (RMA) delivery date ASAP. We need to receive it by end of Jan if possible. [Fii_1228] As Eagle 600K demand in 2024 + Fii shall deliver 300K LEDs to ALT for RMA repair + Fii preparation LEDs, the last time buy PO to Everlight is more than 1M pcs. After the F2F meeting between Foxconn and Everlight, we spent a lot of efforts to convin them to accept our PO and ship base on our requested date. So far, Everlight agree to extend the EOL date until the end of 2024. [ALT_1222] Will provide a feedback on 2024/1/5. [ALT_1215] We are still in the reviewing process and will feedback to you once we have any conclusion. [Fii_1214] As our reply by mail on 12/11. Any feedback from ALT? [ALT_1208] Please reply Mr. Yoon 12/8 mail request and will discuss it later. [Fii_1207] Provided actual test brightness and location result after reducing current(1.8/1.8/1.8mA), Fii also provide 2 DUTs and LED samples to ALT after tuning resistors. Harvatek feedback that they can't make sample of current brightness(AVG:197.8mcd), the only way to reduce brightness is to change the resistors. [ALT_1201] Will discuss this topic while ALT travel to TW (12/4~12/5) [Fii_1130] Please check our feedback on mantis and wechat, Fii doesn't suggest decrease brightness as ppt file. Fii can request Harvatek to increase the number of samples actually tested and get a more similar result as Everlight. Can ALT accept it? [ALT_1124] We will comment this issue on mantis, please check on mantis and give us the feedback. [Fii_1123] Please check our comments and datasheet on mantis and wechat. let us know if ALT agree current brightness and color. [ALT_1117] We need the revision datasheet from Harvatek and will provide feedback and comments on mantis. [Fii_1116] Fii provide brightness and CIE location comparison between Harvatek 2/2/2mA LED and Everlight 7/7/5mA LED on mantis #1823, we also upload 1. minimun turn on current and 2. IV chart on mantis #1823. Let us know if you accept it or need more DUTs for approval. [ALT_1110] ALT tested the LED with Fii modification. The brightness is adjusted, however, sometimes the LED is off during the test. Please provide 1. the minimum ture-on current and 2. IV characteristics chart. [Fii_1109]: The summary of report is that the life of this LED can reach 50000hr/L50, so Harvatek feedback that the summary includes white and other mixed light. Harvatek suggest us to reduce LED current from RGB: 7/7/5mA to 2/2/2mA so that we can achieve brightness similar to Everlight, and the result photo uploaded on mantis #1823. [ALT_1103]: We will review the sample and feedback to you later. mantis 1823 report did not include the white color lifetime test report, please request vendor to provide white color lifetime test result. [Fii_1102]: We reply LED status on mantis 0001823 and also upload: comparison table, Havatek LED test items and datasheet. Please help to check. [Fii_1102]: ALT/SKB need approve it before 11/9 to Fii, Otherwise, there is a risk that the LED will be used up and unable to be shipped. [ALT_1027] We will provide drop test conditions by today. We would like to receive the test report first and then check the sample if is qualified. Please also inform us what is the expected date for implementing this new LED component [Fii_1026]Harvatek feedback that need ALT provide test condition for drop test. Fii have provided sample device for ALT to confirm the LED color. [Fii_1019] Fii Collating Harvatek’s feedback and will provide it to ALT reference tomorrow (10/20). Harvatek will confirm the test fee with the testing lab and get back to Fii. Fii sales will try to ask harvatek to pay the testing fee. [ALT_1006] Will review it and feedback by next week. ALT never paid any changing component test fee before can't understand why changing new components and relative test requests ALT to pay. [Fii_1005] Update Harvatek test items as attached. Need ALT to review it and feedback the comment. [Fii_0928] Harvatek has updated test item. Fii will confirm it and reply to you before 10/4 [ALT_0922] Will mail you about what kinds of test reports we need by today. [Fii_0921] Attached is Harvatek's company information, Harvatek can't provide PPT page with major customers due to confidentiality agreement, but they reply Google, HP, DELL, Amazon, Nintendo, Microsoft etc. They are all their customers. [ALT_0918] Please provide Harvatek's company information, including income, employees, main items and lineup and reference, major customers, etc. And ALT will provide our requests regarding the LED with Fii by this week. [Fii_0914]Harvatek LED uses insulating paste material, insulating paste LED will not cause metal migration problem. We are working with supplier to fine tune the color. Will provide the datasheet to ALT reference when the color tuning is confirmed by the supplier. [ALT_0908] Please provide the product datasheet. Also, if this alternative material has the same problem, what is the corresponding countermeasure? Please let us know. [Fii_0907]Fii will try to introduce Harvatek LED, the reason as below: 1.Color is close to Everlight. 2.Bin code has been adjusted to be almost the same with Everlight. 3.Price is lower than Everligh. Fii has requested Everlight to provide samples with the upper, lower and middle limits of bin codes, the purpose is for Harvatek to accurately produce parts with the same color/brightness as Everlight.
HW | TV screen shake FA Report | FII | close | 2023-09-15 | [Fii_1228] Uploaded 8D report on mantis 1703 [ALT_1222] Closed [Fii_1221] Amlogic had found that the root cuase was VPU module abnormal, Here is AML test report, Fii SQE team will provide 8D report after reviewing. [ALT_1215] Please share the test result when you receive it. [Fii_1214] Amlogic feedback that there will be no report on MBIST test, only the result of pass or fail. For next plan, Amlogic will keep do stress test by reduce VDDQ voltage and verify whether VPU function is normal. Fii also request Amlogic provide test report for these weeks on 12/15. [ALT_1208] Please share the MBIST test report and the Amlogic next test result with us. [Fii_1207] Amlogic feedback that stress test is pass, they are doing stress test after reducing voltage now, so far is normal too. for next plan, Amlogic will reducing frequency to do stress test again. [ALT_1201] Please update the Amlogic SH testing schedule to us. [Fii_1130] Amlogic feedback that MBIST and Scan chain's result are normal, they will send NG board to Shanghai for doing stress test. [Fii_1123] Amlogic reply that they will do MBIST and Scan chain test on 11/24, and will provide test result on next week. [ALT_1117] Please keep update the status. [Fii_1116] Fii provide AML FA report on mantis #1703 previously. Next plan: Amlogic reply that NG SoC is shipping to wafer factory for further analysis(MBIST, Scan Chain test). [ALT_1110] Please provide the AML FA report. [Fii_1109] Amlogic is analyzing now, it seems to be an abnormal in the function module(maybe decoder module). Amlogic are assessing whether to set up a test station to filter NG SoC. The results will be updated to us later. [Fii_1102] Amlogic are analysing now, they reply due date is 11/3 and will update to Fii ASAP. [Fii_1025] Amlogic feedback that they find TV screen shake on screen display, also do issue analysis now. Fii will keep tacking Amlogic to provide test plan or test results next week. [Fii_1019] Amlogic just received NG board today(10/19) due to customs clearance issues. Will provide ALT the test plan and analysis report next week. [Fii_1012] Amlogic Shenzhen RD will receive NG board before tomorrow, Fii will request Amlogic to provide test plan and analysis result before next week. [ALT_1006] Please update the analysis report from Amlogic [Fii_1005] Reduce VDDEE voltage to 0.81V and 0.80V which can solve TV shake issue, Fii will ship NG board to Amlogic Shenzhen, Amlogic will verify NG board and provide test plan after receiving. [Fii_0928] NG SoC has shipped to our MFG and also show TV screen shake. AML recommand that we set VDDEE voltage from 0.86V to 0.80V for confirm whether it is cause by VDDEE voltage is too margin. Current testing shows that reduce VDDEE voltage to 0.81V can be improved. Fii will clarify the root cause with Amlogic. [ALT_0922] Keep updating the information to us when AML & Fii have some new finds out. [Fii_0921] Fii upload AML test report on Mantis #1703,attached is test report and No.2 is TV screen shake SoC. Summary shows #2 only FT fail but the reason is IC encryption, so Amlogic reply this SoC is normal SoC not a NG SoC. We will discuss with Our QA and Amlogic QA about why the analysis results are different. [ALT_0918] Please share the updates if Fii got the AML's test report or any updates. [Fii_0914]Amlogic will provide test report before 9/15
SW | SW Source code issue | FII | CLose |  | [ALT_0202] OK. [Fii_0201] We think this issue can be closed. It can be combined to "Google test environment" of PM&Sales sheet. [ALT_0126] We are preparing the build environment. We are trying to build now, if there are any issues will let you know. [Fii_0125] The test tools were sent to ALT by 1/19. [Fii_0118] The test tools will be sent to ALT by next week.Just waiting for our top manager's signature for this. [ALT_0112] 1. We would like to ask again the Fii for proceed with smoothly the technical support without any other issues mixed up, which is not related. 2. ALT already paid 2024Y NRE, which include the Google test tool, set-up envinorment, and build key. 3. Please help to Fii support technical side immediately. [Fii_0111]As RMA cost is overdue, Fii team locked this process. Fii need to explain to FI team. [ALT_0105] ALT is preparing now. But currently, SKB keeps opening their bitbucket to FII temporarily. Please keep building FW before SKB closes it. Before closing SKB's port, we should set up our build environment. So please provide the Build key and support us in preparing the environment until it is complete. [ALT_1222] Will provide ALT's feedback on 2024/1/5. [Fii_1221] When does ALT need Fii to provide build-key? [ALT_1215] ALT will provide the build server information to Fii, please let us know if have any issues [ALT_1208] ALT will do the internal discussion and feedback it later. [ALT_1201] Will discuss this topic while ALT travel to TW (12/4~12/5) [ALT_1117] Still in the internal discussion, will feedback later. [ALT_1110] ALT're still discussing internally about Fii opinion on F2F meeting, we'll provide our feedback via email by next week. [Fii_1109]discussed via F2F meeting. [ALT_1013] We are still waiting for Vincent's official mail. [ALT_1006] Please ask Vincent to reply to the official mail to inform ALT that the Foxconn SW source code can not be shared. [ALT_0911] Please arrange SW people to join the 10/6 meeting (KR 10:00AM) to discuss the open source code issue.
ME | Eagle ME parts description | FII | close |  | [ALT_1027] If have other questions will send mail to you. [Fii_1026] Have provided feedback to Lonnie on 10/23. [ALT_1020] Please review Lonnie's email request and provide feedback by early next week.
SW | Netflix certification | FII | Close |  | [Fii_0425] Netflix Certification Letter was sent to ALT on 4/23. I think this topic could be closed. Thanks! [Fii_0418] Netflix feedback that The “Revenue share” is not setup yet so they cannot issue the cert letter. So the gating is on business. SKB should know it well. Please notice that. [Fii_0307] Netflix certification passed on 3/4. Waiting for official approval letter. [Fii_0229] Fii had completed Netflix pre-test with v15.542.8 on 2/27. We submit the test result for this version to Netflix on 2/29. Then will provide 2 sets of Eagle(with 2 RCUs) to Netflix TW on 3/1. [Fii_0222] Fii will use v15.542.8 version to do the Netflix pre-test. The target to complete all test cases is 2/27(Tue.). [Fii_0215] We have received the new RCU and use them for Netflix test. Will update the test progress continuously. [ALT_0202] SKB will decide which RCU will use for Netflix certification, we will let you know the result by today. Also please provide the test result and documentation preparation stuff to us. [Fii_0201] We are waiting for new RCU. At the same time, Netflix add new test cases on 2/1, we are testing them and will update in the progress report on 2/2. [ALT_0126] Keep updating the test status for both items. 1. For Automated + manua + Eye Patch 2. ADHOC [Fii_0125] Check the latest progress report. [ALT_0119] SKB thinks that Nexflix certification should start in early February and try to release it in early March, so the certification needs to be completed by the end of Feb. [Fii_0119] So far, there are still 10+17 bugs left for Netflix test. Will continue debugging with AML together. [Fii_1228] Netflix 4K content issue has been resolved by AML by 12/28. Our QA will start Netflix test with Fixed mode immediately. [ALT_1222] 1. Regarding the HDR UI test, please let us know how long it takes the test by this week. 2. Regarding the Netflix 4K content issue, please check and let us know if it runs in Fix mode by this week. [AVL_1221] Fii start the pretest with Real mode first. Need to resolve the Fix mode issue for Netflix test ASAP. [ALT_1215] ALT provided the additional VPN account information to Fii, please let us know if have any issues via WeChat NETFLIX group chat. [ALT_1208] Please update the current status to us. [ALT_1201] Please send us the detailed development schedule plan first and the NRE will discuss it while ALT travel to TW [ALT_1124] Please push Fii's Netfilx contact window and get the reply ASAP. [Fii_1123]Netfilx's PDM has not replied us yet. will update after Netflix replied. [ALT_1117] Please ask SW RD to feedback detailed schedule and Netflix MM workload by early next week. [Fii_1116]SW RD will reply about the schedule by 11/22 [ALT_1110] Please review Mr. Yoon's email on 8th Nov and provide Fii's feedback. [Fii_1109]Sent [ALT_1103] Will reply the mail by next Monday about Netflix MM workload & quotation. [ALT_1027] Please share the Netflix certification plan and Netflix meeting results with us.

## HW &ME
Category | Issue | owner | status | due date | Progress
HW | AMP board layout review by EMC engineer & H/W RD | Fii | close | 2021-03-15
ME | Final ME 3D drawing. For ME/ Package/ HW review | ALT | close | 3/16=>3/19 | [ALT] We will provide it by 3/19 [Fii 0317] When does tooling start? We'd like to review before then. Is the T0 tooling schedule impacted? [ALT 0317] Tooling will start in WK3/22 and no impact on the schedule. [ALT 0319] Will push for the final drawing today.
ME | Part List of housing & speaker and updated designation letter for new parts | ALT | close | 3/19=>3/22=>3/31 | [Fii] Need to register PN and issue EC [ALT] We will check it with INKEL when they can prepare. [Fii 0319] Need the data no later than 3/22 or the schedule will be impacted. [ALT 0401] Inkel is preparing it and will check it with Inkel today. [Fii 0401] Plz provide the data on 4/6. The time left to Fii internal process is less and less. [ALT_0402] INKEL will provide it by 4/5. INKEL said that there is no additional parts, but some parts should be removed. [Fii 0406] Receive and ME is reviewing the parts that need the designation letter.
HW | AMP board DFM review by MFG ME | Fii/ALT | close | 2021-03-17 | [Fii] will send out the file for ALT to review and modify for factory review DFM again.
ME | Final 2D drawings for all parts for IQC inspection and the defined critical dimension | ALT | close | 3/19=>3/31 | [Fii] Need update in the system when applying for PN [ALT] We will check it with INKEL when they can prepare. [ALT 0326] Inkel is preparing it and will check it with Inkel today. [ALT 0401] provided already.
ME | INKEL needs to review the ME design to reduce the assembly process | ALT/Fii | close | 3/23=>3/26=>4/7 | [ALT] If you have any idea, please let me know. Do you have any idea to reduce to assembly for B'd side ? [Fii 0318] The factory will provide the DFx on 3/18. Fii will internally review with ME from 3/19. The advice will be provided by 3/23. [Fii 0323] the factory will update DFM based on ALT updated 3D drawing and internal review by 3/26. [ALT 0402] 3/26 DFM Feedback : not acceptable due to tooling started center(PCBA) area. this is too late. Don't change LED board connector direction (3/30 replied on mantis).
HW | Acoustic testing equipment needs to improve the isolation effect | Fii | close | 2021-03-19 | [Fii] Vendor provided the new pressing material to verify again after DVT2. [ALT 0318] Could you explain what problems you have.
HW | FIT RJ45 connector for Wired Network Authentication | Fii | close | 2021-03-19 | [Fii 0323] informed FIT to proceed with certification
HW | Thermal test with new AMP board | Fii | Close | 2021-05-14 | [Fii 0524] Update HWQA formal report on mantis on 5/24 [Fii 0520] Need ALT/SKB to confirm the final test condition, and then Fii HWQA will provide the formal test report to ALT reference. [Fii 0514] Update the thermal test result in 70% speaker volume (sealing rear venting hole) At 25degC ambient: temperature of housing top & bottom are 34.9degC & 45.3degC At 50degC ambient: temperature of housing top & bottom are 59.3degC & 69.2degC Update the thermal test result in 70% speaker volume. At 25degC ambient: temperature of houng top & bottom are 34.8degC & 43.4degC At 50degC ambient: temperature of housig top & bottom are 58.9degC & 68.8degC [ALT 0513] Update the thermal test result in 50% speaker volume. 1. All of the components and housing surfaces are passed the criteria @ 25degC & 50degC ambient. 2. At 25degC ambient: temperature of houng top & bottom are 33.7degC & 44.5degC At 50degC ambient: temperature of housig top & bottom are 58.7degC & 68.2degC [ALT 0511] Fii rework housing and do the thermal test from 5/12, will get result on 5/13. [Fii 0507] Our QA team confirmed that the thermal test can be started from 5/12 [ALT 0505] Expected to ship out on 5/5. [Fii 0430] Will perform thermal test once receive the housing & new speaker samples and need ALT to fix the thermal solution within WK 5/3. Otherwise the heatspreader tooling schedule will impact MP [ALT 0430] The housing*2 and speaker will be shipped out on 4/30. ALT will also reply the thermal solution on 5/3. [Fii 0428] Will simulate again based on the same condition with additional venting hole, and see if housing surface temperaure is improved or not. [Fii 0426] Reduce 50% speaker volume, the total AMP power changes from 7.7W to 4W, no additional venting hole, both AL & VC HSR @ 25degC & 50degC ambient can pass criteria of all components but the housing surface are still marginal fail. [Fii 0423] Fii will do the simulation based on ALT proposal again. [Fii 0416] The simulation report was provided and need ALT to advise. [Fii 0413] To evaluate chaning of the material of heat spreader/ die-casting from Aluminum to Copper, and consider the VC (Vapor Chamber) cooling method to see if there is any improvement. Will provide the updated simulation report to ALT by 4/15. [Fii 0412] Have provided the update simulation result to ALT. The key components are still fail @ 50degC ambient but the temperaure of the parts on AMP board is indeed lower than the previous results. [Fii 0409] Will start the simulation on 4/9 and expect to provide the report by 4/12. [ALT 0408] Need Fii to do the simulation with ALT proposed solution first then consider Fii proposed solutions to reduce the ambient temp., reduce the watt, enlarged vent holes. [Fii 0407] Have provided an explanation of the power dissipation difference between EVT and the new AMP board for ALT reference. Need further discussion with ALT for the thermal issue. [Fii 0406] Need the concall for discussion. Checking the time slot on 4/8. [ALT_0402] When FII will start to discuss ?
HW | new design AMP board samples & speaker *13 sets for HW EMC/Thermal & SW | ALT | close | AMP:3/19=>3/31 SPK:3/19=>4/23=>4/26=>4/29 | [ALT] AMP board ETD KR 3/31 and the material status is under checking. On speaker, Dreamus will provide it by the end of April. So we will use current Speakers for test for HW, not acoustic feature. [Fii 0317] Need the speaker together to do the EMC and thermal. If ALT decides not to do any EMC/ thermal test before DVT3, plz send a formal email to confirm. [ALT 0317] 1st lot of speaker is 60cs pn 4/23. Fii may provide the risk statement for ALT to confirm. [ALT 0319] AMP board ETD KR still 3/31 [ALT 0401] No any verifications done before shipment. =>ALT shipped on 4/1. [Fii 0406] Speaker needs to pull in to 4/23 [ALT 0423] Speaker sample ETD 4/26 and the samples are not final. Will check the difference with final one. [Fii 0428] After checking with Sophie the ETD is delayed to 4/29. [ALT 0430] Will ship out the speaker samples on 4/30.
| Thermal test | ALT | close | 2021-05-07 | [ALT Philip 0506] ALT will reply the testing spec by 5/7. [Fii 0507] ALT Lonnie have provided the test condition on mantis on 5/6. However, as discussed in weekly meeting, Fii will keep using the SKB's stream content to do the test with 50% speaker volume.
HW | Microphone sealing test | ALT | Close | 2021-07-30 | [Fii 0730] The report will be updated on mantis by today [Fii 0729] 1. Fii can get pass result (25dB) with T1 housing but need to add addtional adhesive type between top cover and sponge rubber. Will provide test report to ALT on 7/30 [Fii 0728] Fii ME RD is checking on the assembly and will retest again tomorrow to see if there is any problems. [Fii 0726] Sample 1: The sealing result is around 21-22 dB @450~600Hz, 2K, 2.5KHz Sample 2: The sealing result is around 17-28dB @ 600~700Hz, 2KHz Need further analysis for the assembly of top cover [Fii 0721] Will arrange the sealing test in our HC Lab. this Friday. [Fii 0714] We don't have enough DVT3 sample on hand. We plan to conduct the sealing test when received DVT3 sample [Fii 0708] The microphone sealing test is expected to be tested on 7/16 [Fii 0707] Have received the T1 housing on 7/7 [Fii 0628] Have received extra 2 new silicon rubber on 6/25. [Fii 0624] 1. The T1 sample will be ready by 6/26? 2. Have received the sealing test report from SH. The test result looks good. Fii will arrange the test when received T1 housing. [Fii 0621] ALT will provide 3 full set T1 housing including MIC rubber pad and extra 2pcs rubber pad for Fii as a replacement if there is any problem. [Fii 0616] The T1 housing can be delivered from Inkel by 6/24. [Fii 0615] Fii will book the internal chamber and start the sealing test with T1 housing & new MIC rubber when received it next week. [Fii 0610] Another vendor "Everything" has sent out the samples on 6/8. The tracking number is 773934722045 (DHL) [Fii 0609]There are two supplier will provide the adhesive tape sample. One of the vendor "MeiGaoMei" has provided and sent 40pcs sample to ALT SH on 6/7. Please check the mantis ID 1177 in details. [Fii 0531] Need ALT to confirm the ETD date of new rubber samples. Fii will ask vendor to prepare the adhesive tape samples *50pcs and deliver to ALT directly. Will confirm the ETD date to ALT when received update from vendor. [Fii 0524] Have received sealing report on mantis from SH. Will reply SH when Fii complete the internal review with the report. [ALT 0514] ALT will test and debugging next week. [ALT 0505] ALT will check with INKEL to book the lab for testing in WK 5/10. The schedule TBC [Fii 0430] ALT provides new sponge MIC silicon and 1.1t silicon MIC rubber with O-ring sample, which the test result is poor than previous setup (old sponge MIC silicon plus 0.5t silicon MIC rubber). Have provided test report to ALT on 4/29. Need ALT to verify the new silicon simultaneously in Korea Lab. and provide us with test results for comparison. [Fii 0428] Arrange sealing test at HC acoustic chamber on 4/29 [Fii 0420] ALT SH has shipped 3 sets of new rubber pad to Fii by 4/19. DHL tracking: 9167971131 [Fii 0413] According to SH, the sponge silicon mic can ship to TW office (1.1t, housing side with O-ring, PCB side is plat.). Can ALT provide us 3pcs samples for testing? Please inform us when ALT can ship out the samples. [Fii 0409] 1. Need ALT to check if possible to provide the sample of silicon rubber within 4/9.
HW | AMP board verification test done before DVT3 gerber out | Fii/ALT | close | 2021-04-06 | [Fii]The verification before gerber out is necessary [ALT] We will provide AMP b'd gerber data by 4/6. [Fii 0317] Remind again the verifications mentioned in the email must be done before 4/6. The gerber must be provided on 4/5 morning. We have internal process for gerber out. [Fii 0325] Will proceed if ALT confirms the risk.
ME | T0 samples*2 for ME in China and factory ME in VN with assembly SOP | ALT | Close | 4/7=>4/23=>4/30 | [Fii 0531] The FFC/PCB contamination issue is own by factory ME engineer.. Since the ME engineer is located in Guang Chau factory now, they can only response it after the factory re-open. I will udpate the schedule to you when the Guang Chau factory reopen. [Fii 0520] Fii have provided the 8D of missing part and NG Label issue to ALT on 5/19. The PCB/FFC contamination issue will be provided by 5/21 [Fii 0514] Fii will provide the final report by 5/18 [ALT 0511] SH provided DVT2 housing review result, Fii to check reason of missing screw and gasp. [Fii 0507] ME & Factory receive sample on 5/7. [ALT 0430] Housing samples are shipping out with speaker samples on 4/30=>delayed and need ALT to check the shipping date again [Fii 0428] Where are the samples for ME review? Received the SOP and Fii ME is reviewing. [ALT 0423] Will check with INKEL for the SOP schedule. [Fii 0423] INKEL needs to provide the SOP ASAP. The date 4/30 is not acceptable. Plz check again if possible to provide no later than 4/27 to keep the schedule. [Fii 0420] Need extra 2 sets of samples to do the thermal test. Need to be as much assembled as possible. [ALT 0326] Likely to be 4/23 or 1 week before. Will check again. Also will check with Inkel or on site support [Fii 0326] Plz provide as early as possible. This will impact the production going smoothly. Also need Inkel on-site support. [Fii 0325] Plz help check the delivery date -ME RD in China Recipient: Jim CHEN Cell: 18376747022 Address: Foxconn Technology Park, No.51, Tongle Road, Jiangnan District, Nanning City, Guangxi Province, China. -ME in VN factory Recipient: Nguyen Thi Thu Thuy Mobile: +84 0912872792 Company : FUNING PRECISION COMPONENT CO., LTD. Address : Lot B, Que Vo Industrial Zone, Nam Son Ward, Bac Ninh City, Bac Ninh Province, Vietnam [ALT 0319] Will request Inkel to provide T0 sample and need Fii to provide the recipient info. [ALT 0318] We asked INKEL about it. But currently they provide T0 sample when they [Fii 0317] With Inkel provided SOP we need to 1. review with real housing and try assembling then evaluate assembly issues 2. transform into our SOP before DVT3. We need to reduce the time to do the trouble shooting when the production starts.
HW | Need power dissipation of all key components in AMP board for thermal simulation | ALT | close | 2021-03-16
HW | IQC for THD & FR of DREAMUS new speaker Fii Q team will on-site check the testing result. Need the updated spec to audit. | ALT | Close | 4/22=>4/29=>5/31 | [ALT 0601] Lonnie will update at Mantis on 6/1. [ALT0514] Next week ALT will provide test item of FR. [ALT0512] Need ALT/Dreamus to provide the OQC test items/SPEC. of the FR [ALT 0511] DREAMUS will test THD & FR full procedure based on Fii's requirement [Fii 0504] ALT Philip feedback Fii could check the defect rate in terms of FR and if the rate is too high, ALT will push DREAMUS to add the FR in production. Currently will do the OQC first. (review the defect rate after DVT3) [Fii 0430] If Dreamus only does FR in OQC and not during production, once Fii discovers FR test fail and does the the SWAP analysis, the rework cost will be transferred to Dreamus. (send email to ALT) [Fii 0428] When the difference report will be provided? Need ALT to push DREAMUS to add the FR test in production and OQC report. [ALT 0423] DVT3 speakers are not final. Performance related testing items for speaker could be waived. Will check the updated schedule with Dreamus on 4/23. Will provide the difference report for Fii to evaluate the impact on the following testing and MP. [Fii 0416] Received the proposal from Dreamus and will check internally and reply by 4/20. [Fii 0406] Plz check the testing items of THD and FR. Besides the speaker schedule needs pull-in. [ALT_0402] ALT sent e-mail that OQC schedule and test items on 4/2. [ALT 0401] Will check with Dreamus if THD&FR are tested. [Fii 0401] Before Dreamus ship out on 4/23, Fii IQC must be done in Dreamus factory. [Fii 0330] Because Dreamus cannot provide the testing equipment to Fii, if any suspect of speaker unit issue, Fii will need to return to Dreamus for analysis.=>[ALT 0409] well noted. [ALT 0318] We will check it when Dreamus start to produce Speaker. [Fii] Dreamus cannot provide the testing equipment and Fii will send the Q team to Dreamus factory to check the testing result before shipment.
HW | What would be the new spec for the soundbar on THD and FR as B&O requested? | ALT | close | 2021-04-12 | [ALT] We will check it to B&O [ALT 0318] B&O didn't have any requirement about THD and FR. They listen sound from speaker and evaluate. They focus on SNR(> 95dB) and Noise level(< 200uV). [ALT 0319] System test spec remains the same as RFP specifies.
ME | DVT3 housing ETA factory | ALT | Close | 4/24=>5/4=>5/7 | [Fii 0504] The customs issue needs to be resolved ASAP or Fii customs department will not agree to take in the shipment for DVT3. [Fii 0428] further delayed to 5/7 and the production schedule provided based on the date. [Fii 0416] The schedule was delayed to 5/4. plz continue to pull in to 4/29. Fii will check the production plan starting from 5/4. [ALT 0401] Still checking with Inkel if ETA factory 4/23. [ALT 0319] Will request Inkel to provide the housings as specified and is aware any delay will cause the production start date delay. [ALT 0318] We asked to provide T0 housing by 4/24 at your factory. But they don't have enough time, so they are discussing with their factory in china. [Fii 0317] We need the materials ready no later than 4/24. Besides, is the shipment from China again? If so how do we start SMT on 4/26 considering the delivery period from DVT1? [ALT] We asked to INKEL, but they will finish tooling by 4/23. So they need a week more. [Fii] Plz confirm the sample qty for DVT3
HW | ECAP lifetime | Fii | close | 2021-05-20 | [Fii]Will verify with the final design [Fii 0415] DVT3 applies ALT provided ECAP, need ALT help check if KC certification will be impacted if the ECAP is changed for MP. [ALT 0416] Confirmed no need to do EMC/ KC for change of ECAP. [Fii 0419] The substitute for ECAP from Fii QVL will not be able to make it to MP. Plz check if possible to go buy and sell for this part [Fii 0423] Fiki will check if any agent could buy the part. If not, will need ALT to help buy and parts for first couple shipment of MP. Will update the progress by 4/26 to ALT first. [Fii 0428] The vendor is surveying how to trade with Fii for MP demand as SAMYOUNG rejected to trade with Fii AVL agent. requested SAMYOUNG to reply by 4/30 [Fii 0430] Will check with factory if the stock is enough to support pre-MP 100pcs.
HW | A113X OTA architecture |  | close |  | [ALT 0317] Design both option 1 and option 2. But option 2 no need to do SMT, just reserve on layout. If needed after, ALT will rework. Fii no need to prepare for the materials.
HW | EMI pre-test and debugging | Fii | close | 2021-04-01 | [Fii 0325] 1. P-two make the new FFC cable and estimated ETD on 3/26. 2. Book 3/30~4/1 3rd party Lab. and debugging [Fii 0326] Target to complete by 4/1 but still need to check the lab time slot [Fii 0329] The new FFC cable ETA is 3/30. Have booked the 3rd party Lab. on 4/1.
HW | DVT heatspreader sample thermal test and improvement | Fii | close | 2021-04-23 | [Fii 0325] Current test result is bottom case 52.8degC @ 25degC ambient (spec.=50degC) 1. Make the new heat spreader top/bottom of AMP board, and estimated ETD on 3/28 2. Make the new heat spreader bottom of main board, and ETD is to be confirmed with vendor NWE [Fii 0329] The new bottom heat spreader is estimated complete and shipped by 4/15. Expect to complete the test by 4/23. [Fii 0419] The new bottom heat spreader was shipped by 4/17, and ETA on 4/23. Need rebook the schedule of HCQA thermal chamber. [Fii 0428] The test result of top and bottom surface are passed @ 25degC & 50degC ambient. (48.6degC & 37.9degC @ 25degC ambient and 70.5degC & 61degC @ 50degC ambient)
HW | Acoustic testing equipment may need to modify due to new speaker location | Fii | Close | 2021-10-09 | [Fii 0421] NI license had updated to mantis. Chamber-1: PC name: L09K18FT2002, ID: LWKL-YNM9-43MR-RPLG Chamber-2: PC name: L09K18FT2--1, ID: DSQ8-G8PY-26F6-H6KV [Fii 0414] VN factory is working on production now. The new NI lisence will be activated in this week. [Fii 0407] NI lisence has updated to mantis. [Fii 0331] NI lisence will be provided by mid. of April [Fii 0324] Test SW and Source code had updated to mantis. NI lisence will update at end of March. [Fii 0317] Before end of March will update the NI lisence. Test SW and source code will be provided on 3/18 [Fii 0310]: Serial number is under investigation through quotation. [Fii 0303]: Chamber and serial number are provided. There are remain two questions need to be confirmed by supplier 1. The 1st chamber back ground noise is similar with 2nd chambe but only measure to 10KHz. 2. One serial number for 2 chambers. [Fii 0224] Factory still collect data, #2 chamber test report is applying. When report is ready, will update to mantis 0911 soon. [Fii 0217]: Update equipment list on mantis 911 Still need some time to collect equipment list and weight from vendor. and require chamber isolated test report from vendor. [Fii 0210]: MFG will provide the data by end of this week. [Fii 0126]: MFG still not ready, will push factory side to provide the data asap. [Fii 0120]: MFG still need some time to collect the data. And will be able to update the data to ALT by next week. [Fii 0113]: No further update for woofer balance test. Wait for next mass production build to collect more data for review. [Fii 0106]: The woofer balance left/right test item had been verified well after changed 2 seconds wav file. The relative data had updated to mantis 911. [Fii1230]: FATP had finished 100pcs test, but had woofer_balance_left and right issue. The test was not stable. The wav file will be changed from 1 second to 2 seconds of 400Hz to verify if ok or not. Test data will update when received. [Fii 1223]: No further update. [Fii 1216] Have changed the FR spec. of woofer from 1KHz to 400Hz in production line. Due to housing shortage, no unit test in FT2. When collected 100 units test data, we will update to mantis 911. [Fii 1209] Woofer speaker left to right ratio(0.7, 1.4) test item fail rate: 6.36% ALT suggests to change frequency from 1KHz to 400Hz and not to change original spec. Fii suggests ALT to re-defined Dreamus OQC more tight spec for better assemble to reduce fail rate. Fii will tracking new freqency for woofer speaker balance test item. Have update our comment on mantis 911. [Fii 1202] 1. Cancel verify reference microphone receiving SPL too low issue of 8KHz FR test. Due to MP build, FATP cannot do any verify with golden sample. Our action is to change 8KHz SPL spec from (65,95)dB to (54, 90)dB which suggested by FATP. Fail rate: 0%, 0 pcs fail/943 pcs on 11/30. 2. Air leakage: We still keep original spec of air leakage due to the spec can identify little gap and non bushing issue. The spec is (-110, -67)dB. Fail rate:1.06%, 10 pcs fail/943 pcs on 11/30. [Fii 1125] 1. The new test criteria and conditions, which ALT requested has been implement in FT2. Will ask TE to provide the test result of last build asap. 2. 8KHz FR SPL too low issue: Due to FR test has lower SPL, we consider to swap ALT volume table into factory test image. Swap ALT volume table to Factory test image and retest again on FT2, found the reference microphone seemed limited at 81dBSPL. But the THD value is higher than before. We need to calibrate the reference microphone and may need to change position for better receive speaker SPL value. Air leakage: Not allow to change new spec yet. Still keep orignal spec for better quality. Have update our comment on mantis 911. [Fii 1118] We have update the FA status for pre-MP and MP build. Found most of the fail units are related to assembly issue. Top issue is 8K FR test: seem unit volume table is different with ALT volume table. Will do verify to improve average SPL value to middle of LSL and USL. Second/Third issue are air leakage. The spec is good to screen out little gap and assemly issue. Will keep the same spec. Report is updated to mantis 911. [Fii 1104] Have collected test data with 200pcs samples in 2K MP and provided it on mantisID 0911. We will set the pass criteria to "-78 ~ -120dB". Need ALT to review the test data and let us know if you would like to adjust the criteria.
HW | ESD risk from the vent hole design for DVT3 housing. | Fii | Close | 2021-05-10 | [ALT 0401] If any ESD issues, will seal the hole in T1 housings. The detailed plan will be discussed later. [Fii] Suggest ALT to seal the venting hole to avoid ESD issue
HW | EMC test with new AMP board, new speaker sets, old housings | Fii | Close | 2021-07-30 | [Fii 0805] Need ALT to confirm the cable twisted solution of left speaker, and also need DREAMUS to pre-twisted the cable of speaker before shipped material to Fii [Fii 0804] There is another team in Fii use the twist cable with speaker and the incoming material has pre-twisted and coverred with sponge in vendor's side [Fii 0802] According to the final test report of ALT, the left speaker cable needs to be twisted 8 times to solve the 159M EMI noise. For this solution, we need the DREAMUS to twist the speaker cable before the material is delivered to Fii to ensure the stable quality of the cable during the production process. [Fii 0726] 1. Have upload the test result on last Thursday to ALT reference. 2. We found that there is an additional gasket needs to be added under on main board (under J814 FFC connector) based on ALT's report. [Fii 0722] 1. We can get passed result for the original sample 2. DVT3 sample + Fii solution + add bead on AMP output, the result is fail. 3. Need to confirm the test condition in ALT side. Fii is using a special version of F/W that can be use ADB command line to execute mode1 & mode2 [Fii 0721] 1. Will verify DVT3 samples in 3M(966) chamber of 3rd party Lab. tomorrow 2. Check with vendor and other teams in Fii to see if there is any 120ohm 25% 100MHz/5A/0.02ohm 0805 bead can be used. [Fii 0719] 1. Have provided the SW image to ALT testing 2. The 10M chamber is owned by Sporton, which is the parent company of ICC. But due to COVID-19, Sporton prohibits their customers from entering their company to work with them. and only supported for projects kicked-off in their company. 3. So, we will prepare two samples for testing this week, one is using Lonnie's solution without ferrite core and another one is prepare golden sample by using our solution. [Fii 0715] 1. According to Lonnie's update, ALT verify the EMI based on Fii's solution but found three frequency point 171M, 221M & 392M are over the limit. However, compare our test result with ALT, we can find 221M & 392M, but our noise level is much lower than ALT. In addtion, we didn't see 171M in our tes result. Therefore, we believe that the main difference may come from 1. different FFC cable routing and management. 2. The difference in PCBA board. 2. Fii have provided the detailed cable routing drawing to Lonnie reference. (mantis ID 928) 3. Fii will arrange the test again to get the pass result in 3rd party Lab. next week. [Fii 0714] 1. Have received the test result and comment from Lonnie this morning. We will check and get back to ALT today asap. [Fii 0712] 1. Have provided the EMI test data of last Thursday for ALT Lonnie reference. 2. Will prepare a summary of EMI debugging points for ALT Lonnie today. [Fii 0708] 1. The test result of proposal 2 is fail. The 141/147MHz EMI test reuslt will be over 7dB (peak) & 5dB (QP) in harizontal 2. Add ferrite core on left & right speaker cable can redue 141MHz around 10dB 3. The gasket under the HDMI is required because it helps to reduce 196MHz EMI noise around 6dB to pass the criteria [Fii 0707] 1. The proposal 1 is not help to the 141MHz EMI. We change the capacitance from 100nF to 1uF, but the result is similar. 2. The proposal 2 is not tested yet since we only have one DVT3 AMP board on hand yesterday. Today, we received another DVT3 AMP board from vendor. So we will rework proposal 2 on it and will verify it in 3rd party Lab. tomorrow. 3. Our EMC engineer found that adding ferrite core on L/R speaker cable can reduce EMI noise of 141M around 7-8 dB. We will verify it in 3rd Lab. tomorrow as well [Fii 0705] 1. Have asked vendor to send the ferrite core samples to ALT on 7/2 2. Fii will continue to debug in internal chamber on 7/6 [Fii 0701] 1. Add 120pF at AMP output circuit but 141M is exceeded 0.5dB. 2. We try to remove ferrite core of the AMP FFC cable, but 196MHz appeared. Then we add a gasket below the USB connector, the 196MhZ can be fixed. 3. The overall EMI is good except 141MHz, which is exceeds 0.5dB. We need focus on AMP board debugging and need ALT to provide us with suggestion [Fii 0630] 1. The 141M noise is come from AMP board speaker traces. Fii will place small capacitance 120p on the D201 ~ D204 & D301~304 and verify it again in 3rd party lab. tomorrow to see how many margin we have. 2. If we can place small cap. in front of inductors, we can get more 3dB to fix 141MHz EMI issue. 3 Need ALT to look into this issue to see if there is anyway to fix this EMI issue. [Fii 0628] 1. Fii found another noise from speaker, which the frequency band is at around 141MHz. Will continue to debug to see if the noise strength can be reduced. The goal is to complete it by this Thursday. 2. The hight of solid ferite we needed is over 4mm, which can not be fixed between top heatspreader of AMP & main board. We are evaluating the different routing method of MIC FFC cable, but need to verify EMI again this week to see if the result is OK or not. [Fii 0624] The gaskets can be removed but the test result can only pass marginally (under criteria around 0.5dB) [Fii 0623] 1. EMC engineer is debugging in Fii internal chamber today to see if the gaskets and solid ferrite on the FFC cable of AMP board can be removed. And will verify EMI result again in 3rd party Lab. tomorrow. 2. ME RD is evaluating the position and the assembly method of solid ferrites on the MIC board FFC cable. [Fii 0621] 1. The EMI horizontal and vertical can be passed the critera by adding rectangular solid ferrites at MIC and AMP FFC cable 2. Need to add two on MIC FFC cable (one must near main board and the another one must to close to MIC board) and one on AMP FFC cable (clamped at the middle position of cable) 3. Fii will continue to debug on this Wednesday and Thursday to see if the gaskets and the solid ferrites on AMP FFC cable be removed. [Fii 0618] Fii will summarized the EMI status & test result on mantis by 6/18 [Fii 0616] Under debugging~ [Fii 0615] MIC FFC cable routing between main board and SOC top heat spreader. EMI: (H) 221M: 6.27dB (QP), (V) 73.6M: 0.11dB (QP), 368.5M: 0.59 dB (QP). Fii will debug in the internal chamber on 6/15 & 6/16 [Fii 0610] Have updated the RS report to mantis. Will provide the SW version for ALT reference today. [Fii 0609] RS test is passed. Will update the test rpeort on mantis once we received report from 3rd party Lab. [Fii 0608] RS can be conducted this afternoon. Fii EMC engineer will book the internal chamber for debugging in parallel but currently, the chamber are full occupied untill 6/21. Will coordinate with other project for the available time slot. [Fii 0601] CS is passed on 06/01. [Fii 0531] Have provide the EMI pre-test raw data on mantis this morning. The vertical is passed but there still have two noise 134MHz & 196MHz over the spec 0.05dB & 1dB in QP. It needs to add two gaskets between main board & bottom heatspreader to fix the EMI of 196MHz & 418MHz, and the location is approximately below the USB & HDMI connectors. Will provide detailed gasket point to Lonnie reference today. [Fii 0524] Confirmed with compliance team that the RS/CS/RE test will continue to test even the Engineer is WFH. But the 3rd party Lab. still have no spare time for RS/CS test until 5/24. [ALT 0517] Have asked VN factory to send 4 sets of PCBA to TuCheng office for RD checking first. The PCBA is estimated to arrived TuCheng by today. We plan to assemble one set of DVT3 sample (DVT3 AMP board+ DVT3 main board + new housing & speakers) for RS/CS debugging this week. [ALT 0514] target to get EMC result by 5/27 before KC cert (start week 5/24). [Fii 0513] The RS/CS are failed for MIC input. We think it's related to the software. We will update the SW of DUT and re-test again in 3rd party Lab. [Fii 0506] The RE test report will be provided on 5/7. RS/CS will be arranged after and the time slot needs to check with lab. [Fii 0504] Arrange RE/RS/CS test on 5/6 [Fii 0426] Have provided the EMI test result to ALT Lonnie reference on 4/26. We found some noise at around 418MHz & 450MHz. We will arrange next debugging when the final FFC cable and the new speakers arrvied at our office. 1. DVT1 sample (DVT2 main board + DVT1 sub-board) + new AMP board + woofer speakers/mid range speakers + enhanced FFC cable [Fii 0416] If the SW for all functions ready by 4/21 then the EMC will start on 4/22. Also the NRE PO for EMC test should be provided ASAP. [Fii 0415] If ALT can provide the complete S/W by 4/16, the function of new AMP board is expected to be verified completed by 4/23. Then Fii wiFll book the 3rd party chamber on week 4/26 ~ 4/30 for EMC testing. [Fii 0409] Need the speaker ETA TW 4/23 for assembly with new AMP board in the old housing.
HW | LED chip color shift issue | Fii | close | 2021-08-27 | [Fii 0830] The report will be uploaded to mantis by today. [Fii 0826] The reliability test for both short team and long term solution are finished and get pass result. The report can be provided by 8/27. [Fii 0825] 1. The reliability test of both short term and long term solution can be finished by today. And QA can provide the report on this Friday (8/27) [Fii 0811] 1. The MTBF demonstration test and thermal shock test are ongoing. No any problems found so far. [Fii 0805] Long term solution LED test status 1. Continuation of temperature cycle is passed 2. High temperature & Humidity Test (OP) & MTBF demonstration are on-going [Fii 0804] The reliability test of long term solution is ongoing and no any further issue so far. [Fii 0729] 1. For the MTBF of short term solution, we will continue to test for 5years MTBF, and the report will be updated by end of Aug. 2. Have updated the reliability test schedule of long term LED solution on mantis ID 1129. The test can be completed by 8/25. [Fii 0728] 1. Have provided the reliability report of short term solution on mantis ID 1129 [Fii 0722] There is no any failure LED found after MTBF demonstration test. Will ask our QA to provide the report by 7/23 [Fii 0719] Thermal shock of short term solution is completed and passed. [Fii 0715] Eagle Long Sample send to TW TRK# 774229004045 , ETD 7/14 [Fii 0714] short term LED reliability test status : Continuation of temperature cycle -> done High Temperature & Humidity Test (Op) -> done Thermal Shock -> due date : --> 7/18 MTBF Demonstration -> due date : 7/22 [Fii 0708] Have provided the production distribution test report on mantis ID 1129 for ALT reference [Fii 0708] LED sample ETA 7/4 -> 7/9 (Vietnam) c. LED sample ETA 7/4 -> 7/9 (Vietnam) d. 7/10~7/15 Eagle sample bulit for Long term solution LED reliability test . e. 7/16~7/20 send back to Taiwan. (Eagle ,Long term solution LED sample). f. 7/21~8/15 Long term solution LED reliability test. g. 8/16 : Provide "Eagle Long term solution" reliability test report to ALT. [Fii 0630] Provide LED verder Long term solution LED 1000hr reliability test report on mantis. [Fii 0624] Fii will provide RD measurement report of long term solution to ALT by 6/28 [Fii 0608->0627] Eagle Long term solution schedule : a. Long term solution LED reliability test 1000hr completed on 6/26. b. Provide LED sample for Eagle bulit on 6/30 ( ETD china). [Fii 0623] 1. The LED supplier recommends using long term LEDs immediately after the parts have been 1000hr LED Reliability test. => Please ALT can agree to start using long term LEDs in July. 2. Have updated the reliablity test items of short & long term solution to ALT review on mantis 1129 [Fii 0617] 1. PM Dennis has updated the test schedule of short term solution on mantis 1129. Also will update the test items on mantis on 6/18 2. The LED compensation report will be provided next week. [Fii 0616] The 20pcs short term solution samples will be sent out from VN today today. PM Dennis will update the schedule and test items on mantis for ALT review. [Fii 0609] already uploaded schedule and SN to mantis [Fii 0608] a.Long term solution schedule : 1. Long term solution LED reliability test 1000hr completed on 6/26. 2. Provde LED sample for Eagle bulit on 6/30. 3. 7/1~7/5 Eagle sample bulit for Long term solution LED reliability test . 4. 7/6~7/10 send back to Taiwan. (Eagle ,Long term solution LED sample. 5. 7/10~7/30 Long term solution LED reliability test. 6. 8/3 : Provde reliability test to ALT. b. SWAN Pre-MP 1K : need to risk buy long term solution LED. [Fii 0524] PM Dennis will work with MFG PM and Everlight to arrange the reliability test of short term and long term solution for Eagle and SWAN project, and provide the udpated schedule by 5/27 [Fii 0520] Have provided 8D report to ALT review on 5/18 [Fii 0513] Short term solution is implemented, sent 10pcs defect to everlight for long term solution verification and will have result by 5/20. [Fii 0507] Recieved Paralight LED sample and test on Eagle DUT for color test. The color is blue and brightness than Everlight. Will request Paralight to modify the LED color issue if CIE can shift to white area. [Fii 0428] There is one vendor will help to provide 2nd LED, Paralight has received our LED samples and will provide one similar LED sample next week(1st wk of May). This LED sample is non-Zenor LED. Will need verify the function first (color/brightness/electrical characteristic) when received the LED sample from Paralight. [Fii 0423] The verification of validity of solutions will be done within WK 4/26. The proposal to handle the defects return will need to discuss with vendor and feedback within the same week. [Fii 0419] Fii will also survey the alternative part for LED. Will provide the update information on 4/23=> by 4/30 [Fii 0413] The vendor proposed the short term solution which should be able to keep the defects from flowing out to Fii and will verify by 4/23. [Fii 0412] Everlight will update the FA with short term solution and the DOE for reproducibility. The final solution schedule will also be updated for fast introduction.
HW | Power consumption measurement w/ new AMP board | Fii | Close | 2021-05-07 | [Fii 0504] Measure power consumption of active standby mode w/ new AMP board [Fii 0505] Fii have provided the test report on 5/5, the power consumption of active mode is 8.9W
HW | USB detection | Fii | Close | 2021-05-12 | [Fii 0524] SQA test another sample and got fail result in 96times test. Fii will continue to complete the detection test and provide the udpated result to ALT asap. [Fii 0520] 1. VN Factory have finished the rework on 5/16. 2. Fii have complete one sample test, change resister value to 0x0a + pull-down resistor, the failure rate is 0/200. 3. Fii SQA will continues to test USB detection with another 2PCBAs 4. Need ALT to provide one USB sticker to Synaptics for USB detection issue debugging. [Fii 0517] 1. Condition: remove USB power SW + external power supply(5V) to VBUS + over 120uF (22uF *6). Test result: 3/10 fail. 2. Have asked VN factory to rework resistor to pull-down of DVT3 PCBA first. 3. Will verify the register value of 0xF7A2503C[5:1] applied to 0x0A + pull down resistor today. [Fii 0514] 1. Need to be finalize before DVT3 assembly start 2. Rework pull down + over 120uF, 3/100 fail. [Fii 0512] Fii will do the test combination as below then we can have further discuss with ALT about the test result 1. Rework pull down + over 120uF 2. Rework pull down resistor only 3. Detection test: 100time, DUT 3EA. [Fii 0507] The test will be started from 5/11. Will udpate the test result to ALT on 5/12 [Fii 0505] Need book the SI test with HC lab. Planned to do it on 5/7
HW | Power consumption required specification | ALT | Close | 2021-06-03 | [Fii 0615] Fu-Chiang has upload the test report of 1.189W passive standby report on mantis. [Fii 0610] Have updated the test report on mantis based on the 1.5W test result. [Fii 0609] Synaptics confirmed that the command "test_disp hdmipwr off" is to turn on/off HDMI TMDS output. We also turned-off the enable pin of power switch, and the pssive standby power can be reduced to 1.1893W. Passive standby = 1.1893W Active standby = 5.9108W [Fii 0608] The current passive standby is 1.97W. To enter "test_disp hdmipwr off" command manually, the passive standby power can be reduced to 1.5W. Checking with Synaptics about this command line and will verify again by integrated image. [Fii 0601] ALT to discuss the details of modification based on passive standby solution, and both parites to discuss if one more build is needed. [Fii 0531] Have provided the active standby test result on mantis on 5/27. The AC power consumption is around 6.3W after turned-off AMP ICs. Will continue to test passive standby on 6/1. [Fii 0524] Have received the active and passive standby requirement from Lonnie but it seem that there has additional HW changes with the enable pin of DCDC converter (24V/5V), and the extra build should be required. Need further discussion with ALT about the PCB preparation and schedule impact. [Fii 0514] ALT is required to confirm the exact requirement for the active and passive standby power consumption
HW | I2S timing issue | Fii | Close | 2021-06-11 | [Fii 0616] The I2S timing of A113 are passed the criteria based on the image provided by ALT Lonnie "aml_upgrade_package.img" [Fii 0615] ALT has provided the image for test. Fii will verify the result today [Fii 0608] The data setup time is passed after invert the BCLK, but the WCK setup time turns into fail (Result=0.065ns, AMP IC spec.=20ns). Need ALT and AML look into this issue
HW | USB detection issue | Fii | Close | 2021-06-16 | [Fii 0623] Have provided the waiver document on mantis 919 on 6/22 [Fii 0617] Fii will prepare the waiver doc to ALT review by 6/21. [Fii 0616] Synaptics only can confirm that the HW design is no problem, but can't provide comment about S/W portion. Jiamin said that he will ask Kail to explain this issue with ALT directly. [Fii 0615] Synaptics PM Jiamin will feedback the comment about the USB detection issue by 6/16
HW | Speaker output volume | Fii | Close | 2021-09-10 | [Fii 0915] The test is completed, and the report has been upload to mantis 1240 on 9/15 [Fii 0909] Need ALT to confirm the LKFS stream are SBS_AAC & SBS_AC3? Checked with River that ALT asked our SW team use these two stream to verify the max volume(32 level) of LKFS only. May I know the purpose of using LKFS stream to test each volume level of the speaker output? [Fii 0906] Will arrange the speaker volume test with QA team and provide the test result by 9/10. [Fii 0830] Need ALT to confirm with SKB whether the speaker power is OK [Fii 0826] 1. We have measured the speaker power again based on the image provided by ALT, which has enabled DRC and fine-tuned the gain. The test result is similar with ALT and have updated it on mantis ID 1240 on 8/25 2. Wait for ALT to confirm the speake power and volume to SKB [Fii 0825] We have tried to change to new PCBA and ensure that the SW version is the same as ALT. And we also use Audio precision to measure the output power but so far we still get the test result. We will try to connect the speaker directly with audio precision instead of resistor to see if the result can be improved. [Fii 0823] Will change another PCBA and measure the speaker power again to clarify this issue [Fii 0818] We have re-test the SPK power after apply set limit 30W@ woofer and 8W@ full range, but we found tbat the volume is set to 30 steps will reach the max power, and then when the volume is set to 31 & 32 setps, the power will reduced. [Fii 0812] The test was completed and have upload the test report on mantis ID 1240 on 8/12 [Fii 0811] Our QA can perform the speaker volume test tomorrow (8/12) [Fii 0809] Our QA will perform the speaker volumne test this Friday (8/13) [Fii 0804] The HDMI LKFS volume test is completed. Will arrange the speaker output volume test next week. [Fii 0726] Refer to mantis ID 1120 for the HDMI LKFS test result The gain tunning of VS550 is completed. Jerry is working with SQA team to verify all the test result (1 to 32 levels), and will update the result later. [Fii 0722] 1. Jerry will update the test result of HDMI & speaker volume tuning by our SQA before 2. According to Jerry, he just completed the gain tuning in VS550 to ensure the maximum speaker volume is the same as HDMI output [Fii 0715] Our SW engineer Jerry is checking whether he can adjust (reduce) the audio output GAIN in VS-550 to ensure that the speaker output volume(power) will not exceed the spec. in maximun volume step 32. I have raised this issue and involve our SW Jerry in the discussion on mantis ID 1240. [Fii 0714] According to our SW, the volume table for HDMI output is no problem now but the power for speaker output will over the spec. We will need further discussion with SW team to clarify if the volume table for speaker output can be fixed. [Fii 0712] The speaker output volume test will be started when SW team fix the volume table issue. [Fii 0628] Test MS11 should be able to complete in these 2 days, and then will arrange the HDMI output volume test. The speaker volume test will be arranged in next week. [Fii 0621] Recently, ALT asked Fii to perform speaker volume of HDMI output and Dolby MS11 test. So, the speaker output volume test will be conducted after those tests are completed. Will need to confirm the schedule with SQA and update it to ALT [Fii 0617] We can arrange one sample prevuously used for thermal test to SQA for speaker volume test (DVT2 main board + new AMP board). This test is handled by Jacky's team and SQA. Can ALT make this request to Jacky's team on mantis and let Fii to follow up? [Fii 0616] Will arrange the test when received DVT3 sample since the speaker design of DVT3 is different with DVT2. [Fii 0615] Will check with Jacky's team and SQA about their plan of speaker output volume testing
HW | Ferrite core winding method | Fii | Close | 2021-07-02 | [Fii 0701] Fii can prepare 8sets of ferrite cores to ALT. Vendor is checking with their RD internlly to see whether they can wrap sponge on ferrite core in their factory. Will confirm the sample ETD schedule to ALT once we get confirmation from vendor. [Fii 0630] Have provided the ferrite core winding proposal to ALT review. Need ALT confirm whether proposal 1 is OK to go?
ME | ALT need to add "TAPE 3M GTM720" in DVT3 assembly production. | ALT | Close | 2021-07-05 | [Fii 0707] Sample TRK# SF1125505130359 , ETA 7/9 [ALT 0702]Don’t wait TAPE 3M GTM720 sample delivery. 1st delivery of 36pcs, it can be skip. ALT will rework on it But, If arrived the tape before DVT3 production, please apply it. And the others DVT3 SWAN, please apply TAPE 3M GTM720. [ALT 0701]On 6/29, ALT need to add "TAPE 3M GTM720" in DVT3 assembly production. Supplier "TAPE 3M GTM720" sample ETD 7/2. The "TAPE 3M GTM720' samples are too late for DVT3 production to start on 7/5. Please advise whether to wait for samples to arrive in Vietnam before starting DVT3 production?
HW | DVT3 AMP board inductir is broken 100% | Fii | Close | 2021-07-30 | [Fii 0729] Vendor has replied that the broken will not affect its performance. We will continue to perform the reliability test. [Fii 0726] 1. Fii confirmed that there will be an inteference between inductor of DVT3 board and the screw of old heat spreader. The new heatspreader will has no such issue. 2. Fii will check with Inductor vendor to see if the broken of body will affect the performance. And will continues to arrange the reliability test if there is no any concern.
HW | Assembly issue for AMP FFC cable | Fii | close | 2021-07-30 | [Fii 0729] ME RD Jim has updated the assembly drawing for AMP FFC cable on mantis ID 1302
HW | The impact of the AMP board changes on reliablity testing | Fii | close | 2021-08-05 | [Fii 0728] The *7 additional reliablity test items must to be tested, and 3 DUT samples is required if AMP board layout modification is required
HW | Change RDT test setup | Fii | Close | 2021-08-20 | [Fii 0823] Have confirmed with Mr.Yoon that the RDT test will be changed to local 4K video playback and Iper 100Mbps. [Fii 0819] Dennis has sent email to SH on 20/July to ask for changing environment setup of RDT by using youtube 4K video as streaming content, but we found that youtube server ot streaming content may have ramdom problems, which will cause the OTT test to be interrupted during the RDT test. Therefore, our QA plan to use local 4K video playback and iperf 50Mbps instead.
HW | MIC delay issue | Fii | Close | 2021/8/2 ==> 8/4 | [Fii 0804] Have received the gerber file on 8/3 but there is a DFM issue raise by our VN factory. The bead FB201 need to move away from the screw pad. Have provided the information to Lonnie on mantis ID 1280. Need ALT to modify the layout and release new gerber asap. [Fii 0802] Need ALT to confirm the final solution for MIC delay issue by today. If the changes related to the AMP HW design, we need ALT to to confirm whether the solution has been tested without problem on current DVT3 AMP board to ensure the solution is workable without risk
HW | No LED & AUDIO issue | Fii | Close | 2021-08-05 | [Fii 0804] 1. The root cause is due to the incorrect FFC cable (w/o shielding outside the cable) used in DVT3 and the FFC cable is easy to be pierceed by connector, and cause the I2S_CLK short to ground.
HW | Additional IR test with latest DVT3 fabric | Fii | Close | 2021-09-09 | [Fii 0909] Have completed the IR test with BMM-BA02/BRM-BA03, the result are all pass with * DUT. Please check the test report on mantis 1097 [Fii 0908] We have BMM-BA02 & BRM-BA03 on hand. Will arrange the test today and provide the report by tomorrow [Fii 0906] Will verify again IR with 3-wave length for BMM-BA03 (Moven) & BRM-BA03 (Remote solution) [Fii 0902] Have upload the IR test report on mantis ID 1097. The IR receiving distance can meet SKB's requirement (exceed 17meters at the required angle)
HW | BQB certification | Fii | Close | 2021-09-10 | [Fii 0916] The BQB certification is completed. The declare ID is D053853. [Fii 0915] Fii have reviewed the draft RF & profile report provided by TUV Lab.and now is proceed with certificate process. [Fii 0913] After providing new APK, our box can send the close stream command when disconnect the Bluetooth. The TUV Lab. is preparing the report now, and need 3-4 working days to complete the certificate. [Fii 0909] We have provided a solution to TUV Lab. this afternoon amd will wait for their verification result. [Fii 0906] 1. During the A2DP test, TUV Lab. will play & stop the music, but the equipment can't get the close streaming command when the music is stopped. Currently, our sample can only send the suspend command. 2. Confirm with Realtek whether the current behavior is correct, and then see how to solve this issue [Fii 0902] 1. BT2.1+EDR & BLE RF-PHY test are done and passed 2. Profile test: Remind one item A2DP fail. S/W team is working with TUV for the debugging now, and estimated to resolve this issues by 9/3
HW | HDMI certification | Fii | close | 2021-09-08 | [Fii 0908] Have upload the HDMI 1.4b certificate and test report on mantis 1110 [Fii 0906] 1. Have received 1.4b certification on 9/4 [Fii 0902] 1. All of HDMI section (SI, protocol and CEC) are finish test. 2. 1.4b certification will be release on 9/3 first, and then release 2.1 certification on 9/8
HWQA | Climate reliability | Fii | Clsoe | 2021-09-17 | [Fii 0916] The final report has been upload on mantis ID 1104 [Fii 0909] The climate reliability test are completed and all the test items are passed. QA will release final test report on 9/13 [Fii 0906] 1. Have upload Climate test report on mantis 1104 and MTBF prediction report on mantis 1102 2. Cold Start, Hot Start, High Temperature and Humidity test (Storage & OP), Operational Temperature cycle test, Thermal Shock Test, Power on/off test with temperature tests are completed [Fii 0901] 1. 9/3 : Will provide the report for the items that we complete the report. 2. 9/14 : Will update the test report, including Thermal, EDVT, HALT, Acoustic Noise Test that we complete till 9/10. 3. The remaining item, MTBF (RDT), report schedule is under confirming.
HWQA | Mechanical reliability | Fii | Close | 2021-09-14 | [Fii 0915] The logo/printing/label abrasion test are passed based on 75% alcohol. Will update the report on mantin on 9/16 [Fii 0911] Fii HWQA will test again the logo/ printing abrasion test with 75% alcohol on 9/13, and if the testing is passed, then will continues to do the printing abrasion of label test. [Fii 0909] The Logo Printing Abrasion Test is fail. Please refer bug report on mantis 1108. As I know that the material of mechanical part should have been shipped to our VN factory. How do we deal with those M/E material? [Fii 0908] Havep uploaded the report on mantis 1108. The rest report will be provided by 9/14 [Fii 0906] 1. Have upload the report on mantis 1104 2. Salt Spray Test, Operational Random Vibration, Operation Shock Test are completed. [Fii 0901] 1. 9/3 : Will provide the report for the items that we complete the report to Mechanical. 2. 9/14 : Will update the test report that we complete till 9/10.
HWQA | Reliabilitt RDT test | Fii | Clsoe | 2021-09-10 | [Fii 0929] The drop test of the gift box has been completed and passed the criteria (we tested *2 DUT). The report can be provided by this Friday (10/1) [Fii 0923] The RDT test is completed without any problem. Have updated the report on mantis 1107 [Fii 0909] Have upgraded the FW of A113 for all the samples in QA Lab. And all the samples are now running well and the MTBF testing is expected to be completed on 9/17. [Fii 0908] Have updated the SW of A113 to version 0x10 with all the DUTs to solve noise issue. So far, there is no any issue found in QA team.
HW | Change the FFC cable length One of FFC relates to ferrite core breaking issue | ALT /Fii | Close | 2021-10-15 | [Fii 1104] Have received the test report from ALT on mantis ID 928 [Fii 1028] Waiting for EMI report. [ALT 1022] Agreed to introduce new FFC based on EMI test result. [Fii 1014] Need ALT to arrange the EMI test in Korea Lab. asap so that Fii can introduce it in MP prodcut to solve ferrite core interference issue. [Fii 1007] Have sent 10 sets of new FFC cable to ALT on 10/6. Please arrange the EMI testing in Korea Lab. and please let us know if you found any problems. [Fii 0929] The 10 set of new FFC cable samples will be ready b this Friday. Will try to deliver the sample to ALT next week. [Fii 0922] The EMI result of new FFC cable can pass the criteria (under 3dB). Please refer to the details in mantis 00928 [Fii 0916] The 10set of new FFC cable will be ready on end of Sept. [Fii 0915] Have received the ferrite core from ALT on 9/10. Will arrange the EMI test on 9/16. [Fii 0909] The ferrite core is still in custom clearance. The EMI test will be arranged next Thursday. [Fii 0908] We will arrange the EMI test tomorrow, .if we can receive the ferrite core before tomorrow noon, [Fii 0906] 1. The Vietnam factory requests to increase microphone (40mm) and button (50mm) FFC cable length to improve assembly. 2. Fii will verify the EMI again this Thursday to see if there is any impact 3. Fii will send 3sets of FFC cable to ALT for testing 4. Need ALT to provide at least 6pcs ferrite core samples for Fii testing
HW | Free fall drop test spec. | Fii | Close | 2021-09-15 | [Fii 0915] We would like to confirm that the following "No visual damage" criteria are only applies to product, but damage to the gift box is acceptable?
HW/ME | R-LED connector interference (Mantis#1362) | ALT /Fii | Close | 2021-10-13 | [Fii 1014] As discussed with Sophie, the layout change on R-side LED board is limited due to the layout rule. So, Fii prefer to rework the screw boss on top cover for 13K material. And we need INKEL/ALT to modify the R-side screw boss to solve this issue [Fii 1005] Our factory found out R-LED connector interference issue in DVT4 (1.1K pre-MP). Please refer to the document that we updated in Mantis. we suggest modifying the R-side screw boss to solve this problem.
ME | Ferrite core interference issue | Fii | Close | 2021-10-15 | [Fii 1021] Have Inkel provide new sponge for evaluation? [Fii 1014] 1. Have upload the FA report of ferrite core interference issue on mantis ID 1366 2. We suggest to paste a sponge(10*10*1mm) on the screw boss to avoid audible noise 3. Fii will suvey the new sponge components, but it will take us a long time on sample evaluation and internal approval. We found that we have existing sponge (484.00430.005) in SWAN that can be used. It is used on LED braket. So, is it possible that ALT to help provide some material for us as consign part as short term solution
HW | AMP board layout modification | ALT | Close | 2021-10-19 | [Fii 1014] 1. Because MPS MP2338GTL-Z material shortage issue, we need introduce Silergy SY8263AIC as 2nd source in AMP board. Need ALT to arrange the layout modification soon and provide the gerber file by 10/19. 2. Please check mantis ID 1357 in details
HW/ME | Datasheet for new L-CH/R-CH speaker cable | ALT | Close | 2021-11-01 | [Fii 1202] Need new manufacturer ticket of class 377 in Foxconn part number system to apply 353 FPN and PSC ticket. Also need material verification ticket. So that needs time to apply. [Fii 1118] The part number application is under processing and estimated to be completely by next Wednesday (11/24) [Fii 1109] Have received datasheet from SH. Will apply the FXN P/N and provide it to SH when it's effectively. [Fii 1104] ALT have updated on data sheet on Mantis, but it need to add some cable and ferrite core by early of next week [Fii 1028] ALT comment will use new L-CH/R-CH speaker cable (includes ferrite core, sponge) from 15.1K. Fii need the datasheet to apply Fii P/N in advance.
HW | Audio noise issue | Fii/ALT | Close | 2021-10-22 | [Fii 1202] Defect rate Audio noise sample NO.1, original design: 2/50, change 5R67 / 5R68 from 200ohm to 51ohm: 0/100 Audio noise sample NO.2, original design: 6/50, change 5R67 / 5R68 from 200ohm to 51ohm: 0/100 Need ALT to check EMI result before issue ECO [Fii 1125] Have received 2pcs fail units from factory. Will analyze the fail symptoms and feedback to ALT by next Tuesday (11/30) [Fii 1104] FII have provided test result on mantisID 1359. Defect rate is 7/20 Need to track the audio noise issue in 2K MP to see if there are any defect sample. [Fii 1028] 1. Have discussed with Amlogic TW and their FAE think it might be timing issue. 2. Since we rework the I2S to DVT3 version, and the issue is disappeared. In DVT3 structure, the I2S data will have some buffers in A113 but in pre-MP structure, it doesn't have any buffers. 3. We will try to increase or decrease the resistance of the resistor in series with BCLK to see if there is any change in the fail rate. 4. Wooshin has provided new AMP s/w (0x31) for our testing (mantis ID 1359). Can you confirm any chnages has been made for this new s/w? [Fii 1021] We did the following tests and found that when we rework the AMP board back to DVT3 version with DVT3 firmware, the audio noise will disapeare. Have upload below test result on mantisID 1359 1. Pre-MP main board+ DVT3 AMP board: test 30 times, defact rate 0/30 2. Pre-MP AMP board: R343/R344: 100ohm ->0ohm, R103/R104: 100ohm->33ohm, C105/C106: remove, => defact rate 9/30, there were 2 severe audio noise 3. Pre-MP AMP board: solution 2 + R107~R110: 100ohm -> 33ohm => defact rate 8/30, there were only a pop noise when the first screen appear (image 0.jpeg) 4. Pre-MP AMP board: separate A113X I2S in and I2S out + DVT3 A113X firmware (as DVT3 design) R343/R344: 100ohm, R103/R104: 100ohm, R107~R110: 100ohm (as Pre-MP BOM) => test 30 times, defact rate 0/30
HW | 2nd source introduction status | Fii/ALT | Close | 2021-12-03 | [Fii 1230] No further update. [Fii 1223] No further update. [Fii 1216] 1.Update DIODES 74LVC125AT14-13 with 5R67/5R68 51ohm test reportin mantis on 12/13. 2.EC capacitor L/T of Rubycon and Panasonic, purchase is under checking. [Fii 1209] Update DIODES 74LVC125AT14-13 test report on mantis on 12/9. We also add EC cap 2nd source comparision table on mantis 1357, Please review it. [Fii 1202] Will update the reliability test report and EMI report on mantis on 12/2 [Fii 1125] 1. Have provided test report on mantis and confirmed by ALT. 2. The reliability test of 3PEAK TPL740F25-5TR & TPL740F18-5TR will be finished by 11/29 3. We just received DIODES 74LVC125AT14-13 samples on 11/25 (replace NEXPERIA 74LVC125APW). Will verify it performance and provide the test report to ALT review next week. [Fii 1118] 1. Have provide the updated status on mantis 1357. Need ALT to review it and let us know if there is any questions. 2. Will provide some test report on mantis this Friday (11/19)
H/W | Designate parts | Fii/ALT | Close | 2021-12-01 | [Fii 1223] We need ALT help to provide one more designated part email for below component since our purchasing team desn't agree to use/introduce it. Our phrchasing team think that VISHAY doesn't have good support in terms of cost & L/T. No. Vendor Part Number (MPN) 1 VISHAY --> TSOP75338TT [Fii 1202] I've discussed with our Biz team and we agreed that those 5 designate parts Fii requested doesn't need to put in SOW, which means that Fii will take all liability for those 5 components. [Fii 1125] Will reply ALT after internal discussions with PM team our thoughts on designation of 5 components No Vendor Part Number (MPN) 1 Synaptics --> VS-550A1 2 Synaptics --> CX20810-11Z 3 SAMYOUNG --> CLZ35VC100MH10TP 4 ITE --> IT66318FN 5 KNOWLES --> SPM0687LR5H-1
H/W | FFC cable and connector defected sample | Fii | Pending | 2021-12-24 | [1118] ALT will inform to Foxconn that they need additional samples 2~3 month before they need it. [1111] Foxconn expects that they can provide additional free sample on May. ALT will inform Foxconn when ALT may meet FFC cable material shortage for repair before next May. [1104] Foxconn cannot fix the date when FFC vendor can provide their new sample. First of all, ALT and Foxconn should decide how they handle idle materials. After that Foxconn can discuss with vendor about new sample delivery schedule. [1028] ALT asked to provide stack status both Foxconn warehouse and Vendor warehouse that already produced according to PO and Open PO. Foxconn feedback that it is same as last week discussion. ALT asked Foxconn to send an e-mail when vendor can provide new sample to us. [1021] BT is Foxconn warehouse in HK [1014] Foxconn's supplier can provide 4.2K FFC cable without cost. But supplier already have 6K original FFC cable in stock. Supplier can provide 4.2K FFC cable after the original FFC cable are out of stock. [1007] Foxconn will have meeting with related companies, include FFC Cable vendor and connector vendor next Tuesday. Foxconn may have some conclusion how they will handle this issue and new FFC cables(4.2K) next Wednesday. [Fii 1006] The 8D report has been provided on mantis 1417 on 10/6. [0930] ALT received 0.5K pcs new FFC cables. Foxconn can fix the date to deliver the rest of new FFC cables(4.2K) after discussion between Foxconn QA and supplier. Foxconn will share 8D report from supplier by today(9/30). [09/29] Schedule 0.5K 9/27 ETD, DHL 74 6664 5550 [09/23] Schedule 0.5K 9/27 ETD, 4.2K Schedule is not fixed yet. Foxconn will provide 8d report that Foxconn provide to supplier by 9/27. [0916] FFC Cable delivery schedule. 0.5K - 10/31(confirmed by Foxconn) 4.2K - Fix later(Foxconn will have meeting with supplier next week. Foxconn can fix the schedule after meeting.) [0901] Foxconn will confirm after meeting whether they can confirm the 0.5K delivery by 10/31 Foxconn didn't have discussion with supplier yet. They will have it next week. Foxconn will update its plan after meeting. [0826] Foxconn has some issues to provide 4.7K FFC cable. But ALT keeps aske to provide it. Foxconn will discuss internally and they will provide how many q'ty Foxconn can provide by next week. [ALT 819] Foxconn will discuss how many FFC cables Foxconn will provide to ALT and it will update by next week. ALT wants to know how many and when Foxconn can provide new FFC Cable to ALT. [ALT 812] Foxconn will update whether Foxconn can provide to ALT 4.7K new FFC for repair. It will not need to send 4.7K at once. 0.5K for each shipment is OK. [Fii 0811] 1. Will apply the EC when the engineering PN transfers to offical PN. We expected the EC will be complated by next Friday(8/19). [Fii 0804] 1. Fii biz team had confirm the cost. Fii RD will apply for EC for the new FFC cable and the new CM choke when getting approal from ALT for new CM choke. [Fii 0728] 1. The Fii biz team will confirm the cost before 7/3, then RD will issue the EC to introduce the new FFC cable. [Fii 0721] 1. Has provided control run report on mantis #0001417. Please kindly review it and feedback comments. [Fii 0714] 1. Production line will finish control run on 7/15. Once got control run report will provide to ALT for reviewing. [Fii 0707] 1. Got confirmed of HALT report on mantis from ALT. Supplier P-TWO has provided the new part number (183005-15110) to Fii and the price is under confirm internally. Fii MFG will control run new AMP FFC cable on next Monday (7/11). [Fii 0630] 1. Has upload revise version of HALT test report on mantis #0001417. Please kindly review it and approve it if no further questions. [Fii 0623] 1. Has upload the HALT test report on mantis # 0001417. Need ALT to review and approve it if there is no questions, and then Fii will inform vendor P-TWO to provide quotation and work with MFG PM to arrange control run schedule for new FFC cable. [Fii 0616] 1. Has upload the test report of "Press 1N on FFC connector top" on mantis #0001417. Please help to review it. 2. Has finished HALT test and result are pass. Will provide test by 6/21. [Fii 0609] 1. The test of "Press 1N on FFC connector top" finished, result pass. Will upload test report by 6/13. [Fii 0602] 1. The test of "Press 1N on FFC connector top" is currently going well, and the test can be finished on 6/7. Will provide test report by 6/10. [Fii 0526] 1. Update test schedule of " Press 1N on FFC connector top": 5/24~6/7, report 6/10. Because HWQA reply that weights are not enough. They can't test two DUT at the same time. So it needs another 5days for testing and the test schedule will be postponed to 6/7. 2. In addition, according to the Lonnie, we need to use FFC cable tested in step 1 for step2 test, then how can we check the FFC cable after step1 test since it will damage the FFC cable after tearing off the inner layer. 3. The test schedule of HALT test will be 6/13~6/14, report 6/17. [Fii 0519] 1. Test schedule of " Press 1N on FFC connector top": 5/24~5/31, report 6/2. 2. HALT test: The estimated test fee is around NTD 20,000, but our supplier only agreed to pay 50% of the test fee. Therefore, we will arrange for this test to be performed by an ineternal laboratory to solve the issue of paying for the test. The test is expected to begin in early July, but has yet to be confirmed. Will keep you posted once we received an update from the QA team. [Fii 0512] 1. Vendor P-TWO has shipped samples on 5/6, 55pcs to Fii VN factory, 15pcs to TW. RD has got samples on 5/12. 2. Will arrange Fii HWQA test "HALT test scenario 1: Press 1N on FFC connector top", will update test schedule to ALT soon. [Fii 0505] 1. Due to the COVID-19, the express is still closed until now. Therefore, vendor P-TWO has not got copper foil samples yet. So FFC cable samples schedule need to be confirmed with supplier. There is no firmed schedule from supplier yet. [Fii 0428] 1. Sample 5/5 ETD. [Fii 0421] 1. FFC cable samples schedule is still not confirmed yet. [Fii 0414] 1. Vendor P-TWO will provide new FFC cable samples to Fii, but sample schedule is not confirmed yet due to COVID-19 is getting worse in Shanghai China now, copper foil supplier can't deliver new copper foil samples to vendor P-TWO. Will update schedule to ALT once there is any update from supplier. [Fii 0407] 1. Vendor P-TWO reply that total thickness of current design with kapton mylar is 557um which over FFC connector specification (500+-50um). So vendor P-TWO suggest to decrease the thickness of "insulated layer+adhesive" ( 60um -> 37um) and "stiffner+ adhesive" (225um -> 205um), as show in the picture. Can ALT agree to this design change ? 2. Please see the detailed in mantis 1471 [Fii 0331] 1. Has provided English version of MXPI-310F test report and standard GBT30776-2014 on mantis 0001417:0009764. Vendor only can provide Chinese version of standard GBT30776-2014. Will provide revise version of datasheet later. [Fii 0324] 1. Kapton vendor reply that test standard (ASTM D3330) of tensile strength is uncorrect in MXPI-310F datasheet. Will update correct version of datasheet to us this week. [Fii 0324] 1. HWQA confirm that HC HWQA Lab. can test scenario 1 ((press 1N force on FFC top)) by surface coating abrasion machine. 2. Double confirm with KAPTON vendor, the denominator of 25mm (N/25mm) is to use a 25mm width KAPTON for the tensile force test, and the denominator of cm^2 (N/cm^2) is to use a 8mm diameter cylinder for the puncture force test. The new capton mylar (MXPI-310F) can indeed pass 90N/cm^2 test. Please review and confirm it. [Fii 0310] 1. Need ALT to confirm whether Fii can only test "Vibration step stress test" and "combined environment stress test" for HALT test. 2. Fii HC HWQA reply that HC HWQA Lab. may can do HALT test scenario 1 ((press 1N force on FFC top)) by surface coating abrasion machine. It need Fii HC HWQA further confirm about this. [Fii 0303] 1. Vendor P-TWO unwilling to pay HALT test fee by themself. The test fee may need to be shared by Fii and P-TWO. It need to further discuss with P-TWO after got the quotation. 2. We have discussed with Fii QA team and we think to only verify "Vibration step stress test" and "combined environment stress test" of HALT test should be enough? And also we only need to pay a lower price. Need ALT to confirm about this. 3. Vendor P-TWO and Fii factory can't test HALT test scenario 1 (press 1N force on FFC top) . Will conduct this test at Fii HC HWQA Lab. [Fii 0224] 1. Fii factory got the samples on 2/21. 2. Because temperarure chamber machine limit issue (70℃~-20℃), HALT cannot be test in Fii factory, and PQE can't go to VN local Lab. from Fii factory due to COVID-19. This test has to be conducted in Taiwan. We are discussing with vendor about this. 3. We plan to use non-p2p samples, which are scheduled to be built in mid. of March. [Fii 0217] 1. Vendor P-TWO has shipout samples on 2/16 via DHL 2. Provided HALT test requirement to Fii factory, and factory is under confirm test environment to see if they can perform the HALT in Vietnam. [Fii 0210] 1. Because manpower shortage after CNY, samples shipout will delay 1week, ETD 2/16. 2. The reliability test plan will be update on mantion on 2/11 3. Supplier can perform the HALT test in 3rd party Lab. but they don't have HALT test plan. Is there any suggestion from ALT about the test condition of HALT test for FFC cable?
H/W | NonP2P 2nd source verification | Fii | Close | 2021-01-05 | [Fii 0526] 1. Do ALT have comments for Motorcomm YT8531C test report ? 2. When can ALT provide the designate email to Fii? [Fii 0519] 1. Has upload Motorcomm YT8531C test report on mantis #0001357. 2. For designate part HL7593WL08, Tom already provide related info. to Lonnie on mantis #0001357. Need ALT to provide approval email asap. [Fii 0512] 1. Do ALT have questions about the reliability test report ? [Fii 0505] 1. - Total test items: 9 items. - Pass items: 9 items. - Fail items: 0 item. - Completed rate: 9/9 = 100% 2. Has upload reliability test report of all items on mantis ID 0001357. [Fii 0428] 1. - Total test items: 9 items. - Pass items: 6 items. - Fail items: 0 item. - On-going item: 2 items. - Completed rate: 6/9 = 67% 2. Has upload reliability test report of the six pass items on mantis ID 0001357. [Fii 0421] 1. Abnormal power on/off: PASS, High temperature & High humidity test - storage: On-going Power On/Off with Temperature: On-going [Fii 0414] The reliability test schedule is 4/16~5/1. The detailed schedule plan has updated on mantis 1357 [Fii 0407] Samples are being custom clearance and haven't arrived at our TuCheng office. [Fii 0331] 1. Waiting for ALT comment to shipment. [Fii 0324] 1. Main board SMT: done, DIP: done Sub-board SMT: done Assembly: 3/24~3/27 ETD VN: 3/28 [Fii 0317] Due to PCB ETA schedule postpone: 1. Main board: SMT 3/18~3/19, DIP: 3/20 ; Sub-board: SMT 3/23~3/24, Assembly: 3/25 [Fii 0310] 1. Main board: SMT 3/16~3/17, DIP: 3/18 ; Sub-board: SMT 3/18~3/19, Assembly: 3/19 [Fii 0303] 1. PCB ETD 03/10. Will start SMT on the 3rd week of Mar. [Fii 0224] 1. Gerber out on 2/23, and start the PCB fab. The sample build schedule is not confirmed yet. Will update to ALT later. [Fii 0217] 1. Has provide LED CIE test report of TI and AWINIC solution to ALT, PLS help review and feedback comments. 2. Need ALT to confirm whether there are any problem on LED animation effect comparison for AWINIC & TI LED driver IC? Need ALT to approve it then Fii will enter to next stage. 3. HW validation test items mention that aging test should be test for GbE PHY and LED driver IC. What are the test conditions of aging test ? 4. Have upload the reliability test plan of ffc cable supplier on mantis 1417. Need ALT to check it and comment if any questions. [Fii 0210] 1. HL7593WL08: SYNAPTICS has finished software development, VCPU and VCORE voltage can change dynamically after system enter Linux kernel. 2. AWINIC LED driver IC: Vendor Everlight start test LED color and brightness on 2/10, and it need to take 3 days to complete the test. The report can be provided on 2/16. 3. Motorcomm GbE PHY: Tuning RX delay register to 8000 that PHY can work normally. 4. TMI TMI3343B DC/DC power: It need to adjust C25 => 200pF, C24 => 200pF, C10 => 180pF to meet transient ripple 240mV (+5~-5%) criteria. Update RD validation test report on mantis 0001357:0009429. [Fii 0126] 1. SYNAPTICS Shanghai site has got the sample on 1/21, and firmware is under development. Will push Synaptics to complete the tuning before 1/28. [Fii 0120] 1. Synaptics send one set PCBA sample via SF express on 1/17. The sample is still on the way to Shanghai. SF: SF1413561920278 [Fii 0113] The sample may arrived to our office on 1/14. Will provide it to Synaptics TW and send to Synaptics China for SW fine tune. s 22pcs sample build.
|  |  | Close |  | [Fii 0331] 1. ALT will review material of stiffner with cable vandor and connector vendor base on last week meeting. [Fii 0324] 1. According to our suppplier, they think the stiffener is forbidden to be broken artificially. So they think that we request to enhance the material is not make sense. Also, the material of stifferner is PET material and common use in FFC cable design, and they don't have other harder material to make for stifferener. [Fii 0317] 1. Has upload FA report on mantis 0001373. Please review it. [Fii 0310] 1. PQE is revising the FA report. Will provide FA report to RD review on 3/11, and provide FA report to ALT on 3/14. [Fii 0303] 1. MFG PQE will provide revise version of FA report and update the report by 3/9 [Fii 0224] 1. Have provided FA report on mantis 0001373. Please review it. 2. Vendor P-TWO request 30pcs FFC connector samples to do reliability test, and got the samples from Fii on 2/24. Vendor will provide reliability test schedule by this week. [Fii 0217] 1. Factory QA can reproduce the FFC broken through the golden finger. Will update 8D report to ALT this week. [Fii 0210] 1. Update P-TWO provided English version of FA report on mantis 0001373: 0009425. 2. The Fii Factory still need some time to prepare the material and the FA report can be provided on 2/11 [Fii 0126] 1. P-TWO provided Chinese version of FA report on 1/24. The English version is not ready yet and will provide it on 1/28. 2. Have sent the FA report to VN factory review. Factory side is under reviewing the process and preparing 8D report now. and the report can be provided after CNY. [Fii 0120] 1. Vendor P-TWO will provide analysis report in Chinese version tomorrow (1/21). The english version can be provided [Fii 0113] 1. Have provided two defect FFC cables to P-TWO and P-two has sent it to their China factory for analysis on 1/13. We expected that the sample will arrived P-two China early next week, and will ask P-two to complete the FA report by next week (1/14).
H/W | 2021.10_first mass production two defected FFC cable | Fii | Close | 2022-01-21 | [Fii 0811] 1. Fixture is ready to build-in on next MP build. [Fii 0804] 1. The fixture has ready for FATP. The test is ok and will build-in to FATP on next MP. [Fii 0728] 1. VN factory just received new fixture on 7/28, and will test it on 7/29. If there is no any further problems, and then wil introduce in production line from next MP build. [Fii 0721] 1. Factory got the new fixture. Some problems were found after trial assemble on 7/21. Factory has ask the fixture supplier to modify the fixture and supplier will return the fixture to Fii factory on 7/25. Production line will trial assemble again on 7/25. [Fii 0714] 1. Fii will finish new assemble fixture's PR/PO this week. Once supplier got PR/PR from Fii, will finish fixture ASAP . [Fii 0707] 1. MFG has got the quotation of new fixture from supplier, and the PR/PO is under processing internally. [Fii 0630] 1. MFG has corrected the fixture, and already send the drawing to supplier for quotation. MFG is expected to get the quotation by next Monday. And then it needs 2 weeks for internal process ( PR/PO). 2. Supplier need 3-5 working day to make the test fixture after receiving PO. [Fii 0623] 1. Production line has produced a first version of new FFC cable assemble fixture, PLS see pictures on the right side. Because it is the first version of new fixture, production line reply that the main board is not easy to place and take out. Will continue to negotiate with production line to optimize the new fixture. [Fii 0609] 1. Production line is making a new fixture at mainboard side for assemble AMP FFC (J814), LED main board FFC (J808), button key FFC (J807) and MIC FFC (J810). The new fixture will be completed by 6/24. Then production line will arrange a control run to see the new fixture is ok or not. Will confirm the control run schedule after new fixture finished. 2. Base on the housing design, the LED main board lock on front cover, MIC board and button board lock on top cover when assemble FFC cable. Because space limitation issue, production line reply that operator can only use hand to put FFC cable into FFC connector. So no fixture for these three boards. [Fii 0602] 1. As Lonnie mention that the 8D report lack of long-term solution for MIC FFC and button FFC. Production line will provide the revise version of 8D by next Thursday (6/9). [Fii 0526] 1. For longterm solution, production line use plastic tweezers put FFC cable into connector on AMP board. Has upload 8D report on mantis #0001373. Need ALT review it and let us know if there are any question. [Fii 0505] 1. No longterm solution provided by VN factory till now. RD will raise this request to VN QA team and need further discussion with production line/QA later. [Fii 0428] 1. ME RD will work with production ME about the feasibility of stick 3M tape on power choke with original FFC cable routing method and will give feed back by 5/4. [Fii 0421] 1. About FFC cable routing is CTQ. Production line reply that it is hard to routing AMP FFC cable between heatspreader_SOC_top and headspreader_AMP_top. Production line has tried three methods. Method 1: Original routing method and stick a 3M tape on AMP FFC cable which the contact position of the FFC cable and power choke. Method 2: Bending the AMP FFC cable before assembly. This method has assemble risks, 1.FFC cable may be broken after folding. 2.OP difficult to assemble (cable is not long enough) 3.FFC cable may be loose or isn't plugged in properly after assembly. Method 3: Routing AMP FFC cable between HS_SOC_top and HS_AMP_top. FFC cable need to be folded a little above the AMP PCBA. This method has assemble risks, 1. OP difficult to assemble 2. FFC cable has broken risk. Production line suggest to use method 1 and because new power choke with LCP top cover, so that it can avoid FFC cable short with power choke. Could ALT agree method 1 ? [Fii 0407] 1. Has uploaded final 8D report on mantis 0001373. Please kindly review it. [Fii 0331] 1. ALT will review material of stiffner with cable vendor and connector vendor base on last week meeting. [Fii 0324] 1. According to our suppplier, they think the stiffener is forbidden to be broken artificially. So they think that we request to enhance the material is not make sense. Also, the material of stifferner is PET material and common use in FFC cable design, and they don't have other harder material to make for stifferener. [Fii 0317] 1. Has upload FA report on mantis 0001373. Please review it. [Fii 0310] 1. PQE is revising the FA report. Will provide FA report to RD review on 3/11, and provide FA report to ALT on 3/14.
H/W | FFC cable melted and common choke burned | Fii | Pending | 2022-02-18 | [0826] Foxconn still have about 10K old common choke filters in stock. After use old part, Foxconn will introduce new one. Before that Foxconn will keep apply short term solution. [ALT 812] New FFC cable and new common mode filter will be applied MP. But it depends on stock status when Foxconn start to apply new one. Both FFC Cable and new common mode filter will apply different date based on stock status. Foxconn will inform when they can apply it. And this issue will be closed after both parts are applied to MP. [Fii 0811] 1. Power choke is applying with FFC cable when FFC cable transfers official PN. [Fii 0804] 1. Control run report had updated to mantis. The results were pass. Fii will apply EC for new choke component after ALT confirms. [Fii 0728] 1. SMT had finished and will start to assemble in FATP on 7/29 with new choke component for control run. [Fii 0721] 110pcs material has been arrived at VN factory, but the control run can not be pulled-in due to there are still some parts has shortage issue (ex. TI LED driver IC) [Fii 0623] 1. Has inform production line to use case 2 (use 3M tape) as short-term solution and production line will use case 2 for next MP. 2. For long-term solution, vendor reply that the sample preparation schedule for the new power choke will be 6 weeks (7/29), and the control run will be scheduled on week 2 of Aug. [Fii 0616] 1. Production line has finished control run. Both choke only with mylar (case 1) and choke only with 3M tape (case 2) can 100% pass FATP test. For case 1: There are no mylay detached during production were found. 2. Factory suggest to implement case 2 in next MP. How about ALT's comments ? [Fii 0609] 1. Production line got new gaskets and will finish control run by 6/13. 2. For long term solution, Fii is dealing the cost with vendor and the new part number application process now. Will provide the control schedule and plan to ALT later. [Fii 0603] 1. Control run stopped due to button key jammed issue. It need add more gasket on bottom housing. Inkel will delivery more new gasket to Fii factory on 6/8, then production can continue to control run. 2. Has upload the vibration test report on mantis #0001428. Need ALT to review and comment. [Fii 0526] 1. Control run status: Production line has tested pass 4pcs at RC1. But remaining board still keep at assembly station due to housing button key jammed issue. 2. Vibration test: The test finished, result pass. Will provide test report by 5/30. 3. Are there any testing conducted in ALT side for new FFC choke? Any test result updated from ALT? [Fii 0519] 1. Control run schedule: Production is under confirm. Vibration test for new choke sample -> schedule: 5/24~5/25, report 5/27. [Fii 0512] 1. Vendor reply that they only do package drop test which follow standard IEC 60068-2-3. They never do single part test. 2. Fii production line reply that they can agree stick 3M tape on power choke if control run is pass. 3. According to the page 11 of "Factory Audit - 5/5", ALT told production line don't remove the Mylar. Could ALT double confirm this. [Fii 0505] 1. Vendor unable to provide the drop test specification of power choke to Fii yet because their Kunshan, China factory is lockdown due to COVID-19. Will provide test spec. to ALT check first, and then provide the test report for review if ALT agree with the test spec. 2. Factory ME reply that stick 3M tape on power choke is ok, it need PE and PQE to double confirm it. Will provide confirm result by 5/11. [Fii 0428] 1. Got the new power choke sample 10pcs, and check the dimension are the same as current used. 2. Will prepare SWAN samples and arrange vibration test schedule with HWQA team. Will update the schedule by 5/4. [Fii 0421] 1. New power choke samples ETD 4/22, ETA 4/25. [Fii 0414] 1. Fii PQE has finished the "Simulated FFC cable folding on the top of power choke" test, and upload on mantis 0001428: 0009879. The maximum Temp. of CHOKE is 66.9 degree C @room Temp. 22.6 degree C, Temp. rise 44.3 degree C. Please kindly review it. 2. The vendor reply that the LCP are thermoplastics materials which are commonly used in SMT type connectors. There should be no cracking and fragile problems. [Fii 0407] 1. Fii PQE start to retest "Simulated FFC cable folding on the top of power choke" following ALT suggestion on 4/6 noon. The testing is expected to be completed by 4/9. 3. Got the new power filter datasheet and has uploaded on mantis 0001428. [Fii 0331] 1. Has provided PCB vendor's FA report on mantis. 2. Fii PQE will retest "Simulated FFC cable folding on the top of power choke" by ALT provided new test condition, and updata to ALT next week. 3. Power choke vendor provide a new type a choke which changed mylar tape to LCP (Liquid Crystal Polymer) cover on the top of choke. As show in the picture left. The LCP cover isn't effect original performance, prices will go up slightly. Vendor will provide datasheet to Fii later. [Fii 0324] 1. VGT will update 8D report (including D6/D7) to Fii on 3/25, and then Fii QA will update the 8D and provide it before next Tuesday (3/29). [Fii 0317] VGT PCB vendor x-section FA results: 1. Component short. (Fii does not thought it is roor cause. One choke and 2 capacitors.) 2. Residual copper in via area to cause short. 3. Will update 8D report to ALT by this week. [Fii 0310]: Have provided English x-section report to ALT on 3/10 (mantis: 1428) Fii QA team is work with PCB supplier (VGT) to prepare the 8D report. The 8D report can be provided by next week. [Fii 0303] VGT vendor had finished X-ray and IR image test. And VGT will provide PCB x-section report to Fii on 3/7. Fii QA team will provide 8D report next week
H/W | CS manual | Fii/ALT | Close | TBD | [Fii 0519] No further request from SH. [Fii 0512] 1. The updated CS manual has been provided to Mr.Son on 5/11. [Fii 0505] No further update from factory. Will ask factory PE/ME to update the CS manual by next week. [Fii 0428] The updated CS manual has been provided to Mr.Son on 4/22. [Fii 0421] Will update the CS manual based on SH's request by this week [Fii 0414] 1. VN factory has been preparing on that and will provide the 1st version for ALT review on 4/15. [Fii 0324] 1. ALT is requesting the CS manual forSWAN. According to Tiffanie, ALT only change PCBA and assembly only. ALT won't repair the board level. Alsp, ALT haven't sign the SOW back yet, so Fii will provide the CS manual after received the signed SOW from ALT.
H/W | MP adaptor conduction issue | Fii/ALT | Close | 2022-05-05 | [1028] ALT received test result. It worked as vendor expected. So their solution will be applied from next production. ALT uploaded test result on mantis. If Foxconn don't have any additoional request about it, then ALT will close this issue. [1021] Vendor produced Line filters for test. It is on track. [1007] Vendor will produce 50 samples for test by mid. of Oct and Test it by the end of Oct. It is for the verification test for their solution. ALT will keep update. Vendor use a same adaptor for test. They make adaptor with Line filter socket. And they will replace Line filter every test. [0930] Adaptor vendor didn't fix the schedule yet. They are discussing internally. ALT hopes to get update by next week. ALT will keep updating on mantis. [0923] ALT already update test data on mantis. And ALT didn't receive any update on additional test from supplier yet. ALT keep in touch with supplier and will update once ALT get any update from supplier. [0916] Adaptor vendor tested EMI for 10 pcs samples that made by their factory. All passed. We will update on mantis early of next week. Adaptor vendor will test with more quantity. Their plan is not fixed yet. [0908] Adaptor vendor will receive new adaptor from factory by 9/13. ALT expect to get their test result by the end of next week. [0901] Adaptor vendor will produce new adaptor with new Line filter on Sep. But there is no detail information yet. ALT will update its schedule soon. [ALT 0826] Adaptor vendor didn't produce it yet due to material shortage. ALT keeps asking vendor to update their plan. But they didn't feedback yet. ALT will check it and update their schedule on Mantis. [ALT 0819] Adaptor vendor produce new adaptor in their factory. They will test EMI with new adaptor next week. Once ALT receive any update from vendor, then ALT will update it on mantis. And ALT will update vendor's test report up to now by today. [ALT 0812] New adaptor production for test by 8/15, EMI test will start 8/22. We will update current status on mantis by 8/16. [Fii 0721] 1. Any update of test result or root cause from adaptor vendor ? [Fii 0714] Any update from ALT after meet adapter vendor last Friday? [Fii 0630] Need ALT to update the PSU fail 8D report from supplier. [Fii 0616] Has vendor finished abnormal adaptor with STB test ? Any further update from adaptor vendor? [Fii 0609] According to ALT Mr.Yoon, adapter vendor will test fail sample from 6/7. When will adapter vendor to complete the test and be able to provide the analysis result? [Fii 0603] 1. Has ALT received any plan or schedule from adapter vendor ? [Fii 0526] 1. For the failure PSU, we need ALT to continue tracking this issue with supplier and find the root cause. We're worried whether this issue is just a case or there may be a potential problem with the mass production products. Please kindly let us know ALT's next plans and the schedule. [Fii 0519] 1. Will send 2 PSU (One pass and one fail), 4 new CM chokes and one main board with two normal FFC cable to ALT by 5/20 [Fii 0511] 1. Got the FedEx account and will delivery adapter x2 (OK x1, failure x1) and new power choke x3 to ALT. [Fii 0505] 1. Need ALT to confirm which adapter needs to be send back, and please also provide the FedEx account to Fii, so that Fii can deliver abnormal adapter to ALT for further analysis. [Fii 0428] 1. Fii test conduction for 2nd build sample of 2nd source, found SWAN + sample NO.0 MP adaptor is fail, SWAN + sample No.1 and No.2 MP adaptors are pass. There seems to be a quality difference issue between MP adaptors. Has upload conduction test report on mantis 0001469. 2. Will delivery fail adaptor to Korea next week. Please ALT provide FedEx account to Fii.
H/W | GPIO issue review | ALT/Fii | Close | 2022-05-20 | [Fii 0707] 1. In design phase, hardware team will provide GPIO mapping table to software team review if there is any hardware changes based on the reference design. 2. Both Fii software and hardware team doesn' aware that the register setting for VDDIO should be changed when changing hardware VDDIO level design. It seems to me that the key point of this issue is that Synaptics didn't inform Fii that this register had to be changed. [Fii 0630] For VDDIO6 power design 1. In the reference schematic: VDDIO6 can be powered from PWR_1V8 or PWR_3V3 via analog switch (U13). VDD of SD card connector is 3.3V, so we think SDIO interface is 3.3V and VDDIO6 is 3.3V. 2. Schematic design of SWAN: SWAN no SD card connector requirement, so change the interface from SDIO to GPIO for button key, remove analog switch (U13) and connect VDDIO6 to PWR_3V3 directlly. For VDDIO9 power design 1. In the reference schematic: SCARD interface connected to NGFF WiFi module and VDDIO9 is 1.8V. 2. Schematic design of SWAN: SWAN no WiFi function requirement, so change SCARD interface to GPIO and change VDDIO9 from PWR_1V8 tp PWR_3V3. From hardware design viewing, both voltage setting of VDDIO6 and VDDIO9 are correct for SWAN. Fii also provide schematic for SYNAPTICS review during schematic design stage, but Synpatics no response register setting issue of changing voltage of VDDIO9. [Fii 0623] AUX in issue: 1. Production line has sent fail SOC to SYNAPTICS for further analysis on 6/17. Once got analysis report from SYNAPTICS, will feedbact to ALT soon. 2. According to Synaptics, the SoC VDDIO6 & VDDIO9 block are set to the wrong register and doesn't match the hardware design. Our SW River is checking on that and will work with Synaptics to correct it. VDDIO1/2/3/6/7/8/9/10/11=3.3V, VDDIO4/5=1.8V. Detec_AUX is R4 of VDDIO9. For Button key: VDDIO2: Power_on_off_key, pin AL20 VDDIO2: Volume up, pin AP21 VDDIO6: Ch_up, Pin AD2 VDDIO6: CH_down, pin AC3 VDDIO6: Volume down, pin AC2 VDDIO6: BT pair, pin Y2 VDDIO6: SoundField, pin AE3 VDDIO8: MIC Mute, pin V2 [Fii 0616] For CH- button key issue such as cold soldering or solder crack, factory can do "Red Dye Penetration Test" to analyze defective sample and see if there are any process soldering issues. [Fii 0610] AUX in issue: 1. Production line has provided the NG SOC evaluation report to SYNAPTICS on 6/3, SYNAPTICS will feedback review result about 2 weeks later. CH- key issue: 2. For CH- button key issue, as factory only got one failure sample and it already been fixed. So, it needs ALT to provide more defective samples to factory side to further root cause analysis and the corrective action. [Fii 0603] 1. Had upload the production line provided "CH- button key FA report" on mantis #0001468. Please help review it. 2. Production line will provide the NG SOC evaluation report to SYNAPTICS on 6/3. If SYNAPTICS approve the report, then Fii production can ship the NG SOC to SYNAPTICS for further analysis. [Fii 0526] 1. AUX detect pin abnormal => The NG board fuction turns into works after mount a new SOC on NG board. PE still under checking whether the failure symptom follows with NG board SoC. [Fii 0519] 1. Button "CH-": Resoldering NG board's SOC, "CH-" key can work normally. It appears that the problem may be caused by soldering issue. 2. AUX detect pin abnormal: The impedance of NG board and OK board are the same. PE resoldering NG board's SOC, function still abnormal. Will need factory PE to do swap test to see if the failure symptom follow the SoC. [Fii 0505] Provide the ESD test report for 2nd build sample of 2nd source on mantis #0001468. The ESD result show that all buttons and AUX port can pass air +-8KV. [Fii 0428] ALT found some defective products in the field, and it looks like ALT has done some preliminary analysis such as x-ray inspection. And these issues are related to GPIO. Mantis #1468
H/W | LKFS issue(#1520) | FII | Monitor | 2022-09-16 | [1223] ALT will inform SKB that Foxconn fail to debug it. Defected sample has been broken during SoC replacement. ALT/Foxconn need another defected unit. ALT will inform that once the same defected unit is provided, ALT/Foxconn will debug more. [Fii-1222] PCBA sent back to VN for rework. The latest status is updated to mantis-1520. We have changed all chipset with new one (DDR/eMMC/SoC) and resoldering it again, also required Synaptics for FA help to boot up by Diag mode to see log, but this NG board still could not boot up. The logs were pointed to DDR issue but we didn't see any soldering abnormal through x-ray between SoC and DDR data/address traces and pads. We suspect that this pcb may be damaged by blister while rework process. [1209] Foxconn VN will bake the PCBA until this noon. And Foxconn will replace SoC and keep updating the debug status. [Fii 1208] PCBA has arrived in VN on 12/03 but it takes a couple of days to submit the internal application and the PE engineer received the board on 12/7. VN PE will rework PCBA after baking process with 70 degC for 24hrs. Will update [1202] Foxconn provide Tracking no. on wechat. Tracking no. is FedEx 770641268140. It will be arrived in Factory by 12/02. Foxconn keep updating the repair status. [Fii 1201] The PCBA has been sent to VN factory for rework on Dec 1. [1125] Foxconn will try to replace SoC again. Fot this Foxconn will send PCBA to Foxconn Factory again. It already reworked twice. So Foxconn think that it has high risk. Foxconn will update its status later. [Fii 1124] 1. The board (good SOC+NG PCBA) for testing LKFS is broken. After downloading new image to PCBA and changed MAC address for VPN, the PCBA was ok and could play video through HDMI. When we were ready to package to transfer to Lab for testing, PCBA rebooted again and again suddenly by itself without any symptom. Debug DDR4/eMMC/SOC power rail, they were all normal and no any symptoms. Suspect the SOC solder ball may non-wetting or cold soldering. 2. VN PE doesn't recommend us to remount anymore since this PCBA has already done twice rework before. [1118] Synaptics checked ATE test first and they took a x-ray picture due to crack on SoC. Synaptics cannot test it on b'd level because it cannot boot. ALT worried about Foxconn's failure rate for remount chip or SoC debug. Foxconn think that the SoC is thinner than others. It makes the higher failure rate. But Foxconn will ask Factory to improve their remount failure rate. [FII 1117] 1. For NG SOC, we received FA report from Synaptics on Nov. 17th,, and Synaptics found obvious die crack. So, our QA team prepare a report explaining it. The report has been uploadedto mantis 1520 for ALT review. 2. For Good SOC+NG PCBA, it has been arrived at our office on 11/17. We will update F/W and then transfer to SQA for testing early next week. [1111] Foxconn Factory is discussing with Synaptics about NG SoC delivery(to CN or Taiwan). FII Factory will send NG SoC to Synaptics Taiwan in this week. [Fii 1110] 1. Synaptics FAE said if the power 1V05 is short to GND, it may not be able to do the board-level test. Normally, Synaptics will do ATE test first when receiving the defective sample. If ATE test is failed, and then they will do the X-ray test, and then decap if they found any problems. 2. For Good SOC+NG PCBA, waiting for express delivery back TW. [1104] Foxconn already informed issue and the their test information for defected SoC. Foxconn expect that Good SoC + NG PCBA B'd will be depature early of next week. [Fii 1103] NG SOC had sent to vendor for FA, component will be arrived vendor on 11/4. Wait for FA report. For good SoC on NG PCBA, we applied for express internally. We will deliver the board to TW once approved. [1028] NG SOC looks damaged. So it cannot review anymore. ALT aske Foxconn to check that Synapctics can investigate this NG SoC. Good SoC on NG PCBA will be sent to FII Taiwan. FII Taiwan will review and update it. [Fii 1027] NG SOC+Good PCBA swap failure due to high 40% risk with blister on SOC board. Currently the both 1V05 power traces on SOC board shorts to GND and cannot remounted anymore. The report has updated to mantis1520. [1020] The NG PBCA with good SOC had finished swap and can work normally. The other good PCBA with NG SOC is reballing 2nd times due to the SOC power rail short to GND. VN PE is reballing for 2nd time and will test it. There are bliters on good PCBA, so Foxconn repace good PCBA. Foxconn will mount defect SOC on god PCBA today, and inform the result later. [1013] VN SMT side had un-mounted the SOC but found some blister on PCBA and SOC. VN PE will reball the SoC carefully and then do the swap test. Will keep update the result to ALT. [1007] 2 PCBA will be arrived in VN Office by today. Foxconn factory will replace SoC after receiving PCBA. Keep updating on its status on mantis. [Fii 1006] Wait for PCBA arrive to VN factory and will do SWAP SOC and its function test. If no problem, PCBA will be sent back to TW for LKFS test. [0930] Foxconn finish Fedex account application this morning. Foxconn will send 2 pcs of PCBA to Foxcon Factory in VN today. Foxconn keep updating it. [0929] The internal FedEX account application is not completed yet. [0923] Foxconn will send 2 units to Foxcon factory. Foxconn factory will replace SoC and defected SoC will be attached on good PCBA too. Foxconn think that there is no additional test item in Taiwan with defected unit. Foxconn will update SoC swap test schedule soon. [Fii 0922] The test result has been updated on mantis. It looks like the problem will follow with the main board. We think the problem may be caused by SoC since the LKFS is tested through the HDMI interface, and if we want to verify it, we have to send this board to VN factory for repair. [0916] The test result will be ready by the end of today. Foxconn will review the result with SW engineers and will have more investigation. [Fii 0915] The DUT just arrived at SQA on 9/14 but the SQA engineer was occupied by other projects until 9/15. The test will be started from 9/16. [0908] 2 DUTs(1 Defected unit and a normal unit) will arrive Foxconn's SQA today. Its test plan will be updated by next week. [0907] Will deliver 1 defect and 1 normal sample to HC SQA for testing first and then check if the symptom is followed with the main board. [0901] ALT sent defected unit that tested in SKB BMT Lab.(Fedex Tracking No. : 777806825554). It is in Philipines. It will be arrive in TW on 9/2. Foxconn will arrage SQA in Taiwan and will test it. Foxconn will keep updating on it on mantis.
H/W | Motorcomm ETH PHY disconnection issue |  | Close |  | [0217] If SKB may download old SW that doesn't support new LED driver and PMIC, then STB doesn't work. That's why we can ask to apply 2nd source for SWAN. We should release new SW and HW for new SW before applying new LED Driver and PMIC. Even though we already provided 2nd source samples, we should provid new Samples and SW for their BMT for new firmware. [Fii-0216] Current field used image can support both AWINIC LED driver IC and PMIC Halo HL7593WL08. Fii warehouse have 22K sets stock of TI LED driver IC and Silergy PMIC SY8824CAIC, this can satisfy SWAN 2023 demand. So no 2nd source requirement for SWAM 2023 demand. [0210] Foxconn doesn't have update for root cause analysis. It needs AML's help. But currently AML doesn't want to pay their resource for it. ALT and Foxconn already decided that they will not use Motorcomm PHY for eagle. ALT think that Motocomm PHY cannot be used for SWAN without root cause analysis. ALT and Foxconn agreed to close this issue. Foxconn informed that no issue on PHY chip delivery. After meeting ALT asked to check LED Driver shortage status. Foxconn should update other 2nd sources that should have SW change for use. [Fii 0209] 1. Fii adjust VDDEE voltage to 0.86V, the failure rate of ethernet disconnection is 3% (totally test 100 times). It looks like VDDEE voltage isn't the root cause. 2. Our SW team found that SPtek has added a mechanism to reset the ethernet (eth0 down/up) if the box is used in any area except Korea. So, if we do the same workaround for Motorcomm, it may have some problems. We have ask AML's help on this but AML replied that they will not help to implement this for Fii because Motorcomm PHY isn't AML's reference design. However, Fii think that this should be done by AML since this is SoC's compatiblity issue. [0203] Foxconn is checking on AML's request. But FII thinks that 1. Driver setting - FII already checked it 2. FII will check the AML Guidance for VDDEE change. 3. FII SW will check the Workaround solution. After check on above no. 2/3 items, ALT will decide whether Motorcomm solution can be used or not. [Fii 0202]AML have two suggestion after initial review Realtek PHY driver 1. Motormomm PHY driver follow RTL8211F setting (RX and TX delay ). 2. The other projects of AML's customer happen package drop issue which can be solve by adjust VDDEE voltage. So AML suggest Fii to adjust VDDEE voltage from 0.80V to 0.86V by 0.01V step. 3. Fii has provided the register to Amlogic to confirm when to unplug and plug cable. Amlogic think they can do work around solution to solve this issue, for example when the SoC detects that the cable is unplugged and plugged in, the SoC can do a software reset of MAC & PHY to avoid disconnetion issue. [Fii 0119] 1. Amlogic will review the latest driver for Realtek PHY and see if there are any can be integrated or revised with Motorcomm PHY driver to resolve disconnection issue. 2. Amlogic replied that they don't have method to reset MAC itself. Fii will provide the register to Amlogic to confirm when the ethernet cable is unplug or plug. And Amlogic will review the ethernet PHY driver to find the root cause or work around solution. [0113] Foxconn doesn't have model that use Motorcomm. The SWAN will be the first product that use motorcomm PHY. But Realtek PHY is the first priority for PHY in Foxconn. [Fii-0112] 1. YT8531C on S905X2 EVB with A12 image can boot up normally, and defect rate of ethernet disconnection is 2% (total test 100 times) 2. Motorcomm FAE debug ethernet disconnection issue, and found below symptom when abnormal. * PC site : Wireshark can receive discover packet from DUT, and receive offer from DHCP server. DUT site: Tcpdump can receive discover packet from DHCP client(DUT), but can't receive offer from Mac. * PHY checker can statistics packet count from MDI received packet. * PHY soft/hard reset, it still abnormal. * Uses commands "ifconfig eth0 down" and "ifconfig eth0 up", DUT can work normally. According to above testing, it looks like SoC issue, so Motorcomm FAE ask below questions to Amlogic for further analysis. Fii will push Amlogic to provide it. * How to reset MAC ? * Does the S905X2 have self TX/RX packet statistics function ? [0106] There is stable SW for A12 on EVB. Foxconn will debug it ASAP. PHY issue can be reproduce easily. So Motorcomm FAE is trying to debug it. The debug status will be updated by next Wednesday. [Fii-0105] 1. Using S905X2 EVB with an A12 image to verify the issue but some times boot up fail. RD is under checking EVB's hardware setting. 2. Work with Motorcomm FAE to debug. Duplicate the fail symptom and use wireshark to track the DHCP info. for analysis. [1223] Foxconn is testing new ECO b'd with "YT8531C+ SWAN RJ45". The test result will be reported by today(12/23). Foxconn didn't test with AML EVB yet. If there is any progress with "YT8531C+ SWAN RJ45", then Foxconn will start test with AML EVB. [Fii-1222] Foxconn has reworked one more "YT8531C+SWAN RJ45 connector" solution on Eagle PCBA and testing ethernet disconnection now. Will update test result to ALT on 12/23. [1209] Motorcomm cannot reproduce this issue after ECO that Foxconn asked ALT. So Motorcomm thinks that there is no issue(voltage level and PHY Part). But they tried just 30 ~ 40 times. Foxconn thinks that they can reproduce this issue when Motorcomm increase the no. of trial. But Motorcomm didn't try more again. ALT provided reproduction sequence more faster than Foxconn tested. ALT took video clip and uploaded Mantis #1519. (https://mantis.cnsbg.foxconn.com/vaas/view.php?id=1519#c11447) And ALT asked to compare register value with SWAN. Foxconn will update AML EVB test result. After AM EVB test, ALT and Foxconn will adjust priority of this issue. The material for SWAN is ready for 1st source for 22K. So it is not urgent now. [Fii 1208] 1. Collect registers value of YT8531C under ping ok and ping fail condition for review by MOTROCOMM FAE. Base on the registers value, Motorcomm FAE confirm that the data from SOC to PHY (RGMII TX) are good and no CRC / frame error occur between PHY to AP(PC) during the test. 2. Fii got the S905X2 EVB on 12/7 noon and the EVB only with 100Base-T XFMR. Has applied 1000Base-T XFMR samples and YT8531C samples from supplier. Once got samples, will start rework and ethernet disconnection test. [1202] DVDDL increment(up to 1.318V) is not a solution to fix this issue. ALT will not test with test Firmware that Foxconn released on 12/1. Foxconn will apply both HW ECO that tried before and DVDDL increment test firmware. AML has experience a model that use Motorcomm PHY. But it is in development stage yet. There is no experience production stage. Foxconn can reproduce when they use DLink router only. And Foxconn provided it to AML CN. And Foxconn just have one. ALT suggest Foxconn that all possible solutions should apply at once. ALT think that it is important to find solution to fix the issue. And ALT ask Foxconn to test with AML reference B'd with Motorcomm PHY. If Foxconn can produce the issue, then it should be discuss with SoC. Foxconn will check with AML and feedback to ALT. [Fii 1201] 1. Motorcomm FAE has provided SW commands of increasing DVDDL voltage. We can measure 1.318V (w/o RJ45 cable) and 1.335V (ping LAN IP) of DVDDL on Eagle after increasing DVDDL voltage. We are testing ethernet disconnection, till now failure rate is 3.125% (tested 64 times, failed *2), Will finish 100 times test by 12/2 afternoon and update result to ALT. 2. Fii software has uploaded test image to ALT ftp server. Path: /release_by_fxn/swan_test_image/20221201_phyVoltage [1125] Foxconn will check how they can change register value to 1.3 V for DVDDL and apply it to test SW. Motorcomm recommended 1.3V for DVDDL. After appling new register value, Foxconn will start to test. Foxconn think that it takes more than 4 days. So it will update by next meeting. ALT asked to provide test SW and Foxconn accepted it. [Fii 1124] 1. CRC Test timing : Fii set the minimum register value (0xff634544 0xC0260) that make CRC error and then test ethernet disconnect issue. We test 100 times, failure rate is 4%. The previous adjusted register (0xff634544 0x20260) of the same PCBA has a similar failure rate of about 4% ( tested 26 times, failed *1). Failure rate of before and after is the same. So Fii think this issue is not relate to CRC. 2. We will continue testing to see if we can improved the failure rate by increasing the voltage level of Motorcomm's DVDDL. [1118] To increase DVDDL voltage for SWAN, it need SW change. But ALT need another BMT to change SW. ALT expects that it will take more than 6 month. CRC Test timing : Foxconn checked the minimum register value that make CRC error. Foxconn keep testing it with new value from 11/17. Foxconn expects that this new value make more higher issue rate than before. Foxconn wants to check the relation between CRC timing and issue rate. Foxconn will test over 100 times. Its failure rate was 1~2% before. New SW : It needs additonal BMT. It will take about another 6 month. So it is not good solution. ALT think that Foxconn should focus HW debug. [Fii 1117] 1. Motorcom reported to us and mentioned that another customer had an unstable ethernet connection issue recently, and its DVDDL(PIN21) is around 1.09V~1.1V, but normal voltage should be higher than 1.15V. 2. We checked the Eagle abnormal PCBA and SWAN, the voltage of Eagle is 1.15V, SWAN is 1.136V. However, Motorcomm think we can try to increase the voltage level by adjust register, and see if the disconnect issue is fixed or not. We will arrange the test next week. 3. CRC testing timing: We adjust SOC's RGMII RX delay (register 0xff634544) value from 0x20260 to 0xc0260, and found some CRC errors occur. We start to test ethernet disconnection on Eagle by using this delay value (0xc0260) on 11/17 afternoon, untill now no abnormal were found (test method: cable disconnect to Eagle for 10 minutes, cable connect to Eagle for 1 minutes) . We will inform ALT test result on 11/21. 4. Our software team is implementing a function to identify PHY/PMIC/LED driver IC in degraded function. If this feature is done, I think we can introduce 2nd source in SWAN without Motorcomm. [1111] Foxconn is discussing this issue with AML and Synaptics. ALT concerned about the CRC Testing timing. But ALT think that it should have same issue during normal operation if AML's concern is correct. ALT asked Foxconn to prepare test plan for both Eagle and SWAN until next weekly meeting. [Fii-1110] 1. SOC vendor - Amlogic replied that MDC / MDIO is controlled by MAC register, MDC oscillate with MDIO is correct, and MDC oscillate behavior can not be modified on S905X2. 2. Synaptics FAE reply MDC always oscillate is RGMII IP behavior. 3. It looks like MDC has different behavior on different platforms, but both Amlogic and Synaptics FAE think that their SoC behavior is no problem. [1104] ALT left some comment on Foxconn's test result on mantis. Foxconn will add ALT's question if it needed. [Fii-1103] Foxconn measured MDC/MDIO waveform of REALTEK and MOTORCOMM PHY chip at each Eagle and SWAN project, the result are the same as ALT 10/19 provided. But waveform of REALTEK and MOTORCOMM PHY are a bit difference during start up condition for Eagle project. We also measure waveform at disable asleep mode, the result are the same as enable asleep mode. Test report as attached. We have informed SOC vendor - Amlogic this issue and and wait for their feedback. The report has uploaded on mantis 1357. [1028] Foxconn already tested the change request from Motorcomm. There is no improvement with ECO that Motorcomm provided. Foxconn thinks that there are 2 difference between Eagle and SWAN. Impedence matching : Eagle - many 75 ohm resister, SWAN - 1 75 ohm resister. Ethernet transformer : Eagle uses external transformer for ethernet, but SWAN uses internal transformer. Foxconn will check with other vendor's transformer with eagle. ALT already test Eagle with SWAN Ethernet connector, but we can reproduce the issue. ALT asked to check the difference of MDIO interface between Swan and Eagle, Foxconn will check and update it. [1021] ALT asked use for the investigation plan for Motorcomm ETH PHY issue.
H/W | GPIO Setting voltage |  | close |  | [0324] It will be tracked by "Factory" Tab-#22. And it is closed [0303] Foxconn started control run on new production line. Foxconn Factory will update the delivery schedule. [0217] Foxconn will provide those additional new PCBA for repairment when Foxconn factory will send next MP units. The schedule will be update. [0210] Foxconn VN Factory will receive defected unit today. Foxconn TW will check it with VN Factory when Factory can send new PCBA to Korea. [0203] ALT asked to check when Foxconn can provide new PCBAs for GPIO defected units replacements, 20 pcs. ALT RMA to Soc(3 pcs), Delivered to FII VN Factory 2(5/4), Delivered to FII VN Factory via Fedex 2(7/7), Delivered to FII VN Factory via Fedex 13(1/12) ALT explained why ALT wants to get new PCBA, not repaired PCBA. Foxconn will inform after discussion with Factory. [Fii 0202] Package is still delay in customs clearance. [ALT 0120] Package is in VN. It delayed in customs clearance. ALT nseeds plan for delivery of new PCBA to exchange defected units. [0113] ALT sent GPIO defected unit to Factory on 1/12. Tracking no. is Fedex# 7710 1314 9142 [0106] The process for TW Foxconn is finished, but now Foxconn is waiting for approval from Foxconn Factory. It takes about an week normally to get approval to send defected unit from VN Foxconn Factory. [1223] ALT already ready to send 16 defected unit to Foxconn VN. The 10 BT defected unit will send later. So ALT asked Foxconn to book fedex for 16 defected units. Foxconn will check it and come back soon. [1209] ALT will provide Chip ID information and packing information by today. [1208-Fii] Need ALT to provide Chip ID for defected units. [1202] ALT found 1 more defected unit. So total no. of defected unit is 20. ALT brought DUTs from factory and will read chip ID and provide package information to Foxconn by next week. [1201-Fii] Need ALT to provide Chip ID for defected units. [1125] ALT cannot accept to replace SoC for repair. Because SoC replacement failure rate in Foxconn Factory is too high. And Foxconn factory cannot filter defected rework(ex : LKFS NG PCBA + Good SoC issue). ALT wants to provide new PCBAs for repair. Foxconn asked to package information to Foxconn to arrange defected unit pick up. ALT will read Chip ID for defected unit and and inform to Foxconn. [Fii 1124] 1. Fii has provided GPIO value of Eagle/SWAN via e-mail. Please kindly review it. 2. SOC chip ID: Test commands is "cat /proc/cmdline ¦grep -ie chipid", then we can read unique chipid in the information. [1118] ALT provide an e-mail to check the GPIO setting voltage. Please check and support us with your HW/SW for both SWAN and Eagle
H/W | Hynix DDR3L 4Gb EOL |  | Close |  | [Fii 0511] SK Hynix inform us that the EOL timeline of DDR3/DDR4 will be extended to 2027E. The last order would be 2026E. Therefore, there is no immediate need to introduce the 2nd source at this time. [0428] ALT is preparing to reduce the cost. So DDR may changed. So please wait for ALT's preparation of cost reduction plan. [Fii 0427] It would be good if ALT can agree to start BMT before SI, and then we can do something in parallel to save the time. However, consider the L/T of SI, ECO and material preparation, it requires about total 26wks. So, we think we have to decide whether to start the DDR SI no later than mid-May in order to meet the last buy time for DDR material. [0331] ALT thinks that Foxconn skipped SI test before becasuse Samsung didn't support SI Test. The critical paths for the DDR ECO are - SI Test / BMT ALT can consider to start BMT before SI Test. It may reduce ECO Time. [Fii 0330] ALT inform Fii that the additional value of SWAN is not received and confirmed from SKB and ask to hold the reliability test. ALT will ask to start the reliability test once received confirmation from SKB and will be announced 5 months prior to production. However, according to Fii development process. The DDR SI testing will take around 12wks normally (SI testing supported by Samsung), and then take at least 2 wks to issue EC and complete it. And normally, we still need to consider the SKB BMT test and the 12wks (90days) L/T of material preparation for MP. So we need to remind ALT that 5 months notice to Fii to start reliability testing is not enough. [0324] ALT will feedback soon after discussion with biz team. [Fii 0323] Fii has sent an email to explain why Fii QA team set a requirement of test condition for DDR 2nd source introduction. Fii will wait for ALT's decision on test items. [0317] Based on ALT request for the reliability test items, Foxconn will provide the quotation again. ALT biz team will review and decide whether those test will conduct or not. As confirmed by Fii, DDR3L for Amp B'd and DDR4 for STB B'd are prepared in q'ty to be used for Y23 22K production. [Fii-0316] Because the factory's 1st priority is SWAN MP. So finish day of rework board's function test will be delayed to 3/18. [Fii-0309] Both Main B'd DDR and AMP B'd DDR: RE team will finish rework by 3/11, finish function test by 3/15. The PCBA samples will be shipped to TW after the cost provided by Fii is confirmed by the ALT biz team. [0303] Foxconn will wait for preparation of Main B'd DDR(Hynix->Samsung) change sample. Foxconn would like to test both Main B'd DDR and AMP B'd DDR at the same time. Foxconn will provide the cost for the test, but ALT didn't receive it. Once ALT receive it, then ALT will inform to FII about next step. [0302] NANYA DDR for AMP B'd : MPM has got DDR3L samples. PM An will arrange RE team to rework 4pcs PCBAs this week. [02/24] NANYA DDR for AMP B'd : Please share any update about it. Samsung DDR for Main B'd : ALT ask to share the plan for Samsung DDR ECO before checking the cost. ALT will inform whether it is OK or not. And please provide cost that we conduct it for Main b'd and Amp b'd seperately and the cost that we conduct it both Main / AMP b'd simultaneously. [2/23] There are some misunderstanding. 1. Fii would like to perform DDR 2nd source introduction and testing for both AMP board and main board in the same time for cost & resource consideration. Miya will prepare the cost proposal and discuss with ALT biz team directly. 2. The Nanya DDR3L memory sample will be hand carry by Fii other project's RD. The sample will be arrived to Vietnam on 3/1. PM An will arrange RE team to rework NANYA DDR3L on AMP board and function test. The schedule should in on early of March. [0217] Foxconn will prepare new DDR3L introduction both SAMSUNG and NANYA. ALT asked Foxconn to send why Foxconn change their preparation and the cost difference(reliability test) by e-mail. ALT will review Foxconn's feedback and will give ALT's opinion. ALT is testing 3 samples with NANYA DDR3L and there is no issuse yet. [Fii 0216] Hynix DDR3L inventory remaining 7271 pcs and may run out around May [0210] ALT will conduct aging test next week. ALT will update the result the end of next week., but ALT will keep testing Foxconn will send new DDR and PCBA to VN Factory to make sample. Foxconn VN send it to Foxconn TW and then it will be delivered to NANYA TW for SI Test. [Fii 0209] Fii will send DDR samples and PCBA to VN for rework and prepare 4pcs samples for DDR test. Applying for a Fedex account internnly. [0203] ALT will check new DDR for aging test. Foxconn will SI test in parallel and Foxconn will conduct reliability test after ALT test. [ALT 0120] ALT contact NANYA Korean agent this week. ALT will receive sample from them. [0113] Delivery cost will be higher than material cost. So ALT will contact in Korea. [Fii-0112] Supplier can only delivery DDR3L memory samples to Fii TW and Fii has got samples on 1/12. Need ALT provide Fedex account to Fii then Fii will delivery samples to ALT. [0106] ALT needs 5 samples. Delivery schedule will be updated by Foxconn TW. It may next week. [Fii 0105] How many pcs of NANYA DDR3L memory sample do ALT need for validation? [1223] ALT will check and inform to Foxconnn about the no. of samples for test by 12/26 [Fii-1222] NANYA can support DDR SI test. How many pcs of NANYA DDR3L do ALT need for validation? We can ask free samples from vendor and send to ALT for verification. [1209] Foxconn asked ALT to pay 4K 4Gb DDR3L memory for 2023 PO. ALT cannot accept it, but it should discuss more seperately. [1208-Fii] Hynix 4Gb DDR3L memory (H5TC4G63EFR-RDA, Location: 3U1, Sub-board: AMP board) has EOL on Jun 2022, LTB is at end of Dec, 2022. Need ALT's approval to buy this part to meet 2023's demand, and also need ALT to validation 2nd source asap.
H/W | USB Hub IC reset control |  | Monitor |  | [0324] ALT is collecting additional defect samples. After that ALT will verify their HW rework. But ALT didn't get additional defected unit yet. [0303] ALT received additional BT defected unit last week. X-Tal was defected, not GPIO. ALT cannot reproduce HDMI issue on defected unit yet. ALT will wait for additonal sample that has same HDMI issue. Before define root cause, ALT will replace PCBA for GPIO issue. [0217] ALT received a BT defected issue. It is GPIO issue. But ALT found HDMI issue in a BT defected unit with HW ECO. ALT will not apply HW ECO again for BT defected unit until HDMI issue is not related GPIO. [0210] ALT will receive new BT fail sample on 2/14. ALT will update the review result next week. [0203] SKB reported additional 17 pcs, SKB will provide 4 defected units. ALT didn't not know that it is related to GPIO issue. After receiving defected units, ALT will update it. SKB already updated new firmware(over 80%), but users may not know the defect. Now it detected by SKB system, not customers. [0113] ALT receive another 2 more defected unit. ALT reworked and will send to customers. [0106] ALT tested with defected unit and SW that support passive Standby. USB HUB is reset at every Passive Standby on by power on reset. ALT tested it with 2 defected unit. So ALT apply the HW change for defected unit and send back to customer. ALT will keep monitoring it. [Fii 0105] The current software reset for USB Hub only operated when the system is powered on. If it's just for repair purposes or to clarify the BT failure. We think it's OK to do this change. However, our S/W engineer is implementing the passive standby now, and we found that the USB hub may be unstable when system resuming from passive standby. So, we have to use SoC to reset USB Hub again to make sure it works normally after passive standby. [1223] This request is not for HW design change. It is for repair BT defected unit related to GPIO issue only. Foxconn will check whether BT reset is required for passive standby. [Fii-1222] Foxconn recommand to keep current design, because USB HUB IC reset control by GPIO can 1. Keep reset pin low during passive standby mode that can fullfill power consumption requirement for SKB. 2. Reset USB HUB after enter operating mode that can avoid BT unstable issue.
H/W | SWAN_VE Consideration |  | close |  | [Fii_0928]Done [ALT_0922] Please provide the price via mail instead of Wechat. ( Fii reply will send it by next week ) [ALT_0825] Fii agreed to give the total price to ALT by next week. [Fii_0824]After internal discussion, the quotation would be procided by next week. [Fii_0810]Fii will reply before 8/18. [ALT_0804] Please let us know the target date for the reply. [Fii_0804]As we know, AML will not support this project.Please make sure AML will support or not. Price is under inter disscussion. will porivde ASAP. [ALT_0728] Fii will provide unit price roughly today. [Fii_0727]Fii will send reply the ref. price to ALT's biz team first. [Fii_0720]Target date is 7/25. [ALT_0714] Fii team will reply it ASAP [ALT_0616] Fii will provide the VE based on the AML solution after TW holidays. [ALT_0609] ALT will reply after internal discussing. [Fii_0601]Miya has replied by mail on 6/1. [ALT0526] ALT will reply to the design concept via mail to Fii by next Tue. ALT will discuss Dolby & SoC issue with SKB and then give feedback to Fii. Please find out the cost-down solution and provide us with a proposal. ( target to cost-down around $70 ) [Fii 0525] ALT provide the doc of SWAN VE consideration to Fii on 5/25. Fii have reviewed the doc and found the design change is big, which will impact the the whole product design including hardware, mechanical, certification..,etc. So, we think the evaluation should take place before both biz team agree on this change.
H/W | SWAN DDR4 and SoC VS550 Compatibility issues boot up fail(Auto reboot) | FII | Close | 2023-10-31 | [ALT_1222] Closed. [Fii_1207] 1. No further update .Fii have shared the Synaptic's opinion mail on 12/20. [ALT_1215] Please share the Synaptic's opinion mail with us ASAP. [Fii_1214] Upload 8D report of hang-up/reboot issue. [Fii_1207] 1. No further update . Snaptics make the conclusion that this maybe a Special marginal issue, which only happens on part of Hynix D-die DDR on U3.Tunning DDR parameter of SoC can’t fix the issue. 2. Will update the test station information by 12/8. [ALT_1201] Please share the test station solution(filter the issue board) with us for further understanding. [Fii_1130]: So far, Synaptic don't have new test item for this issue, and Hynix reply that their DDR are meet the JEDEC standard. From Fii, the solution to fix this issue now will be add a test station to filter the issue board, and then switch the U2&U3 DDR IC to eliminate the reboot issue. Synaptics is considering covering the cost of increased Fii manufacturing expense. [Fii_1123]: 1.Try to bridge with Hynix Shanghai team to support the test mentioned by Synaptics. 2.Hynix and Synaptics test report as beside. [ALT_1117] Please update the Hynix and Synaptics test report to us. [Fii_1116]: 1. Send one more NG board to Synaptics. Synaptics will feedback test result and try to find any tunning for this issue. 2. Try to ask Hynix FA team in China whether can help the test what Synaptics mentioned for narrow the issue. - SI quality of Read waveform for more data bits. Previous report just covers Write and ADCM, and the coverage is just for one data bit, we can’t find out if the weak point is in other data or ADCM lines. The test should be easier on Interpose board. - AC timing protocol test with logic analyzer by Hynix. We don’t have equipment to do that test. [ALT_1110] 1. Please provide the Hynix test report to us. 2. Please include the ALT members in the Hynix and Synaptics emailing list regarding this issue. [Fii_1109]: 1. SI test report on U3 from Hynix is finisfed.The result is pass. 2. Synpatics provide SoC analysis report and indicate that this issue follow the NG DDR IC. It could be special marginal DDR part on U3. 3. Hynix said that DDR production will have different margin timing, but they all follow JEDEC Spec standards. 4. Synpatics countinue try to tune setting and ask Hynix help to do some test for narrow down the problem. [ALT_1103] Please share the Hynix test report with us and let us know your comment on it. [Fii_1026]About Synaptics' analysis report, Synaptics want to wait for the U3 SI test report to find whether there is any possibility of adjustment.Therefore Fii will continue to work with Hynix to complete the DDR SI for U3 location first and then decide the next action. [ALT_1020] Fii confirmed that it can be sorted all the defective units with new test process of 10 times. We are still awaiting Synaptics' analysis report. Please send it to us as soon as possible and keep us updated on the progress. Please forward Synaptics's email to us ASAP. [Fii_1019] 1. The difference between 10 times and 5 times : Production capacity is reduced by 50%, and the test time for 1pcs is increased from 50 minutes to 100 minutes. Factory confirmed that it needs to be increased from 2 OPs to 4 OPs to meet the same production capacity. 2. Synaptics feedback: 2-1.Synaptics have tried to tune the DDR setting, but can’t find any improvement for this NG part at U3. 2-2.Synaptics want to wait for the U3 SI test report to see if there are any failure or weak point, and then the DDR team will consider whether there is any possibility of adjustment. 2-3.If the SI report result is pass, Synaptics will consider that the issue is related to the NG DDR IC.Fii will summarize the test results and feedback to Hynix, and ask Hynix to confirm again. [ALT_1013] Please provide the test time difference from 5 times to 10 times production capacity & working hours first. 2nd, Please forward Synaptics last week's feedback and this week's feedback to us ASAP. [Fii_1012] Factory already add FATP(test station) to filter NG board now,the test method is to power on/off 5times(10 minutes each time). PE test 2 NG board and get the failure rate of NG board is 65%. in the future, we will try to increase from 5 times to 10 times for ensure that NG boards will not be shipped, but the production capacity and working hours need to wait for the factory’s confirmation and reply. 1.On DDR-2133 speed, both NG part and normal part work well on U3, and vTS window shows no difference. 2.Normal part works well on U3 with DDR4-2400, vTS shows good result. 3.Synaptics have put this NG part on U3 of reference board, the issue can be duplicated. Considering this project is MP, Synaptics does not currently recommend adjusting DDR settings to avoid potential impact on shipped product. [ALT_1006] Can the factory add some testing processes to filter out this kind of defective unit? Also please provide this kind of failure rate to us. in the meantime please keep updating the analysis results from Synaptics and Hynix. [Fii_1005] 1. Fii sent the defective board to Synaptics Shanghai and Synaptics start the test from Sept. 11. The following are the current test status provided by Synaptics so far. 1-1. The issue can be duplicated easily on DDR4-2400 on U3. Stress test failed. Failure points are on Byte4&5 1-2. Synaptics tried to change VS550 Driver strength setting, but no help 1-3. Tried DDR4-2133 speed, stress test passed. 1-4. Synaptics have put the NG DDR4 part on U2, and checked vTS window. But found it works well, and vTS window has no difference with normal part. It looks like a marginal issue with special DDR part on U3 2. Fii also ask Hynix to perform 2400Mbps DDR4 SI test at U3 position. Fii have provided a board to Hynix Taiwan on 10/5. It will takes at leat 3 weeks to test and expected to get result by end of this month(October).
H/W | HDMI cable test | ALT | Close | 2023-12-01 | [ALT_1201] SKB require 2pcs HDMI cable for testing purpose. Foxconn confirmed that there is no concern to use HDMI cable for test purpose. So ALT provide SKB with 2 pcs cables.

## Factory
Category | Issue | owner | status |  | Progress
SMT | Microphone Void issue | Fii | close | 2021-09-10 | [Fii 0630] Will follow ALT suggestion on next MP build for 5% x-ray inspection and OBA report. [Fii 0623] VN SMT can do 5% X-ray inspection under 35% mic void. We need ALT to provide the OBA ducument format for VN Factory review. [Fii 0616] VN SMT can only do 2% X-ray inspection under 35% mic gap, because our factory has only one X-ray machine, it can't be occupied by SWAN products only. So, we need further discussion with ALT about the inspection rate. [Fii 0610] Will discuss with factory side and see if factory can accept the x-ray inspection requirement required by ALT. - First: finish SMD board (10pcs, MIC 40pcs) must x-ray inspection for MIC void every SMD lot - Every 1 hour per 5% inspection (only MIC component) - OBA report attached X-ray inspection result and x-ray image [Fii 0602] VN SMT changes new stencil, one is bridge(Type-1), the other is sector aperture(Type-2). If the spec is under 25% of void, the failure is almost 100%. Please check detailed report on mantis 1315. The result is better than the previous test, but still far from what we expected if ALT requires void to be below 25%. Need further discussion about the requirement. [Fii 0526] VN-ME will proivde the internal report to RD/PM on 05/27. Once we review it completely, we will provide to ALT ASAP. [Fii 0519] No further update. [Fii 0512] RD keeps monitor to meet 25% of void. [Fii 0505] No further update. Wait ALT reply. [Fii 0428] The fail rate is 1.07%(22 pcs fail/2060 mic) which is higher than 0.75%(3 pcs fail/400 mic). The report had updated to mantis. Only fail mic components x-ray picture put in report. [Fii 0421] VN SMT has done some quantities. When we get the report, we will update to mantis. [Fii 0414] The next SMT is expected to start from next week. The proposal will be provided and updated to mantis next week. [Fii 0407] Wait VN SMT ME provides proposal of 1000 pcs void x-ray test. [Fii 0331] ALT requires 750~1250 pcs (3000 ~ 5000 mic sensors) and it is a big quantity for VN SMT. Due to X-ray machine is the only one set on SMT line, 250pcs (1000 mic sensors) will be satisfied to ALT first. VN SMT will provide in separated way to collect enough quantities. [Fii 0324] Will do 1000pcs time-4 solution to decide profile solution on VN SMT line. [Fii 0317] VN SMT had provided risk components list, and update to mantis. There are, FFC connectors(J6_1, J3_3, J3_2, J3_1, J1_1), MIC components(Mic1~Mic4) and FFC connector(J813). Critical temperature is 250 deg-C. [Fii 0310]: VN SMT will decide which profile prefers for mic void issue. [Fii 0303] Please refer to our comment on mantis 1315. The new profile seems worst than current profile setting since there are more solder ball issue with new profile. [Fii 0224] Factory arranged 100pcs sample build and has completed on 2/23. The report can be provided on 2/25. [Fii 0217] The test condition of next built will keep the same time for preheat/soldering as VN SMT suggestion but peak temperature will follow ALT require, 248 deg-C. The factory will be able to arrange the sample build next week. [Fii 0210]: Facotry has some problems for preheat/soldering time as decreasing time too short. Facotry suggests 1 deg-C/s is better. Have updated it on mantis 1315 [Fii 0126]: Facotry has done a DOE yesterday (1/25) but the void rate (>30%) is not improved, will update result on mantis 1315 for ALT review today. And will continue to discuss with ALT/factory to see if there are any suggestion for the next test. [Fii 0120]: Stencil verify results: S3X58-M500 (old) solder paste 0.09mm: void:2F/200; solder ball: 4F/200; O-ring void: 5F/200 0.10mm: void: 2F/200; solder ball:2F/200; O-ring void: 0F/200 Next plan: new solder paste + 0.1mm stenceil + Fii optimized profile will be arranged and started from next Tuesday (1/25). [Fii 0113]: Next plan: S3X58-M500 solder paste+stenceil0.09mm+Fii optimized profile. The SMT is on line on 1/13. Updated on mantis 1315. [Fii 0106]: New solder paste S3X58-HF1100 control run had finished and the situdation seems not good enough and less than Fii optimization profile. Void solder: 7f/400, fail rate=1.75%[Fii optimize fail rate=1.50%] Solder ball: 9f/400, fail rate=2.25%[Fii optimize fail rate=2.5%] O-ring: 11f/400, fail rate=2.75%[Fii optimize fail rate=0%] Maintis: 1315 [Fii 1230] No further update. [Fii 1223] 1. DOE report of ALT and vendor suggestions had provided to mantis(1315) 2. The VN factory just received new solder paste sample from vender on 12/23, and MFG PM An/ME engineer will arrange the control run to see if the void can be improved. Will update the schedule to ALT when the schedule confirmed by VN factory. [Fii 1216] 1. Factory has completed experiments to reduce the reflow time, but we found that some O-RING of MICs have void issue. Need factory to update the overall test result. 2. Waiting for new solder paste sample from vender for further experiment. [Fii 1209] As discuss with solder paste vendor and FXN SMT ME, we will change new solder paste. And apply new 1KG smaple of S3X58-HF1100. While receiving new solder paste sample, vendor and SMT will do some DOE for void issue.
Material | Pre-MP (100pcs+ 1K) material shortage | ALT/FII | close | 2021-09-20 | [0910] 1. REALTEK PHY IC (Usage*1) : 2022/12/31 ETA => 100pcs usage: move from Eagle, 1K usage: in shortage 2. Inkel all materials : under checking in factory => 100pcs usage: ok, 1K usage : need ALT to confirm gap q'ty 3. [AMP board related] - CAP CER 120pF 5% 50V (Usage*8, LT=126 days) => 100pcs usage : ETA 9/22, 1K usage : ETA 10/10
Material rework | Pasting the required tape on holder MIC *Rework q'ty: for 1.1K pre-MP only *Holder (446.00185.005) *Tape will be provided by ALT | ALT | close | 2021-09-07 | [Fii 0908] Factory commented that it's not qualified to production based on ALT SOP. The jig is still necessary to pasting the tape. [Fii 0906] Factory received the video and under checking. [ALT 0901] ALT commented that the tape could not be improved because the vendor already did their production. Will provided a video to show how to paste the tape for Fii factory reference. [Fii 0830] Waiting for ALT's comment for further discussion, such as material improve plan, jig plan. [Fii 0825] CFT will provide jig 3D document for reference. ALT could discuss the design with their vendor based on this draft 3D. [Fii 0823] MFG did DFM. There are two major issues 1. The adhesion force of holder side is not enough. The material of tape is too slight and not easy to be sticked. 2. Shall require the vendor to paste it and ship out the holder because it shall be sticked by their exclusive jig.
Material rework | Adding ferrite core and attaching EVA sponge on L-CH and R-CH speaker cable *Rework q'ty: for 1.1K + 15K *L-CH speaker cable (377.00347.005LT) R-CH speaker cable (377.00346.005LT) | ALT | close | 2021-09-07 | [Fii 0910] Waiting for the samples to verification. [Fii 0906] Need ALT to provide the ferrite core and EVA sponge (484.00429.005). [ALT 0901] 1. Spec for IQC: follow the spec that ALT updated on mantis 1308#c8006. 2. SOP for IPQC: follow mantis 1270#c8034. * Adding ferrite core and EVA sponge on both L-CH and R-CH speaker cable. [Fii 0830] Waiting for ALT to update 1. Spec for IQC 2. SOP for IQPC [Fii 0827] Received SOP on 8/26. Need to discuss the details about IQC and IPQC criteria with ALT. [ALT 0820] Will provide SOP by 8/27
SI | SW version for Pre-MP | ALT | close | 2021-09-03 | [ALT 0903] SW version for Pre-MP. Main SoC SW Version : 19.531.16 AMP B’d SW : 0x22 [Fii 0903] Factory is asking when can they receive the image to fine-tune the acoustic test equipment and verify the full production process.
SI | VI specification *Manufacturing Specification *Visual inspection criteria | ALT /Fii | pending |  | [ALT 0126] Inkel will prepare and send the sample on 2/9. So ALT may send Golden samples the 4th week of Feb.(by 2/25) (depends on logistics status) [Fii 0126]Please check when the golden sample can be provided? [Fii 11/24] Need ALT to update visual inspection criteria including Scratch housing, Assembly GAP spec, BTV Deco plate spec, Grille clothe(音響網布). [ALT 1104] INKEL will provide Golden sample 11/8 in China. Due to delivery issue in China, we hope we can receive it 11/15. After we review the golden sample, and then we will provide it to your factory. [Fii 1001] 1. When will our SQE recevie the golden sample? 2. According to the visual inspection criteria that ALT required, it's not possible to run next build (1K) under the current incoming housing status. There ared two suggested plans if SKB still needs the next 1K. a) Our PQE list the attached visual inspection draft based on the current incoming materails status for your reference. Because the criteria is quite different from what you asked before, please discuss with SKB whether they could accept the revised criteria. b) Please discuss with your vendors to improve the materails and redelivery as soon as possible. We'll work with our factory to do 100pcs control run again based on the new incoming materails. After we complete the production, we will update our suggestion again. [Fii 0924] Required q'ty: 2 sets with ALT owner signature and date <recipient informaton> Fuyu precision component Co., LTD Lot M1 and Lot F, Quang Chau Industrial Park, Van Trung Commune, Vietyen district, Bacgiang province Name: SQE Tuan Phone: 0394353939 [Fii 0914] Factory require to have golden sample as the standard of visual inspection. [Fii 0901] Fii did provide our feedback. Please check and list down your question so that we can arrange a meeting with the factory and ALT. [Fii 0825] CFT will update their first verson within today. [Fii 0819] The ME R&D and factory ME checks the customer reply. [Fii 0812] Please check the questions raised by mantis #1126. [ALT 0804] The ALT provides documents to the factory for check. [Fii 0428] factory will compare to the real production status and feedback. [Fii 0423] received the VI spec and will review with factory and reply by 4/27.
Capacity | Monthly demand to be updated | Fii | close | 2021-09-20 | [Fii 0914] Production layout will be 10K/M. But need ALT to consider how to reduce assembly effort (related to cost and quality). [Fii 0909] Factory will update capacity based on 100pcs control run. [Fii 0825] Fii CFT to update assembly daily capacity. [Fii 0823] Capacity : 300/D (7.5K/M) based on w/o air leakage testing. * The capacity is reducing if ALT RD keep asking to add test item. [Fii 0603] Fii to update monthly forecast.
Production | ALT commented DVT3_assembly review result | Fii | close | 2021-09-10 | Factory is under reviewing.
Production | 1. SI test plan 2. OBA test plan | Fii | close | 2021-09-10 | [Fii 0903] Fii to provide the test plan based on pre-MP process (Mantis#1126)
Production | FW confirmation: secure/non-secure | ALT /Fii | close | 2021-09-10 | [ALT 0910] ALL shall use secure image. Would like to confirm the allocation for 100pcs + 1K FW
Production | ALT to review pre-MP PMD | ALT | close | 2021-09-13 | 1. pre-MP assembly PMD (Mantis#1270) 2. ALT assembly SOP => L-CH, R-CH speaker cable is opposite.
Materials | Inkel material in shortage for pre-MP(1.1K) | ALT | close | 2021-09-24 | [Fii 0924]484.00422.005 (usage:6) 1. 300pcs is in shortage for 300 DUT control run. 2. Inkel doesn't commit ETD schedule for 5100pcs. Others: need Inkel to pull in to 9/25.
IQC | IQC criteria on speaker cable | ALT | close | 2021-09-24 | [Fii 0924] ALT require Fii to have tug test on 15K speaker cables. However, our SQE checked with Dreamus that Dreamus didn't follow ALT's instruction to do tug test on their OQC process. Besides, Dreamus only did 10pcs sampling based on their testing criteria. Our IQC is blocking the whole speaker cables right now. Need ALT to check with Dreamus. => Curretnly, the line is lock-out due to material shortage.
MOH | MOH cost down & ME design DFM (Mantis#1131) | ALT | pending |  | [ALT 1104] ＊INKEL will provide their review result by 11/5. 3- Screw issue on heat spreader : ALT asked to INKEL to check to change 1 screw type for all heat spreader screw. INKEL is looking for a way to change all screw to 1 type. For this, they are checking the cost and development time. 4- Screw issue on bottom cover : ALT asked to INKEL to use same screw type for bottom cover. INKEL is checking the cost and development time to change M3x12mm Flat type screw to normal type screw with Tooling change. ALT already inform that FII can use M3x7mm screw for the screws under rubber foot instead of M3x10mm, but torque should be 3Kgf*츠. 5- Hole dimension issue on bottom cover 6- Assembly issue on LED board There is no space to attach sponge on Grill Fabric Ass’y. So there is no way to attach sponge on Grill Fabric Ass’y. 7- Screw issue on main b’d Foxconn can use M3x8mm screw instead of M3x7mm from 2K MP 8- Housing issue INKEL will provide LED Side Bracket with PE bag. It will apply after 2K delivery. ＊ALT will check the cost for Tooling change, schedule, assembly cost reduction due to tooling changes. And ALT will decide which solution will use and when those component change can provide. [Fii 1014] Please check the updated file in Matnis. [Fii 0928] 1. We need to know the target date that ALT agree to apply for production preparation. 2. Factory is preparing their DFM. Will update in Maintis on 10/1.
Assembly | Mechanical change from 1st MP (Mantis#1352) | ALT | close | 2021-09-24 | [Fii 1008] Factory would like to evalute the changed materials to make sure it won't impact the production. Is possible that ALT ask vendors to deliver 2 sets samples? Fuyu precision component Co., LTD Lot M1 and Lot F, Quang Chau Industrial Park, Van Trung Commune, Vietyen district, Bacgiang province Name: PM An Tran Phone: 0327091936 [Fii 0924] Need ALT to double confirm the datasheet/drawing of new materials. [Fii 0915] Because we have to control the component and usage in BOM, we need to check the change list, such as screw, housing, gasket…, and change timing with ALT. Fii to provide the list on 9/16. Please double check and feedback by 9/24.
Quality | Inkel housing quality issues (Mantis#1385) | ALT | Close | 2021-11-12 | [Fii 1125] Need ALT to check the Inkel housing issue can be improved after 13K pcs. [Fii 1105] Please refer to the documents in Mantis#1385. Because their quality impact to our production capacity (Fii factory took time to sort their housing in production line.) , need ALT to push vendors to imrpove immediately.
Quality | [SWAN] [MP] 2022.05 Mass production inspection report | FII | close | 2022-07-06 | [1104] Foxconn didn't apply ethernet unstable solution for factory SW. ALT closed this issue. [1028] ALT would like to know that SW fix on Ethernet Unstable applied for next Factory SW. It should not apply it because customer SW didn't have this changes. This change should apply to both MP SW and Factory SW at once. [1020] Tack switch As per ALT agree with spec. change, we will keep using the same part number and update the datasheet in our system when all tact switch are out of stock. [1014] Tack switch This Tack switch is only for SWAN. So vendor can provide new specification tack switch after original tack switchs are out of stock. VN Factory has 41,592 origianl FFC cables and 60K in HongKong ware house and 75K in vendor's factory. [Fii 1013] Tack switch: Currently there is about 176K of old tact switch(+/-50gf) in stock. We plan to apply new part number for new tact switch and make running changes to the new part after the old part runs out. [1007] Tack switch spec. change Foxconn need the no. of sample that ALT needs. And Foxconn can provide the each press forces for each sample. ALT will check the no. of sample and feedback to Foxconn by next week. Ethernet unstable : Foxconn will collect more defect sample and test again when they have next mass production and validate their solution with more sample. After that Foxconn will apply register change for next build. [Fii 1006] 1. Ethernet unstable: Has finished test. All samples (defective PCBA x2, OK set x10) can pass test. 2. Tack Switch spec. change : 2.1 Vendor confirmed that the spec. change will not impact the cost. 2.2 Vendor can't provide the upper & lower limited samples (130/160/210gf) because it's hard to screen out such samples in their factory. Vendor only can provide new spec. samples (160 +50/-30gf) for testing. 1. Ethernet unstable : Foxconn still have 2 pcs to test 24Hr CRC. It will finish by 10/4. ALT test was OK with 1 defect unit. It tested almost a week. 2. Tack Switch spec. change : ALT accept to change spec. from -50gf to -30gf if there is no cost imact. ALT asked Foxconn to check when Foxconn can apply it. Foxconn will check it and feedback to ALT. ALT asked to provide samples on Mantis. [0929] 1. Ethernet unstable : Will finish 24Hr CRC test on 10/4. 2. Tack Switch spec. change : Wait for ALT reply. [0923] 1. Ethernet unstable : ALT has a defected Unit. ALT is testing for more than 2 days with SW that Foxconn provided. There is no issue, but ALT will keep test it for a week. 2. Tack Switch spec. change : ALT is reviewing it. ALT will inform what ALT think later on mantis. [Fii 0922] 1. The test SW has been provided by River on mantis 1506. How about the test result in ALT side? 2. Can ALT accept the tact switch spec. change to 160 +50/-30gf? [0916] ALT got another Ethernet unstable STB from the inspection. If FII provided test SW, then we will check it. [Fii 0915] 1. Ethernet unstable issue: 1-1. Ethernet unstable- Fii has finished 2 NG PHY and 1 OK PHY each 12hrs high (50˚C) / low (0˚C) ambient temperature test using value 0x60 of SOC internal delay. Test result are pass. 1-2. The long time stability test also has started. There are 2 NG PHY and 1 OK PHY are completed and passed. The rest test will be completed by 9/23. 2. Tact Feeling is not good 2-1 The current supplier FIT can sort the tact switch with 160+50/-30gf component. If SKB only concern about the press force is too lightly, and we think the current FIT's component can be acceptable. 2-2 The datasheet of new tact switch (+/-30gF) has updated to mantis.(mantis:1493). => 내부 검토 후 알려줄게.. Pin configuration이 같은지는 Foxconn이 검토하여 알려주겠다. [0908] Ethernet - Foxconn is testing 12 DUTs now. It takes 1 day/1pcs. ALT asked to conduct this test in parallel at the same time. Foxconn will check it with SW engineer and provide test schedule by today. Tact Feeling is not good - ALT can accept +/- 30gf press force torrence. Foxconn will check the cost and sample delivery with vendor. After receiveing the cost information and sample schedule, Foxconn will update it to ALT. Powerway is in QVL. [Fii 0907] 1. Ethernet Unstable - Fii have found out the middle value(0x60) for SOC delay winodw of 10 good DUTs. The results have updated to mantis(1493). Next will long term to test with 0x60 for CRC error test. 2. Tact feeling is not good -> Have updated the structure of tact switch on mantis for why the vendor only can provide +/-50gf switch. The material of switch is metal dome or spring which is limited by material spec. It looks like the press force +/-50gf is a standard spec. for the switch type we used in SWAN. -> Only one vendor (Powerway) reply that they can customize +/-30gf based on the current mold. Need to discus with ALT if +/-30kg press force is acceptable? [0901] 1. Foxconn will share their test result with both SOC and Realtek. SoC and Realtek already review Circuit diagram and PCB layout when Foxconn developped SWAN. There is no issue, but it need some tune normally. Foxconn will add delay and fine tune with SW Engineer. It will be updated soon. Foxconn thinks that it is related compatibility. So there is no need to exchange defected part to Eagle and test. Foxconn will check compatibility issue adn suitable setting with SW Engineer, and feedback it by this week. 2. Foxconn contacted 2 other vendors. Foxconn can update its test schedule in this week. [0831] 1. Ethernet Unstable - Fii have updated the RGMII timing measurement & SoC CRC windows fine tune report on mantis 1493. Measure the PHY IC delay waveform, no.1 NG PHY IC is 167ps; no.2 NG PHY IC is 442ps with 0ns RX delay pull high resistor. No.1 NG PHY IC is 1.733ns; no.2 NG PHY IC is 1.879ns with 2ns RX delay pull high resistor. They look normal compare with good PHY IC. Fine tune SOC delay window is no.1 0x06~0xB0, no.2 SOC delay window is 0x1E~0xAA. The no.2 NG PHY IC which SOC delay window is narrower than no.1 NG PHY IC. Will test middle SOC delay window value to good PHY IC board for long time test. 2. Tact feeling is not good - We are surveying FXN QVL vendor for +/-20gf torrence switch. [0826] LED issue - Foxconn will update any corrective action from vendor. Tact feeling is not good - Vendor cannot change its specification and handle press force that ALT asked. ALT worried that this tact feeling is handled by operator only in manual. Foxconn TW will discuss with VN Factory and their plan for next step will be informed by next week. Ethernet Unstable - There are 2 defect units. Foxconn TW and Realtek both have one. Factory already have sorting method for it. ALT asked Foxconn to update the no. of defect units of this issue after 1K additional production now. Foxconn is discussing with Realtek to handle this issue. ALT asked Foxconn provide timing information(RGMII CLK/Data) with various condition, such as, no delay, 1ns delay and 2ns delay. Foxconn will do and inform to ALT after test. [Fii 0825] 1. Fii QA have updated the 8D report on mantis 1493 for LED no light issue & power button feeling NG issue. 2. For Ethernet unstable issue, Fii RD tried to add 2ns RX delay on Eth. PHY and the CRC error will improve but it's still not zero. Fii SW RD tries to add 1ns delay on SoC and the CRC error improve to zero. 3. Fii will work with Synaptics and try the Eth. RX delay parameter to find the best solution. [ALT 0819] Status update ? Ethernet Unstable : Foxconn VN Factory received defected part and tested again. It passed on VN Factory test. Foxconn VN Factory sent it to TW and Foxconn Taiwan tested it again. But they found CRC error. Foxconn TW thought it about SoC compatibility issue. Foxconn TW sent its test report to SoC, Realtek. Foxconn will have conference call today afternoon. After conference call, Foxconn will update about SoC feedback. ALT had 3 defected unit, no ethernet 1 pcs, ts loss 2 pcs. All defected units already sent to Foxconn Factory. So ALT doesn't have it. Tact feeling is not good : Foxconn will provide feedback on tact switch push force spec from +/- 50gf to +/-20gf by 8/19 [ALT 0812] MP issue on May,2022. Mantis # 1493 is for MP issue in May, Mantis #1506 is for MP issue in June. Move report from #1506 -> #1493. LED Not work - LED Defect, Corrective action had been applied from 4/23. Until apply auto test, operator check it manually. Ethernet Unstable - Foxconn received Realtek's FA report yesterday night and it uploaded on Mantis. There is no abnormal in vedndor's FA. They think it is NTF Foxconn will discuss about this issue with Realtek first and update what the next step is on Mantis. No sound - There is no issue when they assemble defected AMP b'd. Foxconn think that it is NTF even though some resistors were changed by vendor. No boot - No screen after booting animation(SW issue) Cosmetic damage Screw assembly Tact feeling is not good : Foxconn will update below items by 8/12 Standard tact Switch Tension Measurement value of the defected tact switch tension in both part level and assembly level [Fii 0811] VN QA had update thte 8D report for LED not work. [Fii 0804] VN QA had provided updated 8D report to ALT review on 8/4. [Fii 0714] Factory said vendor is still analysis and will update on 7/16. [Fii 0707] Factory will send the report on 7/11 [ALT 0630] Issue up the BFX-UA300 MP delivered on 2022.05 inspection result on 6/13, but still No update https://mantis.cnsbg.foxconn.com/vaas/view.php?id=1493
Quality | [SWAN] [MP] 2022.01-03 Mass production inspection report | FII | close | 2022-07-06 | [1020] Silergy defect chip has EOS, so there is error on data write. But it is too small to find the defect after decap. But Silergy add some Data RW test in their ATP. [1014] Silergy provided their FA report. Silergy cannot find any abnormal after de-cap. So they reported the root cause of issue is related to EOS. But Foxconnn need more discussion with Silergy why they think. Foxconn will have meeting with Silergy and update their discussion on mantis with Silergy FA report. [0930] Silergy will give their report by 10/12. China has long holidays early of Oct. [0923] Foxconn get FA report from vendor. Vendor suspected the mico-crack on the component level. Vendor will check micro crack after de-Cap. Vendor's ATE test is not enough to check current issue. They think that I2C read has issue and it is root cause of this issue. Foxconn will share new FA report from vendor ater the meeting. [0916] Test result or plan ? Foxconn Factory received review report from silergy, but it is not enough. They will discuss more. [0908] PCBA arrived to silergy yesterday. Foxconn Factory will check the test schedule and inform it by next monday. [0901] Foxconn provided PCBA with defected component last Saterday. It will arrive today in Silergy. Foxconn keeps updating its status. [0826] Silergy sent right part to Foxconn Factory. Foxconn PE send wrong picture for defect sample. So it made some mistake. Foxconn will send PCBA to Silergy with defected component by tomorrow. And Foxconn will explain what Foxconn factory did on mantis detail for ALT understanding [Fii 0825] The VN factory has clarified that the IC sent back by the supplier is a defective unit, and the factory PE inspected the fault symptoms and confirmed that it is a defective unit. [ALT 0819] Foxconn VN Factory received defected unit from vendor, but it is not the part that Foxconn sent to vendor. Foxconn will ask vendor to find the part that Foxconn sent before. ALT ask to improve the RMA process not to happen again this situation. Foxconn will discuss internally and make some process and feedback to ALT soon. [Fii 0818] VN factory already received Silergy IC yesterday, and SQE has sent IC to Bac Giang factory for I-V analysis. Our PE will do further analysis on this IC after I-V analysis. Vietnam QA will update the report on mantis1465 on 8/18. [ALT 0812] Silergy found out the part that they test for defect analysis. Silergy already sent chip to Foxconn. It will take about 10 days. Foxconn VN PE will start analysis more. ALT will check this issue and will ask some tests on mantis when they need any other additional tests. [Fii 0804] For Silergy IC issue, QA will ask vendor to send back the defect PCBA for further analysis. [Fii 0714] Factoy will check and reply. Keep updated. [Fii 0707] Factory provided report on 7/1 [ALT 0630] Issue up the BFX-UA300 MP delivered on 2022.01~03 inspection result on 4/19, but Only the initial analysis was reported. https://mantis.cnsbg.foxconn.com/vaas/view.php?id=1465
Sales | [SWAN] Extra Product, PCBA and Spare parts for RMA | FII | Close | 2022-07-30 | [0901] Close [0826] ALT need some additional information for customs clearance in Korea. Foxconn will provide it after meeting. [ALT 0811] Factory already sent document for customs clearance . The ETD is 8/16. The receiver information will be updated after weekly meeting. [Fii 0714] 1. Extra Product(0.2%) : 60pcs -->Factory will ship on 7/29 2. PCBA(0.2%) : Main, Amp, LED, Side LED R, Side LED L, Mic, Button – 60set -->Factory will ship on 7/29 3. Extra Spare parts -->Factory will ship on 8/12 [ALT 0630] According to the SOW agreed by both parties, please provide the available date of delivery of extra products, PCBA and spare parts for 30K demand in 2021. 1. Extra Product(0.2%) : 60pcs 2. PCBA(0.2%) : Main, Amp, LED, Side LED R, Side LED L, Mic, Button – 60set 3. Extra Spare parts
Quality | [SWAN] [MP] 2022.06 Mass production inspection report | FII | close | 2022-07-29 | [0901] Foxconn already finish test. Foxconn will provide test report by next Monday with CRC Test result. [0826] ALT already give Go sign to Factory. There is no additional acceptance to produce 1K more. Foxconn need additonal GO sign for additional production after 1K production. But ALT asked Foxconn to discuss with ALT Biz team one by one. [Fii 0825] Fii QA have updated the 8D report on mantis1506 on 8/25 [ALT 0819] ALT didn't review about it. ALT will review and leave comment on Mantis if necessary. [Fii 0818] Vietnam QA Toney will update the 8D report on 8/18 for ALT review. [ALT 0812] . No boot : root cause - short 24V pin touch heat spreader and connected GND. Foxconn RD prepare test SW and it's Guide. Foxconn VN will test with defected unit after FII RD eng. provide test guidance and SW. . No ethernet : There is no issue on vibration and strain gauge test. And close it. ALT asked Foxconn not to change its status to closed. It should be ongoing. Foxconn will have internal discussion and will leave action items to analyze this issue. ALT had 3 defect units out of 630 pcs. SKB is inspecting the 4K LOT that produced in june. . Ethernet unstable - RMA report from vendor on 8/12 . HDMI Cable Cable stock(FIT 20.088, Aboard 30K, CNSBG 17,309) => Vendor already sorted FIT/Aboard stock. There was no defect cable. There is no FFC cable that had same LOT no. to defected unit. [Fii 0811] 1. For soldering issue, the SoC pin crack & EOS test method has been provided on mantis 1506. 2. For no ethernet isue, the strain gauge test result showed it's normal and the vibration test of 2 carton didn't found defect. [Fii 0804] VN QA had provided updated 8D report to ALT review on 8/4. [Fii 0728] VN QA manager Qing-Bo will send the initial version of 8D report to ALT review on 7/28. [Fii 0721] The fail analysis is on-going now. Please see current FA status in attached file.
Quality | GPIO issue(mantis #1468) | FII | close |  | [ALT_0512] Tracking no. : Fedex 7720 6541 7572 Plus, please update and share with factory about ALT offices address, which was shared via Emma's email on 8th Feb. [0511]Sent. [0504]GPIO PCBA will be sent on 5/8. Fii will update tracking No. later. [0428] ALT and Foxconn reviewed the no. defected units. ALT sent 17 pcs to Foxconn, and 3 pcs to synaptics for RMA. So total q'ty is 20. Those data in Mantis #1168. [0427]Fii only recieved 16pcs PCBA. so please help to check if ALT could send the other 4pcs with housing golden sample. [0421]ALT refused to send these PCBAs via ALT's account, so Fii will send them and Miya will pay for it. Fii will provide tracking by 4/26. [0414] ALT think that it is not the cost issue. It is Resposibility issue. So ALT cannot pay for Foxconn's fault. It is a common sense. [0413] Fii's FIN team rejected our tracking request. Please help to check if we can send these PCBAs with CS Parts via ALT account. [0330] PCBA has been finished, as this is not a RMA issue, Fii need more time to do internal process and keep update with ALT timely. [0324] GPIO Issue is not RMA issue. It is a DESIGN issue. So Foxconn used their account to return defected units from Korea. ALT think that it should be paid by Foxconn(RD or VN). [0323] Fii has started internal process and will keep update with ALT timely. As this is kind of RMA issue. Please provide ALT's Fedex account to ship these samples back. [0317] ALT aske to provide tracking no. when Foxconn send new PCBA. [0313]Fii will send new GPIO PCBA by 3/23. [Fii-1117] Synaptics FAE reply SOC ID can be read in the console log but we cannot found the keyword RKEK_ID in console log. We will continue to work with Synaptics on this issue, and update the status by early of next week. [1111] ALT asked to replace all defected SoC even if FII cannot reproduce GPIO issue in their Factory. Foxconn should provide how ALT can check the SoC chip ID. Foxconn will check with SW or Synaptics and comeback soon. [1104] Foxconn will check the process for PCBA RMA with Factory. Foxconn TW think that it is complicated and need time. [Fii 1103] The factory has checked the production record and confirmed that these 19pcs samples were all produced normally without rework process before. [Fii 1027] Got GPIO list from SH. Will provide this list to factory QA to check the production records first. [1021] GPIO issue is caused from SW and HW mismatch. So ALT asked Foxconn exchange defect units to new one. It is design issue so it is not managed RMA contract. ALT will send detail information about defected units. ALT asked Foxconn to replace defected PCBA to new one without any cost, include delivery cost. And to change factory firmware and customer firmware, Foxconn factory should do control run and OTA test. After test, Foxconn should share the result with ALT. [Fii-1020] Current software version of changing register for improvement EOS should be QT.19.534.26. RD has provided this version of image to Fii factory for verification. [1014] Foxconn doesn't want to upgrade SW on defected unit that Foxconn asked on mantis. Foxconn prepared new Factory SW that applied changed register value for improvement for EOS. ALT thinks that Motorcomm ethernet PHY can use after find the root cause and soltuion about ethernet disconnection issue. Foxconn think that 2nd source introduction is not urgent except Hynix DDR4 8Gb Die change. [Fii 1013] Software version of both units are QT.19.531.20. The software version fix VDDIO6/VDDIO9 register values is QT.19.536.26 which also pass google 3PL certification. Will check whether apply this register set value on Factory SW by 10/14. [1007] ALT had 2 more defect unit. And ALT received 2 RMA report from Synaptics. ALT uploaded it on mantis(#1468) Foxconn will check whether they apply this register set value on Factory SW and feedback to ALT. [0916] Cross section. Foxconn doesn't have defected unit. So we cannot take photo higher magnification. Next time we can do it. The Photo that Mr. SH Son's requested cannot be provided because Foxconn doesn't have defected unit now. [0908] ALT left some comments on mantis(#1468). Foxconn will check it after meeting and update it later. [0901] Foxconn is collecting the photo now. Foxconn will provide photos by next monday afternoon. [0826] Foxconn Factory will follow up ALT's additonal request for cross section test result. [ALT 0819] Cross section data was updated this morning. ALT will review and leave comments on Mantis next week if necessary. [Fii 0818] Need Vietnam QA/ME provide status update on the cross section report - Any update from Lab. about adding all of row picture and pin number? - Is is possible to attaches the high resolution image files? [ALT 0812] ALT reviewed test report on Dye and Pry, Cross section. ALT left some questions and comment on mantis #1468 Foxconn will check and update soon.
Manufacturing | Line Transfer(#1579) | FII | close |  | [0217] Due to SWAN material preparation, SWAN MP schedule may be delayed. ALT concerned that ALT engineer visit VN Factory 2 times for Line transfer audit. Anyway ALT will inform the factory visit schedule for Eagle audit on 2/20. [0210] Manufacturing schedule : Eagle (19K, 3/6), Swan(5K, 3/1) ALT will update engineer visit plan. [0203] Foxconn Factory has some issue to install new line. It may need a week to buy new conveyer. Foxconn will provide new schedule. ALT asked Foxconn to include mass production schedule and quantity. Foxconn will provide it by 2/7. [ALT 0120] ALT reviewed Gauge R&R format. ALT is waiting for Gauge R&R update from FII. [0113] No update. Foxconn will check it and feedback soon. [1/6] ALT asked some additional request on mantis on 1/3. Gauge R&R plan for equipment verification step. [12/23] ALT asked Foxconn to update below data on mantis. Foxconn TW will check and update about target date. SMT/PTH line information ME setup plan and layout. FAC & IT setup plan and layout Equipment list and layout plan Control run plan Manufacturing and quality validation plan. Engineer / worker training plan Add job position / names lists to the document. ALT should inform it to SKB and get approval before production in changed Line. SKB may aked to audit new Line. ALT will start to discuss with SKB once ALT collect all data. ALT think that we should get approval within Jan..
Manufacturing | Eagle RMA | FII | close |  | [Fii 0309] Have sync up with MFG side about the RMA flow, and VN MFG will change the RMA process according to SH's suggestion during his visiting in VN factory. [0303] ALT is discussing with Foxconn Factory about this issue. What ALT asked to add is in case 1. Add Burning 2 Hrs after downlod Factory SW success after 1st trial fail. So Case 1 step should be below : Case 1: Download Fac SW fail -> Download Fac SW success -> Burning 2hrs -> Re-download 5 times -> DL OK -> Normal FATP -> DL fail -> PE check ( NTF change material) -> Normail repair process -> Normal FATP [Fii 0302] Here is the updated RMA process from factory '- Old process : Sorting -> Change LED -> AOI (100%) -> Link -> UK -> FT -> FT1 -> RC -> Burning 8m ->RC1 -> VI - >RC2 -> Packing '- New process : Sorting -> Change LED -> AOI (100%) -> Link -> UK -> Case 1/ Case 2 '+ Case 1: Download Fac SW fail -> Re-download 5 times -> DL OK -> Normal FATP -> DL fail -> PE check ( NTF change material) -> Normail repair process -> Normal FATP '+ Case 2: After RE change Soc+DL Fac SW OK -> Burning 2hrs in Buring Chamber ( 50 degree) -> Normal FATP [0224] ALT is waiting for feedback from FII. [Fii 0223] Fii VN factory will reply this by 2/24. [0217] ALT asked Foxconn VN to add below 2 test for the defected unit under the following conditionns. Condition : 1st Test - Factory SW download Fail. 2nd Test - Factoty SW download success. Additional Test : 2Hr in Burning chamber 5 times additional download test If Foxconn Factory cannot accept this, then Foxconn will provide another solution to check it. ALT think that the no. of download test retrial for Factory SW download failed units is not enough. [Fii 0216] Vietnam PE update the document in the attachment to explain ALT's questions [0210] Document provided Foxconn are about current Repair process. There are Good 5 units out of 10 for Factory SW download test, even though all 10 units had failed to Factory SW download test at first. Foxconn made additional process for Factory SW download fail defected unit. Foxconn will put those STBs to normal repair process when those defected units work well without issue at 2nd download trial. ALT asked Foxconn to provide normal repair process. ALT will check wether Foxconn's repair process can check the SW download issue. ALT also asked to provide how Foxconn check VF/Impedence of SoC. ALT wants to know the exact test point and condition for Foxconn's measurement. [Fii 0209] VN PE update the FA report as attachment. 1. In last page (#11), the checking and repair process for "can't fatory download SW" will be added "PE checking" to avoid misrepair 2. VN PE prepared the 5pcs material FA report(attached PDF file), and will send those defective SoC and report to Amlogic on 2/10. Will kepp update the plan after discussing with Amlogic QA team [0203] Foxconn filtered 10 pcs that all 10 units cannot be download Factory SW. But some defected unit worked well after Foxconn rework precess. Foxconn keep updating about Failure analysis for defected unit. [Fii 0202] PE filtered out the top 1 defective NG SoC T99X171.00 RMA model (random 10pcs, SoC+eMMC), fail symptom: Can’t download Factory SW - 5/10pcs ( NG3, NG4, NG6, NG7, NG10) download Factory SW OK ==> NTF Material issue - 5/10pcs ( NG1, NG2, NG5, NG8, NG9) can’t download Factory SW ==> Continue follow analysis process. Please check the attached report in details [Fii 0119] VN PE will filter out the top 1 defective NG SoC 10pcs for analysis. Please see the planned schedule in attachment. [Fii 0112] After further discussion with the Vietnam QA team, they think the defect rate should be calculated on the total number of shipments instead of just checking the number of each defect issue. Therefore, the anaysis plan provided by VN PE/QA is that they will analyze top1 issue and sort 10pcs defect SoC to do the inspection, baking, reball, measurement and swap test. If the SoC still fail after swap test, then they will send SoC to the vendor for further FA. For the major 2nd and 3rd issues, Vietnam QA will monitor it. If defect is above 500ppm, it will be analyzed. [0106] Foxconn didn't know whether there is defected parts that repaired before in the factory. Foxconn will check it by next week. If there is no defected components then Foxconn will review the defected unit in 4th RMA. [0105] VN QA/PE will sort the defective SoC/eMMC/Eth PHY in different failed symptoms, and then send them back to the vendor for further FA. Will update VN factory's plan to ALT later. [1216] Foxconn will receive RMA data from factory and review major 3 issues of RMA((SoC, eMMC, Eth PHY).
Manufacturing | The use of long-storage PCB for SWAN | FII | close |  | [0414] Foxconn already used PCB stock, so they don't need additional test any more. [0413]According to ZYX's schedule, Fii has to produce SWAN until 11k. PCB stock is only 6k. [0331] ALT would like to know whether Foxconn will test for next MP. If Foxconn will test PCB again, then can Foxconn add test item that ALT wants to add ? [0324] ALT add report on mantis #1682 and asked to add test items from next test(#1682). ALT is waiting for the feedback from Foxconn. [0323] Miya has send reports on 3/6. [0318] Mantis No ? [0313] Fii updated report on Mantis. [0303] Test result is pass. ALT is waiting for test report. [0224] No update. ALT is worried about for the schedule. If PCB may not use for MP, then it should waste time to produce PCB again. [0217] Foxconn MPM will check it. ALT asked Foxconn to update it on wechat first. Ms. Miya Wang informed that it will finish this week. and the result will be share early of next week. [0210] Foxconn concerned about using long-storage PCBs. Foxconn will test 2 pcs for each date code and inform ALT about the result by 2/18. Foxconn will inform the test items and date code by today(2/10). It should be decided whether those PCB can use for MP or not.
Manufacturing | Shortage of SWAN housing | ALT |  |  | [0317] ALT will inform the RCU and Adaptor delivery schedule and Q'ty by today. [03/16] 1. ZYX's delivery and quantity are not stable. Fii is concered about Mar and May's MP 2. Fii still do not receive status about "ADP SW 200~240VAC 57~63Hz 24V". ETA should be 3/8. Please help to check.
Qaulity | EPD certification(#1180) | FII | open | 2023-03-24 | [0413]Done [0331] Foxconn VN provide 1st data on 3/27, but some data are missing, assembly time and outputs. ALT asked those data by 4/1. [0323] Fii will update on Manti(#1180) within this week. [0317] Request fill out the manufacting data "LCA_manufacturing Data collection_20230302.xlsx"
| New BI control run |  | close |  | [ALT_0602] - Top case: Ok. - Bottom case: Regarding the introduce the Jig, it's up to your side to keep the current process or adop the new step with Jig. That means quality is your responsibility. So, please keep and make sure your quality control in order that there are no quality issues during production and on finished product. [Fii_0601] TopCase: Sorry, the report will be provided within this week. Front Cover: Thank you for providing the JIGs, but after evaluating our factory, it was determined that there are no production plans for SWAN after Sep this year. If we were to introduce new JIGs, we would also need 1-2 months to validate them. Therefore, the factory prefers to continue using our existing method for IQC. [ALT0526] please update on mantis, will feedback on our opinion once we receive it. ALT will upload Front cover Test zig data on mantis by today. [Fii_0525] Top case: Fii will provide IQC report before 5/29. visual inspection report will be provided by 5/29 too. Front cover:Please share us the IQC Test zig, factory's QE will review it. Thanks. [ALT_0519] ALT wants to know the result of IQC for issued lot. Top case : If there are so many NG parts when Factory check it by eye for MP before assembling, then please enhance IQC. And please let us know the failure rate of visual inspection before assembling. If Foxconn found out some defect after assembling, then FII should provide any evidence that it is not cause from assembling. Front cover : If you have any difficulty to inspect Front cover, then please make some IQC Test zig. INKEL already use this kind of zig in VN Factory. If you want, then we can provide some guide for you. [0518_Fii] IQC stantard is AQL 0.4. Top case: IQC OK->pick up 500pcs for MP->check quality by eye 100% before assembling->found NG->go back and pick up another top case. Go back and pick up another top cover take too many time for factory. Normally factory could produce 500pcs, and now only 400pcs. Front cover: After assembly, the NG can only be found through LED. and factory need to disassemble and replace another front cover. [0512] This issue was additional support sponge material. If there is any issue after IQC, then there was no issue. So ALT would like to know the IQC Level and IQC result about the LOT that happened issue. Foxconn will check it more detail with Factory and feedback it soon. [Fii_0511] Factory is checking with SQE about the NG rate. and will sugest a IQC percentage to ALT. If ALT accepted, will update the MOH later. [0508] ALT asked below items : Current IQC level Result of the LOT that the issue happened. IQC Result / Failure q'ty and rate during Full ass'y, especially visual issue. ALT think that the IQC Level change is the normal Quality process. So the cost of it should be discuss based on your above information. [0504]Fii need to do 100% IQC from next month, it will raise the sorting cost and impact to SWAN's u/p. Fii will keep update with ALT's biz team. [0428] Foxconn will check what the exact issue is. ALT think that VN factory should check the housing status before assembly. And if VN factory didn't have enough sponge parts, then it should be ask ZYX to provide it before shortage. [0427]ZYX's delivery and quality is not stable. will charge ZYX for the shut down line cost. [ALT_0424] ZYX provided delivery plan on May today. [0421]ALT said ZYX will update their schedule by 4/17. But Fii did NOT receive any update until now. If there will not be any shipment Jun, Fii will check the idle and charge to ALT. [0414] ZYX will update housing schedule by 4/17 and discuss delivery schedule for 5K q'ty based on production schedule next week. [0413] because of ZYX's schedule.According to ZYX's schedule, there will be only 4k shipment on Apr, 1k on May. Please check May's housing schedule. For your ref, PO q'ty is 6k. [0331] ALT would like to know why FII have plan for control run from 4/7. ALT Biz team will discuss with Foxconn on the schedule and make plan for 5K delivery. [0323] Factory will arrange control run for SWAN's new housing. But housing delivery has been delayed for too many times. Please help to check with supplier and update status with Fii.Fii's general manager is challenging us about stock and shipment, please make sure SWAN's control run could be start on time.
Qaulity | Eagle RMA Status | FII | open |  | [Fii_0222] We have received the PO from ALT. Thanks! [ALT_0216] We will proceed the PO process by next week. [Fii_0215] We saw SH's feedback he has no issues by today. Need ALT to release PO by this week and arrange the payment ASAP. Thanks! [ALT_0202] SH Son will feedback about our comments of the excel file which sent by last week, if there is no issues then we will proceed the payment process by next week. [Fii_0201] We had provide the excel file already. Wait for ALT's review and confirm the parment date to us. [ALT_0126] Please provide the excel file to us, then we will feedback to you. [Fii_0125] Miya sent the latest RMA cost to SH and JW on 1/23. Need ALT's help to review and comfirm the payment at soonest. [ALT_0119] We will share the shipping information once we receive it from FW. [Fii_0118] Yes. We know there will be 1,812pcs RMA return in the end of Jan. [ALT_0112] ALT updated the list for Lot 11 & 12 on the mantis, and those are going to ship out with Lot 13. [ALT_0105] Lot 11 & 12 will be sorted again and updated to mantis, the shipment will be arranged within Jan. [Fii_0118] Yes. We know there will be 1,812pcs RMA return in the end of Jan. [Fii_0104] Fii's target to ship the rest RMA by next week. [Fii_1228] Fii shipped 9,156 pcs by 12/27. There are around 3K RMA waiting for repair in Factory. [ALT_1222] OK, please keep us in the loop. [Fii_1221] till 12/21, our factory had repaired 1055pcs of 12967pcs. Will update shipping plan and shipping Q'ty on 12/25. [ALT_1215] Please share the 6th~10th shipment plan with us. [ALT_1201] Will discuss this topic while ALT travel to TW (12/4~12/5) [Fii_1123]Will reply by mail by 11/27. [ALT_1117] Please feedback to us about the decision that the warranty period of 3y6m is valid for Fii. About the RMA valid date calculation, it should be set for the reported date(mantis) as the calculate standard. Please mail reply about the RMA valid date calculation standard or ask the decision maker to join the meeting. RMA valid date calculation standard : Calculate Warranty Period is from delivery to RMA report date on mantis. According to both parties agreeded RMA process. Due to Fii Stop the RMA process, so ALT can't deliver RMA units until Fii comfirmed the RMA Period. [Fii_1116]Replied via mail. Our legal department is closely monitoring the situation regarding RMA and is currently in discussions with Everlight's legal team regarding the material purchase contract. There is the possibility of taking legal action against Everlight in the future, and our legal team requested us to gather evidence. [ALT_1110] Please provide Fii's feedback within Today. [Fii_1109]Wii reply Steve's mail [Fii_1102]We are still fighting with internal different dic., will reply ALT how long we can extend the warranty for OLD-LED in next week. [ALT_1006] Will reply ALT's opinion via mail by today. [Fii_0928]4&5th LED RMA is coverd by Fii. If ALT won't confirm 6-10th RMA's warranty time, Fii will ship them back as NTF. [ALT_0922] We will re-negotiate with SKB next week and update Fii if there are any changes. We need to confirm the 11th RMA shipment schedule and solve the 4th & 5th RMA delivery issues ASAP. [Fii_0921]Per phone call with JW, Fii's stance remains unchanges. If ALT requires any data for evidence during disscussion with SKB, Fii will support. [ALT_0918] Please respond regarding ALT's email by JW on 12 September first. [Fii_0914] 4&5th RMA must be ship out before 9/25, or VN customs will impose fines. [ALT_0908] Will reply it by 9/11 [Fii_0907]Waiting for ALT's reply. [ALT_0901] Will reply ALT's opinion via mail. Please confirm when ALT can ship out the 11th RMA ASAP. [Fii_0831]According to 0823-0824's meeting status, the LED's warranty time would be 2year 8months, Fii uploaded the list again and please help to check. [ALT_0825] Please feedback on when ALT can ship out the 11th RMA within AUG. [Fii_0817]10th RMA finished clearance process. there will be no change about RMA process [ALT_0811] We can't understand the procedural issue Fii mentioned. There have been no issues so far, and it is a mutually agreed-upon process. Please check it with the factory and firstly deal with it ASAP. It's accruing cost. [Fii_0810]10th RMA is still pending at HK port. [ALT_0804] If need to get the Factory's confirmation, please reply it within 3 working days. [Fii_0804]Fii got payment. But before ship back RMA, please get Fii factory's confirmation first. Thanks. [Fii_0720]Fii replied e-mail this week, please notice when ALT will feedback the mail. [Fii_0706]after RFP, will reply by 7/7. [Fii_0629]Sorry that due to the holiday, will reply by 7/1. [ALT_0616] will check after received the cost [Fii_0615]After talk to Mr. Son, Fii will check and send the revised cost by this week. [ALT_0609] About the RMA issue discussion, please get the summary from factory and share to ALT first then hold the meeting afterward. [Fii_0608]Fii and ALT will discuss these issues via CC on 6/9. [ALT_0602] Please reply first about Mr. SH Son's email that is about question of RMA issue. [Fii_0601] replied by mail on 6/1. [ALT0526] ALT can't wait for 6 months returned RMA, please figure out a solution to fix this issue. ALT would like to receive RMA repaired units on a manthly basis. [Fii_0525]Fii will reply by 5/24. [ALT_0519] Please answer to Mr. JW KIM's e-mail. [Fii_0518]According to VN's policy, RMA to VN need to pack with RCU and ADT, even from HK warehous. Fii is find a way to solve this problem and will send e-mail to explain this situation by 5/24. [0512] ALT asked again that FII Taiwan should be checked the status of Factory before meeting and update it in the meeting. Foxconn Taiwan said that Factory will update but there is no update. Please check the status before meeting and update real data in the meeting. [Fii_0511]Yuri will update these status on Mantis. [0508] It takes too much time to check the status and schedule of RMA. ALT cannot understand why it takes too much time. ALT would like to know when Foxconn can provide it. And ALT wants to get an update regularly. [0504]Fii will check and pull in RMA schedule. VN factory will keep update to SH SON. [0428] ALT asked VN Factory to update current status of RMA units. But it is hard to receive feedback. And Foxconn should return RMA unit within 6 weeks after arrived in HK Factory. But VN Factory didn't keep it. ALT ask Foxconn not to violate the terms of contract of RMA. What ALT asked VN Factory to update the status is as follow : - RMA Lot3 (13,440pcs) #1541 : Total 13616pcs (12pallet) Smart3 only ->Update the status remained q’ty of Smart3 (121 pcs) -RMA Lot4 + Lot5 (12728 + 3360pcs) #1574, #1629 : Hongkong ATA (2/28). this lot RMA due date was ~4/4. (6 weeks after arrival HK). -> Please update the production status, - 2023.2 5040pcs #1660 : Hongkong ATA (3/10). this lot RMA due date was ~4/21. (6 weeks after arrival HK). ->Please update this lot arrived at the factory? - 2023.3 3822pcs #1691 : this lot RMA due date is ~6/5. (6 weeks after arrival HK) -> Hongkong ATA (4/23). Please update the next plan – ETD HK, ETA Factory, ETD Factory (after RMA),
Manufacturing | PCB Solderability Test | FII | close |  | [Fii_0706]Vendor send CN version EN: De-mold and measure copper in the holes. If the measurement is satisfactory, proceed with the next steps; otherwise, consider it as scrap. The PCB is then subjected to baking at 125°C for 4 hours, followed by OSPFOC rework, Out of Autoclave (OOA) treatment, and packaging for storage. Note: Before initiating the rework, take 10-20 sets of boards and follow the rework process. After rework, conduct relevant performance tests by QA or QE. Only if the boards pass these tests can the bulk rework process be executed. QA is responsible for sampling the reworked PCB boards to perform reflow soldering tests and solderability tests. If the boards meet the criteria, they can be shipped; otherwise, they will be treated as scrap. Reworked boards that exceed the expiration period must be utilized within 6 months, or else they will be treated as scrap. KR:포말 해체 후 구멍의 구리를 측정합니다. 측정 결과가 적합하면 다음 절차를 진행하고, 그렇지 않으면 폐기물로 처리합니다. PCB는 125°C에서 4시간 동안 구워지며, 이후 OSPFOC 재작업, OOA 처리 및 포장을 통해 저장됩니다. 참고: 재작업하기 전에 10-20세트의 보드를 가져와 재작업 절차를 따릅니다. 재작업 후 QA 또는 QE가 관련 성능 테스트를 수행합니다. 이러한 테스트를 통과한 경우에만 대규모 재작업 과정을 실행할 수 있습니다. QA는 재작업된 PCB 보드의 샘플링을 담당하여 리플로우 납땜 테스트와 납땜성 테스트를 수행합니다. 보드가 기준을 충족하면 배송됩니다. 그렇지 않은 경우, 폐기물로 처리됩니다. 기한이 지난 재작업된 보드는 6개월 이내에 사용되어야 하며, 그렇지 않으면 폐기물로 처리됩니다. [ALT_0630] please let us know the rework process from vendor [Fii_0629]Fii ask vendor to rework with their own cost. So there will be no over date code issue this time. [ALT_0616] ALT asked additional test items for PCB solderability test that ALT asked before on mantis #1682)
Quality | SWAN DOA devices Status | FII | close |  | [ALT_0112] FYI, that was just complted KR customs process. [Fii_0104] The target shipping date for the DOA will be 1/8. [ALT_1229] Please feedback to us the DOA shipping schedule. [Fii_1228] 2K had been shipped to ALT by 12/12. [ALT_1222] Please provide the target day, the MP 2K was already completed. [ALT_1201] Please feedback on the target date while finishing 2K production. [Fii_1123]There are some issues about the MP materials, Fii factory will reply by 11/30. [ALT_1117] Please feedback the status by next week. [Fii_1116]Please help to make sure INKEL could ship housings on time. [ALT_1110] Please let us know the Swan production schedule based on the current estimated delivery schedule for Inkel Housing. [Fii_1109]will produce these samples after MP [ALT_1027] Please check the MP Q'ty including DOA parts need. [Fii_1012]MP schedule has been delayed. will reply after checking INKEL's schedule. [Fii_0928]SWAN MP schedule delayed, will send after Otc's MP. The target date will be 10/10. [ALT_0922] Fii reply will send out by next week. [Fii_0914]DOA devices will be sent via Fii's account. total q'ty would be 9pcs. [ALT_0901] Due to the factory can't find the PCBAs, the factory will ship back the new PCBAs to ALT. If need to combine the shipment with PHY samples, please check how many Q'ty of DOA / PHY you plan to ship out. [Fii_0831]Fii will send back these devices by 9/14. [ALT_0825] Please feedback us the status "on TIME"(8/25) [Fii_0824]Fii is finding PCBAs. will reply by 8/25. [ALT_0818] Do you mean the NG board will be fixed and sent to us? If yes, then we don't care if the SN number is different from the previous one. We don't care the SN is different from previous ones, due to it doesn't relative to SKB's SN. [Fii_0817]Please help to check if the new ones' SN is different from previous ones.And please help to check if we can send NG boards instand? [ALT_0811] Please send as many new ones as the DOA quantity ALT sent. [Fii_0810]As 2022's DOA devices has been in stock for too long, they have already been scraped. [ALT_0804] Please let us know the replied target date. [Fii_0804]Factory still checking this stocks, Fii will reply ASAP. [ALT_0728] Please feedback before next week [Fii_0728] Fii will check with VN factory and feedback Soon. [ALT_0721] will feedback detail information by next week Monday [Fii_0706]We can not find record of these DOA devices. Please help to advise invoice&packing list&DOA issue details. Thanks. [ALT_0630] we sent DOA devices back to VN before, when we can receive these devices (with good quality) ship back to KR?
Quality | CS part | FII | close |  | [ALT_0112] FYI, that was just complted KR customs process. [Fii_0111]material list will be provided by next week. [ALT_0105] Please check with the factory if bundle shipment will scheduled on 1/8 ( DOA & CS parts ), also provide the remaining material list to us. [Fii_0104] The SPK will be ETA VN factory by 1/5. [ALT_1229] Please feedback to us about CS parts shipping schedule when receive the SPK. [Fii_1228] Fii doesn't receive the SPK yet. The vendor feedback the shipping date is 1/5. [ALT_1222] Please inform us if you receive the SPK material. [ALT_1215] The factory is still waiting for SPK to complete 40 sets SWAN, currently only finished 40 pcs PCBA, please check the materials status and feedback to us ASAP. [Fii_1214]The 40 pieces of swans have been completed, ready for shipment. The 40 pieces of PCBA , and we will update materials status next week. If there is a shortage of materials, could you please confirm if there will be any demand in 2024? If not, we will proceed with the last order of materials and arrange for SMT. If there is demand in 2024, can we combine the production with the requirements for that year? [ALT_1201] Please feedback on the target date while finishing 2K production. [Fii_1123]There are some issues about the MP materials, Fii factory will reply by 11/30. [ALT_1117] Please feedback the status by next week. [Fii_1116]Please help to make sure INKEL could ship housings on time. [ALT_1110] Please let us know the Swan production schedule based on the current estimated delivery schedule for Inkel Housing. [Fii_1109]will produce these products after MP [ALT_1027] Please check the MP Q'ty including CS parts need. [Fii_1012]MP schedule has been delayed. will reply after Nov's MP. [Fii_0907]Will reply after Sep's MP. [ALT_0901] Please check the remaining material Q'ty after Sep production to discuss how to handle this issue. [Fii_0831]There is no demand in 2024, so Fii do not have enough stock for these CS parts, pleaes help to check if ALT could release 2024 open PO by 9/4, we could order these materials. Please help. [Fii_0824]Factory will reply this until LED issue solved. [ALT_0818] It doesn't relative to 2024's PO, please prepare the materials ASAP. [Fii_0817]Fii need to prepare materials for these devices, but there is no PO for 2024. Fii would prepare materias with after receiving 2024's PO. [ALT_0811] Please check if Fii can provide CS parts within this year, and let us know if there is anything you need our cooperation on. [Fii_0810]Fii will check if the materials is ready. Some materials need to book with 2024's demand, so please also help to check when ALT could provide 2024's PO to Fii. [ALT_0804] We sent the email on 7/24 to request the CS parts delivery plan, but we haven't received any feedback yet. Additionally, please check when the deadline is for the B&S materials to arrive at the VN factory in order to meet the production plan and the CS parts delivery. [Fii_0706]An requested B&S materials based on Fii's production plan to HS Kim and keep tracking with ALT. [ALT_0630] according to the contract, we should receive CS parts, please check the materials status and let us know when you will arrange CS parts shipment
Quality | material management | FII | close |  | [Fii_0118] Plz keep us posted if ALT didn't get the feedback from our factory. [ALT_0112] Thanks for providing the response. ALT will send the feedback on 12th Jan, so please check it after getting it. [ALT_0105] Mr. Yoon replied to the mail today, please check and give feedback to us. [Fii_1228] An had replied the email by 12/27. [ALT_1222] Please check and provide Fii's feedback about ALT's email (by Mr Lonnie Kim). [ALT_1215] We will feedback on our opinion by next week. [Fii_1214] An had replied and updated 8D on 12/14 again. Plz help to double check. [ALT_1208] We got the 8D report and feedback on our opinions already, please check and feedback to us ASAP. [ALT_1201] We didn't get the 8D report by 11/30, please send the 8D report to us ASAP. [ALT_1124] SPK/SPK cable/Sponge..etc. During the 2K production, it has material shortage or missing materials issue, this kind of issue should be discovered before the production starts or while receiving the material, and if has any issue then should inform us to take action ASAP. Please give us the 8D report and prevention action plan to us.
General | contact window list | FII | close |  | [ALT_1201] Please share the factory contact list with ALT for production issue communication.
Quality | SWAN RMA Q'ty | FII | Close |  | [ALT_0202] OK, discuss it on PM& Sales sheet. [Fii_0201] We think this issue can be closed. It can be combined to "SWAN Last Order" of PM&Sales sheet. [ALT_0126] Please check how many Q'ty PCBAs( main & daughters ) can be made with current idle materials and list out Q'ty separately main & daughters boards. If there are any insufficient materials, please list them also, thanks.

## AI3
Category | Issue | owner | status | due date | Progress
PM | Eagle additional sample (w/ DIODES, 3PEAK 2nd source) | FII | close | 2021-08-26 | [Fii 0901] VN will ship out 20pcs DUT to Taiwan on 9/1. ETA date will be 9/9 because VN is in holiday during 9/2~9/5. Reliability schedule is under checking with HWQA. [Fii 0827] ALT require to run 100% aging test (100pcs) on control run. However, ALT also require CFT to ship out 25K by 8/31. =>CFT will ship out the shipment first and go back to run aging test. Expect to run aging test from 8/31. After CFT complete the againg thest test, will deliver 20pcs to Taiwan. [Fii 0825] CFT will deliver out 20pcs to Taiwan RD team by 8/28. [Fii 0820] According to the requirement from ALT RD, the sample that ALT required is 20pcs. MFG is checking when they can ship out 20pcs because normal shipment is the first priority.
HWQA | Reliability testing for 20pcs (w/ DIODES, 3PEAK 2nd source) | FII | close | 2021/9/24 -->10/15 | [ALT 1013] Approved for 2nd source Diodes+3Peak phase in. [ALT 1001] Will feedback next week. (mantis#1321) [Fii 0924] Reliability test report provided on Mantis, need ALT to agree to phase in. [Fii 0903] Target testing period: 9/18 ~ 9/21. Target to provide the testing report: 9/24.
Sales | Eagle RMA carton | ALT | close | TBD | [Fii 0305] Factory provided RMA report for ALT review. [Fii 0224] Factory team is handling RMA. Traget to complete RMA by 2/25 and provide FA report on 2/28. [Fii 0119] Factory PM provided RMA schedule. 1/26 ETA VN factory, target to finish RMA and ship to Korea around 2/15. [Fii 0113] Factory PM William will handle the following process. Currently waiting for logistics team to confirm the vessel schedule. [ALT 1224] ALT shipped 1st carton of RMA DUT. [Fii 1215] Factory provided the RMA rules. [Fii 1210] Factory is checking the RMA shipping requirement internally, will update ASAP. [Fii 1123] Provided judgement from package RD. [ALT 1118] ALT provided another solution from Korea--> Fii will check with package RD for suggestion based on the information provided. [Fii 1104] Due to custom policy, need ALT to purchase directly from YUTO(package vendor). [Fii 1022] Checking the final cost and process(customs policy) at factory side, will feedback ASAP. [ALT 1020] confirmed to issue PO for Fii to purchase the carton from VN(by vessel) [Fii 1012] Provided solutions and need ALT to finalize the decision and execute ASAP. Please be aware of the warranty period. [ALT 1008] ALT feedback the cost and spec form korean vendor. [ALT 1001] Will feedback next week. [Fii 0909] Fii provided shipping cost (sea/air) from VN to ALT. Wait for ALT's decision. [Fii 0903] After checking with Fii sourcer and logistics members: Shipping cost from VN to Korea is much higher than Carton cost. --> Fii provide drawings and ALT will check with suppliers in Korea [ALT 0901] RMA >6000pcs, will check exact quantity after the meeting--> Till 9/3 Total 3107pcs [Fii 0825] Fii will disucss the expense internally and propose to ALT. Package test estimates to be finished on 9/10; [Fii 0820] Under packing reliability testing at Fii site.
HW/PM | New RCU (Mantis #1344) | ALT/FII | close | 2021-09-24 | [Fii 0930] As the old/new RCU will both exists, need ALT to clearly instruct which batch to ship with new RCU in the future. [Fii 0922] New RCU PN provided (Mantis #1344) [ALT 0915] Update datasheet for new RCU [Fii 0908] Fii will apply for new PN and check how factory can control it. CE team asked to provide high resolution datasheet. [ALT 0908] ALT informed to introduce new RCU for Eagle adding Smart TV control function.
PM | EPD certification | ALT | close | TBD | [Fii 0117]Factory PM An already feedback the factory visit question. [ALT 1123] Request to provide more details of pallet packaging info. --> provided [Fii 1118] Electricity consumption data provided to ALT. [Fii 1111] Factory will check internally and collect data. (Target to provide next week) [Fii 1110] Factory requested ALT to provide english template form for them to fill in the electricity consumption data required. [Fii 1104] Need Steve to send out an official request mail for EPD certification. And please list the information and document needed with template to fill in.
HW/PM | 2nd source (Eth PHY/BT/IC) (Mantis #1353) | ALT/FII | close | TBD | [0324] ALT is closed it due not to apply 2nd source. Motorcomm PHY has issue when Ethernet cable plug and unplug repeatedly. [Fii 0421] The CRC and autonegotiation test report has been provided to mantis #1459 on 4/19. [Fii 0414] Fii QA team is working on the CRC test now. And the report can be provided by next Tuesday (4/19) [Fii 0408] 1. Motorcomm YT8531C: waiting for BMT. [Fii 0331] 1. Motorcomm YT8531C - Samples already shipped out. - Need ALT to confirm BMT schedule. Fii would like to introduce this materail from 5/1. [Fii 0324] 1. Motorcomm YT8531C: Will ship out on 3/25. 2. Ampak W511: stop the development due to SKB reject to use Ampak W511. [Fii 0317] 1. Motorcomm YT8531C : VN is running control run. Will ship out the samples by 3/23. 2. Ampak W511 - SW progress for BT compatibility: Samples arrived at AML China office. However, due to China government policy for COVID19, they cannot enter into their office for analysis. - SKB comment: SKB reject to use Ampak W511. Cypress still in critical shortage isse. [Fii 1216] As Movon is not Fii QVL, Fii will introduce Ampak as 2nd source. [ALT 1215] Foxconn can decide to use Ampak or Movon for BT 2nd source. [Fii 1119] ALT feedback to make decisions on BT module by next Monday.(11/22-->12/7) [Fii 1111] Have reviewed the MOVON's datasheet. The module size is about 1mm wider than AMPAK module but the current space can still be placed in. We don't have questions to using this module in Eagle. [ALT 1110] ALT suggested BT 2nd source (Movon(MD-BRC101)) [Fii 1104] EFUSE 2nd source Toshiba cannot provide samples for verification. [Fii 1022] Fii provided cost to Steve, wait for update. [ALT 1015] ALT will discuss internally if accept Fii rule for test samples. (4pcs for reliability test and 100pcs control run) [Fii 1014] Tiffanie will discussed about the cost with Steve. According to Fii's rule, we need 4pcs for reliability test and 100pcs control run in the factory. For the phase in plan, we will arrange 2 rounds introduction. 1st round (pin to pin): IC 3peak TPV809S-3TR ETH PHY Motorcomm YT8531C 2nd round (re-layout): EFUSE Toshiba TCKE712BNL BT Ampak W511 [ALT 1008] Need Fii to provide the phase in plan and cost liability. [Fii 1007] Need ALT to agree with the 2nd source introduction ASAP (except for BT module) [Fii 1001] For ETH PHY Motorcomm, as it is not QVL material, Fii will need ALT to designated Motorcomm as 2nd source via email if the reliability and control run passed in order to apply for Fii PN. [ALT 0924] Please check who will pay the new certification fee and test. [Fii 0917] Update comparison datasheet on Mantis. Need ALT to check and officially confirm to start the phase in process. [Fii 0915] Due to the long LT of current materials, please check below suggested 2nd source.
SW/PM | SW upgrade | ALT/FII | close | 2022-03-01 | [Fii 0223] RD applied EC to introduce new FW based on parties conclusion. [Fii 0214] Eagle: control run from 2/15. providing report by 2/18. SWAN: control run from 2/16. providing report by 2/19. [Fii 0210] Factory will do control run after MP shipment on 2/14. Target to introduce the new SW from March.
HW/Sales | BT module issue | ALT/FII | Pending | 2022-03-28 | [Fii 0331] Pending due to parties biz team have not reach the conclusion. [Fii 0324] 1. We heard from Sales team that ALT will going to propose Movon's BT solution to SKB and move it to B/S if SKB accept it. Need ALT to update the current status. [Fii 0317] 1. ALT inform Fii that SKB doesn't agree to use AMPAK W511 module since SKB concern about BT change, and would like to keep BT chipset as it is. 2. Need to find another way to solve it.
Quality | CS materials for out of warranty | FII | close | 2022-07-06 | [Fii 0714] Fii has provided on 7/14. [Fii 0707] There are 3 material which need sourcer to maintain price, due date:7/11 [ALT 0630] SKB is request the CS parts below for out of warranty STB . Please let us know the quotataion and lead time and MOQ. - Each part can be requested separately - LD1301, U301, U302, U303, U30, U307, L1001, T801, J801, U1402, D901, U1401, U801, U306, Q1001, Q1002, Q1103
Quality | FA report | FII | Close | 2022-07-06 | [Fii 0707] Factoy will check and reply. Keep updated. [ALT 0630] Issue up the BFX-AT100 defected units from incomming inspection end customer on 4/19, but Only the initial analysis was reported. https://mantis.cnsbg.foxconn.com/vaas/view.php?id=1484
HW | Camera design | FII | OPEN | 2023-04-21 | [Fii_0706]Done [ALT_0630] Please send the camera vendor information to us by today. ALT will help Fii to talk to Korea vendor to get the carmea information [ALT_0616] Please share the Camera vendor information to ALT. when can share the camera module price with ALT, please advise. [0504]Fii replied via wechat, Flash type : there is not enough space for camera module. And this type might not pass the drop test. ALT [0428] ALT will review the proposal. Foxconn's opinion is pop-up style camera has many weak point. So Foxconn doesn't recommend it. Foxconn recommend original type(shutter type). ALT asked to check the flash type mechanism that applied for old Film camera. ALT provide its photo to Foxconn via wechat. [Fii 0427] Fii will provide the camera proposal to ALT on 4/27. ALT[4/24] SKB asked another design today. ALT forwarded to Ms. Miya Wang and Mr. Sean Chiang. [4/14] ALT provide FII's idea of camera shutter on 4/12. SKB will discuss it internally. ALT is waiting for their feedback. [Fii 04/13] 1. SKB ask for camera shutter design. Fii has come up with automatics designs controlled by software and semi-automatic design that can be manually controlled by the user with an additional tact switch. Is there any feedback from SKB about the shutter design? 2. The camera has a hinge design and a shutter design, and Fii has great concerns about the reliability issues caused by such requirement. 3. What is the reliability test requirement of shutter door if SKB requird the design?
PM | RFP | FII | OPEN | 2023-02-28 | [ALT_0714] SKB's feedback about our Proposal for AI3 was - ID is very similar that SKB recommended. There is no ALT/Foxconn's idea. SKB needs some ID idea from manfacturer. - Camera cover looked not reliable for the house with children. It may increase RMA Rate - ALT didn't have mechanical engineer. So it is difficult to cowork with ALT/FII when SKB desing new product. ALT can support Foxconn Mechanical engineer, but SKB worried about language issue. - ALT/Foxconn feedback about SW side, especially Google/3PL issues. ALT should have account to contact Google directly. ALT HW team think that Foxconn keep using parts that use SWAN and Eagle. There are many competitive parts. ALT think that Foxconn should keep searching new competitive parts in the market. [ALT_0630] Please review the RFP file first and then discuss with ALT later ID: Fii reply that design drawing will provide by next Tue iOXT certification information need to share to ALT ASAP [Fii_0629] 1. Thermal solution report: sent 2. ID: ALT will choose 1 design by 6/30. [ALT_0616] 1. Thermal simulation: the current thermal result looks ok, but the design is not fixed yet, when the design settles down then do the thermal test again. ( 2 design types of thermal test result needed). SKB needs both simulation for ambient 25 and 50 degree. 2. Please proceed with concept ID with two kind of proposal shape. [Fii 0615] 1. Fii is optimizing the thermal solution to reduce costs. The thermal material will be changed from graphite to AL foil and the size of heat spreader for proposal 2 will be reduced. The report will be provided by 6/16. 2. Camera module's vendor is a Chinese company, and it is aslo vendor of Google and Samsung, please help to check if there will be any concern from SKB firstly. [ALT_0609] The RFP may release by next Tuesday. will keep updated once we received it from SKB. The camera module's price and security level need to discuss more, please share information about camera module vender and specification with ALT ASAP. [Fii 0608] 1. Fii is conducting the thermal simulation (@50degC ambient) for the two concept of dimension and the report will be provided by 6/9. 2. When will SKB release us an official RFP? [ALT_0602] Please review ALT update by Emma's email and provide your feedback. [Fii 0601] Fii have provided the estimated housing size (170mm x 110mm x 35mm) and camera shutter design. Need ALT to review it and provide comments if there are any concern on size or shape before starts the ID proposal design. [ALT0526] Please use current ref to study first and provide us the first draft proposal ( at least 2 design proposals ) [Fii_0525] According to ALT's ref., Fii need to get Dreamus speaker's 3D for new ME&ID design. [ALT_0519] ALT will share the reference design for new concept design. [Fii_0518]Fii ask ALT to provide ID concept. ALT [4/24] SKB didn't release RFP yet. And they check camera specification more. So we cannot estimate when they release RFP. [4/14] SKB is reviewing their specification and security issue on camera. They have plan to release RFP on 4/17, but it may delay as before. [Fii 04/13] When will SKB release the formal RFP?

## YEM_HW
Stage | Item | Model | Issuer | Status | Action Item
EVT/DVT/PVT | Design Review for each development stage | All | ALT | Close | [12/15] Foxconn confirmed. | Open
| Documents support - Schematic Drawing, Layout, Gerber, BOM, Mechanical Drawing | All | ALT | Close | [0113] Foxconn keep their policy. [Fii 0112] After internal discussion and in accordance with Fii's policy, Fii will share schematics and board file in PDF format and ME drawing in step file as appropriate if ALT requests any critical designs or issues to review in each develpment build. [0106] ALT can discuss which documents can provide it or not. ALT accepted not to provide Gerber data if Foxconn can provide layout data. ALT accepted to provide BOM at the final stage only. Foxconn will discuss internally and answer about documents early of next week. [Fii 0105] The SCH, Layout and BOM can be provided as usual when the project goes into the MP stage. The additinal design material may be provided depending on the situation if a design review is required after each development build, but the gerber in not included. [12/15] Foxconn will review internally | Close
RoHS Support | RoHS Support for self declaration by one company Foxconn will check to declare by themselves or provide all data for delaration to ALT. | All | ALT | Close | [12/15] Foxconn will check it with relative teams [Fii 0105] Fii QS team verbally replied and agreed to provide self-declaration by one company, but will require ALT to provide all the data of consign parts for Fii review. [0106] It can be closed after receiving Foxconn's opinion by e-mail. [Fii 0112] Fii can provide self-declaration of the whole product including the consign parts, but ALT need to provide the ROHS documents of the consign parts required by Fii. | All
MP | RMA issue Review - Foxconn should review RMA issue report from Factory befor ALT. | Eagle | ALT | Close | [12/15] Foxconn will review new RMA issue from now on.. | Eagle
| Vaule Engieering | All | ALT | Close | [12/15] Foxconn has VE process once within a year after launch. But Foxconn will review any suggestion about VE from ALT. | Swan
| Shielding Removal Verification | Eagle | Foxconn | Close | [12/16] SW v. R13 has some connection issue. ALT ask to use VPN. [1/2] Foxconn used VPN, but the result was same. Foxconn will check it with 15.502.43. It didn't have any connection issue. But Thermal test will be start by 1/30. CPU load of 15.502.43 is similar to SW v. 15.520.8 If possible, ALT can explain using the result of 15.520.8 result to SKB. [01/06] ALT will discuss with SKB by next Tuesday(1/10) [0113] It closed here, but it handle on Eagle. | ALT
| Eagle RMA | Eagle | ALT | Close | [12/16] Foxconn will receive RMA data from factory and review major 3 issues of RMA((SoC, eMMC, Eth PHY). [1/5] VN QA/PE will sort the defective SoC/eMMC/Eth PHY in different failed symptoms, and then send them back to the vendor for further FA. Will update VN factory's plan to ALT later. [01/06] Foxconn didn't know whether there is defected parts that repaired before in the factory. Foxconn will check it by next week. If there is no defected components then Foxconn will review the defected unit in 4th RMA. [Fii 0112] After further discussion with the Vietnam QA team, they think the defect rate should be calculated on the total number of shipments instead of just checking the number of each defect issue. Therefore, the anaysis plan provided by VN PE/QA is that they will analyze top1 issue and sort 10pcs defect SoC to do the inspection, baking, reball, measurement and swap test. If the SoC still fail after swap test, then they will send SoC to the vendor for further FA. For the major 2nd and 3rd issues, Vietnam QA will monitor it. If defect is above 500ppm, it will be analyzed. [0113] It closed here, but it handle on Factory tab. | Foxconn
2nd source | Motorcomm Ethernet PHY | Eagle | Foxconn | Close | [0113] It closed here, but it handle on HW tab. [12/16] RJ45 connector change to SWAN's. => Rework error.
| SWAN DDR EOL for AMP B'd | Swan | Foxconn | Close | [12/16] Foxconn will check that NANYA can provide SI Test result. [12/23] NANYA can provide SI test result. Foxconn is checking the no. of samples that they can provide to ALT.
| Reliability test item for ABS resin use. | Eagle | Foxconn | Close | [12/16] ALT will check that below test items. Non-op test(Vibration, shock), package test [12/21] ALT Feedback - Non-op test(Vibration random/Shock) can skip.

## YEM_SW
Item | Model | Issuer | Status | Action Item
Mantis comm - Due date should be included | All | ALT | Close | [12/16] Both parties accepted. | Open
Source code of Foxconn Lib. should be opened for fast debug. | All | ALT | Close | [0113] Foxconn keep their policy. [12/16] Foxconn will discuss internally. But Foxconn will add some log to debug issue. | Close
Build Key support to build SD image build | All | ALT | Close | [0113] Foxconn keep their policy. [12/16] ALT need to add some log to debug the issues. Sometimes ALT need to release it for some restricted customer. It may improve the speed of interact with SKB. | All
Eagle A12 xTS test result | Eagle | Foxconn | Close | [0113] Foxconn keep their policy. [1/2] It finished but ALT didn't receive the detail result. [12/16] It will be finish by the end of Dec. | Eagle
How not to kill SKB apps under LMK condition | All | Foxconn | Open | [1/2] ALT suggested it and is waiting for SKB's feedback. [12/16] Foxconn suggested to use the method that they use for CTS. | Swan
ALT
Foxconn

## Pre-MP issues
Open issues for 100pcs pre MP=>check if possible to pull in to ETD 6/25?
1. Thermal issue -
1.1 ALT request to reduce 50% speaker volume, the total AMP power changes from 7.7W to 4W, no additional venting hole, both AL & VC HSR @ 25degC & 50degC ambient can pass criteria of all components but the housing surface are still marginal fail.
1.2 The thermal solution of VC is the maximum limit for the current design. The temperature of all components can be passed based on VC solution with maximum AMP power but the surface temperature are still marginal fail.
1.3 Fii will arrange the real case thermal test based on DVT3 sample but that mean Fii don't have enough time to implement any solutions if we need to shipped 1st 100pcs sample by June.
1.4 Thermal solution should be fixed within this week for MP demand. The heatspreader sample price is very expensive and the capacity will not be able to meet 4.9K demand later.
2. DREAMUS Speaker
2.1 100pcs will use the same speaker as DVT3?=>not yet finalized
2.2 Need the comparison of old and new speakers to evaluate the impact.
3. Test
3.1 Reliability will not be able to complete before shipment
3.2 BQB and HDMI pre test doesn't have enough time to go through completely
4. Material
4.1 MP PO was provided late on 4/19. Fii only prepared the materials with long LT(greater than 90days) excluding AMP boards with new design. Will need to check with vendor if possible to meet the target. If not, will need to buy from spot market. The same for MP order later. | WK5/3給出那些物料需要採買現貨，提供清單給ALT
4.2 ALT controlled parts such as DREAMUS speaker, INKEL housing, Wellang amplifier (also need ECAP) should ETA VN 6/9 =>need to check with factory for the ECAP qty , if enough for 100pcs??
5. SW
5.1 OTA function on A113X should be ready by 5/14
6. Selling price related to payment
6.1 The final quotation is not fixed yet.
7. EMC
7.1 The system RE/RS/CE is being tested and debugged with new AMP board. Even if we use the latest speakers and enhanced FFC cables for testing, but the housing is not the final one, which means that the cable routing will not be the final setup. and this may bring some risks when using DVT3 sample for certification.=>need ALT to send out the DVT3 housing sample ASAP
7.2 There are some venting holes in the DVT3 housing, which may cause the risk of ESD failure.

## AMP board R&R
AMP board (AML A113X & Wellang) R&R
Items |  | ALT | FII | Comments
SW | Source code management
| -Source management System | O |  | Git : http://altserver01.iptime.org:8282/
| -Build Development environment | O | O | What support is needed from Fii?? [ALT] FII make develop environment in FII side
| -Develop Bootloader | O
| -Develop Main SW in DSP include Audio weaver porting | O
| -AMP control function |  | O
DSP B’d Bring up
| -I/O Port set (I2S, I2C, USB etc) | O
OTA
| -Build OTA server | O |  | Should be discussed with SKB
| -Develop OTA download APP for DSP B’d – VS-550 side |  | O | Same way to RCU Firmware update method
| -Develop Image Transfer(to A113X) | O | O
| -Develop Image update (bootloader) | O |  | Download certain area of NAND and it will be updated when DSP b’d reboot
Audio I/O Implementation
| - Develop I2S path : I2S input port -> DSP -> I2S ouput port | O
I2C comm
Implement I2C Slave – DSP
| -Check comm. status | O
| - Implement command list | O |  | check if all A113 command list is implemented by ALT; what is the difference between the command list for DSP and VS550
| -status check | O |  | [ALT] For example, we need below functions to run reboot.
| - Reboot | O |  | VS-550 asked DSP to reboot, then the command function should be implemented VS-550.
And the commands for receiving command and reboot in DSP should be implemented in DSP side
| Implement I2C Master – VS-550 |  |  | So, FII implement SW in VS-550, and ALT implement SW in DSP.
| -Check comm. status |  | O
| - Implement command list |  | O
Function for Mass production
| - A113 Status Check | O
| - Firmware release for MP | O |  | We should discuss which format FII need for MP.
| Share Data |  |  | Is this A113X source code? What's the purpose of this item [ALT] source code share is more efficient to understand each others. It is an language for SW development side.
- Source code
- Development environment
HW | Circuit design | O
| PCB Artwork – for DVT3 | O
| For MP | O |  | [ALT] We would like to devide R&R for development(ALT) and MP(FII) of AMP B'd. But if you want to provide Artwork for MP from us, then please share the cost of PCB for MP.
| Bring up | O
HW Test
AMP Performance test
| -Max. Power | O
| -THD+N vs. Freq.(1W) | O
| -THD+N vs. Freq.(Max. Po) | O
| -Max. Hum noise(Output Noise) | O
| -Min. Hum noise(Output Noise) | O
| -SNR@ Max. Power | O
| -Frequency Response | O
| -Cross talk | O
Etc
| - Thermal |  | O
| - EMC |  | O
| Share Data |  |  | What about this column? It means the data will be provided by ALT? [ALT] We can provide it if you want. I think it is for time saving.
Circuit diagram
Gerber data(DVT3+MP)
AMP performance test report
Components datasheet
Data for production