## PM&Sales
Category | Issue | owner | status | due date | Progress
PM | DVT3 sample qty for ALT/SKB | ALT | close | 2021-03-15 | [Fii] Nominally ALT has 176pcs left for DVT3 (320-36-108) but will need to calculate the actual qty left with increased BOM cost after design change. [Fii 0317] If the qty is not informed by 3/18 the schedule will be delayed for another week because the factoy load the demand once a week. [ALT] Will provide on 3/17
PM | R&R discussion | Fii/ALT | close | 3/23=>3/26=>4/9 | [Fii] Fii will update the R&R list and ALT needs to check if additional items needed. [ALT 0319] Will provide the detailed items about HW development for discussion. [Fii 0326] Fii will review and reply by 3/29 [ALT 0329] We add some feedback on your comment in "AMP Board R&R" Tab. [ALT 0401] R&R for AMP board PCB artwork for MP still needs to be discussed. [Fii 0408] Fii willdo the EMC test and provide the solutions for EMC issue. [ALT 0408] MP artwork will be owned by ALT.
Sales | pre-MP+MP PO for 1K | ALT | close | 3/26=>4/8 | [Fii] will evaluate the BOM bassed on final ME design by 3/19 first. The final PO should be provided by 3/26. [Fii 0319] Before 3/24 Fii will evaluate the BOM cost based on the design as of 3/19. If there are design changes after then the price will be updated again. Also the E&O will be handled by ALT. [Fii 0325] ALT needs to provide the UP for amplifier [ALT 0326] will provide it today for Fii to update the quote. [Fii 0401] Will provide the quotation within this week. [Fii 0412] Those LT greater than 90 days are not prepared. Need ALT to provide the PO ASAP to lead the demand based on current design.
Sales | E&O amount for DVT and 1K (pre MP+MP) after design change | Fii/ALT | pending | 4/7=>4/29=>8/31 | [Fii 0901] Fii will summarize all E&O once BOM fix. [Fii 0826] ALT consigned P/N for TMI3252S will be ready on 8/26.=> Released on 8/27. [ALT 0825] AMP design: HW is final. But there are 4pcs 1K resistance that need Fii to issue ECR to remove. [Fii 0823]Need ALT to confirm a) whether AMP design is final b) whether ALT will consign TMI3252S in further (close) ALT commented that TMI3252S will be consigned part in forther on 8/23 meeting. [Fii 0504] BOM is not finalized yet. [Fii 0415] ALT updated BOM again on 4/13 and the EC process is still ongoing. [Fii 0409] Will provide the 1st version but will update again before MP due to possible design change after the verification of DVT3. [Fii 0325] HW Tom will isse EC by 3/26 and the list will be updated later. [ALT] Final ME Design will be derivered by 3/19. We can deliver Speaker cable data by 3/19 Speaker data will be ready by 4/9 [Fii] Will evaluate when receiving the final ME drawing together with HW design
PM | Fii will scrap all the ALT provided parts such as hosuing sub-assembly, speakers and speaker cables after DVT2 | Fii | close | 2021-04-09 | [ALT 0317] Fii provide the list for ALT to review first. [Fii 0325] List provided to ALT [Fii 0326] Received the reply from ALT and will scrap based on the confirmation column.
PM | DVT3 material preparation | Fii/ALT | open | 4/29=>5/19 | [Fii 0520] to check SD report [ALT 0513] reworked housing and speaker cable ETA TBC by ALT [ALT 0512] 5/13 ETA Fii factory by ALT/Inkel [ALT 0511] Inkel to reowork housing, target to be finished on 5/12. [Fii 0510] Housing sample can't perfect match, under checking by ALT SH when receiving. [Fii 0428] The most gating is Inkel housing. Fii controlled parts will be ready by 5/4. [ALT 0423] Inkel finished T0 tooling. DVT3 ETD 4/28. SOP should be provided no later than 4/27 to keep the DVT3 schedule. [Fii 0420] The shortage will be updated on 4/21.=>4/26 [Fii 0416] Plz prepare the documents needed for ECAP PN application. Need the PO for DVT3 ASAP. The schedule will be delayed if not provided by 4/19. [ALT 0413] We will send AMP and ECAP by this Friday. We are checking on Mechanical part delivery schedule. We will inform Mechanical part delivery schedule when we get feedback from INKEL. [Fii 0412] Need check ALT provided parts schedule. Need amplifier & ECAP ETA factory 4/21. ME parts & speaker sets ETA factory 4/23. [Fii 0409] Fii QVL don't have stock ready for ECAP with spec requested by ALT and need ALT to check the originally designated vendor for DVT3 sample build demand. Fii will change to QVL part for MP. Mantis #0001143~0006640 [Fii 0406] Need the PO to place the order for extra parts from the design change for DVT3 ASAP. [ALT 0401] Already talked to AML Korea BD and got the reply in need of PO. [ALT 0326] ALT talked to AML and will check with AML BD for the preparation of A113X. [Fii 0324] Fii will prepare materials for AMP board for DVT3 and MP based on ALT provided BOM on 3/19 on Mantis 1143. The 1st EC will be released by 3/26 by HW Tom. [Fii 0319] -A113X was kicked off by ALT with AML and ALT has the power to push AML BD Demian to book MP 1K demand. Fii will place the order to AML when receiving the PO from ALT later. -ALT helps to check the Wellang amplifier LT and start the preparation of DVT3 first. [Fii 0317] -A113X LT*32WK. Will need ALT to have AML Demian book the materials for DVT3 and MP. Fii will also check with vendor. [Fii] Fii will finalize the AMP BOM for production and place order for DVT3 by 3/17.(Sean)
PM | New speaker sets data sheet for application of new PNs | ALT | close | 4/7=>4/13 | [ALT 0401] will reply by 4/5 if the data sheet could be released as planned. [Fii 0406] Need apply for PN immediately. Plz provide it no later than 4/12. [Fii 0412] Got the data sheet for cables. Need the speaker's ASAP. [ALT 0413] Dreamus answered that they will send their datasheet by tomorrow morning.
PM | Philips business trip visa documents | Fii-Dennis | close | 2021/4/12=>4/28 | [Fii 0325] 1. 外國法人指派文件Travel Order_ALT_revised更新上傳法務系統。(3/24,done) 2. 待孫律師核簽 (3/25,done) [0326] 1. 用印簽核。(3/29,done)=> 目前核簽到鄭總 2. 3/25 和人事怡廷及Call Philips 查詢, 簽證申請以韓國辦事處規定為準 , 簽證需有邀請函及工作許可才核發簽證。 [0330] 1. 3/29送虎躍廠用印。 2. 3/30 文件送勞動部開案審查。 [0331] 已送勞動局 , 編號: 1100565962 ( 勞動局回覆,申請需要12個工作天) [0401] 1. 詢問勞動局加急需求 ,勞動局回覆,目前沒有這項申請管道,也沒有加費用申請加急的作法。 2. 可到網站:http://www.wda.gov.tw , 查詢申請進度,已經提供 ALT Philip 了解目前進度及查詢訊息。 [0406-0408] 查詢勞動局網站:http://www.wda.gov.tw , 進度為審查中。 [0409] 所附的合約是新加坡的公司和韓國ALT Co,.Ltd兩家外國公司簽約，不符合規定。需要補件。 note : 需提供買賣訂單或合約 , 是新加坡公司台灣分公司和 ALT 之間有關的文件。 [0412] ALT 提供訂單 , 先用原用印申請單,將ALT 訂單送虎躍廠用印。 [0415] 1. ALT 訂單用印已重新送勞動局審核,依辦理周小姐回覆依3/31收件, 4/1開始計算12個工作天為 (4/20完成) 。 note : 1. 4/20 勞動局核可後會將公文郵寄出 , 4/23可收到公文。 2. ALT 再依公文申請簽證,韓國台灣辦事處回覆需5個工作天 , 預計4/28完成。 [0421] 1. 4/16 下午收到勞動局核可公文 , 4/17郵寄到韓國。 2. 4/21 Tracking number : EE940708313TW , ALT Philips 已經收到文件。 [防疫規定 : 人事周怡廷 ) 1. 依據國內防疫規定 , 客戶來台之後 => 先隔離 14天 => 再自主健康管理 7天 2. 鴻海公司內部規定 , 再自主健康管理 7天期間 , 如果要進公司開會...等等 , 需持有核酸檢驗核格報告才可到公司。 3. 完成自主健康管理 7天者 , 鴻海公司內部規定不需提供核酸檢驗核格報告。
PM | Wellang AMP designation letter & vendor contact to register vendor code and PN =>changed to B&S | ALT | close | 2021-06-30 | [Fii 0507] ALT request change to be consign. [Fii 0428] Sales Tiffanie is checking with ALT the buy and sell part list. [Fii 0326] Vendor code registration is in process and expected to complete by end of June. Will notify ALT once the process is done and before then will need ALT to support buy and sell. [Fii 0325] Documents are submitted in the system for DVT3 PN application and will finish by 4/9. [Fii 0317] Need to apply for PN with B&S mode and direct trading mode at the same time. Need ALT to provide the needed documents and reply email.
PM | AMP eMMC 4G changed to NAND flash | ALT/Fii | close | 2021-04-07 | [ALT 0402] Could you check NAND Flash that Mr. Lonnie KIM informed in e-mail ? [Fii 0406] Fii buyer is checking the supply and will reply by 4/7 [Fii 0409] Will change to NAND flash starting from DVT3.
PM | Package final artwork for MP version | ALT | close | 2021/6/22 =>8/10 | [ALT 0810] Energy label : ALT checked and there is no issue, so please proceeds with MP. [Fii 0802] energy efficiency label sample built ( due date : 8/10) [ALT 0729] I'm sending the final artwork of the energy efficiency label for SWAN. Please share the schedule of the sample photo. [Fii 0728] The printing provide by 7/27. [Fii 0721] Label L/T 20 day , sample bulit L/T 10 day , artwork due date : 7/22. [Fii 0719] The printing will be confirmed on the 7/15->7/27 of the Giftbox production. [Fii 0621] Suppliers are unwilling to do giftbox new printing, so purchase assistance helps. (A total of seven samples have been made so far) [Fii 0617] 1. new QSG sample ETD 6/19. (new vender) 2. Please take a picture of giftbox sample badly logo printed. In addition,a good logo printing sample picture, will be provided for vender evaluation and comparison. 3. The ALT confirms EPE on 6/8. [Fii 0603] (1) QSG new sample ETD 6/4 (2) Vendor will print again gift box to check printing quality (3) EPE foam sample ETD 6/4.(4) KC label artwork to be provided. [Fii 0601] (1) wrong QSG sample with previous artwork, vendor is remaking right now, sample ETD by 6/4 (2) Gift box sample has printing quality issue, ALT/SKB has conditional approval for this sample (3) EPE Foam can't fit into gift box perfectly. [Fii 0520] ALT provide artwork of giftbox and QSG, but artwork of KC label to be confirmed. [Fii 0514] ALT request to update artwork again, sample preparation is stopped and pending now. [Fii 0513] to provide sample by 5/31 for ALT's approval [ALT 0511] To keep current artowrk to meet schedule [ALT0507] ALT to update artwork [Fii 0428] The vendor agreed to ship out 5pcs to Korea(shipped on 4/27) and need ALT to advise FEDEX account for the rest samples. [Fii 0423] The vendor feedback they can support samples but the delivery cost needs to be born by customer. Plz advise [Fii 0412] sample ETD no later than 4/23. [Fii 0409] Need to check with vendor for the sample qty and schedule by 4/13. [Fii 0406] ALT approves to use up old stock for DVT3. Need ALT to provide the updated artwork for MP version and check the sample qty.
PM | ALT advised FFC cable + bushing vendor HWASUNG | Fii | close |  | [Fii 0406] Notified the vendor to prepare the sample for verification. EMI performance is worse than P Two
PM | Sub-boards PCB hold production as ALT requested | ALT/Fii | close | 2021-04-14 | [Fii 0413] ALT notifed to hold production on 4/13 and update the gerber of AMP board. The gerber out date from Fii to PCB vendor will be on 4/14. Total delay of 5 days will impact the DVT3 build schedule. [Fii 0414] There will be cost for PCB as the old one cannot be used and need to scrap. The DVT3 start date changed to 5/3.
Sales | PO for acoustic chamber modification | ALT/Fii | close | 2021-04-16 | [Fii 0415] Will provide the breakdown list for SW within 4/15 and need the PO by 4/16 as the SW modification is still needed for DVT3. [Fii 0416] The PO should be provided by 4/19.
PM | 2nd source list to be introduced after MP | Fii | close | 2021-08-30 | [Fii 0901] RD to provide the proposal today. [Fii 0820] Since there is no difference between 24CH or 36CH (L/T:392), RD to survey whehter there is any other solution to improve L/T issue. [ALT 0505] Please confirm if Sunlord's inductor should be pass BMT [Fii 0423] The introduction process follows Eagle. [Fii 0421] Including ECAP from NICHICON
PM | LS communication inductor OPO cancel(Mantis 0001131~0006674) | ALT | close | 2021-05-07 | [Fii 0513] ALT confirm the running change plan. [Fii 0512] Fii issued PO to LS communication, Fii double confirm Sunlord's L/T, ALT confirm running change after 30K. [Fii 0511] Fii will release 30K PO to LS commnunication. [ALT 0510] Sunlord's contact window and L/T. and need to decide how many pcs to issue PO to LS communication. [ALT 0507] Will try to provide it on 5/7 [Fii 0505] IND-Sunlord Fii checks if QVL again. And Philip will help check the change reason and more information (how the IND affects the acoustic performance, FR? THD?) [Fii 0428] Plz check if will continue to use the inductor SPH10040-100M for MP and onward. This will impact the 100pcs material preparation and the heatspreader design. | 1131
PM | 30pcs heatspreader allocated to ALT for urgent request to BMT | Fii | close | 2021-05-14 | [Fii 0428] N.W.E shipped out 30pcs AMP heatspreader top and bottom to ALT on 4/27 from 195sets demand for DVT3. Need to push to re-make 30 sets for DVT3
PM | Final design of heatspreader *25pcs sample | Fii | close | 2021-06-07 | [Fii0615] New Heatspreader 6/15 ETA (VN) [Fii 0601] 25pcs samples ETA 6/10 , haven't get ALT's PO [Fii 0524] Under tooling modification due to T1 housing design change and request vendor to ETD 5/31 [ALT 0521] ALT to confirm if final heatspreader sampe Korea. [ALT 0520] ALT inform to hold tooling kick off due to top case of housing is going to change, heatspreader sample will need to be modified again. [ALT 0513] Fii updated final design, need ALT to confirm then Fii will kick off tooling [Fii 0511] Quotation provided to ALT Steve, wait for PO. [Fii 0507] ALT agree on tooling kick off.
PM | ALT designation letter for BQB lab | ALT | close | 2021-05-04 | [ALT 0430] Will reply by 5/4.
PM | DREAMUS REACH (SVHC 211 items) Compliance Declaration | ALT | close | 2021-06-04 | [ALT 0705] ALT provide by 7/5. (Fii QC team inspection document) [Fii 0617] REACH_符合性宣告(FK3N00002007_I).xls => need to fill in and company's seal. [ALT 0527] target to provide by 6/4 [Fii 0510] Fii QC team sent requirement to ALT for confirmation [ALT 0507] Provide the documents within WK 5/10. [Fii 0430] Plz check with DREAMUS for the declaration with general format for REACH.
PM | Final version of FFC cable/Heatspreader/Housing Assembly | Fii | close | 2021-05-20 | [0623]supplier has sent to Korea (TRK# 774034212546) [Fii 0617] 5 set new FFC cable : The supplier now has five sets of FFC (Enhanced shielding) cable sample to provide ALT. Please agree to use the ALT Fedex account to send FFC (Enhanced shielding) cable sample. [Fii 0601] To confirm schedule for 2 gaskets samples in order to add into final version of 25 pcs sample for KC/BMT [Fii 0520] ALT request to assembly 30pcs(20pcs for ALT, 5 for Fii) advanced FFC cable with shielding , final heatspreader of mainboard, current top heatspreader and T0 housing in VN factory. (20pcs final top heatspreader to be sent to Korea) Fii to check with factory about work order, and ETA schedule of FFC cable and heatspreader. ALT to check the T1 housing ETA schedule.
PM | VN factory lock down issue | Fii | close | 2021-06-15 | [Fii 0527] Guang Chau site is under application to VN government for unblock.
PM | T1 housing sample qty | Fii | close | 2021-06-02 | [ALT 0624] T1 sample will be ready by 6/26. [Fii 0615] provide 4 more T1 housing samples =>T1 housing samples (4pcs) will be used in DVT3 production and assembly four groups to provide housing reliability test . Note : Test Item :T1 Housing => Free Fail Drop Test/Operational Random Vibretion/Operational Shock Test [Fii 0603] Fii to update T1 housing sample purpose. [Fii 0602] Fii to confirm required T1 housing sample to be shipped on 18th June.
PM | Extra acoustic equipment purchaising | Fii | close | 2021-06-10 | [Fii 0621] New acoustic equipment order can be confirmed and provided on 7/1. [Fii 0617] New acoustic equipment L/T : 8week ~ 10week. [ALT 0603] ALT to provide extra acoustic equipment PO.
PM | 5 set DVT3 PCBA send to Korea | Fii | close | 2021-06-30 | [ALT 0702] sample have been received. [Fii 0630] 5 set DVT3 PCBA ETD 6/30 =>(TRK# 774112265640) [Fii 0627] 5 set DVT3 PCBA ETD 6/30 (Vietnam) [ALT 0624 ] SW version => secure [Fii 0623] SWAN five sets of DVT3 PCBA sample : 1. SW version ( secure or non secure ?). 2. DVT3 MP will reduce " New 25pcs sample for KC version" 5 unit shipped to Korea. 3. The application can be sent on 6/30 => Please agree to use tht ALT Fedex account to send the PCBA sample.
PM | Dolby MS11 certification | ALT | close | 7/20=>8/31 | [Fii 0901] Provided Dolby certification on 9/1. [Fii 0820]Under Fii internal legal process. [Fii 0728]Our legal team received MS11 exception letter agreement from Dolby today which describes the following points. 1. Licensee will have until August 30th, 2021 to certify the new STB(model name: BFX-UA300). 2. The sell-off period for this specific STB will be extended until June 30th, 2024. 3. Licensee shall not manufacture or Sell any products incorporating MS11 Technology that are not approved by August 30, 2021 However, ALT team told us that we don't need to sign any extension agreement, and only resubmit the new test result with modifying documentation to Dolby certification engineer Steve, and the royalty paid by ALT. But Dolby US asked us to sign this letter/agreement before we get the MS11 certification by Aug. 30 We think it needs to discuss this critical issue with ALT team for how to deal with it in tomorrow's daily call. [Fii 0707] First priority - Option A : Submit based on MS11 w/o HE-AAC (to confirm by end of this week) 1) Synaptics to provide the patch which turn off MS11 AAC , and keep Synaptics in-house AAC, 2) Fii Brent and ALT will test IPTV all channels in Korea by this week (owner: ALT/Fii ) 3) SPTek to modify IPTV player instead of Synaptics SDK (owner: ALT-Mr. Yoon) 4) Fii to double check if Synaptics has experience of " in-house AAC only" (Owner: Fii-Jacky) 5) Extend due date issue: ALT will negotiate with Dolby Korea to sign amendment for extension. (owner: ALT- JW) 6) ALT will submit the MS11 w/o HE-AAC certification and pay to Dolby. Option B: Submit based on MS11 w/ HE-AAC (ALT will check if optionA isn't work) - Submit based on current SW - ALT to get Dolby's MS11 w/ HE-AAC or MS12 w/ HE-AAC (owner: ALT- JW) - Suggest to find the discussion record btw Dolby and ALT last year to see what proposal Dolby provided. If they didn't mention that ALT should get Via Licensing's AAC before sign MS12 w/ HE-AAC with Dolby, then ALT can strongly request Dolby to find solution for it. (No matter it's a waiver for this project only or to grant ALT : MS12 w/ HE-AAC, it's Dolby's call) - ALT to submit the MS11 w/ HE-AAC certification and pay to Dolby according to our supply agreement. [Fii 0706] In summary of Jacky and my comment, there are two options: Option A : Submit based on MS11 w/o HE-AAC - Precondition: 1) Synaptics to provide the library which turn off all AAC (owner: Fii-Jacky) 2) SPTek to modify IPTV player instead of Synaptics SDK (owner: ALT-Mr. Yoon) - ALT to submit the MS11 w/o HE-AAC certification and pay to Dolby according to our supply agreement. Option B: Submit based on MS11 w/ HE-AAC - Submit based on current SW - ALT to get Dolby's MS11 w/ HE-AAC or MS12 w/ HE-AAC (owner: ALT- JW) - Suggest to find the discussion record btw Dolby and ALT last year to see what proposal Dolby provided. If they didn't mention that ALT should get Via Licensing's AAC before sign MS12 w/ HE-AAC with Dolby, then ALT can strongly request Dolby to find solution for it. (No matter it's a waiver for this project only or to grant ALT : MS12 w/ HE-AAC, it's Dolby's call) - ALT to submit the MS11 w/ HE-AAC certification and pay to Dolby according to our supply agreement. Extend due date issue: - Synaptics will negotiate with Dolby USA and provide the documents for ALT to sign in order to extend.
PM | AMP Board E cap SAMYOUNG 100uF/35V (FII not verder code) | ALT | close | 2021-07-20 | [Fii 0715] The order has been completed. [Fii 0713] 1.7/13 first places an order for 30 sets of 120K capacitors to the agent, and the agent and the capacitor agent (三瑩) discuss the delivery process. 2. The establishment of agent (三瑩) Vender Code is expected to be completed in three months. [Fii 0712] Can it be changed to ALT buy & sell material ?
PM | Pre-MP buy & sell 1K materials | ALT | close | 2021-07-25 | [ALT 0722] Provide a schedule list of buy & sell materials . [Fii 0715]When will the materials arrive at the factroy?
PM | September 4K order | ALT | close | 2021-07-25 | [Fii 0803] start 12k materials prepare [Fii 0802]As per our weekly review meeting minutes, ALT will confirm AMP/Main board solution on next Monday (08/02). => In order to reduce th risk, the materials production of 12k will also be suspended. ( Main PCB/FFC Cable/Heatsink..) [ALT 0723] ALT agrees to 12K order risk buy. [Fii 0721] Provide a list of risk buy materials. [Fii 0715] Need to risk buy ?
PM | Pre-MP SPOT 1K materials and 2nd source part list | ALT/FII | close | 2021-07-25 | [Fii 0721] Provide a list of 2nd part materials. ( for sopt list) [Fii 0719] Some materials cannot be found in the spot market (TI LP5036RJVR).
PM | BFX-AT100 (T99X171.00) DIODES & 3peak 2nd source reliability test | ALT/FII | close | 2021-08-31 | [Fii 0825] 1. Diodes 40pcs control run done; 3PEAK 100pcs control run on 8/25--> will provide control run report before next week. 2. CFT will deliver out 20pcs to Taiwan RD team by 8/28. [Fii 0821] Reliability is completed based on Fii testing rule. [Fii 0819]provide the control run report. [ALT 0818] I asked test items on attached e-mail. In our test conditions, we asked as follows : 4) 20 sets AC power on/off 100 times 5) 20 sets Passive standby on/off 100 time (We don’t support this function) 6) DUT full load & 45℃ Condition 20 sets minimum 72h aging test In your report, 1. You used 2 samples. We asked 20 samples. 2. There are “RED LED” in your picture. So we need to check your test environment. . Did you connect HDMI / Ethernet cable ? . Did you connect USB for Full load condition ? . What is the iperf test spec ? In your test condition, it looks DUT didn’t connect nothing except Adaptor. So this picture cannot use for test report. We cannot accept this test condition.
PM | SWAN reliability test | ALT | close | 2021-08-23 | [ALT 0823] ALT comment to waive single unit test. (with package is necessary) [Fii 0819] Free Fall Drop Test (Single unit test) (fail / please check test report) Need ALT to check how to fix this issue.
PM | KC certification BMT schedule | ALT | close | KC:9/20->10/5 BMT:close | [Fii 1008] Did KC complete on schedule? [ALT 1001] KC postpone to 10/5. [Fii 1001] How about the progress? [ALT 0901] KC: testing is completed. Target to obtained KC is 9/20. BMT: Target to complete BMT is 9/30. [Fii 0901] Please comment when will ALT complete KC certification and BMT so that Fii could start pre-MP.
PM | The datasheet for B&S, consign materials | ALT | close | 2021-09-09 | [Fii 0910] Need to confirm L-CH, R-CH speaker cable MPN with ALT. [Fii 0901] To prepare IQC for MP, please double-check whehter all datasheet is the latest version. If ALT has any update, please provide to us by 9/9 to prevent IQC failure.
PM | RoHS | Fii | open | 2021-10-01 | [Fii 0915] Need ALT to upload RoHS information for ALT's B&S/consign/designated materials. https://supplier-gp.ambit.com.tw/supplier/Login.aspx [ALT 0903] Need Fii to try to pull in one week. [Fii 0903] Kicked off document collection with QA team based on ALT confirmed declaration format.
PKRD | Package improved solution | Fii | close | 2021-09-14 | [Fii 0915] Giftbox: The bursting strength is limitation in B flute. Vendor comment there is no way to imporve. Carton: PK RD is working with vendor to have improved sample based on BC flute. Will be cost up.
PM | Alternative parts approval from ALT/SKB Eagle's Ethernet: Realtek -> Motocom Swan's LED: TI -> Awinic | ALT/SKB | Open | 2022-06-01 | [Fii 03/29 ] Arrange the alternative sample to ALT - Eagle 03/29 / Swan 04/2
PM | Eagle LED 21496870012022011126732 / 21496870012022011126654 | ALT | Closed | TBD | [Fii 04/19 ] Canon Provide the test log reports to SH [ALT 04/20] SH feedback the concerns in test log report [Fii 04/21] Canon co-work with internal team to figure out the abnormal syndrom in log file [Fii 04/22] Canon would like to know whether SH will hand carry the defected units to VN facility during the audit visit
PM | 2nd Source | Fii/ALT | Open | TBD | [Fii 05/20 ] Eagle BT Module Cypress (L/T=378 days = 54 weeks) Have to get the Q4 P.O ASAP since long L/T
PM | Supply of Components | Fii/ALT | Open | TBD | [ALT/Fii 05/25 ] Biz meeting: ALT-Steve will update the decision about the risk buy on 05/27 ALT/Fii weekly meeting [Fii 05/20 ] SWAN AWINIC Risk Buy 20K due to the long L/T of testing
PM | Eagle RMA 13K | Fii | Open | TBD | [1125] There are differences between no. of NON-LED defect for 2nd RMA. Foxconn reported that it was 1,112, but finally it was 585 exclude 105 units that need t scrap. Foxconn informed that the 1st q'ty is based on no. of units before repair. But the 2nd q'ty is exact no. after repair. ALT asked Foxconn to leave a comment when there is some changes about no. or status on Mantis. [1118] ALT asked Foxconn to provide RMA 2 Report. RMA units almost all repaired. It is not provided yet. There is no scrap units in RMA 2. Foxconn will check it about no. of scrap unit. RMA 2 report wil be provide by 11/25. [1028] It already discussed with Mr. Steve Lee and Mr. Vincent yesterday. It will followed their discussion. [1021]Fii is still checking RMA cost with VN. VN will ship out 1st RMA1594pcs next time(include scrap 76pcs) Foxconn Factory needs more discussion. So Foxconn TW will ask ALT to have meeting after their internal discussion. [1014] Foxconn asked ALT to have a meeting for RMA cost discussion. It is about cost for Out of warrent units except LED issue. Foxconn will provide the details about it by 10/17. ALT will review the details and make a schedule to discuss. [1007] FII asked to change the RMA Label contents from "Made in Vietnam" to "assembled in Vietnam". Foxconn will send an e-mail about it. There are some wrong information on Serial no. of 2nd Batch RMA. ALT will check the information that Foxconn think wrong after receiving the information. There is no invoice packing list in 8.4K shipping document. Foxconn will provide it by today. [9/30] Foxconn VN will ship out 8.4K pcs of 1st RMA on 10/3 and ETD VN is 10/5. 2nd RMA batch will arrive today(9/30). [0923] The rest of 1st RMA(9.3K) will ship out on 9/26, 2nd RMA is on the way to VN. ETA VN is 9/28. Foxconn will inform exact no. of q'ty not to ship to Korea after meeting. [0908] If RMA unit shipped from VN to Korea directly, then it may cause customs clearance. For this ALT need some additional discusstion to reduce Tax. Foxconn will support it. So ALT donexn't need to worry about it. [901] Shipping schedule: Foxconn Factory will ship 2.9 K 1st RMA return batch. It will ship on 9/6 with 2K shipment of SWAN at the same time. 2 batch RMA : ALT shipped already and it arrived in HK 8/31 [0826] Foxconn will ship 1st RMA return batch(1.9K) next week. Detail schedule will be updated by this afternoon. 2nd batch of RMA will be shipped out on 8/27, not 8/16. And ETA HK is 8/30. 1 day delay for shipping schedule. Q'ty is 12,732. [ALT 0819] Foxconn VN can ship first 3K RMA units. Foxconn VN will update when they can ship to Korea. Based on RMA repair schedule, Foxconn VN factory repaired about 340 units per day. But Foxconn VN keep their daily repair capacity to 1200 units. To achieve it, Foxconn VN Factory will increase man power after Eagle MP. [ALT 08/12] Foxconn Factory will update RMA Status. Currently Foxconn cannot meet schedule. It will update by this week. [Fii 07/14] Leave Hong Kong to Vietnam on 07/19. Logistics& Custom 7~10 days. RMA will start from 7/31. [Fii 05/25] Screen the devices SN: 98.2% is related to old issue LED Diode Est total L/T 35days+ = Logistics (HK to VN) 7 days + Custom 7 days + In house repair at least 7 days + Logistics (HK to VN) 7 days + Custom 7 days
PM | License and Royalty for exFAT/NTFS (1540) | FII | Open |  | [1111] Other manufacturer support exFAT/NTFS R/W function. So we should provide Read funtion at least. [1104] ALT wants to know whether Foxconn can support it or not. ALT heard from SKB that other manufacturers will support R/W function from A12. ALT cannot know whether other manufacturers have File system license and their STB can support it. [1028] Foxconn think that there is no issue to support Read function for exFAT/NTFS. ALT already asked to support it from next build. ALT already asked it to Mr. Jacky Chiang. [1021] exFAT/NTFS will be free on A13. ALT asked Foxconn which File system can support for A12. Can Foxconn support exFAT Read function ? ALT needs Foxconn's opinion about File system. [1014] ALT doesn't have any information for other vendors. SKB would like to make a specification on File system for A 12 version. [1007] ALT asked Foxconn to update it on Mantis. Foxconn updated. [0930] Foxconn doesn't have license for exFAT and NTFS. ALT asked to provide about this answer by e-mail. [0923] Foxconn Support exFAT/NTFS File system for Android 12. Is there any issue on Royalty and License ? Foxconn is checking on it with legal team ALT asked FII to update Foxconn internal discussion status and result on mantis.
| EOL DDR4 4G | FII/ALT | Close |  | [1021]Fii booked the DDR4 4G base on ALT forecast. But as Hynix DDR4 4G has already been EOL, second source is still indeed. ALT will ask Foxconn to start 2nd source introduction when it need. Foxconn estimate DDR 2nd source introduction will take for 4 month. [1014] ALT provide the forecast about SWAN 2023. If Foxconn didn't have enough Hynix DDR, then Foxconn can order based on the forecast. ALT doesn't want to release ECO this time. If ECO will be needed, then it will be done by next year. ALT asked to Foxconn when ALT start to ECO decision. [1007] Eagle already has 2nd source for Samsung. So ALT asked Foxconn to use Hynix DDR for SWAN. Foxconn need PO for DDR for Eagle . [0930] ALT asked to Foxconn to go on and asked to provide the schedule for this ECO. ALT informed that it need 40 samples for BMT(20), QA(10) and ALT(10). But it may change after discussion with SKB. [0923] Hynix DDR4 4G EOL. ALT will check it and update on mantis.
| [SWAN]Synnex_Hynix DDR4 8Gb C-die EOL | FII | Close |  | [1104] SKB accepted it. Foxconn wants to get an e-mail about it. ALT will send e-mail early of next week. [1028] ALT will update about any feedback from SKB. [1021] Has upload Hynix DDR4 8Gb D-die report on mantis #0001547. Need ALT to review and approve it. ALT will inform to SKB and come back soon [1014] Hynix DDR4 8Gb die already EOL. ALT is checking which documents are needed for ECO request for SKB. Foxconn will provide their DDR Test report by 10/17. But customers always don't want this kinds of mistakes. ALT will discuss it with SKB, but ALT asked Foxconn not to happen it again strongly.
| Idle Stock | Fii | Open | 2022-10-30 | [1118] Foxconn will discuss with JW Kim of ALT. [1028] It is dicussed yesterday. It will handle based on yesterday discussion. [1021] Fii booked materials based on SWAN forecast. But the needs is put off by 2023. There are too many idle in VN/BT. Fii is asking ALT to buy the idle stock.
| ATV12 NRE&AMAZON Prime Video NRE | Fii | Close | 2022-10-30 | [1028] NRE was discussed yesterday. ALT asked Foxconn to provide Amazon Prime Video test plan. SKB hopes it will finish within month. [1021] Fii asked ALT/SKB to pay NRE about ATB12&AMAZON Prime Video.
| PCR(Post Consumer Materials) use - Portion/cost | FII | Open |  | [1118] Question about cost for PCR-ABS : SKB asked ALT about cost for Mechanical parts using PCR-ABS. ALT knew alreay that Foxconn isn't inform about cost about component. But it is request from SKB, not ALT. ALT asked Foxconn to support about it. ALT think that there is no requirement to use LG Chemical product only. ALT thinks that Foxconn can suggest other vendor that already has GRS Certification. [1111] PCR-PC can use 50% and cost will increase about $0.1. And PCR-ABS cannot be use for IR issue. [1104] Foxconn will feedback it after check internally and comeback soon. [1102] SKB asked ALT to check the following items. It was FII's reply 2 years ago. How much portion that PCR material can use for mechanical parts : 50% Cost increase when we use PCR material : US$ 0.1
| BI |  |  |  | [1118] ALT needs new Housing sample to check Housing and marks. And ALT will need samples with PCBA. ALT will check and comeback about no. of samples. ALT wants to know how Foxconn will test IR transmissivity. Foxconn will provide drawing abot test by 11/21. [1111] Foxconn can keep BI change schedule that provided in this week. [1104] ALT asked Foxconn to provide BI change schedule.

## HW &ME
Category | Issue | owner | status | due date | Progress
HW | AMP board layout review by EMC engineer & H/W RD | Fii | close | 2021-03-15
ME | Final ME 3D drawing. For ME/ Package/ HW review | ALT | close | 3/16=>3/19 | [ALT] We will provide it by 3/19 [Fii 0317] When does tooling start? We'd like to review before then. Is the T0 tooling schedule impacted? [ALT 0317] Tooling will start in WK3/22 and no impact on the schedule. [ALT 0319] Will push for the final drawing today.
ME | Part List of housing & speaker and updated designation letter for new parts | ALT | close | 3/19=>3/22=>3/31 | [Fii] Need to register PN and issue EC [ALT] We will check it with INKEL when they can prepare. [Fii 0319] Need the data no later than 3/22 or the schedule will be impacted. [ALT 0401] Inkel is preparing it and will check it with Inkel today. [Fii 0401] Plz provide the data on 4/6. The time left to Fii internal process is less and less. [ALT_0402] INKEL will provide it by 4/5. INKEL said that there is no additional parts, but some parts should be removed. [Fii 0406] Receive and ME is reviewing the parts that need the designation letter.
HW | AMP board DFM review by MFG ME | Fii/ALT | close | 2021-03-17 | [Fii] will send out the file for ALT to review and modify for factory review DFM again.
ME | Final 2D drawings for all parts for IQC inspection and the defined critical dimension | ALT | close | 3/19=>3/31 | [Fii] Need update in the system when applying for PN [ALT] We will check it with INKEL when they can prepare. [ALT 0326] Inkel is preparing it and will check it with Inkel today. [ALT 0401] provided already.
ME | INKEL needs to review the ME design to reduce the assembly process | ALT/Fii | close | 3/23=>3/26=>4/7 | [ALT] If you have any idea, please let me know. Do you have any idea to reduce to assembly for B'd side ? [Fii 0318] The factory will provide the DFx on 3/18. Fii will internally review with ME from 3/19. The advice will be provided by 3/23. [Fii 0323] the factory will update DFM based on ALT updated 3D drawing and internal review by 3/26. [ALT 0402] 3/26 DFM Feedback : not acceptable due to tooling started center(PCBA) area. this is too late. Don't change LED board connector direction (3/30 replied on mantis).
HW | Acoustic testing equipment needs to improve the isolation effect | Fii | close | 2021-03-19 | [Fii] Vendor provided the new pressing material to verify again after DVT2. [ALT 0318] Could you explain what problems you have.
HW | FIT RJ45 connector for Wired Network Authentication | Fii | close | 2021-03-19 | [Fii 0323] informed FIT to proceed with certification
HW | Thermal test with new AMP board | Fii | Close | 2021-05-14 | [Fii 0524] Update HWQA formal report on mantis on 5/24 [Fii 0520] Need ALT/SKB to confirm the final test condition, and then Fii HWQA will provide the formal test report to ALT reference. [Fii 0514] Update the thermal test result in 70% speaker volume (sealing rear venting hole) At 25degC ambient: temperature of housing top & bottom are 34.9degC & 45.3degC At 50degC ambient: temperature of housing top & bottom are 59.3degC & 69.2degC Update the thermal test result in 70% speaker volume. At 25degC ambient: temperature of houng top & bottom are 34.8degC & 43.4degC At 50degC ambient: temperature of housig top & bottom are 58.9degC & 68.8degC [ALT 0513] Update the thermal test result in 50% speaker volume. 1. All of the components and housing surfaces are passed the criteria @ 25degC & 50degC ambient. 2. At 25degC ambient: temperature of houng top & bottom are 33.7degC & 44.5degC At 50degC ambient: temperature of housig top & bottom are 58.7degC & 68.2degC [ALT 0511] Fii rework housing and do the thermal test from 5/12, will get result on 5/13. [Fii 0507] Our QA team confirmed that the thermal test can be started from 5/12 [ALT 0505] Expected to ship out on 5/5. [Fii 0430] Will perform thermal test once receive the housing & new speaker samples and need ALT to fix the thermal solution within WK 5/3. Otherwise the heatspreader tooling schedule will impact MP [ALT 0430] The housing*2 and speaker will be shipped out on 4/30. ALT will also reply the thermal solution on 5/3. [Fii 0428] Will simulate again based on the same condition with additional venting hole, and see if housing surface temperaure is improved or not. [Fii 0426] Reduce 50% speaker volume, the total AMP power changes from 7.7W to 4W, no additional venting hole, both AL & VC HSR @ 25degC & 50degC ambient can pass criteria of all components but the housing surface are still marginal fail. [Fii 0423] Fii will do the simulation based on ALT proposal again. [Fii 0416] The simulation report was provided and need ALT to advise. [Fii 0413] To evaluate chaning of the material of heat spreader/ die-casting from Aluminum to Copper, and consider the VC (Vapor Chamber) cooling method to see if there is any improvement. Will provide the updated simulation report to ALT by 4/15. [Fii 0412] Have provided the update simulation result to ALT. The key components are still fail @ 50degC ambient but the temperaure of the parts on AMP board is indeed lower than the previous results. [Fii 0409] Will start the simulation on 4/9 and expect to provide the report by 4/12. [ALT 0408] Need Fii to do the simulation with ALT proposed solution first then consider Fii proposed solutions to reduce the ambient temp., reduce the watt, enlarged vent holes. [Fii 0407] Have provided an explanation of the power dissipation difference between EVT and the new AMP board for ALT reference. Need further discussion with ALT for the thermal issue. [Fii 0406] Need the concall for discussion. Checking the time slot on 4/8. [ALT_0402] When FII will start to discuss ?
HW | new design AMP board samples & speaker *13 sets for HW EMC/Thermal & SW | ALT | close | AMP:3/19=>3/31 SPK:3/19=>4/23=>4/26=>4/29 | [ALT] AMP board ETD KR 3/31 and the material status is under checking. On speaker, Dreamus will provide it by the end of April. So we will use current Speakers for test for HW, not acoustic feature. [Fii 0317] Need the speaker together to do the EMC and thermal. If ALT decides not to do any EMC/ thermal test before DVT3, plz send a formal email to confirm. [ALT 0317] 1st lot of speaker is 60cs pn 4/23. Fii may provide the risk statement for ALT to confirm. [ALT 0319] AMP board ETD KR still 3/31 [ALT 0401] No any verifications done before shipment. =>ALT shipped on 4/1. [Fii 0406] Speaker needs to pull in to 4/23 [ALT 0423] Speaker sample ETD 4/26 and the samples are not final. Will check the difference with final one. [Fii 0428] After checking with Sophie the ETD is delayed to 4/29. [ALT 0430] Will ship out the speaker samples on 4/30.
| Thermal test | ALT | close | 2021-05-07 | [ALT Philip 0506] ALT will reply the testing spec by 5/7. [Fii 0507] ALT Lonnie have provided the test condition on mantis on 5/6. However, as discussed in weekly meeting, Fii will keep using the SKB's stream content to do the test with 50% speaker volume.
HW | Microphone sealing test | ALT | Close | 2021-07-30 | [Fii 0730] The report will be updated on mantis by today [Fii 0729] 1. Fii can get pass result (25dB) with T1 housing but need to add addtional adhesive type between top cover and sponge rubber. Will provide test report to ALT on 7/30 [Fii 0728] Fii ME RD is checking on the assembly and will retest again tomorrow to see if there is any problems. [Fii 0726] Sample 1: The sealing result is around 21-22 dB @450~600Hz, 2K, 2.5KHz Sample 2: The sealing result is around 17-28dB @ 600~700Hz, 2KHz Need further analysis for the assembly of top cover [Fii 0721] Will arrange the sealing test in our HC Lab. this Friday. [Fii 0714] We don't have enough DVT3 sample on hand. We plan to conduct the sealing test when received DVT3 sample [Fii 0708] The microphone sealing test is expected to be tested on 7/16 [Fii 0707] Have received the T1 housing on 7/7 [Fii 0628] Have received extra 2 new silicon rubber on 6/25. [Fii 0624] 1. The T1 sample will be ready by 6/26? 2. Have received the sealing test report from SH. The test result looks good. Fii will arrange the test when received T1 housing. [Fii 0621] ALT will provide 3 full set T1 housing including MIC rubber pad and extra 2pcs rubber pad for Fii as a replacement if there is any problem. [Fii 0616] The T1 housing can be delivered from Inkel by 6/24. [Fii 0615] Fii will book the internal chamber and start the sealing test with T1 housing & new MIC rubber when received it next week. [Fii 0610] Another vendor "Everything" has sent out the samples on 6/8. The tracking number is 773934722045 (DHL) [Fii 0609]There are two supplier will provide the adhesive tape sample. One of the vendor "MeiGaoMei" has provided and sent 40pcs sample to ALT SH on 6/7. Please check the mantis ID 1177 in details. [Fii 0531] Need ALT to confirm the ETD date of new rubber samples. Fii will ask vendor to prepare the adhesive tape samples *50pcs and deliver to ALT directly. Will confirm the ETD date to ALT when received update from vendor. [Fii 0524] Have received sealing report on mantis from SH. Will reply SH when Fii complete the internal review with the report. [ALT 0514] ALT will test and debugging next week. [ALT 0505] ALT will check with INKEL to book the lab for testing in WK 5/10. The schedule TBC [Fii 0430] ALT provides new sponge MIC silicon and 1.1t silicon MIC rubber with O-ring sample, which the test result is poor than previous setup (old sponge MIC silicon plus 0.5t silicon MIC rubber). Have provided test report to ALT on 4/29. Need ALT to verify the new silicon simultaneously in Korea Lab. and provide us with test results for comparison. [Fii 0428] Arrange sealing test at HC acoustic chamber on 4/29 [Fii 0420] ALT SH has shipped 3 sets of new rubber pad to Fii by 4/19. DHL tracking: 9167971131 [Fii 0413] According to SH, the sponge silicon mic can ship to TW office (1.1t, housing side with O-ring, PCB side is plat.). Can ALT provide us 3pcs samples for testing? Please inform us when ALT can ship out the samples. [Fii 0409] 1. Need ALT to check if possible to provide the sample of silicon rubber within 4/9.
HW | AMP board verification test done before DVT3 gerber out | Fii/ALT | close | 2021-04-06 | [Fii]The verification before gerber out is necessary [ALT] We will provide AMP b'd gerber data by 4/6. [Fii 0317] Remind again the verifications mentioned in the email must be done before 4/6. The gerber must be provided on 4/5 morning. We have internal process for gerber out. [Fii 0325] Will proceed if ALT confirms the risk.
ME | T0 samples*2 for ME in China and factory ME in VN with assembly SOP | ALT | Close | 4/7=>4/23=>4/30 | [Fii 0531] The FFC/PCB contamination issue is own by factory ME engineer.. Since the ME engineer is located in Guang Chau factory now, they can only response it after the factory re-open. I will udpate the schedule to you when the Guang Chau factory reopen. [Fii 0520] Fii have provided the 8D of missing part and NG Label issue to ALT on 5/19. The PCB/FFC contamination issue will be provided by 5/21 [Fii 0514] Fii will provide the final report by 5/18 [ALT 0511] SH provided DVT2 housing review result, Fii to check reason of missing screw and gasp. [Fii 0507] ME & Factory receive sample on 5/7. [ALT 0430] Housing samples are shipping out with speaker samples on 4/30=>delayed and need ALT to check the shipping date again [Fii 0428] Where are the samples for ME review? Received the SOP and Fii ME is reviewing. [ALT 0423] Will check with INKEL for the SOP schedule. [Fii 0423] INKEL needs to provide the SOP ASAP. The date 4/30 is not acceptable. Plz check again if possible to provide no later than 4/27 to keep the schedule. [Fii 0420] Need extra 2 sets of samples to do the thermal test. Need to be as much assembled as possible. [ALT 0326] Likely to be 4/23 or 1 week before. Will check again. Also will check with Inkel or on site support [Fii 0326] Plz provide as early as possible. This will impact the production going smoothly. Also need Inkel on-site support. [Fii 0325] Plz help check the delivery date -ME RD in China Recipient: Jim CHEN Cell: 18376747022 Address: Foxconn Technology Park, No.51, Tongle Road, Jiangnan District, Nanning City, Guangxi Province, China. -ME in VN factory Recipient: Nguyen Thi Thu Thuy Mobile: +84 0912872792 Company : FUNING PRECISION COMPONENT CO., LTD. Address : Lot B, Que Vo Industrial Zone, Nam Son Ward, Bac Ninh City, Bac Ninh Province, Vietnam [ALT 0319] Will request Inkel to provide T0 sample and need Fii to provide the recipient info. [ALT 0318] We asked INKEL about it. But currently they provide T0 sample when they [Fii 0317] With Inkel provided SOP we need to 1. review with real housing and try assembling then evaluate assembly issues 2. transform into our SOP before DVT3. We need to reduce the time to do the trouble shooting when the production starts.
HW | Need power dissipation of all key components in AMP board for thermal simulation | ALT | close | 2021-03-16
HW | IQC for THD & FR of DREAMUS new speaker Fii Q team will on-site check the testing result. Need the updated spec to audit. | ALT | Close | 4/22=>4/29=>5/31 | [ALT 0601] Lonnie will update at Mantis on 6/1. [ALT0514] Next week ALT will provide test item of FR. [ALT0512] Need ALT/Dreamus to provide the OQC test items/SPEC. of the FR [ALT 0511] DREAMUS will test THD & FR full procedure based on Fii's requirement [Fii 0504] ALT Philip feedback Fii could check the defect rate in terms of FR and if the rate is too high, ALT will push DREAMUS to add the FR in production. Currently will do the OQC first. (review the defect rate after DVT3) [Fii 0430] If Dreamus only does FR in OQC and not during production, once Fii discovers FR test fail and does the the SWAP analysis, the rework cost will be transferred to Dreamus. (send email to ALT) [Fii 0428] When the difference report will be provided? Need ALT to push DREAMUS to add the FR test in production and OQC report. [ALT 0423] DVT3 speakers are not final. Performance related testing items for speaker could be waived. Will check the updated schedule with Dreamus on 4/23. Will provide the difference report for Fii to evaluate the impact on the following testing and MP. [Fii 0416] Received the proposal from Dreamus and will check internally and reply by 4/20. [Fii 0406] Plz check the testing items of THD and FR. Besides the speaker schedule needs pull-in. [ALT_0402] ALT sent e-mail that OQC schedule and test items on 4/2. [ALT 0401] Will check with Dreamus if THD&FR are tested. [Fii 0401] Before Dreamus ship out on 4/23, Fii IQC must be done in Dreamus factory. [Fii 0330] Because Dreamus cannot provide the testing equipment to Fii, if any suspect of speaker unit issue, Fii will need to return to Dreamus for analysis.=>[ALT 0409] well noted. [ALT 0318] We will check it when Dreamus start to produce Speaker. [Fii] Dreamus cannot provide the testing equipment and Fii will send the Q team to Dreamus factory to check the testing result before shipment.
HW | What would be the new spec for the soundbar on THD and FR as B&O requested? | ALT | close | 2021-04-12 | [ALT] We will check it to B&O [ALT 0318] B&O didn't have any requirement about THD and FR. They listen sound from speaker and evaluate. They focus on SNR(> 95dB) and Noise level(< 200uV). [ALT 0319] System test spec remains the same as RFP specifies.
ME | DVT3 housing ETA factory | ALT | Close | 4/24=>5/4=>5/7 | [Fii 0504] The customs issue needs to be resolved ASAP or Fii customs department will not agree to take in the shipment for DVT3. [Fii 0428] further delayed to 5/7 and the production schedule provided based on the date. [Fii 0416] The schedule was delayed to 5/4. plz continue to pull in to 4/29. Fii will check the production plan starting from 5/4. [ALT 0401] Still checking with Inkel if ETA factory 4/23. [ALT 0319] Will request Inkel to provide the housings as specified and is aware any delay will cause the production start date delay. [ALT 0318] We asked to provide T0 housing by 4/24 at your factory. But they don't have enough time, so they are discussing with their factory in china. [Fii 0317] We need the materials ready no later than 4/24. Besides, is the shipment from China again? If so how do we start SMT on 4/26 considering the delivery period from DVT1? [ALT] We asked to INKEL, but they will finish tooling by 4/23. So they need a week more. [Fii] Plz confirm the sample qty for DVT3
HW | ECAP lifetime | Fii | close | 2021-05-20 | [Fii]Will verify with the final design [Fii 0415] DVT3 applies ALT provided ECAP, need ALT help check if KC certification will be impacted if the ECAP is changed for MP. [ALT 0416] Confirmed no need to do EMC/ KC for change of ECAP. [Fii 0419] The substitute for ECAP from Fii QVL will not be able to make it to MP. Plz check if possible to go buy and sell for this part [Fii 0423] Fiki will check if any agent could buy the part. If not, will need ALT to help buy and parts for first couple shipment of MP. Will update the progress by 4/26 to ALT first. [Fii 0428] The vendor is surveying how to trade with Fii for MP demand as SAMYOUNG rejected to trade with Fii AVL agent. requested SAMYOUNG to reply by 4/30 [Fii 0430] Will check with factory if the stock is enough to support pre-MP 100pcs.
HW | A113X OTA architecture |  | close |  | [ALT 0317] Design both option 1 and option 2. But option 2 no need to do SMT, just reserve on layout. If needed after, ALT will rework. Fii no need to prepare for the materials.
HW | EMI pre-test and debugging | Fii | close | 2021-04-01 | [Fii 0325] 1. P-two make the new FFC cable and estimated ETD on 3/26. 2. Book 3/30~4/1 3rd party Lab. and debugging [Fii 0326] Target to complete by 4/1 but still need to check the lab time slot [Fii 0329] The new FFC cable ETA is 3/30. Have booked the 3rd party Lab. on 4/1.
HW | DVT heatspreader sample thermal test and improvement | Fii | close | 2021-04-23 | [Fii 0325] Current test result is bottom case 52.8degC @ 25degC ambient (spec.=50degC) 1. Make the new heat spreader top/bottom of AMP board, and estimated ETD on 3/28 2. Make the new heat spreader bottom of main board, and ETD is to be confirmed with vendor NWE [Fii 0329] The new bottom heat spreader is estimated complete and shipped by 4/15. Expect to complete the test by 4/23. [Fii 0419] The new bottom heat spreader was shipped by 4/17, and ETA on 4/23. Need rebook the schedule of HCQA thermal chamber. [Fii 0428] The test result of top and bottom surface are passed @ 25degC & 50degC ambient. (48.6degC & 37.9degC @ 25degC ambient and 70.5degC & 61degC @ 50degC ambient)
HW | Acoustic testing equipment may need to modify due to new speaker location | Fii | Close | 2021-10-09 | [Fii 0421] NI license had updated to mantis. Chamber-1: PC name: L09K18FT2002, ID: LWKL-YNM9-43MR-RPLG Chamber-2: PC name: L09K18FT2--1, ID: DSQ8-G8PY-26F6-H6KV [Fii 0414] VN factory is working on production now. The new NI lisence will be activated in this week. [Fii 0407] NI lisence has updated to mantis. [Fii 0331] NI lisence will be provided by mid. of April [Fii 0324] Test SW and Source code had updated to mantis. NI lisence will update at end of March. [Fii 0317] Before end of March will update the NI lisence. Test SW and source code will be provided on 3/18 [Fii 0310]: Serial number is under investigation through quotation. [Fii 0303]: Chamber and serial number are provided. There are remain two questions need to be confirmed by supplier 1. The 1st chamber back ground noise is similar with 2nd chambe but only measure to 10KHz. 2. One serial number for 2 chambers. [Fii 0224] Factory still collect data, #2 chamber test report is applying. When report is ready, will update to mantis 0911 soon. [Fii 0217]: Update equipment list on mantis 911 Still need some time to collect equipment list and weight from vendor. and require chamber isolated test report from vendor. [Fii 0210]: MFG will provide the data by end of this week. [Fii 0126]: MFG still not ready, will push factory side to provide the data asap. [Fii 0120]: MFG still need some time to collect the data. And will be able to update the data to ALT by next week. [Fii 0113]: No further update for woofer balance test. Wait for next mass production build to collect more data for review. [Fii 0106]: The woofer balance left/right test item had been verified well after changed 2 seconds wav file. The relative data had updated to mantis 911. [Fii1230]: FATP had finished 100pcs test, but had woofer_balance_left and right issue. The test was not stable. The wav file will be changed from 1 second to 2 seconds of 400Hz to verify if ok or not. Test data will update when received. [Fii 1223]: No further update. [Fii 1216] Have changed the FR spec. of woofer from 1KHz to 400Hz in production line. Due to housing shortage, no unit test in FT2. When collected 100 units test data, we will update to mantis 911. [Fii 1209] Woofer speaker left to right ratio(0.7, 1.4) test item fail rate: 6.36% ALT suggests to change frequency from 1KHz to 400Hz and not to change original spec. Fii suggests ALT to re-defined Dreamus OQC more tight spec for better assemble to reduce fail rate. Fii will tracking new freqency for woofer speaker balance test item. Have update our comment on mantis 911. [Fii 1202] 1. Cancel verify reference microphone receiving SPL too low issue of 8KHz FR test. Due to MP build, FATP cannot do any verify with golden sample. Our action is to change 8KHz SPL spec from (65,95)dB to (54, 90)dB which suggested by FATP. Fail rate: 0%, 0 pcs fail/943 pcs on 11/30. 2. Air leakage: We still keep original spec of air leakage due to the spec can identify little gap and non bushing issue. The spec is (-110, -67)dB. Fail rate:1.06%, 10 pcs fail/943 pcs on 11/30. [Fii 1125] 1. The new test criteria and conditions, which ALT requested has been implement in FT2. Will ask TE to provide the test result of last build asap. 2. 8KHz FR SPL too low issue: Due to FR test has lower SPL, we consider to swap ALT volume table into factory test image. Swap ALT volume table to Factory test image and retest again on FT2, found the reference microphone seemed limited at 81dBSPL. But the THD value is higher than before. We need to calibrate the reference microphone and may need to change position for better receive speaker SPL value. Air leakage: Not allow to change new spec yet. Still keep orignal spec for better quality. Have update our comment on mantis 911. [Fii 1118] We have update the FA status for pre-MP and MP build. Found most of the fail units are related to assembly issue. Top issue is 8K FR test: seem unit volume table is different with ALT volume table. Will do verify to improve average SPL value to middle of LSL and USL. Second/Third issue are air leakage. The spec is good to screen out little gap and assemly issue. Will keep the same spec. Report is updated to mantis 911. [Fii 1104] Have collected test data with 200pcs samples in 2K MP and provided it on mantisID 0911. We will set the pass criteria to "-78 ~ -120dB". Need ALT to review the test data and let us know if you would like to adjust the criteria.
HW | ESD risk from the vent hole design for DVT3 housing. | Fii | Close | 2021-05-10 | [ALT 0401] If any ESD issues, will seal the hole in T1 housings. The detailed plan will be discussed later. [Fii] Suggest ALT to seal the venting hole to avoid ESD issue
HW | EMC test with new AMP board, new speaker sets, old housings | Fii | Close | 2021-07-30 | [Fii 0805] Need ALT to confirm the cable twisted solution of left speaker, and also need DREAMUS to pre-twisted the cable of speaker before shipped material to Fii [Fii 0804] There is another team in Fii use the twist cable with speaker and the incoming material has pre-twisted and coverred with sponge in vendor's side [Fii 0802] According to the final test report of ALT, the left speaker cable needs to be twisted 8 times to solve the 159M EMI noise. For this solution, we need the DREAMUS to twist the speaker cable before the material is delivered to Fii to ensure the stable quality of the cable during the production process. [Fii 0726] 1. Have upload the test result on last Thursday to ALT reference. 2. We found that there is an additional gasket needs to be added under on main board (under J814 FFC connector) based on ALT's report. [Fii 0722] 1. We can get passed result for the original sample 2. DVT3 sample + Fii solution + add bead on AMP output, the result is fail. 3. Need to confirm the test condition in ALT side. Fii is using a special version of F/W that can be use ADB command line to execute mode1 & mode2 [Fii 0721] 1. Will verify DVT3 samples in 3M(966) chamber of 3rd party Lab. tomorrow 2. Check with vendor and other teams in Fii to see if there is any 120ohm 25% 100MHz/5A/0.02ohm 0805 bead can be used. [Fii 0719] 1. Have provided the SW image to ALT testing 2. The 10M chamber is owned by Sporton, which is the parent company of ICC. But due to COVID-19, Sporton prohibits their customers from entering their company to work with them. and only supported for projects kicked-off in their company. 3. So, we will prepare two samples for testing this week, one is using Lonnie's solution without ferrite core and another one is prepare golden sample by using our solution. [Fii 0715] 1. According to Lonnie's update, ALT verify the EMI based on Fii's solution but found three frequency point 171M, 221M & 392M are over the limit. However, compare our test result with ALT, we can find 221M & 392M, but our noise level is much lower than ALT. In addtion, we didn't see 171M in our tes result. Therefore, we believe that the main difference may come from 1. different FFC cable routing and management. 2. The difference in PCBA board. 2. Fii have provided the detailed cable routing drawing to Lonnie reference. (mantis ID 928) 3. Fii will arrange the test again to get the pass result in 3rd party Lab. next week. [Fii 0714] 1. Have received the test result and comment from Lonnie this morning. We will check and get back to ALT today asap. [Fii 0712] 1. Have provided the EMI test data of last Thursday for ALT Lonnie reference. 2. Will prepare a summary of EMI debugging points for ALT Lonnie today. [Fii 0708] 1. The test result of proposal 2 is fail. The 141/147MHz EMI test reuslt will be over 7dB (peak) & 5dB (QP) in harizontal 2. Add ferrite core on left & right speaker cable can redue 141MHz around 10dB 3. The gasket under the HDMI is required because it helps to reduce 196MHz EMI noise around 6dB to pass the criteria [Fii 0707] 1. The proposal 1 is not help to the 141MHz EMI. We change the capacitance from 100nF to 1uF, but the result is similar. 2. The proposal 2 is not tested yet since we only have one DVT3 AMP board on hand yesterday. Today, we received another DVT3 AMP board from vendor. So we will rework proposal 2 on it and will verify it in 3rd party Lab. tomorrow. 3. Our EMC engineer found that adding ferrite core on L/R speaker cable can reduce EMI noise of 141M around 7-8 dB. We will verify it in 3rd Lab. tomorrow as well [Fii 0705] 1. Have asked vendor to send the ferrite core samples to ALT on 7/2 2. Fii will continue to debug in internal chamber on 7/6 [Fii 0701] 1. Add 120pF at AMP output circuit but 141M is exceeded 0.5dB. 2. We try to remove ferrite core of the AMP FFC cable, but 196MHz appeared. Then we add a gasket below the USB connector, the 196MhZ can be fixed. 3. The overall EMI is good except 141MHz, which is exceeds 0.5dB. We need focus on AMP board debugging and need ALT to provide us with suggestion [Fii 0630] 1. The 141M noise is come from AMP board speaker traces. Fii will place small capacitance 120p on the D201 ~ D204 & D301~304 and verify it again in 3rd party lab. tomorrow to see how many margin we have. 2. If we can place small cap. in front of inductors, we can get more 3dB to fix 141MHz EMI issue. 3 Need ALT to look into this issue to see if there is anyway to fix this EMI issue. [Fii 0628] 1. Fii found another noise from speaker, which the frequency band is at around 141MHz. Will continue to debug to see if the noise strength can be reduced. The goal is to complete it by this Thursday. 2. The hight of solid ferite we needed is over 4mm, which can not be fixed between top heatspreader of AMP & main board. We are evaluating the different routing method of MIC FFC cable, but need to verify EMI again this week to see if the result is OK or not. [Fii 0624] The gaskets can be removed but the test result can only pass marginally (under criteria around 0.5dB) [Fii 0623] 1. EMC engineer is debugging in Fii internal chamber today to see if the gaskets and solid ferrite on the FFC cable of AMP board can be removed. And will verify EMI result again in 3rd party Lab. tomorrow. 2. ME RD is evaluating the position and the assembly method of solid ferrites on the MIC board FFC cable. [Fii 0621] 1. The EMI horizontal and vertical can be passed the critera by adding rectangular solid ferrites at MIC and AMP FFC cable 2. Need to add two on MIC FFC cable (one must near main board and the another one must to close to MIC board) and one on AMP FFC cable (clamped at the middle position of cable) 3. Fii will continue to debug on this Wednesday and Thursday to see if the gaskets and the solid ferrites on AMP FFC cable be removed. [Fii 0618] Fii will summarized the EMI status & test result on mantis by 6/18 [Fii 0616] Under debugging~ [Fii 0615] MIC FFC cable routing between main board and SOC top heat spreader. EMI: (H) 221M: 6.27dB (QP), (V) 73.6M: 0.11dB (QP), 368.5M: 0.59 dB (QP). Fii will debug in the internal chamber on 6/15 & 6/16 [Fii 0610] Have updated the RS report to mantis. Will provide the SW version for ALT reference today. [Fii 0609] RS test is passed. Will update the test rpeort on mantis once we received report from 3rd party Lab. [Fii 0608] RS can be conducted this afternoon. Fii EMC engineer will book the internal chamber for debugging in parallel but currently, the chamber are full occupied untill 6/21. Will coordinate with other project for the available time slot. [Fii 0601] CS is passed on 06/01. [Fii 0531] Have provide the EMI pre-test raw data on mantis this morning. The vertical is passed but there still have two noise 134MHz & 196MHz over the spec 0.05dB & 1dB in QP. It needs to add two gaskets between main board & bottom heatspreader to fix the EMI of 196MHz & 418MHz, and the location is approximately below the USB & HDMI connectors. Will provide detailed gasket point to Lonnie reference today. [Fii 0524] Confirmed with compliance team that the RS/CS/RE test will continue to test even the Engineer is WFH. But the 3rd party Lab. still have no spare time for RS/CS test until 5/24. [ALT 0517] Have asked VN factory to send 4 sets of PCBA to TuCheng office for RD checking first. The PCBA is estimated to arrived TuCheng by today. We plan to assemble one set of DVT3 sample (DVT3 AMP board+ DVT3 main board + new housing & speakers) for RS/CS debugging this week. [ALT 0514] target to get EMC result by 5/27 before KC cert (start week 5/24). [Fii 0513] The RS/CS are failed for MIC input. We think it's related to the software. We will update the SW of DUT and re-test again in 3rd party Lab. [Fii 0506] The RE test report will be provided on 5/7. RS/CS will be arranged after and the time slot needs to check with lab. [Fii 0504] Arrange RE/RS/CS test on 5/6 [Fii 0426] Have provided the EMI test result to ALT Lonnie reference on 4/26. We found some noise at around 418MHz & 450MHz. We will arrange next debugging when the final FFC cable and the new speakers arrvied at our office. 1. DVT1 sample (DVT2 main board + DVT1 sub-board) + new AMP board + woofer speakers/mid range speakers + enhanced FFC cable [Fii 0416] If the SW for all functions ready by 4/21 then the EMC will start on 4/22. Also the NRE PO for EMC test should be provided ASAP. [Fii 0415] If ALT can provide the complete S/W by 4/16, the function of new AMP board is expected to be verified completed by 4/23. Then Fii wiFll book the 3rd party chamber on week 4/26 ~ 4/30 for EMC testing. [Fii 0409] Need the speaker ETA TW 4/23 for assembly with new AMP board in the old housing.
HW | LED chip color shift issue | Fii | close | 2021-08-27 | [Fii 0830] The report will be uploaded to mantis by today. [Fii 0826] The reliability test for both short team and long term solution are finished and get pass result. The report can be provided by 8/27. [Fii 0825] 1. The reliability test of both short term and long term solution can be finished by today. And QA can provide the report on this Friday (8/27) [Fii 0811] 1. The MTBF demonstration test and thermal shock test are ongoing. No any problems found so far. [Fii 0805] Long term solution LED test status 1. Continuation of temperature cycle is passed 2. High temperature & Humidity Test (OP) & MTBF demonstration are on-going [Fii 0804] The reliability test of long term solution is ongoing and no any further issue so far. [Fii 0729] 1. For the MTBF of short term solution, we will continue to test for 5years MTBF, and the report will be updated by end of Aug. 2. Have updated the reliability test schedule of long term LED solution on mantis ID 1129. The test can be completed by 8/25. [Fii 0728] 1. Have provided the reliability report of short term solution on mantis ID 1129 [Fii 0722] There is no any failure LED found after MTBF demonstration test. Will ask our QA to provide the report by 7/23 [Fii 0719] Thermal shock of short term solution is completed and passed. [Fii 0715] Eagle Long Sample send to TW TRK# 774229004045 , ETD 7/14 [Fii 0714] short term LED reliability test status : Continuation of temperature cycle -> done High Temperature & Humidity Test (Op) -> done Thermal Shock -> due date : --> 7/18 MTBF Demonstration -> due date : 7/22 [Fii 0708] Have provided the production distribution test report on mantis ID 1129 for ALT reference [Fii 0708] LED sample ETA 7/4 -> 7/9 (Vietnam) c. LED sample ETA 7/4 -> 7/9 (Vietnam) d. 7/10~7/15 Eagle sample bulit for Long term solution LED reliability test . e. 7/16~7/20 send back to Taiwan. (Eagle ,Long term solution LED sample). f. 7/21~8/15 Long term solution LED reliability test. g. 8/16 : Provide "Eagle Long term solution" reliability test report to ALT. [Fii 0630] Provide LED verder Long term solution LED 1000hr reliability test report on mantis. [Fii 0624] Fii will provide RD measurement report of long term solution to ALT by 6/28 [Fii 0608->0627] Eagle Long term solution schedule : a. Long term solution LED reliability test 1000hr completed on 6/26. b. Provide LED sample for Eagle bulit on 6/30 ( ETD china). [Fii 0623] 1. The LED supplier recommends using long term LEDs immediately after the parts have been 1000hr LED Reliability test. => Please ALT can agree to start using long term LEDs in July. 2. Have updated the reliablity test items of short & long term solution to ALT review on mantis 1129 [Fii 0617] 1. PM Dennis has updated the test schedule of short term solution on mantis 1129. Also will update the test items on mantis on 6/18 2. The LED compensation report will be provided next week. [Fii 0616] The 20pcs short term solution samples will be sent out from VN today today. PM Dennis will update the schedule and test items on mantis for ALT review. [Fii 0609] already uploaded schedule and SN to mantis [Fii 0608] a.Long term solution schedule : 1. Long term solution LED reliability test 1000hr completed on 6/26. 2. Provde LED sample for Eagle bulit on 6/30. 3. 7/1~7/5 Eagle sample bulit for Long term solution LED reliability test . 4. 7/6~7/10 send back to Taiwan. (Eagle ,Long term solution LED sample. 5. 7/10~7/30 Long term solution LED reliability test. 6. 8/3 : Provde reliability test to ALT. b. SWAN Pre-MP 1K : need to risk buy long term solution LED. [Fii 0524] PM Dennis will work with MFG PM and Everlight to arrange the reliability test of short term and long term solution for Eagle and SWAN project, and provide the udpated schedule by 5/27 [Fii 0520] Have provided 8D report to ALT review on 5/18 [Fii 0513] Short term solution is implemented, sent 10pcs defect to everlight for long term solution verification and will have result by 5/20. [Fii 0507] Recieved Paralight LED sample and test on Eagle DUT for color test. The color is blue and brightness than Everlight. Will request Paralight to modify the LED color issue if CIE can shift to white area. [Fii 0428] There is one vendor will help to provide 2nd LED, Paralight has received our LED samples and will provide one similar LED sample next week(1st wk of May). This LED sample is non-Zenor LED. Will need verify the function first (color/brightness/electrical characteristic) when received the LED sample from Paralight. [Fii 0423] The verification of validity of solutions will be done within WK 4/26. The proposal to handle the defects return will need to discuss with vendor and feedback within the same week. [Fii 0419] Fii will also survey the alternative part for LED. Will provide the update information on 4/23=> by 4/30 [Fii 0413] The vendor proposed the short term solution which should be able to keep the defects from flowing out to Fii and will verify by 4/23. [Fii 0412] Everlight will update the FA with short term solution and the DOE for reproducibility. The final solution schedule will also be updated for fast introduction.
HW | Power consumption measurement w/ new AMP board | Fii | Close | 2021-05-07 | [Fii 0504] Measure power consumption of active standby mode w/ new AMP board [Fii 0505] Fii have provided the test report on 5/5, the power consumption of active mode is 8.9W
HW | USB detection | Fii | Close | 2021-05-12 | [Fii 0524] SQA test another sample and got fail result in 96times test. Fii will continue to complete the detection test and provide the udpated result to ALT asap. [Fii 0520] 1. VN Factory have finished the rework on 5/16. 2. Fii have complete one sample test, change resister value to 0x0a + pull-down resistor, the failure rate is 0/200. 3. Fii SQA will continues to test USB detection with another 2PCBAs 4. Need ALT to provide one USB sticker to Synaptics for USB detection issue debugging. [Fii 0517] 1. Condition: remove USB power SW + external power supply(5V) to VBUS + over 120uF (22uF *6). Test result: 3/10 fail. 2. Have asked VN factory to rework resistor to pull-down of DVT3 PCBA first. 3. Will verify the register value of 0xF7A2503C[5:1] applied to 0x0A + pull down resistor today. [Fii 0514] 1. Need to be finalize before DVT3 assembly start 2. Rework pull down + over 120uF, 3/100 fail. [Fii 0512] Fii will do the test combination as below then we can have further discuss with ALT about the test result 1. Rework pull down + over 120uF 2. Rework pull down resistor only 3. Detection test: 100time, DUT 3EA. [Fii 0507] The test will be started from 5/11. Will udpate the test result to ALT on 5/12 [Fii 0505] Need book the SI test with HC lab. Planned to do it on 5/7
HW | Power consumption required specification | ALT | Close | 2021-06-03 | [Fii 0615] Fu-Chiang has upload the test report of 1.189W passive standby report on mantis. [Fii 0610] Have updated the test report on mantis based on the 1.5W test result. [Fii 0609] Synaptics confirmed that the command "test_disp hdmipwr off" is to turn on/off HDMI TMDS output. We also turned-off the enable pin of power switch, and the pssive standby power can be reduced to 1.1893W. Passive standby = 1.1893W Active standby = 5.9108W [Fii 0608] The current passive standby is 1.97W. To enter "test_disp hdmipwr off" command manually, the passive standby power can be reduced to 1.5W. Checking with Synaptics about this command line and will verify again by integrated image. [Fii 0601] ALT to discuss the details of modification based on passive standby solution, and both parites to discuss if one more build is needed. [Fii 0531] Have provided the active standby test result on mantis on 5/27. The AC power consumption is around 6.3W after turned-off AMP ICs. Will continue to test passive standby on 6/1. [Fii 0524] Have received the active and passive standby requirement from Lonnie but it seem that there has additional HW changes with the enable pin of DCDC converter (24V/5V), and the extra build should be required. Need further discussion with ALT about the PCB preparation and schedule impact. [Fii 0514] ALT is required to confirm the exact requirement for the active and passive standby power consumption
HW | I2S timing issue | Fii | Close | 2021-06-11 | [Fii 0616] The I2S timing of A113 are passed the criteria based on the image provided by ALT Lonnie "aml_upgrade_package.img" [Fii 0615] ALT has provided the image for test. Fii will verify the result today [Fii 0608] The data setup time is passed after invert the BCLK, but the WCK setup time turns into fail (Result=0.065ns, AMP IC spec.=20ns). Need ALT and AML look into this issue
HW | USB detection issue | Fii | Close | 2021-06-16 | [Fii 0623] Have provided the waiver document on mantis 919 on 6/22 [Fii 0617] Fii will prepare the waiver doc to ALT review by 6/21. [Fii 0616] Synaptics only can confirm that the HW design is no problem, but can't provide comment about S/W portion. Jiamin said that he will ask Kail to explain this issue with ALT directly. [Fii 0615] Synaptics PM Jiamin will feedback the comment about the USB detection issue by 6/16
HW | Speaker output volume | Fii | Close | 2021-09-10 | [Fii 0915] The test is completed, and the report has been upload to mantis 1240 on 9/15 [Fii 0909] Need ALT to confirm the LKFS stream are SBS_AAC & SBS_AC3? Checked with River that ALT asked our SW team use these two stream to verify the max volume(32 level) of LKFS only. May I know the purpose of using LKFS stream to test each volume level of the speaker output? [Fii 0906] Will arrange the speaker volume test with QA team and provide the test result by 9/10. [Fii 0830] Need ALT to confirm with SKB whether the speaker power is OK [Fii 0826] 1. We have measured the speaker power again based on the image provided by ALT, which has enabled DRC and fine-tuned the gain. The test result is similar with ALT and have updated it on mantis ID 1240 on 8/25 2. Wait for ALT to confirm the speake power and volume to SKB [Fii 0825] We have tried to change to new PCBA and ensure that the SW version is the same as ALT. And we also use Audio precision to measure the output power but so far we still get the test result. We will try to connect the speaker directly with audio precision instead of resistor to see if the result can be improved. [Fii 0823] Will change another PCBA and measure the speaker power again to clarify this issue [Fii 0818] We have re-test the SPK power after apply set limit 30W@ woofer and 8W@ full range, but we found tbat the volume is set to 30 steps will reach the max power, and then when the volume is set to 31 & 32 setps, the power will reduced. [Fii 0812] The test was completed and have upload the test report on mantis ID 1240 on 8/12 [Fii 0811] Our QA can perform the speaker volume test tomorrow (8/12) [Fii 0809] Our QA will perform the speaker volumne test this Friday (8/13) [Fii 0804] The HDMI LKFS volume test is completed. Will arrange the speaker output volume test next week. [Fii 0726] Refer to mantis ID 1120 for the HDMI LKFS test result The gain tunning of VS550 is completed. Jerry is working with SQA team to verify all the test result (1 to 32 levels), and will update the result later. [Fii 0722] 1. Jerry will update the test result of HDMI & speaker volume tuning by our SQA before 2. According to Jerry, he just completed the gain tuning in VS550 to ensure the maximum speaker volume is the same as HDMI output [Fii 0715] Our SW engineer Jerry is checking whether he can adjust (reduce) the audio output GAIN in VS-550 to ensure that the speaker output volume(power) will not exceed the spec. in maximun volume step 32. I have raised this issue and involve our SW Jerry in the discussion on mantis ID 1240. [Fii 0714] According to our SW, the volume table for HDMI output is no problem now but the power for speaker output will over the spec. We will need further discussion with SW team to clarify if the volume table for speaker output can be fixed. [Fii 0712] The speaker output volume test will be started when SW team fix the volume table issue. [Fii 0628] Test MS11 should be able to complete in these 2 days, and then will arrange the HDMI output volume test. The speaker volume test will be arranged in next week. [Fii 0621] Recently, ALT asked Fii to perform speaker volume of HDMI output and Dolby MS11 test. So, the speaker output volume test will be conducted after those tests are completed. Will need to confirm the schedule with SQA and update it to ALT [Fii 0617] We can arrange one sample prevuously used for thermal test to SQA for speaker volume test (DVT2 main board + new AMP board). This test is handled by Jacky's team and SQA. Can ALT make this request to Jacky's team on mantis and let Fii to follow up? [Fii 0616] Will arrange the test when received DVT3 sample since the speaker design of DVT3 is different with DVT2. [Fii 0615] Will check with Jacky's team and SQA about their plan of speaker output volume testing
HW | Ferrite core winding method | Fii | Close | 2021-07-02 | [Fii 0701] Fii can prepare 8sets of ferrite cores to ALT. Vendor is checking with their RD internlly to see whether they can wrap sponge on ferrite core in their factory. Will confirm the sample ETD schedule to ALT once we get confirmation from vendor. [Fii 0630] Have provided the ferrite core winding proposal to ALT review. Need ALT confirm whether proposal 1 is OK to go?
ME | ALT need to add "TAPE 3M GTM720" in DVT3 assembly production. | ALT | Close | 2021-07-05 | [Fii 0707] Sample TRK# SF1125505130359 , ETA 7/9 [ALT 0702]Don’t wait TAPE 3M GTM720 sample delivery. 1st delivery of 36pcs, it can be skip. ALT will rework on it But, If arrived the tape before DVT3 production, please apply it. And the others DVT3 SWAN, please apply TAPE 3M GTM720. [ALT 0701]On 6/29, ALT need to add "TAPE 3M GTM720" in DVT3 assembly production. Supplier "TAPE 3M GTM720" sample ETD 7/2. The "TAPE 3M GTM720' samples are too late for DVT3 production to start on 7/5. Please advise whether to wait for samples to arrive in Vietnam before starting DVT3 production?
HW | DVT3 AMP board inductir is broken 100% | Fii | Close | 2021-07-30 | [Fii 0729] Vendor has replied that the broken will not affect its performance. We will continue to perform the reliability test. [Fii 0726] 1. Fii confirmed that there will be an inteference between inductor of DVT3 board and the screw of old heat spreader. The new heatspreader will has no such issue. 2. Fii will check with Inductor vendor to see if the broken of body will affect the performance. And will continues to arrange the reliability test if there is no any concern.
HW | Assembly issue for AMP FFC cable | Fii | close | 2021-07-30 | [Fii 0729] ME RD Jim has updated the assembly drawing for AMP FFC cable on mantis ID 1302
HW | The impact of the AMP board changes on reliablity testing | Fii | close | 2021-08-05 | [Fii 0728] The *7 additional reliablity test items must to be tested, and 3 DUT samples is required if AMP board layout modification is required
HW | Change RDT test setup | Fii | Close | 2021-08-20 | [Fii 0823] Have confirmed with Mr.Yoon that the RDT test will be changed to local 4K video playback and Iper 100Mbps. [Fii 0819] Dennis has sent email to SH on 20/July to ask for changing environment setup of RDT by using youtube 4K video as streaming content, but we found that youtube server ot streaming content may have ramdom problems, which will cause the OTT test to be interrupted during the RDT test. Therefore, our QA plan to use local 4K video playback and iperf 50Mbps instead.
HW | MIC delay issue | Fii | Close | 2021/8/2 ==> 8/4 | [Fii 0804] Have received the gerber file on 8/3 but there is a DFM issue raise by our VN factory. The bead FB201 need to move away from the screw pad. Have provided the information to Lonnie on mantis ID 1280. Need ALT to modify the layout and release new gerber asap. [Fii 0802] Need ALT to confirm the final solution for MIC delay issue by today. If the changes related to the AMP HW design, we need ALT to to confirm whether the solution has been tested without problem on current DVT3 AMP board to ensure the solution is workable without risk
HW | No LED & AUDIO issue | Fii | Close | 2021-08-05 | [Fii 0804] 1. The root cause is due to the incorrect FFC cable (w/o shielding outside the cable) used in DVT3 and the FFC cable is easy to be pierceed by connector, and cause the I2S_CLK short to ground.
HW | Additional IR test with latest DVT3 fabric | Fii | Close | 2021-09-09 | [Fii 0909] Have completed the IR test with BMM-BA02/BRM-BA03, the result are all pass with * DUT. Please check the test report on mantis 1097 [Fii 0908] We have BMM-BA02 & BRM-BA03 on hand. Will arrange the test today and provide the report by tomorrow [Fii 0906] Will verify again IR with 3-wave length for BMM-BA03 (Moven) & BRM-BA03 (Remote solution) [Fii 0902] Have upload the IR test report on mantis ID 1097. The IR receiving distance can meet SKB's requirement (exceed 17meters at the required angle)
HW | BQB certification | Fii | Close | 2021-09-10 | [Fii 0916] The BQB certification is completed. The declare ID is D053853. [Fii 0915] Fii have reviewed the draft RF & profile report provided by TUV Lab.and now is proceed with certificate process. [Fii 0913] After providing new APK, our box can send the close stream command when disconnect the Bluetooth. The TUV Lab. is preparing the report now, and need 3-4 working days to complete the certificate. [Fii 0909] We have provided a solution to TUV Lab. this afternoon amd will wait for their verification result. [Fii 0906] 1. During the A2DP test, TUV Lab. will play & stop the music, but the equipment can't get the close streaming command when the music is stopped. Currently, our sample can only send the suspend command. 2. Confirm with Realtek whether the current behavior is correct, and then see how to solve this issue [Fii 0902] 1. BT2.1+EDR & BLE RF-PHY test are done and passed 2. Profile test: Remind one item A2DP fail. S/W team is working with TUV for the debugging now, and estimated to resolve this issues by 9/3
HW | HDMI certification | Fii | close | 2021-09-08 | [Fii 0908] Have upload the HDMI 1.4b certificate and test report on mantis 1110 [Fii 0906] 1. Have received 1.4b certification on 9/4 [Fii 0902] 1. All of HDMI section (SI, protocol and CEC) are finish test. 2. 1.4b certification will be release on 9/3 first, and then release 2.1 certification on 9/8
HWQA | Climate reliability | Fii | Clsoe | 2021-09-17 | [Fii 0916] The final report has been upload on mantis ID 1104 [Fii 0909] The climate reliability test are completed and all the test items are passed. QA will release final test report on 9/13 [Fii 0906] 1. Have upload Climate test report on mantis 1104 and MTBF prediction report on mantis 1102 2. Cold Start, Hot Start, High Temperature and Humidity test (Storage & OP), Operational Temperature cycle test, Thermal Shock Test, Power on/off test with temperature tests are completed [Fii 0901] 1. 9/3 : Will provide the report for the items that we complete the report. 2. 9/14 : Will update the test report, including Thermal, EDVT, HALT, Acoustic Noise Test that we complete till 9/10. 3. The remaining item, MTBF (RDT), report schedule is under confirming.
HWQA | Mechanical reliability | Fii | Close | 2021-09-14 | [Fii 0915] The logo/printing/label abrasion test are passed based on 75% alcohol. Will update the report on mantin on 9/16 [Fii 0911] Fii HWQA will test again the logo/ printing abrasion test with 75% alcohol on 9/13, and if the testing is passed, then will continues to do the printing abrasion of label test. [Fii 0909] The Logo Printing Abrasion Test is fail. Please refer bug report on mantis 1108. As I know that the material of mechanical part should have been shipped to our VN factory. How do we deal with those M/E material? [Fii 0908] Havep uploaded the report on mantis 1108. The rest report will be provided by 9/14 [Fii 0906] 1. Have upload the report on mantis 1104 2. Salt Spray Test, Operational Random Vibration, Operation Shock Test are completed. [Fii 0901] 1. 9/3 : Will provide the report for the items that we complete the report to Mechanical. 2. 9/14 : Will update the test report that we complete till 9/10.
HWQA | Reliabilitt RDT test | Fii | Clsoe | 2021-09-10 | [Fii 0929] The drop test of the gift box has been completed and passed the criteria (we tested *2 DUT). The report can be provided by this Friday (10/1) [Fii 0923] The RDT test is completed without any problem. Have updated the report on mantis 1107 [Fii 0909] Have upgraded the FW of A113 for all the samples in QA Lab. And all the samples are now running well and the MTBF testing is expected to be completed on 9/17. [Fii 0908] Have updated the SW of A113 to version 0x10 with all the DUTs to solve noise issue. So far, there is no any issue found in QA team.
HW | Change the FFC cable length One of FFC relates to ferrite core breaking issue | ALT /Fii | Close | 2021-10-15 | [Fii 1104] Have received the test report from ALT on mantis ID 928 [Fii 1028] Waiting for EMI report. [ALT 1022] Agreed to introduce new FFC based on EMI test result. [Fii 1014] Need ALT to arrange the EMI test in Korea Lab. asap so that Fii can introduce it in MP prodcut to solve ferrite core interference issue. [Fii 1007] Have sent 10 sets of new FFC cable to ALT on 10/6. Please arrange the EMI testing in Korea Lab. and please let us know if you found any problems. [Fii 0929] The 10 set of new FFC cable samples will be ready b this Friday. Will try to deliver the sample to ALT next week. [Fii 0922] The EMI result of new FFC cable can pass the criteria (under 3dB). Please refer to the details in mantis 00928 [Fii 0916] The 10set of new FFC cable will be ready on end of Sept. [Fii 0915] Have received the ferrite core from ALT on 9/10. Will arrange the EMI test on 9/16. [Fii 0909] The ferrite core is still in custom clearance. The EMI test will be arranged next Thursday. [Fii 0908] We will arrange the EMI test tomorrow, .if we can receive the ferrite core before tomorrow noon, [Fii 0906] 1. The Vietnam factory requests to increase microphone (40mm) and button (50mm) FFC cable length to improve assembly. 2. Fii will verify the EMI again this Thursday to see if there is any impact 3. Fii will send 3sets of FFC cable to ALT for testing 4. Need ALT to provide at least 6pcs ferrite core samples for Fii testing
HW | Free fall drop test spec. | Fii | Close | 2021-09-15 | [Fii 0915] We would like to confirm that the following "No visual damage" criteria are only applies to product, but damage to the gift box is acceptable?
HW/ME | R-LED connector interference (Mantis#1362) | ALT /Fii | Close | 2021-10-13 | [Fii 1014] As discussed with Sophie, the layout change on R-side LED board is limited due to the layout rule. So, Fii prefer to rework the screw boss on top cover for 13K material. And we need INKEL/ALT to modify the R-side screw boss to solve this issue [Fii 1005] Our factory found out R-LED connector interference issue in DVT4 (1.1K pre-MP). Please refer to the document that we updated in Mantis. we suggest modifying the R-side screw boss to solve this problem.
ME | Ferrite core interference issue | Fii | Close | 2021-10-15 | [Fii 1021] Have Inkel provide new sponge for evaluation? [Fii 1014] 1. Have upload the FA report of ferrite core interference issue on mantis ID 1366 2. We suggest to paste a sponge(10*10*1mm) on the screw boss to avoid audible noise 3. Fii will suvey the new sponge components, but it will take us a long time on sample evaluation and internal approval. We found that we have existing sponge (484.00430.005) in SWAN that can be used. It is used on LED braket. So, is it possible that ALT to help provide some material for us as consign part as short term solution
HW | AMP board layout modification | ALT | Close | 2021-10-19 | [Fii 1014] 1. Because MPS MP2338GTL-Z material shortage issue, we need introduce Silergy SY8263AIC as 2nd source in AMP board. Need ALT to arrange the layout modification soon and provide the gerber file by 10/19. 2. Please check mantis ID 1357 in details
HW/ME | Datasheet for new L-CH/R-CH speaker cable | ALT | Close | 2021-11-01 | [Fii 1202] Need new manufacturer ticket of class 377 in Foxconn part number system to apply 353 FPN and PSC ticket. Also need material verification ticket. So that needs time to apply. [Fii 1118] The part number application is under processing and estimated to be completely by next Wednesday (11/24) [Fii 1109] Have received datasheet from SH. Will apply the FXN P/N and provide it to SH when it's effectively. [Fii 1104] ALT have updated on data sheet on Mantis, but it need to add some cable and ferrite core by early of next week [Fii 1028] ALT comment will use new L-CH/R-CH speaker cable (includes ferrite core, sponge) from 15.1K. Fii need the datasheet to apply Fii P/N in advance.
HW | Audio noise issue | Fii/ALT | Close | 2021-10-22 | [Fii 1202] Defect rate Audio noise sample NO.1, original design: 2/50, change 5R67 / 5R68 from 200ohm to 51ohm: 0/100 Audio noise sample NO.2, original design: 6/50, change 5R67 / 5R68 from 200ohm to 51ohm: 0/100 Need ALT to check EMI result before issue ECO [Fii 1125] Have received 2pcs fail units from factory. Will analyze the fail symptoms and feedback to ALT by next Tuesday (11/30) [Fii 1104] FII have provided test result on mantisID 1359. Defect rate is 7/20 Need to track the audio noise issue in 2K MP to see if there are any defect sample. [Fii 1028] 1. Have discussed with Amlogic TW and their FAE think it might be timing issue. 2. Since we rework the I2S to DVT3 version, and the issue is disappeared. In DVT3 structure, the I2S data will have some buffers in A113 but in pre-MP structure, it doesn't have any buffers. 3. We will try to increase or decrease the resistance of the resistor in series with BCLK to see if there is any change in the fail rate. 4. Wooshin has provided new AMP s/w (0x31) for our testing (mantis ID 1359). Can you confirm any chnages has been made for this new s/w? [Fii 1021] We did the following tests and found that when we rework the AMP board back to DVT3 version with DVT3 firmware, the audio noise will disapeare. Have upload below test result on mantisID 1359 1. Pre-MP main board+ DVT3 AMP board: test 30 times, defact rate 0/30 2. Pre-MP AMP board: R343/R344: 100ohm ->0ohm, R103/R104: 100ohm->33ohm, C105/C106: remove, => defact rate 9/30, there were 2 severe audio noise 3. Pre-MP AMP board: solution 2 + R107~R110: 100ohm -> 33ohm => defact rate 8/30, there were only a pop noise when the first screen appear (image 0.jpeg) 4. Pre-MP AMP board: separate A113X I2S in and I2S out + DVT3 A113X firmware (as DVT3 design) R343/R344: 100ohm, R103/R104: 100ohm, R107~R110: 100ohm (as Pre-MP BOM) => test 30 times, defact rate 0/30
HW | 2nd source introduction status | Fii/ALT | Close | 2021-12-03 | [Fii 1230] No further update. [Fii 1223] No further update. [Fii 1216] 1.Update DIODES 74LVC125AT14-13 with 5R67/5R68 51ohm test reportin mantis on 12/13. 2.EC capacitor L/T of Rubycon and Panasonic, purchase is under checking. [Fii 1209] Update DIODES 74LVC125AT14-13 test report on mantis on 12/9. We also add EC cap 2nd source comparision table on mantis 1357, Please review it. [Fii 1202] Will update the reliability test report and EMI report on mantis on 12/2 [Fii 1125] 1. Have provided test report on mantis and confirmed by ALT. 2. The reliability test of 3PEAK TPL740F25-5TR & TPL740F18-5TR will be finished by 11/29 3. We just received DIODES 74LVC125AT14-13 samples on 11/25 (replace NEXPERIA 74LVC125APW). Will verify it performance and provide the test report to ALT review next week. [Fii 1118] 1. Have provide the updated status on mantis 1357. Need ALT to review it and let us know if there is any questions. 2. Will provide some test report on mantis this Friday (11/19)
H/W | Designate parts | Fii/ALT | Close | 2021-12-01 | [Fii 1223] We need ALT help to provide one more designated part email for below component since our purchasing team desn't agree to use/introduce it. Our phrchasing team think that VISHAY doesn't have good support in terms of cost & L/T. No. Vendor Part Number (MPN) 1 VISHAY --> TSOP75338TT [Fii 1202] I've discussed with our Biz team and we agreed that those 5 designate parts Fii requested doesn't need to put in SOW, which means that Fii will take all liability for those 5 components. [Fii 1125] Will reply ALT after internal discussions with PM team our thoughts on designation of 5 components No Vendor Part Number (MPN) 1 Synaptics --> VS-550A1 2 Synaptics --> CX20810-11Z 3 SAMYOUNG --> CLZ35VC100MH10TP 4 ITE --> IT66318FN 5 KNOWLES --> SPM0687LR5H-1
H/W | FFC cable and connector defected sample | Fii | Open | 2021-12-24 | [1118] ALT will inform to Foxconn that they need additional samples 2~3 month before they need it. [1111] Foxconn expects that they can provide additional free sample on May. ALT will inform Foxconn when ALT may meet FFC cable material shortage for repair before next May. [1104] Foxconn cannot fix the date when FFC vendor can provide their new sample. First of all, ALT and Foxconn should decide how they handle idle materials. After that Foxconn can discuss with vendor about new sample delivery schedule. [1028] ALT asked to provide stack status both Foxconn warehouse and Vendor warehouse that already produced according to PO and Open PO. Foxconn feedback that it is same as last week discussion. ALT asked Foxconn to send an e-mail when vendor can provide new sample to us. [1021] BT is Foxconn warehouse in HK [1014] Foxconn's supplier can provide 4.2K FFC cable without cost. But supplier already have 6K original FFC cable in stock. Supplier can provide 4.2K FFC cable after the original FFC cable are out of stock. [1007] Foxconn will have meeting with related companies, include FFC Cable vendor and connector vendor next Tuesday. Foxconn may have some conclusion how they will handle this issue and new FFC cables(4.2K) next Wednesday. [Fii 1006] The 8D report has been provided on mantis 1417 on 10/6. [0930] ALT received 0.5K pcs new FFC cables. Foxconn can fix the date to deliver the rest of new FFC cables(4.2K) after discussion between Foxconn QA and supplier. Foxconn will share 8D report from supplier by today(9/30). [09/29] Schedule 0.5K 9/27 ETD, DHL 74 6664 5550 [09/23] Schedule 0.5K 9/27 ETD, 4.2K Schedule is not fixed yet. Foxconn will provide 8d report that Foxconn provide to supplier by 9/27. [0916] FFC Cable delivery schedule. 0.5K - 10/31(confirmed by Foxconn) 4.2K - Fix later(Foxconn will have meeting with supplier next week. Foxconn can fix the schedule after meeting.) [0901] Foxconn will confirm after meeting whether they can confirm the 0.5K delivery by 10/31 Foxconn didn't have discussion with supplier yet. They will have it next week. Foxconn will update its plan after meeting. [0826] Foxconn has some issues to provide 4.7K FFC cable. But ALT keeps aske to provide it. Foxconn will discuss internally and they will provide how many q'ty Foxconn can provide by next week. [ALT 819] Foxconn will discuss how many FFC cables Foxconn will provide to ALT and it will update by next week. ALT wants to know how many and when Foxconn can provide new FFC Cable to ALT. [ALT 812] Foxconn will update whether Foxconn can provide to ALT 4.7K new FFC for repair. It will not need to send 4.7K at once. 0.5K for each shipment is OK. [Fii 0811] 1. Will apply the EC when the engineering PN transfers to offical PN. We expected the EC will be complated by next Friday(8/19). [Fii 0804] 1. Fii biz team had confirm the cost. Fii RD will apply for EC for the new FFC cable and the new CM choke when getting approal from ALT for new CM choke. [Fii 0728] 1. The Fii biz team will confirm the cost before 7/3, then RD will issue the EC to introduce the new FFC cable. [Fii 0721] 1. Has provided control run report on mantis #0001417. Please kindly review it and feedback comments. [Fii 0714] 1. Production line will finish control run on 7/15. Once got control run report will provide to ALT for reviewing. [Fii 0707] 1. Got confirmed of HALT report on mantis from ALT. Supplier P-TWO has provided the new part number (183005-15110) to Fii and the price is under confirm internally. Fii MFG will control run new AMP FFC cable on next Monday (7/11). [Fii 0630] 1. Has upload revise version of HALT test report on mantis #0001417. Please kindly review it and approve it if no further questions. [Fii 0623] 1. Has upload the HALT test report on mantis # 0001417. Need ALT to review and approve it if there is no questions, and then Fii will inform vendor P-TWO to provide quotation and work with MFG PM to arrange control run schedule for new FFC cable. [Fii 0616] 1. Has upload the test report of "Press 1N on FFC connector top" on mantis #0001417. Please help to review it. 2. Has finished HALT test and result are pass. Will provide test by 6/21. [Fii 0609] 1. The test of "Press 1N on FFC connector top" finished, result pass. Will upload test report by 6/13. [Fii 0602] 1. The test of "Press 1N on FFC connector top" is currently going well, and the test can be finished on 6/7. Will provide test report by 6/10. [Fii 0526] 1. Update test schedule of " Press 1N on FFC connector top": 5/24~6/7, report 6/10. Because HWQA reply that weights are not enough. They can't test two DUT at the same time. So it needs another 5days for testing and the test schedule will be postponed to 6/7. 2. In addition, according to the Lonnie, we need to use FFC cable tested in step 1 for step2 test, then how can we check the FFC cable after step1 test since it will damage the FFC cable after tearing off the inner layer. 3. The test schedule of HALT test will be 6/13~6/14, report 6/17. [Fii 0519] 1. Test schedule of " Press 1N on FFC connector top": 5/24~5/31, report 6/2. 2. HALT test: The estimated test fee is around NTD 20,000, but our supplier only agreed to pay 50% of the test fee. Therefore, we will arrange for this test to be performed by an ineternal laboratory to solve the issue of paying for the test. The test is expected to begin in early July, but has yet to be confirmed. Will keep you posted once we received an update from the QA team. [Fii 0512] 1. Vendor P-TWO has shipped samples on 5/6, 55pcs to Fii VN factory, 15pcs to TW. RD has got samples on 5/12. 2. Will arrange Fii HWQA test "HALT test scenario 1: Press 1N on FFC connector top", will update test schedule to ALT soon. [Fii 0505] 1. Due to the COVID-19, the express is still closed until now. Therefore, vendor P-TWO has not got copper foil samples yet. So FFC cable samples schedule need to be confirmed with supplier. There is no firmed schedule from supplier yet. [Fii 0428] 1. Sample 5/5 ETD. [Fii 0421] 1. FFC cable samples schedule is still not confirmed yet. [Fii 0414] 1. Vendor P-TWO will provide new FFC cable samples to Fii, but sample schedule is not confirmed yet due to COVID-19 is getting worse in Shanghai China now, copper foil supplier can't deliver new copper foil samples to vendor P-TWO. Will update schedule to ALT once there is any update from supplier. [Fii 0407] 1. Vendor P-TWO reply that total thickness of current design with kapton mylar is 557um which over FFC connector specification (500+-50um). So vendor P-TWO suggest to decrease the thickness of "insulated layer+adhesive" ( 60um -> 37um) and "stiffner+ adhesive" (225um -> 205um), as show in the picture. Can ALT agree to this design change ? 2. Please see the detailed in mantis 1471 [Fii 0331] 1. Has provided English version of MXPI-310F test report and standard GBT30776-2014 on mantis 0001417:0009764. Vendor only can provide Chinese version of standard GBT30776-2014. Will provide revise version of datasheet later. [Fii 0324] 1. Kapton vendor reply that test standard (ASTM D3330) of tensile strength is uncorrect in MXPI-310F datasheet. Will update correct version of datasheet to us this week. [Fii 0324] 1. HWQA confirm that HC HWQA Lab. can test scenario 1 ((press 1N force on FFC top)) by surface coating abrasion machine. 2. Double confirm with KAPTON vendor, the denominator of 25mm (N/25mm) is to use a 25mm width KAPTON for the tensile force test, and the denominator of cm^2 (N/cm^2) is to use a 8mm diameter cylinder for the puncture force test. The new capton mylar (MXPI-310F) can indeed pass 90N/cm^2 test. Please review and confirm it. [Fii 0310] 1. Need ALT to confirm whether Fii can only test "Vibration step stress test" and "combined environment stress test" for HALT test. 2. Fii HC HWQA reply that HC HWQA Lab. may can do HALT test scenario 1 ((press 1N force on FFC top)) by surface coating abrasion machine. It need Fii HC HWQA further confirm about this. [Fii 0303] 1. Vendor P-TWO unwilling to pay HALT test fee by themself. The test fee may need to be shared by Fii and P-TWO. It need to further discuss with P-TWO after got the quotation. 2. We have discussed with Fii QA team and we think to only verify "Vibration step stress test" and "combined environment stress test" of HALT test should be enough? And also we only need to pay a lower price. Need ALT to confirm about this. 3. Vendor P-TWO and Fii factory can't test HALT test scenario 1 (press 1N force on FFC top) . Will conduct this test at Fii HC HWQA Lab. [Fii 0224] 1. Fii factory got the samples on 2/21. 2. Because temperarure chamber machine limit issue (70℃~-20℃), HALT cannot be test in Fii factory, and PQE can't go to VN local Lab. from Fii factory due to COVID-19. This test has to be conducted in Taiwan. We are discussing with vendor about this. 3. We plan to use non-p2p samples, which are scheduled to be built in mid. of March. [Fii 0217] 1. Vendor P-TWO has shipout samples on 2/16 via DHL 2. Provided HALT test requirement to Fii factory, and factory is under confirm test environment to see if they can perform the HALT in Vietnam. [Fii 0210] 1. Because manpower shortage after CNY, samples shipout will delay 1week, ETD 2/16. 2. The reliability test plan will be update on mantion on 2/11 3. Supplier can perform the HALT test in 3rd party Lab. but they don't have HALT test plan. Is there any suggestion from ALT about the test condition of HALT test for FFC cable?
H/W | NonP2P 2nd source verification | Fii | Close | 2021-01-05 | [Fii 0526] 1. Do ALT have comments for Motorcomm YT8531C test report ? 2. When can ALT provide the designate email to Fii? [Fii 0519] 1. Has upload Motorcomm YT8531C test report on mantis #0001357. 2. For designate part HL7593WL08, Tom already provide related info. to Lonnie on mantis #0001357. Need ALT to provide approval email asap. [Fii 0512] 1. Do ALT have questions about the reliability test report ? [Fii 0505] 1. - Total test items: 9 items. - Pass items: 9 items. - Fail items: 0 item. - Completed rate: 9/9 = 100% 2. Has upload reliability test report of all items on mantis ID 0001357. [Fii 0428] 1. - Total test items: 9 items. - Pass items: 6 items. - Fail items: 0 item. - On-going item: 2 items. - Completed rate: 6/9 = 67% 2. Has upload reliability test report of the six pass items on mantis ID 0001357. [Fii 0421] 1. Abnormal power on/off: PASS, High temperature & High humidity test - storage: On-going Power On/Off with Temperature: On-going [Fii 0414] The reliability test schedule is 4/16~5/1. The detailed schedule plan has updated on mantis 1357 [Fii 0407] Samples are being custom clearance and haven't arrived at our TuCheng office. [Fii 0331] 1. Waiting for ALT comment to shipment. [Fii 0324] 1. Main board SMT: done, DIP: done Sub-board SMT: done Assembly: 3/24~3/27 ETD VN: 3/28 [Fii 0317] Due to PCB ETA schedule postpone: 1. Main board: SMT 3/18~3/19, DIP: 3/20 ; Sub-board: SMT 3/23~3/24, Assembly: 3/25 [Fii 0310] 1. Main board: SMT 3/16~3/17, DIP: 3/18 ; Sub-board: SMT 3/18~3/19, Assembly: 3/19 [Fii 0303] 1. PCB ETD 03/10. Will start SMT on the 3rd week of Mar. [Fii 0224] 1. Gerber out on 2/23, and start the PCB fab. The sample build schedule is not confirmed yet. Will update to ALT later. [Fii 0217] 1. Has provide LED CIE test report of TI and AWINIC solution to ALT, PLS help review and feedback comments. 2. Need ALT to confirm whether there are any problem on LED animation effect comparison for AWINIC & TI LED driver IC? Need ALT to approve it then Fii will enter to next stage. 3. HW validation test items mention that aging test should be test for GbE PHY and LED driver IC. What are the test conditions of aging test ? 4. Have upload the reliability test plan of ffc cable supplier on mantis 1417. Need ALT to check it and comment if any questions. [Fii 0210] 1. HL7593WL08: SYNAPTICS has finished software development, VCPU and VCORE voltage can change dynamically after system enter Linux kernel. 2. AWINIC LED driver IC: Vendor Everlight start test LED color and brightness on 2/10, and it need to take 3 days to complete the test. The report can be provided on 2/16. 3. Motorcomm GbE PHY: Tuning RX delay register to 8000 that PHY can work normally. 4. TMI TMI3343B DC/DC power: It need to adjust C25 => 200pF, C24 => 200pF, C10 => 180pF to meet transient ripple 240mV (+5~-5%) criteria. Update RD validation test report on mantis 0001357:0009429. [Fii 0126] 1. SYNAPTICS Shanghai site has got the sample on 1/21, and firmware is under development. Will push Synaptics to complete the tuning before 1/28. [Fii 0120] 1. Synaptics send one set PCBA sample via SF express on 1/17. The sample is still on the way to Shanghai. SF: SF1413561920278 [Fii 0113] The sample may arrived to our office on 1/14. Will provide it to Synaptics TW and send to Synaptics China for SW fine tune. s 22pcs sample build.
|  |  | Close |  | [Fii 0331] 1. ALT will review material of stiffner with cable vandor and connector vendor base on last week meeting. [Fii 0324] 1. According to our suppplier, they think the stiffener is forbidden to be broken artificially. So they think that we request to enhance the material is not make sense. Also, the material of stifferner is PET material and common use in FFC cable design, and they don't have other harder material to make for stifferener. [Fii 0317] 1. Has upload FA report on mantis 0001373. Please review it. [Fii 0310] 1. PQE is revising the FA report. Will provide FA report to RD review on 3/11, and provide FA report to ALT on 3/14. [Fii 0303] 1. MFG PQE will provide revise version of FA report and update the report by 3/9 [Fii 0224] 1. Have provided FA report on mantis 0001373. Please review it. 2. Vendor P-TWO request 30pcs FFC connector samples to do reliability test, and got the samples from Fii on 2/24. Vendor will provide reliability test schedule by this week. [Fii 0217] 1. Factory QA can reproduce the FFC broken through the golden finger. Will update 8D report to ALT this week. [Fii 0210] 1. Update P-TWO provided English version of FA report on mantis 0001373: 0009425. 2. The Fii Factory still need some time to prepare the material and the FA report can be provided on 2/11 [Fii 0126] 1. P-TWO provided Chinese version of FA report on 1/24. The English version is not ready yet and will provide it on 1/28. 2. Have sent the FA report to VN factory review. Factory side is under reviewing the process and preparing 8D report now. and the report can be provided after CNY. [Fii 0120] 1. Vendor P-TWO will provide analysis report in Chinese version tomorrow (1/21). The english version can be provided [Fii 0113] 1. Have provided two defect FFC cables to P-TWO and P-two has sent it to their China factory for analysis on 1/13. We expected that the sample will arrived P-two China early next week, and will ask P-two to complete the FA report by next week (1/14).
H/W | 2021.10_first mass production two defected FFC cable | Fii | Close | 2022-01-21 | [Fii 0811] 1. Fixture is ready to build-in on next MP build. [Fii 0804] 1. The fixture has ready for FATP. The test is ok and will build-in to FATP on next MP. [Fii 0728] 1. VN factory just received new fixture on 7/28, and will test it on 7/29. If there is no any further problems, and then wil introduce in production line from next MP build. [Fii 0721] 1. Factory got the new fixture. Some problems were found after trial assemble on 7/21. Factory has ask the fixture supplier to modify the fixture and supplier will return the fixture to Fii factory on 7/25. Production line will trial assemble again on 7/25. [Fii 0714] 1. Fii will finish new assemble fixture's PR/PO this week. Once supplier got PR/PR from Fii, will finish fixture ASAP . [Fii 0707] 1. MFG has got the quotation of new fixture from supplier, and the PR/PO is under processing internally. [Fii 0630] 1. MFG has corrected the fixture, and already send the drawing to supplier for quotation. MFG is expected to get the quotation by next Monday. And then it needs 2 weeks for internal process ( PR/PO). 2. Supplier need 3-5 working day to make the test fixture after receiving PO. [Fii 0623] 1. Production line has produced a first version of new FFC cable assemble fixture, PLS see pictures on the right side. Because it is the first version of new fixture, production line reply that the main board is not easy to place and take out. Will continue to negotiate with production line to optimize the new fixture. [Fii 0609] 1. Production line is making a new fixture at mainboard side for assemble AMP FFC (J814), LED main board FFC (J808), button key FFC (J807) and MIC FFC (J810). The new fixture will be completed by 6/24. Then production line will arrange a control run to see the new fixture is ok or not. Will confirm the control run schedule after new fixture finished. 2. Base on the housing design, the LED main board lock on front cover, MIC board and button board lock on top cover when assemble FFC cable. Because space limitation issue, production line reply that operator can only use hand to put FFC cable into FFC connector. So no fixture for these three boards. [Fii 0602] 1. As Lonnie mention that the 8D report lack of long-term solution for MIC FFC and button FFC. Production line will provide the revise version of 8D by next Thursday (6/9). [Fii 0526] 1. For longterm solution, production line use plastic tweezers put FFC cable into connector on AMP board. Has upload 8D report on mantis #0001373. Need ALT review it and let us know if there are any question. [Fii 0505] 1. No longterm solution provided by VN factory till now. RD will raise this request to VN QA team and need further discussion with production line/QA later. [Fii 0428] 1. ME RD will work with production ME about the feasibility of stick 3M tape on power choke with original FFC cable routing method and will give feed back by 5/4. [Fii 0421] 1. About FFC cable routing is CTQ. Production line reply that it is hard to routing AMP FFC cable between heatspreader_SOC_top and headspreader_AMP_top. Production line has tried three methods. Method 1: Original routing method and stick a 3M tape on AMP FFC cable which the contact position of the FFC cable and power choke. Method 2: Bending the AMP FFC cable before assembly. This method has assemble risks, 1.FFC cable may be broken after folding. 2.OP difficult to assemble (cable is not long enough) 3.FFC cable may be loose or isn't plugged in properly after assembly. Method 3: Routing AMP FFC cable between HS_SOC_top and HS_AMP_top. FFC cable need to be folded a little above the AMP PCBA. This method has assemble risks, 1. OP difficult to assemble 2. FFC cable has broken risk. Production line suggest to use method 1 and because new power choke with LCP top cover, so that it can avoid FFC cable short with power choke. Could ALT agree method 1 ? [Fii 0407] 1. Has uploaded final 8D report on mantis 0001373. Please kindly review it. [Fii 0331] 1. ALT will review material of stiffner with cable vendor and connector vendor base on last week meeting. [Fii 0324] 1. According to our suppplier, they think the stiffener is forbidden to be broken artificially. So they think that we request to enhance the material is not make sense. Also, the material of stifferner is PET material and common use in FFC cable design, and they don't have other harder material to make for stifferener. [Fii 0317] 1. Has upload FA report on mantis 0001373. Please review it. [Fii 0310] 1. PQE is revising the FA report. Will provide FA report to RD review on 3/11, and provide FA report to ALT on 3/14.
H/W | FFC cable melted and common choke burned | Fii | Open | 2022-02-18 | [0826] Foxconn still have about 10K old common choke filters in stock. After use old part, Foxconn will introduce new one. Before that Foxconn will keep apply short term solution. [ALT 812] New FFC cable and new common mode filter will be applied MP. But it depends on stock status when Foxconn start to apply new one. Both FFC Cable and new common mode filter will apply different date based on stock status. Foxconn will inform when they can apply it. And this issue will be closed after both parts are applied to MP. [Fii 0811] 1. Power choke is applying with FFC cable when FFC cable transfers official PN. [Fii 0804] 1. Control run report had updated to mantis. The results were pass. Fii will apply EC for new choke component after ALT confirms. [Fii 0728] 1. SMT had finished and will start to assemble in FATP on 7/29 with new choke component for control run. [Fii 0721] 110pcs material has been arrived at VN factory, but the control run can not be pulled-in due to there are still some parts has shortage issue (ex. TI LED driver IC) [Fii 0623] 1. Has inform production line to use case 2 (use 3M tape) as short-term solution and production line will use case 2 for next MP. 2. For long-term solution, vendor reply that the sample preparation schedule for the new power choke will be 6 weeks (7/29), and the control run will be scheduled on week 2 of Aug. [Fii 0616] 1. Production line has finished control run. Both choke only with mylar (case 1) and choke only with 3M tape (case 2) can 100% pass FATP test. For case 1: There are no mylay detached during production were found. 2. Factory suggest to implement case 2 in next MP. How about ALT's comments ? [Fii 0609] 1. Production line got new gaskets and will finish control run by 6/13. 2. For long term solution, Fii is dealing the cost with vendor and the new part number application process now. Will provide the control schedule and plan to ALT later. [Fii 0603] 1. Control run stopped due to button key jammed issue. It need add more gasket on bottom housing. Inkel will delivery more new gasket to Fii factory on 6/8, then production can continue to control run. 2. Has upload the vibration test report on mantis #0001428. Need ALT to review and comment. [Fii 0526] 1. Control run status: Production line has tested pass 4pcs at RC1. But remaining board still keep at assembly station due to housing button key jammed issue. 2. Vibration test: The test finished, result pass. Will provide test report by 5/30. 3. Are there any testing conducted in ALT side for new FFC choke? Any test result updated from ALT? [Fii 0519] 1. Control run schedule: Production is under confirm. Vibration test for new choke sample -> schedule: 5/24~5/25, report 5/27. [Fii 0512] 1. Vendor reply that they only do package drop test which follow standard IEC 60068-2-3. They never do single part test. 2. Fii production line reply that they can agree stick 3M tape on power choke if control run is pass. 3. According to the page 11 of "Factory Audit - 5/5", ALT told production line don't remove the Mylar. Could ALT double confirm this. [Fii 0505] 1. Vendor unable to provide the drop test specification of power choke to Fii yet because their Kunshan, China factory is lockdown due to COVID-19. Will provide test spec. to ALT check first, and then provide the test report for review if ALT agree with the test spec. 2. Factory ME reply that stick 3M tape on power choke is ok, it need PE and PQE to double confirm it. Will provide confirm result by 5/11. [Fii 0428] 1. Got the new power choke sample 10pcs, and check the dimension are the same as current used. 2. Will prepare SWAN samples and arrange vibration test schedule with HWQA team. Will update the schedule by 5/4. [Fii 0421] 1. New power choke samples ETD 4/22, ETA 4/25. [Fii 0414] 1. Fii PQE has finished the "Simulated FFC cable folding on the top of power choke" test, and upload on mantis 0001428: 0009879. The maximum Temp. of CHOKE is 66.9 degree C @room Temp. 22.6 degree C, Temp. rise 44.3 degree C. Please kindly review it. 2. The vendor reply that the LCP are thermoplastics materials which are commonly used in SMT type connectors. There should be no cracking and fragile problems. [Fii 0407] 1. Fii PQE start to retest "Simulated FFC cable folding on the top of power choke" following ALT suggestion on 4/6 noon. The testing is expected to be completed by 4/9. 3. Got the new power filter datasheet and has uploaded on mantis 0001428. [Fii 0331] 1. Has provided PCB vendor's FA report on mantis. 2. Fii PQE will retest "Simulated FFC cable folding on the top of power choke" by ALT provided new test condition, and updata to ALT next week. 3. Power choke vendor provide a new type a choke which changed mylar tape to LCP (Liquid Crystal Polymer) cover on the top of choke. As show in the picture left. The LCP cover isn't effect original performance, prices will go up slightly. Vendor will provide datasheet to Fii later. [Fii 0324] 1. VGT will update 8D report (including D6/D7) to Fii on 3/25, and then Fii QA will update the 8D and provide it before next Tuesday (3/29). [Fii 0317] VGT PCB vendor x-section FA results: 1. Component short. (Fii does not thought it is roor cause. One choke and 2 capacitors.) 2. Residual copper in via area to cause short. 3. Will update 8D report to ALT by this week. [Fii 0310]: Have provided English x-section report to ALT on 3/10 (mantis: 1428) Fii QA team is work with PCB supplier (VGT) to prepare the 8D report. The 8D report can be provided by next week. [Fii 0303] VGT vendor had finished X-ray and IR image test. And VGT will provide PCB x-section report to Fii on 3/7. Fii QA team will provide 8D report next week
H/W | CS manual | Fii/ALT | Close | TBD | [Fii 0519] No further request from SH. [Fii 0512] 1. The updated CS manual has been provided to Mr.Son on 5/11. [Fii 0505] No further update from factory. Will ask factory PE/ME to update the CS manual by next week. [Fii 0428] The updated CS manual has been provided to Mr.Son on 4/22. [Fii 0421] Will update the CS manual based on SH's request by this week [Fii 0414] 1. VN factory has been preparing on that and will provide the 1st version for ALT review on 4/15. [Fii 0324] 1. ALT is requesting the CS manual forSWAN. According to Tiffanie, ALT only change PCBA and assembly only. ALT won't repair the board level. Alsp, ALT haven't sign the SOW back yet, so Fii will provide the CS manual after received the signed SOW from ALT.
H/W | MP adaptor conduction issue | Fii/ALT | Close | 2022-05-05 | [1028] ALT received test result. It worked as vendor expected. So their solution will be applied from next production. ALT uploaded test result on mantis. If Foxconn don't have any additoional request about it, then ALT will close this issue. [1021] Vendor produced Line filters for test. It is on track. [1007] Vendor will produce 50 samples for test by mid. of Oct and Test it by the end of Oct. It is for the verification test for their solution. ALT will keep update. Vendor use a same adaptor for test. They make adaptor with Line filter socket. And they will replace Line filter every test. [0930] Adaptor vendor didn't fix the schedule yet. They are discussing internally. ALT hopes to get update by next week. ALT will keep updating on mantis. [0923] ALT already update test data on mantis. And ALT didn't receive any update on additional test from supplier yet. ALT keep in touch with supplier and will update once ALT get any update from supplier. [0916] Adaptor vendor tested EMI for 10 pcs samples that made by their factory. All passed. We will update on mantis early of next week. Adaptor vendor will test with more quantity. Their plan is not fixed yet. [0908] Adaptor vendor will receive new adaptor from factory by 9/13. ALT expect to get their test result by the end of next week. [0901] Adaptor vendor will produce new adaptor with new Line filter on Sep. But there is no detail information yet. ALT will update its schedule soon. [ALT 0826] Adaptor vendor didn't produce it yet due to material shortage. ALT keeps asking vendor to update their plan. But they didn't feedback yet. ALT will check it and update their schedule on Mantis. [ALT 0819] Adaptor vendor produce new adaptor in their factory. They will test EMI with new adaptor next week. Once ALT receive any update from vendor, then ALT will update it on mantis. And ALT will update vendor's test report up to now by today. [ALT 0812] New adaptor production for test by 8/15, EMI test will start 8/22. We will update current status on mantis by 8/16. [Fii 0721] 1. Any update of test result or root cause from adaptor vendor ? [Fii 0714] Any update from ALT after meet adapter vendor last Friday? [Fii 0630] Need ALT to update the PSU fail 8D report from supplier. [Fii 0616] Has vendor finished abnormal adaptor with STB test ? Any further update from adaptor vendor? [Fii 0609] According to ALT Mr.Yoon, adapter vendor will test fail sample from 6/7. When will adapter vendor to complete the test and be able to provide the analysis result? [Fii 0603] 1. Has ALT received any plan or schedule from adapter vendor ? [Fii 0526] 1. For the failure PSU, we need ALT to continue tracking this issue with supplier and find the root cause. We're worried whether this issue is just a case or there may be a potential problem with the mass production products. Please kindly let us know ALT's next plans and the schedule. [Fii 0519] 1. Will send 2 PSU (One pass and one fail), 4 new CM chokes and one main board with two normal FFC cable to ALT by 5/20 [Fii 0511] 1. Got the FedEx account and will delivery adapter x2 (OK x1, failure x1) and new power choke x3 to ALT. [Fii 0505] 1. Need ALT to confirm which adapter needs to be send back, and please also provide the FedEx account to Fii, so that Fii can deliver abnormal adapter to ALT for further analysis. [Fii 0428] 1. Fii test conduction for 2nd build sample of 2nd source, found SWAN + sample NO.0 MP adaptor is fail, SWAN + sample No.1 and No.2 MP adaptors are pass. There seems to be a quality difference issue between MP adaptors. Has upload conduction test report on mantis 0001469. 2. Will delivery fail adaptor to Korea next week. Please ALT provide FedEx account to Fii.
H/W | GPIO issue review | ALT/Fii | Close | 2022-05-20 | [Fii 0707] 1. In design phase, hardware team will provide GPIO mapping table to software team review if there is any hardware changes based on the reference design. 2. Both Fii software and hardware team doesn' aware that the register setting for VDDIO should be changed when changing hardware VDDIO level design. It seems to me that the key point of this issue is that Synaptics didn't inform Fii that this register had to be changed. [Fii 0630] For VDDIO6 power design 1. In the reference schematic: VDDIO6 can be powered from PWR_1V8 or PWR_3V3 via analog switch (U13). VDD of SD card connector is 3.3V, so we think SDIO interface is 3.3V and VDDIO6 is 3.3V. 2. Schematic design of SWAN: SWAN no SD card connector requirement, so change the interface from SDIO to GPIO for button key, remove analog switch (U13) and connect VDDIO6 to PWR_3V3 directlly. For VDDIO9 power design 1. In the reference schematic: SCARD interface connected to NGFF WiFi module and VDDIO9 is 1.8V. 2. Schematic design of SWAN: SWAN no WiFi function requirement, so change SCARD interface to GPIO and change VDDIO9 from PWR_1V8 tp PWR_3V3. From hardware design viewing, both voltage setting of VDDIO6 and VDDIO9 are correct for SWAN. Fii also provide schematic for SYNAPTICS review during schematic design stage, but Synpatics no response register setting issue of changing voltage of VDDIO9. [Fii 0623] AUX in issue: 1. Production line has sent fail SOC to SYNAPTICS for further analysis on 6/17. Once got analysis report from SYNAPTICS, will feedbact to ALT soon. 2. According to Synaptics, the SoC VDDIO6 & VDDIO9 block are set to the wrong register and doesn't match the hardware design. Our SW River is checking on that and will work with Synaptics to correct it. VDDIO1/2/3/6/7/8/9/10/11=3.3V, VDDIO4/5=1.8V. Detec_AUX is R4 of VDDIO9. For Button key: VDDIO2: Power_on_off_key, pin AL20 VDDIO2: Volume up, pin AP21 VDDIO6: Ch_up, Pin AD2 VDDIO6: CH_down, pin AC3 VDDIO6: Volume down, pin AC2 VDDIO6: BT pair, pin Y2 VDDIO6: SoundField, pin AE3 VDDIO8: MIC Mute, pin V2 [Fii 0616] For CH- button key issue such as cold soldering or solder crack, factory can do "Red Dye Penetration Test" to analyze defective sample and see if there are any process soldering issues. [Fii 0610] AUX in issue: 1. Production line has provided the NG SOC evaluation report to SYNAPTICS on 6/3, SYNAPTICS will feedback review result about 2 weeks later. CH- key issue: 2. For CH- button key issue, as factory only got one failure sample and it already been fixed. So, it needs ALT to provide more defective samples to factory side to further root cause analysis and the corrective action. [Fii 0603] 1. Had upload the production line provided "CH- button key FA report" on mantis #0001468. Please help review it. 2. Production line will provide the NG SOC evaluation report to SYNAPTICS on 6/3. If SYNAPTICS approve the report, then Fii production can ship the NG SOC to SYNAPTICS for further analysis. [Fii 0526] 1. AUX detect pin abnormal => The NG board fuction turns into works after mount a new SOC on NG board. PE still under checking whether the failure symptom follows with NG board SoC. [Fii 0519] 1. Button "CH-": Resoldering NG board's SOC, "CH-" key can work normally. It appears that the problem may be caused by soldering issue. 2. AUX detect pin abnormal: The impedance of NG board and OK board are the same. PE resoldering NG board's SOC, function still abnormal. Will need factory PE to do swap test to see if the failure symptom follow the SoC. [Fii 0505] Provide the ESD test report for 2nd build sample of 2nd source on mantis #0001468. The ESD result show that all buttons and AUX port can pass air +-8KV. [Fii 0428] ALT found some defective products in the field, and it looks like ALT has done some preliminary analysis such as x-ray inspection. And these issues are related to GPIO. Mantis #1468
H/W | LKFS issue(#1520) | FII | Open | 2022-09-16 | [Fii 1201] The PCBA has been sent to VN factory for rework on Dec 1. [1125] Foxconn will try to replace SoC again. Fot this Foxconn will send PCBA to Foxconn Factory again. It already reworked twice. So Foxconn think that it has high risk. Foxconn will update its status later. [Fii 1124] 1. The board (good SOC+NG PCBA) for testing LKFS is broken. After downloading new image to PCBA and changed MAC address for VPN, the PCBA was ok and could play video through HDMI. When we were ready to package to transfer to Lab for testing, PCBA rebooted again and again suddenly by itself without any symptom. Debug DDR4/eMMC/SOC power rail, they were all normal and no any symptoms. Suspect the SOC solder ball may non-wetting or cold soldering. 2. VN PE doesn't recommend us to remount anymore since this PCBA has already done twice rework before. [1118] Synaptics checked ATE test first and they took a x-ray picture due to crack on SoC. Synaptics cannot test it on b'd level because it cannot boot. ALT worried about Foxconn's failure rate for remount chip or SoC debug. Foxconn think that the SoC is thinner than others. It makes the higher failure rate. But Foxconn will ask Factory to improve their remount failure rate. [FII 1117] 1. For NG SOC, we received FA report from Synaptics on Nov. 17th,, and Synaptics found obvious die crack. So, our QA team prepare a report explaining it. The report has been uploadedto mantis 1520 for ALT review. 2. For Good SOC+NG PCBA, it has been arrived at our office on 11/17. We will update F/W and then transfer to SQA for testing early next week. [1111] Foxconn Factory is discussing with Synaptics about NG SoC delivery(to CN or Taiwan). FII Factory will send NG SoC to Synaptics Taiwan in this week. [Fii 1110] 1. Synaptics FAE said if the power 1V05 is short to GND, it may not be able to do the board-level test. Normally, Synaptics will do ATE test first when receiving the defective sample. If ATE test is failed, and then they will do the X-ray test, and then decap if they found any problems. 2. For Good SOC+NG PCBA, waiting for express delivery back TW. [1104] Foxconn already informed issue and the their test information for defected SoC. Foxconn expect that Good SoC + NG PCBA B'd will be depature early of next week. [Fii 1103] NG SOC had sent to vendor for FA, component will be arrived vendor on 11/4. Wait for FA report. For good SoC on NG PCBA, we applied for express internally. We will deliver the board to TW once approved. [1028] NG SOC looks damaged. So it cannot review anymore. ALT aske Foxconn to check that Synapctics can investigate this NG SoC. Good SoC on NG PCBA will be sent to FII Taiwan. FII Taiwan will review and update it. [Fii 1027] NG SOC+Good PCBA swap failure due to high 40% risk with blister on SOC board. Currently the both 1V05 power traces on SOC board shorts to GND and cannot remounted anymore. The report has updated to mantis1520. [1020] The NG PBCA with good SOC had finished swap and can work normally. The other good PCBA with NG SOC is reballing 2nd times due to the SOC power rail short to GND. VN PE is reballing for 2nd time and will test it. There are bliters on good PCBA, so Foxconn repace good PCBA. Foxconn will mount defect SOC on god PCBA today, and inform the result later. [1013] VN SMT side had un-mounted the SOC but found some blister on PCBA and SOC. VN PE will reball the SoC carefully and then do the swap test. Will keep update the result to ALT. [1007] 2 PCBA will be arrived in VN Office by today. Foxconn factory will replace SoC after receiving PCBA. Keep updating on its status on mantis. [Fii 1006] Wait for PCBA arrive to VN factory and will do SWAP SOC and its function test. If no problem, PCBA will be sent back to TW for LKFS test. [0930] Foxconn finish Fedex account application this morning. Foxconn will send 2 pcs of PCBA to Foxcon Factory in VN today. Foxconn keep updating it. [0929] The internal FedEX account application is not completed yet. [0923] Foxconn will send 2 units to Foxcon factory. Foxconn factory will replace SoC and defected SoC will be attached on good PCBA too. Foxconn think that there is no additional test item in Taiwan with defected unit. Foxconn will update SoC swap test schedule soon. [Fii 0922] The test result has been updated on mantis. It looks like the problem will follow with the main board. We think the problem may be caused by SoC since the LKFS is tested through the HDMI interface, and if we want to verify it, we have to send this board to VN factory for repair. [0916] The test result will be ready by the end of today. Foxconn will review the result with SW engineers and will have more investigation. [Fii 0915] The DUT just arrived at SQA on 9/14 but the SQA engineer was occupied by other projects until 9/15. The test will be started from 9/16. [0908] 2 DUTs(1 Defected unit and a normal unit) will arrive Foxconn's SQA today. Its test plan will be updated by next week. [0907] Will deliver 1 defect and 1 normal sample to HC SQA for testing first and then check if the symptom is followed with the main board. [0901] ALT sent defected unit that tested in SKB BMT Lab.(Fedex Tracking No. : 777806825554). It is in Philipines. It will be arrive in TW on 9/2. Foxconn will arrage SQA in Taiwan and will test it. Foxconn will keep updating on it on mantis.
H/W | Motorcomm ETH PHY disconnection issue |  |  |  | [Fii 1201] 1. Motorcomm FAE has provided SW commands of increasing DVDDL voltage. We can measure 1.318V (w/o RJ45 cable) and 1.335V (ping LAN IP) of DVDDL on Eagle after increasing DVDDL voltage. We are testing ethernet disconnection, till now failure rate is 3.125% (tested 64 times, failed *2), Will finish 100 times test by 12/2 afternoon and update result to ALT. 2. Fii software has uploaded test image to ALT ftp server. Path: /release_by_fxn/swan_test_image/20221201_phyVoltage [1125] Foxconn will check how they can change register value to 1.3 V for DVDDL and apply it to test SW. Motorcomm recommended 1.3V for DVDDL. After appling new register value, Foxconn will start to test. Foxconn think that it takes more than 4 days. So it will update by next meeting. ALT asked to provide test SW and Foxconn accepted it. [Fii 1124] 1. CRC Test timing : Fii set the minimum register value (0xff634544 0xC0260) that make CRC error and then test ethernet disconnect issue. We test 100 times, failure rate is 4%. The previous adjusted register (0xff634544 0x20260) of the same PCBA has a similar failure rate of about 4% ( tested 26 times, failed *1). Failure rate of before and after is the same. So Fii think this issue is not relate to CRC. 2. We will continue testing to see if we can improved the failure rate by increasing the voltage level of Motorcomm's DVDDL. [1118] To increase DVDDL voltage for SWAN, it need SW change. But ALT need another BMT to change SW. ALT expects that it will take more than 6 month. CRC Test timing : Foxconn checked the minimum register value that make CRC error. Foxconn keep testing it with new value from 11/17. Foxconn expects that this new value make more higher issue rate than before. Foxconn wants to check the relation between CRC timing and issue rate. Foxconn will test over 100 times. Its failure rate was 1~2% before. New SW : It needs additonal BMT. It will take about another 6 month. So it is not good solution. ALT think that Foxconn should focus HW debug. [Fii 1117] 1. Motorcom reported to us and mentioned that another customer had an unstable ethernet connection issue recently, and its DVDDL(PIN21) is around 1.09V~1.1V, but normal voltage should be higher than 1.15V. 2. We checked the Eagle abnormal PCBA and SWAN, the voltage of Eagle is 1.15V, SWAN is 1.136V. However, Motorcomm think we can try to increase the voltage level by adjust register, and see if the disconnect issue is fixed or not. We will arrange the test next week. 3. CRC testing timing: We adjust SOC's RGMII RX delay (register 0xff634544) value from 0x20260 to 0xc0260, and found some CRC errors occur. We start to test ethernet disconnection on Eagle by using this delay value (0xc0260) on 11/17 afternoon, untill now no abnormal were found (test method: cable disconnect to Eagle for 10 minutes, cable connect to Eagle for 1 minutes) . We will inform ALT test result on 11/21. 4. Our software team is implementing a function to identify PHY/PMIC/LED driver IC in degraded function. If this feature is done, I think we can introduce 2nd source in SWAN without Motorcomm. [1111] Foxconn is discussing this issue with AML and Synaptics. ALT concerned about the CRC Testing timing. But ALT think that it should have same issue during normal operation if AML's concern is correct. ALT asked Foxconn to prepare test plan for both Eagle and SWAN until next weekly meeting. [Fii-1110] 1. SOC vendor - Amlogic replied that MDC / MDIO is controlled by MAC register, MDC oscillate with MDIO is correct, and MDC oscillate behavior can not be modified on S905X2. 2. Synaptics FAE reply MDC always oscillate is RGMII IP behavior. 3. It looks like MDC has different behavior on different platforms, but both Amlogic and Synaptics FAE think that their SoC behavior is no problem. [1104] ALT left some comment on Foxconn's test result on mantis. Foxconn will add ALT's question if it needed. [Fii-1103] Foxconn measured MDC/MDIO waveform of REALTEK and MOTORCOMM PHY chip at each Eagle and SWAN project, the result are the same as ALT 10/19 provided. But waveform of REALTEK and MOTORCOMM PHY are a bit difference during start up condition for Eagle project. We also measure waveform at disable asleep mode, the result are the same as enable asleep mode. Test report as attached. We have informed SOC vendor - Amlogic this issue and and wait for their feedback. The report has uploaded on mantis 1357. [1028] Foxconn already tested the change request from Motorcomm. There is no improvement with ECO that Motorcomm provided. Foxconn thinks that there are 2 difference between Eagle and SWAN. Impedence matching : Eagle - many 75 ohm resister, SWAN - 1 75 ohm resister. Ethernet transformer : Eagle uses external transformer for ethernet, but SWAN uses internal transformer. Foxconn will check with other vendor's transformer with eagle. ALT already test Eagle with SWAN Ethernet connector, but we can reproduce the issue. ALT asked to check the difference of MDIO interface between Swan and Eagle, Foxconn will check and update it. [1021] ALT asked use for the investigation plan for Motorcomm ETH PHY issue.
| GPIO Setting voltage |  |  |  | [1201-Fii] Need ALT to provide Chip ID for defected units. [1125] ALT cannot accept to replace SoC for repair. Because SoC replacement failure rate in Foxconn Factory is too high. And Foxconn factory cannot filter defected rework(ex : LKFS NG PCBA + Good SoC issue). ALT wants to provide new PCBAs for repair. Foxconn asked to package information to Foxconn to arrange defected unit pick up. ALT will read Chip ID for defected unit and and inform to Foxconn. [Fii 1124] 1. Fii has provided GPIO value of Eagle/SWAN via e-mail. Please kindly review it. 2. SOC chip ID: Test commands is "cat /proc/cmdline ¦grep -ie chipid", then we can read unique chipid in the information. [1118] ALT provide an e-mail to check the GPIO setting voltage. Please check and support us with your HW/SW for both SWAN and Eagle

## Factory
Category | Issue | owner | status | due date | Progress
SMT | Microphone Void issue | Fii | close | 2021-09-10 | [Fii 0630] Will follow ALT suggestion on next MP build for 5% x-ray inspection and OBA report. [Fii 0623] VN SMT can do 5% X-ray inspection under 35% mic void. We need ALT to provide the OBA ducument format for VN Factory review. [Fii 0616] VN SMT can only do 2% X-ray inspection under 35% mic gap, because our factory has only one X-ray machine, it can't be occupied by SWAN products only. So, we need further discussion with ALT about the inspection rate. [Fii 0610] Will discuss with factory side and see if factory can accept the x-ray inspection requirement required by ALT. - First: finish SMD board (10pcs, MIC 40pcs) must x-ray inspection for MIC void every SMD lot - Every 1 hour per 5% inspection (only MIC component) - OBA report attached X-ray inspection result and x-ray image [Fii 0602] VN SMT changes new stencil, one is bridge(Type-1), the other is sector aperture(Type-2). If the spec is under 25% of void, the failure is almost 100%. Please check detailed report on mantis 1315. The result is better than the previous test, but still far from what we expected if ALT requires void to be below 25%. Need further discussion about the requirement. [Fii 0526] VN-ME will proivde the internal report to RD/PM on 05/27. Once we review it completely, we will provide to ALT ASAP. [Fii 0519] No further update. [Fii 0512] RD keeps monitor to meet 25% of void. [Fii 0505] No further update. Wait ALT reply. [Fii 0428] The fail rate is 1.07%(22 pcs fail/2060 mic) which is higher than 0.75%(3 pcs fail/400 mic). The report had updated to mantis. Only fail mic components x-ray picture put in report. [Fii 0421] VN SMT has done some quantities. When we get the report, we will update to mantis. [Fii 0414] The next SMT is expected to start from next week. The proposal will be provided and updated to mantis next week. [Fii 0407] Wait VN SMT ME provides proposal of 1000 pcs void x-ray test. [Fii 0331] ALT requires 750~1250 pcs (3000 ~ 5000 mic sensors) and it is a big quantity for VN SMT. Due to X-ray machine is the only one set on SMT line, 250pcs (1000 mic sensors) will be satisfied to ALT first. VN SMT will provide in separated way to collect enough quantities. [Fii 0324] Will do 1000pcs time-4 solution to decide profile solution on VN SMT line. [Fii 0317] VN SMT had provided risk components list, and update to mantis. There are, FFC connectors(J6_1, J3_3, J3_2, J3_1, J1_1), MIC components(Mic1~Mic4) and FFC connector(J813). Critical temperature is 250 deg-C. [Fii 0310]: VN SMT will decide which profile prefers for mic void issue. [Fii 0303] Please refer to our comment on mantis 1315. The new profile seems worst than current profile setting since there are more solder ball issue with new profile. [Fii 0224] Factory arranged 100pcs sample build and has completed on 2/23. The report can be provided on 2/25. [Fii 0217] The test condition of next built will keep the same time for preheat/soldering as VN SMT suggestion but peak temperature will follow ALT require, 248 deg-C. The factory will be able to arrange the sample build next week. [Fii 0210]: Facotry has some problems for preheat/soldering time as decreasing time too short. Facotry suggests 1 deg-C/s is better. Have updated it on mantis 1315 [Fii 0126]: Facotry has done a DOE yesterday (1/25) but the void rate (>30%) is not improved, will update result on mantis 1315 for ALT review today. And will continue to discuss with ALT/factory to see if there are any suggestion for the next test. [Fii 0120]: Stencil verify results: S3X58-M500 (old) solder paste 0.09mm: void:2F/200; solder ball: 4F/200; O-ring void: 5F/200 0.10mm: void: 2F/200; solder ball:2F/200; O-ring void: 0F/200 Next plan: new solder paste + 0.1mm stenceil + Fii optimized profile will be arranged and started from next Tuesday (1/25). [Fii 0113]: Next plan: S3X58-M500 solder paste+stenceil0.09mm+Fii optimized profile. The SMT is on line on 1/13. Updated on mantis 1315. [Fii 0106]: New solder paste S3X58-HF1100 control run had finished and the situdation seems not good enough and less than Fii optimization profile. Void solder: 7f/400, fail rate=1.75%[Fii optimize fail rate=1.50%] Solder ball: 9f/400, fail rate=2.25%[Fii optimize fail rate=2.5%] O-ring: 11f/400, fail rate=2.75%[Fii optimize fail rate=0%] Maintis: 1315 [Fii 1230] No further update. [Fii 1223] 1. DOE report of ALT and vendor suggestions had provided to mantis(1315) 2. The VN factory just received new solder paste sample from vender on 12/23, and MFG PM An/ME engineer will arrange the control run to see if the void can be improved. Will update the schedule to ALT when the schedule confirmed by VN factory. [Fii 1216] 1. Factory has completed experiments to reduce the reflow time, but we found that some O-RING of MICs have void issue. Need factory to update the overall test result. 2. Waiting for new solder paste sample from vender for further experiment. [Fii 1209] As discuss with solder paste vendor and FXN SMT ME, we will change new solder paste. And apply new 1KG smaple of S3X58-HF1100. While receiving new solder paste sample, vendor and SMT will do some DOE for void issue.
Material | Pre-MP (100pcs+ 1K) material shortage | ALT/FII | close | 2021-09-20 | [0910] 1. REALTEK PHY IC (Usage*1) : 2022/12/31 ETA => 100pcs usage: move from Eagle, 1K usage: in shortage 2. Inkel all materials : under checking in factory => 100pcs usage: ok, 1K usage : need ALT to confirm gap q'ty 3. [AMP board related] - CAP CER 120pF 5% 50V (Usage*8, LT=126 days) => 100pcs usage : ETA 9/22, 1K usage : ETA 10/10
Material rework | Pasting the required tape on holder MIC *Rework q'ty: for 1.1K pre-MP only *Holder (446.00185.005) *Tape will be provided by ALT | ALT | close | 2021-09-07 | [Fii 0908] Factory commented that it's not qualified to production based on ALT SOP. The jig is still necessary to pasting the tape. [Fii 0906] Factory received the video and under checking. [ALT 0901] ALT commented that the tape could not be improved because the vendor already did their production. Will provided a video to show how to paste the tape for Fii factory reference. [Fii 0830] Waiting for ALT's comment for further discussion, such as material improve plan, jig plan. [Fii 0825] CFT will provide jig 3D document for reference. ALT could discuss the design with their vendor based on this draft 3D. [Fii 0823] MFG did DFM. There are two major issues 1. The adhesion force of holder side is not enough. The material of tape is too slight and not easy to be sticked. 2. Shall require the vendor to paste it and ship out the holder because it shall be sticked by their exclusive jig.
Material rework | Adding ferrite core and attaching EVA sponge on L-CH and R-CH speaker cable *Rework q'ty: for 1.1K + 15K *L-CH speaker cable (377.00347.005LT) R-CH speaker cable (377.00346.005LT) | ALT | close | 2021-09-07 | [Fii 0910] Waiting for the samples to verification. [Fii 0906] Need ALT to provide the ferrite core and EVA sponge (484.00429.005). [ALT 0901] 1. Spec for IQC: follow the spec that ALT updated on mantis 1308#c8006. 2. SOP for IPQC: follow mantis 1270#c8034. * Adding ferrite core and EVA sponge on both L-CH and R-CH speaker cable. [Fii 0830] Waiting for ALT to update 1. Spec for IQC 2. SOP for IQPC [Fii 0827] Received SOP on 8/26. Need to discuss the details about IQC and IPQC criteria with ALT. [ALT 0820] Will provide SOP by 8/27
SI | SW version for Pre-MP | ALT | close | 2021-09-03 | [ALT 0903] SW version for Pre-MP. Main SoC SW Version : 19.531.16 AMP B’d SW : 0x22 [Fii 0903] Factory is asking when can they receive the image to fine-tune the acoustic test equipment and verify the full production process.
SI | VI specification *Manufacturing Specification *Visual inspection criteria | ALT /Fii | pending |  | [ALT 0126] Inkel will prepare and send the sample on 2/9. So ALT may send Golden samples the 4th week of Feb.(by 2/25) (depends on logistics status) [Fii 0126]Please check when the golden sample can be provided? [Fii 11/24] Need ALT to update visual inspection criteria including Scratch housing, Assembly GAP spec, BTV Deco plate spec, Grille clothe(音響網布). [ALT 1104] INKEL will provide Golden sample 11/8 in China. Due to delivery issue in China, we hope we can receive it 11/15. After we review the golden sample, and then we will provide it to your factory. [Fii 1001] 1. When will our SQE recevie the golden sample? 2. According to the visual inspection criteria that ALT required, it's not possible to run next build (1K) under the current incoming housing status. There ared two suggested plans if SKB still needs the next 1K. a) Our PQE list the attached visual inspection draft based on the current incoming materails status for your reference. Because the criteria is quite different from what you asked before, please discuss with SKB whether they could accept the revised criteria. b) Please discuss with your vendors to improve the materails and redelivery as soon as possible. We'll work with our factory to do 100pcs control run again based on the new incoming materails. After we complete the production, we will update our suggestion again. [Fii 0924] Required q'ty: 2 sets with ALT owner signature and date <recipient informaton> Fuyu precision component Co., LTD Lot M1 and Lot F, Quang Chau Industrial Park, Van Trung Commune, Vietyen district, Bacgiang province Name: SQE Tuan Phone: 0394353939 [Fii 0914] Factory require to have golden sample as the standard of visual inspection. [Fii 0901] Fii did provide our feedback. Please check and list down your question so that we can arrange a meeting with the factory and ALT. [Fii 0825] CFT will update their first verson within today. [Fii 0819] The ME R&D and factory ME checks the customer reply. [Fii 0812] Please check the questions raised by mantis #1126. [ALT 0804] The ALT provides documents to the factory for check. [Fii 0428] factory will compare to the real production status and feedback. [Fii 0423] received the VI spec and will review with factory and reply by 4/27.
Capacity | Monthly demand to be updated | Fii | close | 2021-09-20 | [Fii 0914] Production layout will be 10K/M. But need ALT to consider how to reduce assembly effort (related to cost and quality). [Fii 0909] Factory will update capacity based on 100pcs control run. [Fii 0825] Fii CFT to update assembly daily capacity. [Fii 0823] Capacity : 300/D (7.5K/M) based on w/o air leakage testing. * The capacity is reducing if ALT RD keep asking to add test item. [Fii 0603] Fii to update monthly forecast.
Production | ALT commented DVT3_assembly review result | Fii | close | 2021-09-10 | Factory is under reviewing.
Production | 1. SI test plan 2. OBA test plan | Fii | close | 2021-09-10 | [Fii 0903] Fii to provide the test plan based on pre-MP process (Mantis#1126)
Production | FW confirmation: secure/non-secure | ALT /Fii | close | 2021-09-10 | [ALT 0910] ALL shall use secure image. Would like to confirm the allocation for 100pcs + 1K FW
Production | ALT to review pre-MP PMD | ALT | close | 2021-09-13 | 1. pre-MP assembly PMD (Mantis#1270) 2. ALT assembly SOP => L-CH, R-CH speaker cable is opposite.
Materials | Inkel material in shortage for pre-MP(1.1K) | ALT | close | 2021-09-24 | [Fii 0924]484.00422.005 (usage:6) 1. 300pcs is in shortage for 300 DUT control run. 2. Inkel doesn't commit ETD schedule for 5100pcs. Others: need Inkel to pull in to 9/25.
IQC | IQC criteria on speaker cable | ALT | close | 2021-09-24 | [Fii 0924] ALT require Fii to have tug test on 15K speaker cables. However, our SQE checked with Dreamus that Dreamus didn't follow ALT's instruction to do tug test on their OQC process. Besides, Dreamus only did 10pcs sampling based on their testing criteria. Our IQC is blocking the whole speaker cables right now. Need ALT to check with Dreamus. => Curretnly, the line is lock-out due to material shortage.
MOH | MOH cost down & ME design DFM (Mantis#1131) | ALT | pending |  | [ALT 1104] ＊INKEL will provide their review result by 11/5. 3- Screw issue on heat spreader : ALT asked to INKEL to check to change 1 screw type for all heat spreader screw. INKEL is looking for a way to change all screw to 1 type. For this, they are checking the cost and development time. 4- Screw issue on bottom cover : ALT asked to INKEL to use same screw type for bottom cover. INKEL is checking the cost and development time to change M3x12mm Flat type screw to normal type screw with Tooling change. ALT already inform that FII can use M3x7mm screw for the screws under rubber foot instead of M3x10mm, but torque should be 3Kgf*츠. 5- Hole dimension issue on bottom cover 6- Assembly issue on LED board There is no space to attach sponge on Grill Fabric Ass’y. So there is no way to attach sponge on Grill Fabric Ass’y. 7- Screw issue on main b’d Foxconn can use M3x8mm screw instead of M3x7mm from 2K MP 8- Housing issue INKEL will provide LED Side Bracket with PE bag. It will apply after 2K delivery. ＊ALT will check the cost for Tooling change, schedule, assembly cost reduction due to tooling changes. And ALT will decide which solution will use and when those component change can provide. [Fii 1014] Please check the updated file in Matnis. [Fii 0928] 1. We need to know the target date that ALT agree to apply for production preparation. 2. Factory is preparing their DFM. Will update in Maintis on 10/1.
Assembly | Mechanical change from 1st MP (Mantis#1352) | ALT | close | 2021-09-24 | [Fii 1008] Factory would like to evalute the changed materials to make sure it won't impact the production. Is possible that ALT ask vendors to deliver 2 sets samples? Fuyu precision component Co., LTD Lot M1 and Lot F, Quang Chau Industrial Park, Van Trung Commune, Vietyen district, Bacgiang province Name: PM An Tran Phone: 0327091936 [Fii 0924] Need ALT to double confirm the datasheet/drawing of new materials. [Fii 0915] Because we have to control the component and usage in BOM, we need to check the change list, such as screw, housing, gasket…, and change timing with ALT. Fii to provide the list on 9/16. Please double check and feedback by 9/24.
Quality | Inkel housing quality issues (Mantis#1385) | ALT | Close | 2021-11-12 | [Fii 1125] Need ALT to check the Inkel housing issue can be improved after 13K pcs. [Fii 1105] Please refer to the documents in Mantis#1385. Because their quality impact to our production capacity (Fii factory took time to sort their housing in production line.) , need ALT to push vendors to imrpove immediately.
Quality | [SWAN] [MP] 2022.05 Mass production inspection report | FII | close | 2022-07-06 | [1104] Foxconn didn't apply ethernet unstable solution for factory SW. ALT closed this issue. [1028] ALT would like to know that SW fix on Ethernet Unstable applied for next Factory SW. It should not apply it because customer SW didn't have this changes. This change should apply to both MP SW and Factory SW at once. [1020] Tack switch As per ALT agree with spec. change, we will keep using the same part number and update the datasheet in our system when all tact switch are out of stock. [1014] Tack switch This Tack switch is only for SWAN. So vendor can provide new specification tack switch after original tack switchs are out of stock. VN Factory has 41,592 origianl FFC cables and 60K in HongKong ware house and 75K in vendor's factory. [Fii 1013] Tack switch: Currently there is about 176K of old tact switch(+/-50gf) in stock. We plan to apply new part number for new tact switch and make running changes to the new part after the old part runs out. [1007] Tack switch spec. change Foxconn need the no. of sample that ALT needs. And Foxconn can provide the each press forces for each sample. ALT will check the no. of sample and feedback to Foxconn by next week. Ethernet unstable : Foxconn will collect more defect sample and test again when they have next mass production and validate their solution with more sample. After that Foxconn will apply register change for next build. [Fii 1006] 1. Ethernet unstable: Has finished test. All samples (defective PCBA x2, OK set x10) can pass test. 2. Tack Switch spec. change : 2.1 Vendor confirmed that the spec. change will not impact the cost. 2.2 Vendor can't provide the upper & lower limited samples (130/160/210gf) because it's hard to screen out such samples in their factory. Vendor only can provide new spec. samples (160 +50/-30gf) for testing. 1. Ethernet unstable : Foxconn still have 2 pcs to test 24Hr CRC. It will finish by 10/4. ALT test was OK with 1 defect unit. It tested almost a week. 2. Tack Switch spec. change : ALT accept to change spec. from -50gf to -30gf if there is no cost imact. ALT asked Foxconn to check when Foxconn can apply it. Foxconn will check it and feedback to ALT. ALT asked to provide samples on Mantis. [0929] 1. Ethernet unstable : Will finish 24Hr CRC test on 10/4. 2. Tack Switch spec. change : Wait for ALT reply. [0923] 1. Ethernet unstable : ALT has a defected Unit. ALT is testing for more than 2 days with SW that Foxconn provided. There is no issue, but ALT will keep test it for a week. 2. Tack Switch spec. change : ALT is reviewing it. ALT will inform what ALT think later on mantis. [Fii 0922] 1. The test SW has been provided by River on mantis 1506. How about the test result in ALT side? 2. Can ALT accept the tact switch spec. change to 160 +50/-30gf? [0916] ALT got another Ethernet unstable STB from the inspection. If FII provided test SW, then we will check it. [Fii 0915] 1. Ethernet unstable issue: 1-1. Ethernet unstable- Fii has finished 2 NG PHY and 1 OK PHY each 12hrs high (50˚C) / low (0˚C) ambient temperature test using value 0x60 of SOC internal delay. Test result are pass. 1-2. The long time stability test also has started. There are 2 NG PHY and 1 OK PHY are completed and passed. The rest test will be completed by 9/23. 2. Tact Feeling is not good 2-1 The current supplier FIT can sort the tact switch with 160+50/-30gf component. If SKB only concern about the press force is too lightly, and we think the current FIT's component can be acceptable. 2-2 The datasheet of new tact switch (+/-30gF) has updated to mantis.(mantis:1493). => 내부 검토 후 알려줄게.. Pin configuration이 같은지는 Foxconn이 검토하여 알려주겠다. [0908] Ethernet - Foxconn is testing 12 DUTs now. It takes 1 day/1pcs. ALT asked to conduct this test in parallel at the same time. Foxconn will check it with SW engineer and provide test schedule by today. Tact Feeling is not good - ALT can accept +/- 30gf press force torrence. Foxconn will check the cost and sample delivery with vendor. After receiveing the cost information and sample schedule, Foxconn will update it to ALT. Powerway is in QVL. [Fii 0907] 1. Ethernet Unstable - Fii have found out the middle value(0x60) for SOC delay winodw of 10 good DUTs. The results have updated to mantis(1493). Next will long term to test with 0x60 for CRC error test. 2. Tact feeling is not good -> Have updated the structure of tact switch on mantis for why the vendor only can provide +/-50gf switch. The material of switch is metal dome or spring which is limited by material spec. It looks like the press force +/-50gf is a standard spec. for the switch type we used in SWAN. -> Only one vendor (Powerway) reply that they can customize +/-30gf based on the current mold. Need to discus with ALT if +/-30kg press force is acceptable? [0901] 1. Foxconn will share their test result with both SOC and Realtek. SoC and Realtek already review Circuit diagram and PCB layout when Foxconn developped SWAN. There is no issue, but it need some tune normally. Foxconn will add delay and fine tune with SW Engineer. It will be updated soon. Foxconn thinks that it is related compatibility. So there is no need to exchange defected part to Eagle and test. Foxconn will check compatibility issue adn suitable setting with SW Engineer, and feedback it by this week. 2. Foxconn contacted 2 other vendors. Foxconn can update its test schedule in this week. [0831] 1. Ethernet Unstable - Fii have updated the RGMII timing measurement & SoC CRC windows fine tune report on mantis 1493. Measure the PHY IC delay waveform, no.1 NG PHY IC is 167ps; no.2 NG PHY IC is 442ps with 0ns RX delay pull high resistor. No.1 NG PHY IC is 1.733ns; no.2 NG PHY IC is 1.879ns with 2ns RX delay pull high resistor. They look normal compare with good PHY IC. Fine tune SOC delay window is no.1 0x06~0xB0, no.2 SOC delay window is 0x1E~0xAA. The no.2 NG PHY IC which SOC delay window is narrower than no.1 NG PHY IC. Will test middle SOC delay window value to good PHY IC board for long time test. 2. Tact feeling is not good - We are surveying FXN QVL vendor for +/-20gf torrence switch. [0826] LED issue - Foxconn will update any corrective action from vendor. Tact feeling is not good - Vendor cannot change its specification and handle press force that ALT asked. ALT worried that this tact feeling is handled by operator only in manual. Foxconn TW will discuss with VN Factory and their plan for next step will be informed by next week. Ethernet Unstable - There are 2 defect units. Foxconn TW and Realtek both have one. Factory already have sorting method for it. ALT asked Foxconn to update the no. of defect units of this issue after 1K additional production now. Foxconn is discussing with Realtek to handle this issue. ALT asked Foxconn provide timing information(RGMII CLK/Data) with various condition, such as, no delay, 1ns delay and 2ns delay. Foxconn will do and inform to ALT after test. [Fii 0825] 1. Fii QA have updated the 8D report on mantis 1493 for LED no light issue & power button feeling NG issue. 2. For Ethernet unstable issue, Fii RD tried to add 2ns RX delay on Eth. PHY and the CRC error will improve but it's still not zero. Fii SW RD tries to add 1ns delay on SoC and the CRC error improve to zero. 3. Fii will work with Synaptics and try the Eth. RX delay parameter to find the best solution. [ALT 0819] Status update ? Ethernet Unstable : Foxconn VN Factory received defected part and tested again. It passed on VN Factory test. Foxconn VN Factory sent it to TW and Foxconn Taiwan tested it again. But they found CRC error. Foxconn TW thought it about SoC compatibility issue. Foxconn TW sent its test report to SoC, Realtek. Foxconn will have conference call today afternoon. After conference call, Foxconn will update about SoC feedback. ALT had 3 defected unit, no ethernet 1 pcs, ts loss 2 pcs. All defected units already sent to Foxconn Factory. So ALT doesn't have it. Tact feeling is not good : Foxconn will provide feedback on tact switch push force spec from +/- 50gf to +/-20gf by 8/19 [ALT 0812] MP issue on May,2022. Mantis # 1493 is for MP issue in May, Mantis #1506 is for MP issue in June. Move report from #1506 -> #1493. LED Not work - LED Defect, Corrective action had been applied from 4/23. Until apply auto test, operator check it manually. Ethernet Unstable - Foxconn received Realtek's FA report yesterday night and it uploaded on Mantis. There is no abnormal in vedndor's FA. They think it is NTF Foxconn will discuss about this issue with Realtek first and update what the next step is on Mantis. No sound - There is no issue when they assemble defected AMP b'd. Foxconn think that it is NTF even though some resistors were changed by vendor. No boot - No screen after booting animation(SW issue) Cosmetic damage Screw assembly Tact feeling is not good : Foxconn will update below items by 8/12 Standard tact Switch Tension Measurement value of the defected tact switch tension in both part level and assembly level [Fii 0811] VN QA had update thte 8D report for LED not work. [Fii 0804] VN QA had provided updated 8D report to ALT review on 8/4. [Fii 0714] Factory said vendor is still analysis and will update on 7/16. [Fii 0707] Factory will send the report on 7/11 [ALT 0630] Issue up the BFX-UA300 MP delivered on 2022.05 inspection result on 6/13, but still No update https://mantis.cnsbg.foxconn.com/vaas/view.php?id=1493
Quality | [SWAN] [MP] 2022.01-03 Mass production inspection report | FII | close | 2022-07-06 | [1020] Silergy defect chip has EOS, so there is error on data write. But it is too small to find the defect after decap. But Silergy add some Data RW test in their ATP. [1014] Silergy provided their FA report. Silergy cannot find any abnormal after de-cap. So they reported the root cause of issue is related to EOS. But Foxconnn need more discussion with Silergy why they think. Foxconn will have meeting with Silergy and update their discussion on mantis with Silergy FA report. [0930] Silergy will give their report by 10/12. China has long holidays early of Oct. [0923] Foxconn get FA report from vendor. Vendor suspected the mico-crack on the component level. Vendor will check micro crack after de-Cap. Vendor's ATE test is not enough to check current issue. They think that I2C read has issue and it is root cause of this issue. Foxconn will share new FA report from vendor ater the meeting. [0916] Test result or plan ? Foxconn Factory received review report from silergy, but it is not enough. They will discuss more. [0908] PCBA arrived to silergy yesterday. Foxconn Factory will check the test schedule and inform it by next monday. [0901] Foxconn provided PCBA with defected component last Saterday. It will arrive today in Silergy. Foxconn keeps updating its status. [0826] Silergy sent right part to Foxconn Factory. Foxconn PE send wrong picture for defect sample. So it made some mistake. Foxconn will send PCBA to Silergy with defected component by tomorrow. And Foxconn will explain what Foxconn factory did on mantis detail for ALT understanding [Fii 0825] The VN factory has clarified that the IC sent back by the supplier is a defective unit, and the factory PE inspected the fault symptoms and confirmed that it is a defective unit. [ALT 0819] Foxconn VN Factory received defected unit from vendor, but it is not the part that Foxconn sent to vendor. Foxconn will ask vendor to find the part that Foxconn sent before. ALT ask to improve the RMA process not to happen again this situation. Foxconn will discuss internally and make some process and feedback to ALT soon. [Fii 0818] VN factory already received Silergy IC yesterday, and SQE has sent IC to Bac Giang factory for I-V analysis. Our PE will do further analysis on this IC after I-V analysis. Vietnam QA will update the report on mantis1465 on 8/18. [ALT 0812] Silergy found out the part that they test for defect analysis. Silergy already sent chip to Foxconn. It will take about 10 days. Foxconn VN PE will start analysis more. ALT will check this issue and will ask some tests on mantis when they need any other additional tests. [Fii 0804] For Silergy IC issue, QA will ask vendor to send back the defect PCBA for further analysis. [Fii 0714] Factoy will check and reply. Keep updated. [Fii 0707] Factory provided report on 7/1 [ALT 0630] Issue up the BFX-UA300 MP delivered on 2022.01~03 inspection result on 4/19, but Only the initial analysis was reported. https://mantis.cnsbg.foxconn.com/vaas/view.php?id=1465
Sales | [SWAN] Extra Product, PCBA and Spare parts for RMA | FII | Close | 2022-07-30 | [0901] Close [0826] ALT need some additional information for customs clearance in Korea. Foxconn will provide it after meeting. [ALT 0811] Factory already sent document for customs clearance . The ETD is 8/16. The receiver information will be updated after weekly meeting. [Fii 0714] 1. Extra Product(0.2%) : 60pcs -->Factory will ship on 7/29 2. PCBA(0.2%) : Main, Amp, LED, Side LED R, Side LED L, Mic, Button – 60set -->Factory will ship on 7/29 3. Extra Spare parts -->Factory will ship on 8/12 [ALT 0630] According to the SOW agreed by both parties, please provide the available date of delivery of extra products, PCBA and spare parts for 30K demand in 2021. 1. Extra Product(0.2%) : 60pcs 2. PCBA(0.2%) : Main, Amp, LED, Side LED R, Side LED L, Mic, Button – 60set 3. Extra Spare parts
Quality | [SWAN] [MP] 2022.06 Mass production inspection report | FII | close | 2022-07-29 | [0901] Foxconn already finish test. Foxconn will provide test report by next Monday with CRC Test result. [0826] ALT already give Go sign to Factory. There is no additional acceptance to produce 1K more. Foxconn need additonal GO sign for additional production after 1K production. But ALT asked Foxconn to discuss with ALT Biz team one by one. [Fii 0825] Fii QA have updated the 8D report on mantis1506 on 8/25 [ALT 0819] ALT didn't review about it. ALT will review and leave comment on Mantis if necessary. [Fii 0818] Vietnam QA Toney will update the 8D report on 8/18 for ALT review. [ALT 0812] . No boot : root cause - short 24V pin touch heat spreader and connected GND. Foxconn RD prepare test SW and it's Guide. Foxconn VN will test with defected unit after FII RD eng. provide test guidance and SW. . No ethernet : There is no issue on vibration and strain gauge test. And close it. ALT asked Foxconn not to change its status to closed. It should be ongoing. Foxconn will have internal discussion and will leave action items to analyze this issue. ALT had 3 defect units out of 630 pcs. SKB is inspecting the 4K LOT that produced in june. . Ethernet unstable - RMA report from vendor on 8/12 . HDMI Cable Cable stock(FIT 20.088, Aboard 30K, CNSBG 17,309) => Vendor already sorted FIT/Aboard stock. There was no defect cable. There is no FFC cable that had same LOT no. to defected unit. [Fii 0811] 1. For soldering issue, the SoC pin crack & EOS test method has been provided on mantis 1506. 2. For no ethernet isue, the strain gauge test result showed it's normal and the vibration test of 2 carton didn't found defect. [Fii 0804] VN QA had provided updated 8D report to ALT review on 8/4. [Fii 0728] VN QA manager Qing-Bo will send the initial version of 8D report to ALT review on 7/28. [Fii 0721] The fail analysis is on-going now. Please see current FA status in attached file.
Quality | GPIO issue(mantis #1468) | FII | open |  | [Fii-1117] Synaptics FAE reply SOC ID can be read in the console log but we cannot found the keyword RKEK_ID in console log. We will continue to work with Synaptics on this issue, and update the status by early of next week. [1111] ALT asked to replace all defected SoC even if FII cannot reproduce GPIO issue in their Factory. Foxconn should provide how ALT can check the SoC chip ID. Foxconn will check with SW or Synaptics and comeback soon. [1104] Foxconn will check the process for PCBA RMA with Factory. Foxconn TW think that it is complicated and need time. [Fii 1103] The factory has checked the production record and confirmed that these 19pcs samples were all produced normally without rework process before. [Fii 1027] Got GPIO list from SH. Will provide this list to factory QA to check the production records first. [1021] GPIO issue is caused from SW and HW mismatch. So ALT asked Foxconn exchange defect units to new one. It is design issue so it is not managed RMA contract. ALT will send detail information about defected units. ALT asked Foxconn to replace defected PCBA to new one without any cost, include delivery cost. And to change factory firmware and customer firmware, Foxconn factory should do control run and OTA test. After test, Foxconn should share the result with ALT. [Fii-1020] Current software version of changing register for improvement EOS should be QT.19.534.26. RD has provided this version of image to Fii factory for verification. [1014] Foxconn doesn't want to upgrade SW on defected unit that Foxconn asked on mantis. Foxconn prepared new Factory SW that applied changed register value for improvement for EOS. ALT thinks that Motorcomm ethernet PHY can use after find the root cause and soltuion about ethernet disconnection issue. Foxconn think that 2nd source introduction is not urgent except Hynix DDR4 8Gb Die change. [Fii 1013] Software version of both units are QT.19.531.20. The software version fix VDDIO6/VDDIO9 register values is QT.19.536.26 which also pass google 3PL certification. Will check whether apply this register set value on Factory SW by 10/14. [1007] ALT had 2 more defect unit. And ALT received 2 RMA report from Synaptics. ALT uploaded it on mantis(#1468) Foxconn will check whether they apply this register set value on Factory SW and feedback to ALT. [0916] Cross section. Foxconn doesn't have defected unit. So we cannot take photo higher magnification. Next time we can do it. The Photo that Mr. SH Son's requested cannot be provided because Foxconn doesn't have defected unit now. [0908] ALT left some comments on mantis(#1468). Foxconn will check it after meeting and update it later. [0901] Foxconn is collecting the photo now. Foxconn will provide photos by next monday afternoon. [0826] Foxconn Factory will follow up ALT's additonal request for cross section test result. [ALT 0819] Cross section data was updated this morning. ALT will review and leave comments on Mantis next week if necessary. [Fii 0818] Need Vietnam QA/ME provide status update on the cross section report - Any update from Lab. about adding all of row picture and pin number? - Is is possible to attaches the high resolution image files? [ALT 0812] ALT reviewed test report on Dye and Pry, Cross section. ALT left some questions and comment on mantis #1468 Foxconn will check and update soon.

## Eagle
Category | Issue | owner | status | due date | Progress
PM | Eagle additional sample (w/ DIODES, 3PEAK 2nd source) | FII | close | 2021-08-26 | [Fii 0901] VN will ship out 20pcs DUT to Taiwan on 9/1. ETA date will be 9/9 because VN is in holiday during 9/2~9/5. Reliability schedule is under checking with HWQA. [Fii 0827] ALT require to run 100% aging test (100pcs) on control run. However, ALT also require CFT to ship out 25K by 8/31. =>CFT will ship out the shipment first and go back to run aging test. Expect to run aging test from 8/31. After CFT complete the againg thest test, will deliver 20pcs to Taiwan. [Fii 0825] CFT will deliver out 20pcs to Taiwan RD team by 8/28. [Fii 0820] According to the requirement from ALT RD, the sample that ALT required is 20pcs. MFG is checking when they can ship out 20pcs because normal shipment is the first priority.
HWQA | Reliability testing for 20pcs (w/ DIODES, 3PEAK 2nd source) | FII | close | 2021/9/24 -->10/15 | [ALT 1013] Approved for 2nd source Diodes+3Peak phase in. [ALT 1001] Will feedback next week. (mantis#1321) [Fii 0924] Reliability test report provided on Mantis, need ALT to agree to phase in. [Fii 0903] Target testing period: 9/18 ~ 9/21. Target to provide the testing report: 9/24.
Sales | Eagle RMA carton | ALT | close | TBD | [Fii 0305] Factory provided RMA report for ALT review. [Fii 0224] Factory team is handling RMA. Traget to complete RMA by 2/25 and provide FA report on 2/28. [Fii 0119] Factory PM provided RMA schedule. 1/26 ETA VN factory, target to finish RMA and ship to Korea around 2/15. [Fii 0113] Factory PM William will handle the following process. Currently waiting for logistics team to confirm the vessel schedule. [ALT 1224] ALT shipped 1st carton of RMA DUT. [Fii 1215] Factory provided the RMA rules. [Fii 1210] Factory is checking the RMA shipping requirement internally, will update ASAP. [Fii 1123] Provided judgement from package RD. [ALT 1118] ALT provided another solution from Korea--> Fii will check with package RD for suggestion based on the information provided. [Fii 1104] Due to custom policy, need ALT to purchase directly from YUTO(package vendor). [Fii 1022] Checking the final cost and process(customs policy) at factory side, will feedback ASAP. [ALT 1020] confirmed to issue PO for Fii to purchase the carton from VN(by vessel) [Fii 1012] Provided solutions and need ALT to finalize the decision and execute ASAP. Please be aware of the warranty period. [ALT 1008] ALT feedback the cost and spec form korean vendor. [ALT 1001] Will feedback next week. [Fii 0909] Fii provided shipping cost (sea/air) from VN to ALT. Wait for ALT's decision. [Fii 0903] After checking with Fii sourcer and logistics members: Shipping cost from VN to Korea is much higher than Carton cost. --> Fii provide drawings and ALT will check with suppliers in Korea [ALT 0901] RMA >6000pcs, will check exact quantity after the meeting--> Till 9/3 Total 3107pcs [Fii 0825] Fii will disucss the expense internally and propose to ALT. Package test estimates to be finished on 9/10; [Fii 0820] Under packing reliability testing at Fii site.
HW/PM | New RCU (Mantis #1344) | ALT/FII | close | 2021-09-24 | [Fii 0930] As the old/new RCU will both exists, need ALT to clearly instruct which batch to ship with new RCU in the future. [Fii 0922] New RCU PN provided (Mantis #1344) [ALT 0915] Update datasheet for new RCU [Fii 0908] Fii will apply for new PN and check how factory can control it. CE team asked to provide high resolution datasheet. [ALT 0908] ALT informed to introduce new RCU for Eagle adding Smart TV control function.
PM | EPD certification | ALT | close | TBD | [Fii 0117]Factory PM An already feedback the factory visit question. [ALT 1123] Request to provide more details of pallet packaging info. --> provided [Fii 1118] Electricity consumption data provided to ALT. [Fii 1111] Factory will check internally and collect data. (Target to provide next week) [Fii 1110] Factory requested ALT to provide english template form for them to fill in the electricity consumption data required. [Fii 1104] Need Steve to send out an official request mail for EPD certification. And please list the information and document needed with template to fill in.
HW/PM | 2nd source (Eth PHY/BT/IC) (Mantis #1353) | ALT/FII | Pending | TBD | [Fii 0421] The CRC and autonegotiation test report has been provided to mantis #1459 on 4/19. [Fii 0414] Fii QA team is working on the CRC test now. And the report can be provided by next Tuesday (4/19) [Fii 0408] 1. Motorcomm YT8531C: waiting for BMT. [Fii 0331] 1. Motorcomm YT8531C - Samples already shipped out. - Need ALT to confirm BMT schedule. Fii would like to introduce this materail from 5/1. [Fii 0324] 1. Motorcomm YT8531C: Will ship out on 3/25. 2. Ampak W511: stop the development due to SKB reject to use Ampak W511. [Fii 0317] 1. Motorcomm YT8531C : VN is running control run. Will ship out the samples by 3/23. 2. Ampak W511 - SW progress for BT compatibility: Samples arrived at AML China office. However, due to China government policy for COVID19, they cannot enter into their office for analysis. - SKB comment: SKB reject to use Ampak W511. Cypress still in critical shortage isse. [Fii 1216] As Movon is not Fii QVL, Fii will introduce Ampak as 2nd source. [ALT 1215] Foxconn can decide to use Ampak or Movon for BT 2nd source. [Fii 1119] ALT feedback to make decisions on BT module by next Monday.(11/22-->12/7) [Fii 1111] Have reviewed the MOVON's datasheet. The module size is about 1mm wider than AMPAK module but the current space can still be placed in. We don't have questions to using this module in Eagle. [ALT 1110] ALT suggested BT 2nd source (Movon(MD-BRC101)) [Fii 1104] EFUSE 2nd source Toshiba cannot provide samples for verification. [Fii 1022] Fii provided cost to Steve, wait for update. [ALT 1015] ALT will discuss internally if accept Fii rule for test samples. (4pcs for reliability test and 100pcs control run) [Fii 1014] Tiffanie will discussed about the cost with Steve. According to Fii's rule, we need 4pcs for reliability test and 100pcs control run in the factory. For the phase in plan, we will arrange 2 rounds introduction. 1st round (pin to pin): IC 3peak TPV809S-3TR ETH PHY Motorcomm YT8531C 2nd round (re-layout): EFUSE Toshiba TCKE712BNL BT Ampak W511 [ALT 1008] Need Fii to provide the phase in plan and cost liability. [Fii 1007] Need ALT to agree with the 2nd source introduction ASAP (except for BT module) [Fii 1001] For ETH PHY Motorcomm, as it is not QVL material, Fii will need ALT to designated Motorcomm as 2nd source via email if the reliability and control run passed in order to apply for Fii PN. [ALT 0924] Please check who will pay the new certification fee and test. [Fii 0917] Update comparison datasheet on Mantis. Need ALT to check and officially confirm to start the phase in process. [Fii 0915] Due to the long LT of current materials, please check below suggested 2nd source.
SW/PM | SW upgrade | ALT/FII | close | 2022-03-01 | [Fii 0223] RD applied EC to introduce new FW based on parties conclusion. [Fii 0214] Eagle: control run from 2/15. providing report by 2/18. SWAN: control run from 2/16. providing report by 2/19. [Fii 0210] Factory will do control run after MP shipment on 2/14. Target to introduce the new SW from March.
HW/Sales | BT module issue | ALT/FII | Pending | 2022-03-28 | [Fii 0331] Pending due to parties biz team have not reach the conclusion. [Fii 0324] 1. We heard from Sales team that ALT will going to propose Movon's BT solution to SKB and move it to B/S if SKB accept it. Need ALT to update the current status. [Fii 0317] 1. ALT inform Fii that SKB doesn't agree to use AMPAK W511 module since SKB concern about BT change, and would like to keep BT chipset as it is. 2. Need to find another way to solve it.
Quality | CS materials for out of warranty | FII | close | 2022-07-06 | [Fii 0714] Fii has provided on 7/14. [Fii 0707] There are 3 material which need sourcer to maintain price, due date:7/11 [ALT 0630] SKB is request the CS parts below for out of warranty STB . Please let us know the quotataion and lead time and MOQ. - Each part can be requested separately - LD1301, U301, U302, U303, U30, U307, L1001, T801, J801, U1402, D901, U1401, U801, U306, Q1001, Q1002, Q1103
Quality | FA report | FII | Close | 2022-07-06 | [Fii 0707] Factoy will check and reply. Keep updated. [ALT 0630] Issue up the BFX-AT100 defected units from incomming inspection end customer on 4/19, but Only the initial analysis was reported. https://mantis.cnsbg.foxconn.com/vaas/view.php?id=1484
HW | Test plan of shielding removal | FII | OPEN | 2022-08-12 | [Fii 1201] 1. The thermal chamber are full occupied by other projects until mid. Dec. Have asked QA team to pull-in the schedule and will keep ALT informed abuot the confirmed schedule. 2. The old software version that will be used for testing is 15.502.13 [1125] ALT asked to provide the plan for thermal test with INTEK STB. ALT will provide old SW version that DVT thermal test used. Link is as follows. https://drive.google.com/file/d/1xz1jR9QQMqmpp_52kYvz864BdFm6Q2eh/view?usp=share_link [Fii 1124] According to the vmstat result provided by ALT. It seems the result is different from what I expected because the CPU load of A10 (v15.522.9) is higher than A9 (v15.502.39), and it means the temperature of A10 should be higher than A9 but our thermal test result is just opposite. [1118] ALT asked the cost difference between with and without shield can. Foxconn's explanation is not enough. So ALT asked to provide the cost for Shield CAN components and thermal pads each. Foxconn will provide it to ALT Biz side. ALT provided test result to SKB in this week. Once ALT receive the review result from SKB, then ALT will feedback to Foxconn ASAP. [Fii 1110] The reliability test report has been provided to ALT on 11/7. Need ALT/SKB to approve for the change, and then Fii will arrange the control run & EC to implement the change. [1104] Foxconn can provide test report by next week. [Fii 1103] The test is in progress without any issues. It can be finished by 11/4. [Fii 1027] The reliability test of HFC & TIANMAI 1.5W Thermal pad has been started from 10/26, and will be finished by 11/4 [1021] ALT needs reliability test result. Foxconn will share test plan by today. If ALT has any question or request, then let Foxconn know. ALT didn't receive mechanical dimension information for 1.5W yet. ALT needs update cost information with final spec. Foxconn will inform it later. [Fii 1020] The related info. (datasheet, electrical diagram, mechnical dimension..) of both HFC&TIAMAI 1.5W thermal pad has provided on mantis on 10/19 [1014] We are preparing the document for SKB. [1007] We will contact to SKB with your report and ALT will update on mantis on SKB's feedback. [Fii 1006] The reason for the 5W thermal pad temperature difference has been left on mantis 1499. If 5W test result is just a reference, shall we just provide 1.5W & 3W test result to SKB? [09/30] ALT ask Foxconn why SoC temperature with 1.5W and 3W thermal Pad was lower than with 5W thermal pad. Foxconn will verify more and feedback to ALT. ALT asked Foxconn to provide the photo of test equipment setup or pictures that ALT can understand the test environment. [Fii 0929] 1. Fii have updated the 1.5W test result on mantis 1499. Fii recommanded to use 1.5W thermal pad to have more margin on housing, and the SoC also has enough margin. Needs ALT to review it and confirm which solution should be applied in Eagle project. [0923] Foxconn is testing with 1.5 W thermal pad for both TIANMAI and HFC. Foxconn will share the test result. [Fii 0922] 1. We already sent thermal test result of the new 3W thermal pad (HFC) on mantis 1499 for ALT review. The result is similar with TIANMAI (slights better). 2. The 1.5W thermal pad test has been started. The result can be updated by next Tuesday. [0916] Thermal test will be finish by next monday. Foxconn will test 3/5W first and 1.5W later. Foxconn can provide test result by 9/21. [Fii 0915] The thermal test will start on 9/16. Fii will update thermal test result by 9/21 [0908] Foxconn will keep updating on the status. [Fii 0907] 1. Have received the new thermal pad samples from another vendor HFC. We will arrange thermal test on 9/19~9/23 because the thermal chamber has been occupied by other team nex week. [0901] ALT accepts the EMI Test result without shield can. Foxconn will update test schedule and result by this week. [Fii 0831] 1. We have requested 3W&5W thermal pad samples from another vendor(鴻富城) and the sample will be arrived in our office next week. Will arrange the thermal test again when received samples next week. 2. Can ALT accept the EMI without shield test result in Korea Lab.? [0826] ALT think that the margin for Thermal test result(0.9 ℃) for Top case is not enough now. So ALT asked Foxconn to find another vendor who can provide better Thermal pad. ALT prefer not to use didn't accept to use Shiuli thermal pad. Foxconn is looking for another vendor now. It will be update Foxconn's acitivies next week. ALT will test EMI without Shield can today. ALT will update its test result after the test on mantis. [FII 0825] 1. Thermal pad datasheet has been upload to mantis. 2. The antenna performance test can be completed by 9/2 due to the chamber is full occupied this week. Fii can provide the report by 9/6. 3. Have provided thermal test result to ALT review. The SHIULI's thermal pad only pass with 0.1degC margin but ALT think it's not enough to cover the variation. Fii suggest to reduce K value to get more margin but SoC & buttom cover temperature may increase a bit. 4. Need ALT to update the EMI test result in Koread Lab. [ALT 0819] 1. ALT arranged EMI Lab next Friday. 2. Foxconn will provide thermal pad data sheet and antenna test schedule by later today. 3. ALT asked Foxconn to provide thermal test result both with shield can and without shield can. Foxconn will check it their QA and feedback it next week. [Fii 0818] 1. Fii think that the failed frequency seems doesn't come from our box. We suggest ALT to change TV in Korea Lab. to see if result can be improved. 2. Will update the thermal pad datasheet and antenna test schedule to ALT later. 3. For thermal test, I think SKB have waived the requirement of temperature raising within 15degC at housing bottom in Eagle project. So, can we just removed the housing bottom test result from the report and update it to ALT? [ALT 0812] ALT already share test result on mantis #1499. But we have issue on low freq. range. But ALT should review more and feedback to Foxconn. Foxconn will share it to their EMI Engineer. [FII 0811] 1. BT sensitivity has been provided to ALT on 8/5. Need ALT to review and approval. 2. Thermal test & reliability test are completed by 8/11. The test result are passed. The report can be provided by 8/15 3. 10M chamber EMI test - waiting test result from ALT's Lab in Korea for further action. [Fii 0804] 1. BT sensitivity test - completed, the sensitivity distance can reach 20M+ after remove shielding cover 2. 10M chamber - We had verified RE on 8/3 but found one fail point at 890MHz, (horizontal mode Peak: +1.09dB, QP: +0.21dB). We found that the EMI is radiated from HDMI cable. We can continue to debug in 966 but we suggest ALT can perform EMI in Korea site in parallel since there might be environment difference in TW & Korea, and we should get EMI pass result in Korea chamber in order to get the KC certification. 3. Thermal test - 8/12, changed new thermal pad (thickness = 4mm)
SW/HW | Passive Standby | FII | Close | 2022-08-26 | [ALT 812] Eagle. Current SW has issues related to wakeup. It caused by ramdom timer in BL3.bin. Foxconn already received new patch from AML. It will test today. The boot issueis no ethernet after passive standby. ALT need test SW to measure Passive standby power consumption. Foxconn can provide after apply BL3.bin patch. SWAN - Wake lock, Currently Foxconn have SW issue on passive Standby. If LED is on, then Power consumption will be increase. ALT needs test SW. ALT will measure passive standby power consumption. Foxconn will let ALT know when Foxconn can provide test SW. [Fii 0811] Will need SW team update the status in weekly meeting
SW | Motorocom Eth disconnection issue | FII | Close | 2022-08-26 | [1028] ALT suggested to close this issue. If Foxconn asked to review Motorcomm issue again in Eagle, then it will reopen. [1021] Foxconn will not investigate anymore for eagle. Foxconn will use Motocomm PHY for next gen. eagle. [1014] ALT can reproduce this issue with ECO that FII proposed. ALT shared the video clip on mantis how ALT can reproduce it. [1007] ALT is trying to reproduce this issue with auto test environment. But ALT cannot reproduce it for a week. ALT is trying to find the sequence of reproduction. Test condition (connection/disconnection time, minute) : 5/10, 5/3, 1/1 with 3 units. [0930] ALT tested again without rework and reproduce the issue after 5 days test. ALT set up auto test environment today. ALT will start test from today. But ALT cannot sure Foxconn's solution even though the issue cannot reproduce during the teset. To confirm the solution, ALT needs technical explanation why Foxconn's solution can solve the issue and what the root cause is. [Fii 0929] Any update from ALT about the test result of rework solutions provided by Fii? [0923] The rework guide is not the same as before Foxconn asked ALT to test. ALT will check the guide and try to test it. If ALT has some question on your test and rework guide, then ALT will leave some comments on Mantis. [Fii 0922] We will provide hardware rework to ALT reference. Can ALT check to see if the reproduction rate can be improved? [0916] Foxconn didn't finish the review of this issue yet. But ALT cannot apply 2nd source when 2nd source Eth PHY has some issue. ALT tested with SWAN but ALT cannot reproduce with SWAN. So ALT will check SWAN after enagle debugging result again. [ALT 0812] Foxconn add some log and released test SW. And Foxconn tried to reproduce this issue, but failed. ALT thought that Foxconn didn't test it enough. It need to test more than 3 hours. ALT tested with different 3 STBs. but ALT can saw the issue. Foxconn should increase test time. ALT will test with new SW and feedback it by 8/16. [Fii 0811] Will need SW team update the status in weekly meeting
| GPIO Setting voltage |  | Close | 2022-11-25 | [Fii 1124] 1. Fii has provided GPIO value of Eagle/SWAN via e-mail. Please kindly review it. [1118] ALT provide an e-mail to check the GPIO setting voltage. Please check and support us with your HW/SW for both SWAN and Eagle

## Pre-MP issues
Open issues for 100pcs pre MP=>check if possible to pull in to ETD 6/25?
1. Thermal issue -
1.1 ALT request to reduce 50% speaker volume, the total AMP power changes from 7.7W to 4W, no additional venting hole, both AL & VC HSR @ 25degC & 50degC ambient can pass criteria of all components but the housing surface are still marginal fail.
1.2 The thermal solution of VC is the maximum limit for the current design. The temperature of all components can be passed based on VC solution with maximum AMP power but the surface temperature are still marginal fail.
1.3 Fii will arrange the real case thermal test based on DVT3 sample but that mean Fii don't have enough time to implement any solutions if we need to shipped 1st 100pcs sample by June.
1.4 Thermal solution should be fixed within this week for MP demand. The heatspreader sample price is very expensive and the capacity will not be able to meet 4.9K demand later.
2. DREAMUS Speaker
2.1 100pcs will use the same speaker as DVT3?=>not yet finalized
2.2 Need the comparison of old and new speakers to evaluate the impact.
3. Test
3.1 Reliability will not be able to complete before shipment
3.2 BQB and HDMI pre test doesn't have enough time to go through completely
4. Material
4.1 MP PO was provided late on 4/19. Fii only prepared the materials with long LT(greater than 90days) excluding AMP boards with new design. Will need to check with vendor if possible to meet the target. If not, will need to buy from spot market. The same for MP order later. | WK5/3給出那些物料需要採買現貨，提供清單給ALT
4.2 ALT controlled parts such as DREAMUS speaker, INKEL housing, Wellang amplifier (also need ECAP) should ETA VN 6/9 =>need to check with factory for the ECAP qty , if enough for 100pcs??
5. SW
5.1 OTA function on A113X should be ready by 5/14
6. Selling price related to payment
6.1 The final quotation is not fixed yet.
7. EMC
7.1 The system RE/RS/CE is being tested and debugged with new AMP board. Even if we use the latest speakers and enhanced FFC cables for testing, but the housing is not the final one, which means that the cable routing will not be the final setup. and this may bring some risks when using DVT3 sample for certification.=>need ALT to send out the DVT3 housing sample ASAP
7.2 There are some venting holes in the DVT3 housing, which may cause the risk of ESD failure.

## AMP board R&R
AMP board (AML A113X & Wellang) R&R
Items |  | ALT | FII | Comments
SW | Source code management
| -Source management System | O |  | Git : http://altserver01.iptime.org:8282/
| -Build Development environment | O | O | What support is needed from Fii?? [ALT] FII make develop environment in FII side
| -Develop Bootloader | O
| -Develop Main SW in DSP include Audio weaver porting | O
| -AMP control function |  | O
DSP B’d Bring up
| -I/O Port set (I2S, I2C, USB etc) | O
OTA
| -Build OTA server | O |  | Should be discussed with SKB
| -Develop OTA download APP for DSP B’d – VS-550 side |  | O | Same way to RCU Firmware update method
| -Develop Image Transfer(to A113X) | O | O
| -Develop Image update (bootloader) | O |  | Download certain area of NAND and it will be updated when DSP b’d reboot
Audio I/O Implementation
| - Develop I2S path : I2S input port -> DSP -> I2S ouput port | O
I2C comm
Implement I2C Slave – DSP
| -Check comm. status | O
| - Implement command list | O |  | check if all A113 command list is implemented by ALT; what is the difference between the command list for DSP and VS550
| -status check | O |  | [ALT] For example, we need below functions to run reboot.
| - Reboot | O |  | VS-550 asked DSP to reboot, then the command function should be implemented VS-550.
And the commands for receiving command and reboot in DSP should be implemented in DSP side
| Implement I2C Master – VS-550 |  |  | So, FII implement SW in VS-550, and ALT implement SW in DSP.
| -Check comm. status |  | O
| - Implement command list |  | O
Function for Mass production
| - A113 Status Check | O
| - Firmware release for MP | O |  | We should discuss which format FII need for MP.
| Share Data |  |  | Is this A113X source code? What's the purpose of this item [ALT] source code share is more efficient to understand each others. It is an language for SW development side.
- Source code
- Development environment
HW | Circuit design | O
| PCB Artwork – for DVT3 | O
| For MP | O |  | [ALT] We would like to devide R&R for development(ALT) and MP(FII) of AMP B'd. But if you want to provide Artwork for MP from us, then please share the cost of PCB for MP.
| Bring up | O
HW Test
AMP Performance test
| -Max. Power | O
| -THD+N vs. Freq.(1W) | O
| -THD+N vs. Freq.(Max. Po) | O
| -Max. Hum noise(Output Noise) | O
| -Min. Hum noise(Output Noise) | O
| -SNR@ Max. Power | O
| -Frequency Response | O
| -Cross talk | O
Etc
| - Thermal |  | O
| - EMC |  | O
| Share Data |  |  | What about this column? It means the data will be provided by ALT? [ALT] We can provide it if you want. I think it is for time saving.
Circuit diagram
Gerber data(DVT3+MP)
AMP performance test report
Components datasheet
Data for production