## Smart4
Category | Issue | owner | status | due date | Progress
HW | IO order swap request | FII | open | 2024-07-10 | [ALT_0710] ALT will provide SKB's opinion about I/O order by today. [Fii_0709] Base on the IO order confirm by ALT, the USB/HDMI/Ethernet routing are cross by each other, need to confirm is we could tune the IO order(swap USB and Ethernet) for layout easy and reduce PCB layer?
HW | MiPi CSI connector pin define | FII | open | 2024-07-12 | [ALT_0710] ALT will provide the pin definition by today. [Fii_0709] ALT have been reply the MiPi CSI connector pin define to follow-up pin map as S905X5 reference circuit, but the Mipi CSI connector which ALT appoint is difference with S905X5 reference circuit, please help to confirm.
Sales | Cost up for 84*84mm PCB | ALT | open | 2024-07-10 | [ALT_0710] Please provide the cost information and gap between Eagle and Smart4. (SoC, Memory, Amp and Mic., PCB, Housing, etc.) It would be very helpul to provide Fii quotation ASAP. [Fii_0709] The cost between Smart3 and Smart4 is more than US$30. Is it acceptable for ALT and SKB?
ME | Height of housing | FII | open | 2024-07-12 | [ALT_0710] ALT is checking a speaker unit with a 3mm lower height compared to the current unit. Please help to design the entire product to have a height less than 30mm.
PM | Milestone | FII | open | 2024-07-15 | [ALT_0710] Please share the milestone for Smart4 POC by next Mon.

## MIPI Conn
Pin No. | Pin Assign
1 | CM_VCC3V3
2 | CM_VCC5V
3 | GND
4 | CM_CMLK
5 | GND
6 | ICR_ON
7 | ICR_OFF
8 | CMA_RST_L
9 | CMA_SCL
10 | CMA_SDA
11 | GND
12 | GND
13 | N/C
14 | N/C
15 | CSI_D3_N
16 | CSI_D3_P
17 | GND
18 | GND
19 | CSI_D2_N
20 | CSI_D2_P
21 | CSI_CLKA_N
22 | CSI_CLKA_P
23 | GND
24 | GND
25 | CSI_D1_N
26 | CSI_D1_P
27 | CSI_D0_N
28 | CSI_D0_P
29 | GND
30 | CMA_PWRDN