## Smart4
Category | Issue | owner | status | due date | Progress
HW | IO order swap request | FII | Close | 2024-07-10 | [Fii_0718] We have known the I/O order can't be changed. This item can be closed. [ALT_0710] ALT will provide SKB's opinion about I/O order by today. [Fii_0709] Base on the IO order confirm by ALT, the USB/HDMI/Ethernet routing are cross by each other, need to confirm is we could tune the IO order(swap USB and Ethernet) for layout easy and reduce PCB layer?
HW | MiPi CSI connector pin define | FII | Close | 2024-07-12 | [Fii_0716} Loonie has provided the pin difinition of MIPI connector. This item can be closed. [ALT_0710] ALT will provide the pin definition by today. [Fii_0709] ALT have been reply the MiPi CSI connector pin define to follow-up pin map as S905X5 reference circuit, but the Mipi CSI connector which ALT appoint is difference with S905X5 reference circuit, please help to confirm.
Sales | Cost up for 84*84mm PCB | ALT | open | 2024-07-10 | [Fii_0716] Plz help to pay the SWAN EOL NRE first. Or sales can't provide the cost information to ALT. [ALT_0710] Please provide the cost information and gap between Eagle and Smart4. (SoC, Memory, Amp and Mic., PCB, Housing, etc.) It would be very helpul to provide Fii quotation ASAP. [Fii_0709] The cost between Smart3 and Smart4 is more than US$30. Is it acceptable for ALT and SKB?
ME | Height of housing | FII | open | 2024-07-12 | [ALT_0717] ALT will check whether we can provide the SPK unit sample with similar spec for POC with the SPK vendor. [Fii_0716} We are preparing the materials for Smart4 POC now. Can we get the speaker samples in mid of Aug.? [ALT_0710] ALT is checking a speaker unit with a 3mm lower height compared to the current unit. Please help to design the entire product to have a height less than 30mm.
PM | Milestone | FII | open | 2024-07-15 | [ALT_0717] - Fii will provide the thermal simulation on the 19th July. - Fii will provide the SoC power consumption after checking it with Cooper. - Fii will let us know the progress of ID on the 19th July. - Please check Fii can provide the SDK to ALT. This request is for preparing of POC in advance. [Fii_0716] Milestone is showed in another sheet and sent by email as well. [ALT_0710] Please share the milestone for Smart4 POC by next Mon.