## 1. Smart4
Category | Issue | owner | status | due date | Progress
HW | IO order swap request | FII | Close | 2024-07-10 | [Fii_0718] We have known the I/O order can't be changed. This item can be closed. [ALT_0710] ALT will provide SKB's opinion about I/O order by today. [Fii_0709] Base on the IO order confirm by ALT, the USB/HDMI/Ethernet routing are cross by each other, need to confirm is we could tune the IO order(swap USB and Ethernet) for layout easy and reduce PCB layer?
HW | MiPi CSI connector pin define | FII | Close | 2024-07-12 | [Fii_0716} Loonie has provided the pin difinition of MIPI connector. This item can be closed. [ALT_0710] ALT will provide the pin definition by today. [Fii_0709] ALT have been reply the MiPi CSI connector pin define to follow-up pin map as S905X5 reference circuit, but the Mipi CSI connector which ALT appoint is difference with S905X5 reference circuit, please help to confirm.
Sales | Cost up for 84*84mm PCB | ALT | Close | 2024-07-10 | [Fii_0716] Plz help to pay the SWAN EOL NRE first. Or sales can't provide the cost information to ALT. [ALT_0710] Please provide the cost information and gap between Eagle and Smart4. (SoC, Memory, Amp and Mic., PCB, Housing, etc.) It would be very helpul to provide Fii quotation ASAP. [Fii_0709] The cost between Smart3 and Smart4 is more than US$30. Is it acceptable for ALT and SKB?
ME | Height of housing | FII | open | 2024-07-12 | [Fii_0813] ME has updated the latest SPK 3D for the design. [ALT_0807] We have uploaded the SPK 3D data on the Mantis, please check the Mantis no. 1972. [ALT_0801] It will be assamble in Korea. ALT will review assembly feasibility with the SPK once Fii provides the ME 3D data. And ALT will check the SPK 3D data to the vendor. [Fii_0730] Any update for the slim speaker? [ALT_0717] ALT will check whether we can provide the SPK unit sample with similar spec for POC with the SPK vendor. [Fii_0716} We are preparing the materials for Smart4 POC now. Can we get the speaker samples in mid of Aug.? [ALT_0710] ALT is checking a speaker unit with a 3mm lower height compared to the current unit. Please help to design the entire product to have a height less than 30mm.
PM | Milestone | FII | open | 2024-07-15 | [Fii_0820]Done [ALT_0814] Please update the milestone again. - Update timeline of week, etc. - Update some typo : HW Bring up, and SW porting --> "Complete", not "Start" - Please let us know the EVB arrive schedule. - Please send two more samples, total 4pcs sample, when Fii sends it on the 13rd Sep. [Fii_0813} Milestone was updated [ALT_0807] 1. Please update the milestone: - Modify the milestones as there are some mismatched events. - Include the PCBA delivery schedule. - Include action plans for the software part, such as the AML SDK release, etc. 2. Regarding the B'd bring-up: - The functions that need to be implemented first are basic Android TV features, such as YouTube, and integration with the SKB RCU. - If AML has any solutions related to AI, like super resolution, voice enhancement, and so on, please let us know. It would be great if we could demonstrate the Smart 4 POC with these new functions to SKB. [Fii_0806] The updated milestone is attached in sheet 4. [ALT_0801] *Note: The EVB will be released about middle of Aug. [Fii_0730] Sent with email on 7/25 already. "S905X5M Ref Android U Power Consumption". [ALT_0724] Please let us know the exact title of docs regarding the SoC power consumption, then ALT will check it with AML korea. [Fii_0723] - Thermal simulation report will be provided once ID settle down. - The SoC power consumption should be requested by ALT to AML Korea directly. - Fii sent ID on 7/19 already. - After checking with AML, Fii is not authorized to provide SDK to ALT. [ALT_0717] - Fii will provide the thermal simulation on the 19th July. - Fii will provide the SoC power consumption after checking it with Cooper. - Fii will let us know the progress of ID on the 19th July. - Please check Fii can provide the SDK to ALT. This request is for preparing of POC in advance. [Fii_0716] Milestone is showed in another sheet and sent by email as well. [ALT_0710] Please share the milestone for Smart4 POC by next Mon.
ID | ID lock down | ALT | open | 2024-07-23 | [Fii_0905] Sent drawing of screw to ALT. [Fii_0827]Please check which parts is needed for 3D mock-up. Fii will prepare them and send to ALT from NN. [Fii_0820]Fii ME list some risk about 3D print. After reviewing with ALT, will send to ALT immediately. [ALT_0814] Please provide the 3D data once Fii finishes the ME design. The target date is on the 20th Aug. [Fii_0813] Fii has sent updated ID on 8/9. [ALT_0807] It's ok to proceed with the current ID to the next step except for BT button location. Please move the BT button to the next the Mic mute button, then share the updated file. ALT will email about ID lock down today. [Fii_0806] Updated ID sent by email. Need ALT to reply the confirmation of ID. [ALT_0801] Here is our conclustion. Please review and let us know how long it will be taken seperately ID and I/O change by tomorrow. - ID: Please remove the asymmetrical elements and simplify the ID based on the proposal A. - I/O: Please modify as below. 1. Move the USB port to the right side and change to orientation to horizontal. 2. Move the BT button to the top side next to other buttons. 3. Change the HDMI port to the orientation to horizontal. [Fii_0730] ALT to confirm by 8/1 whether to proceed with the existing POC(PCBA&ID) version. [Fii_0723] We replied the ALT comments for ID proposal. We will update the ID by 7/25. Before ID lock down, the schedule might be delayed.
| Mock-up |  |  |  | [Fii_0820] To avoid any misundertanding, will discuss with ALT on 8/21 meeting and reply this request. [ALT_0814] Please send below items to KR. 1. The suface finishing chip of the VDI 27 that is marked Fii's ID proposal. 2. Rubber foots, Screws for the mock-up
HW | Designated parts | ALT | open | 2024-07-23 | [Fii_0820]About B&S materials. Fii have some internal process which need to be completed. and will keep updating with ALT. [ALT_0814] ALT confirms the table besides. And please check again that Fii needs the signed docs of "Quality~", we have already provided the signed docs in 2019. [Fii_0813] We would like to confirm the feedback from Mr. YOON. [ALT_0807] Fii will use the designated components by ALT for POC stage. If ALT decides to use those components for MP, then ALT need to provide [Quality and Environmental Liability Declaration-Fii] signed. [Fii_0807] Fii will select mic from our QVL. [ALT_0801] FII requests this document for assigning the Fii part number of the mic component, since that isn't included in the FXN QVL. --> Please suggest sort of mic components Fii can use. [Fii_0730] Sent with email on 7/25 already. For the designated parts. We need ALT to sign back the document "Quality and Environmental Liability Declaration-Fii" as attached. Thanks! [ALT_0724] Please let us know the part number of components which Fii will use for POC. (BT, AMP, Mic.) [Fii_0723] To avoid further shcedule delay, BT and Speaker AMP we suggest to keep our current design for POC. We can change after project award. Does ALT provide the pricing for three designated parts?
| Bring Up | Fii | open | 2024-09-30 | [Fii_1001]Regarding our bring-up process, we are still pending by the burn-in issue. We have requested AML’s assistance in analyzing and resolving the issue. However, due to the holidays in China, our RD team is going to start work on October 4th. We will provide the latest update at that time. [Fii_0924]waiting for PCBA delivery. After checking with AML, if the schedule need to be modified, will update to ALT. [Fii_0920]Of the PCBA currently in Nanning's possession, 5 units have been tested, and 4 units keep resetting during bring-up. Fii will continue testing the remaining PCBAs. (Fii Willin, 9/23) One of these 4 PCBAs will be sent to Taiwan Amlogic for analysis. (Fii Kay, 9/23) [Fii_0919] Sample arrived TW. and will deliver NN on 9/20. [Fii_0910]About the list provided by ALT, there are some functions and schedules that we still need to confirm with them during the meeting. [Fii_0905]The design of Amlogic EVB and Smart 4 is not exactly the same. Considering shortening the whole bring-up L/T on Smart 4, we borrow Amlogic EVB and use it to bring up the basic functions in advance. It's what Kerwin in charge to do. After VN complete SMT process, we ship out PCBAs to NN (Willin as SW leader of Smart 4) and Taiwan. So that Willin team can work with Kerwin to bring up on Smart 4 board.
| ME | FII |  | 2024-09-25 | [Fii_1001]sent [Fii_0925]will make report about mock-up reviewing. [Fii_0924] Sent by 9/24 The mock-up's top case and bottom are 3D printed, and the buttons are CNC machined. The buttons are not designed as tac switch; instead, they are a combination of a metal dome on the PCB and heat-fused buttons. Fii RD will evaluate for interference after receiving the mock-up and make necessary adjustments.
| ME | FII | open | 2024-09-30 | [Fii_1001]sent [Fii_0920]Fii will provide the ratio of recycled materials and the assessment results regarding reliability impact to ALT. ALT will forward this to SKB. After the final project award, SKB will decide whether to use the materials and in what proportion.
| Bring Up | FII |  | 2024-09-24 | [Fii_0924] sent by 9/24 [Fii_0920]Fii will provide a schedule for FW releases, including the features and release timing of each version. ALT will test once the FW is received. (Fii Willin, 9/23)
| Bring Up | FII | close | 2024-09-24 | [Fii_0924] uploaded by 9/23 [Fii_0920]Fii will provide Amlogic's tool to ALT to facilitate ALT's buring FWof 4 sets of PCBA in Korea after the bring-up process. (Fii Kerwin, 9/23)
| Power consumption | FII | open | 2024-09-30 | [Fii_1001] will provide the data after bring up. [Fii_0925]Fii will provide the power consumption for LPDDR4 & LPDDR4X on the S905X5-M and the power consumption of LPDDR4 and LPDDR4X for the S905X5. Following the AML design guide, LPDDR4X requires two separate voltages: VDD_DDR (0.75V) and VDDQ (0.6V). LPDDR4 can combine these into a single 0.78V voltage. Using 0.6V LPDDR4X would increase PCB size, enlarge PCB size, and raise costs. Therefore, the Smart 4 design only uses LPDDR4 with 0.78V.

## 2. ID
[Smart4] Industrial Design development
Category | Status | Date | ALT Comments | Fii Comments
General | Open | 2024.07.22 | [0724] Please provide two more proposal later and let us know the target schedule. [0722] When can we get the remaining two proposals? | We havo no plan to provide further proposals so far. Or it will delay the SOC schedule seriersly.
General | Open | 2024.07.22 | [0722] Is there any possibility to apply PCR plastic to the POC? | The PCR plastic is only for Tooling. It can't be used in mock-up samples.
General | Open | 2024.07.22 | [0722] DId you have any chance to conduct an analysis of the trends in Korea market for POC. | What kind of trend do you notice in Korea market? Please share it with us.
Concept | Open | 2024.07.22 | [0722] What is the main concept behind this proposal? | It continues the sense of asymmetry in the smart3 design and retains the circle within the square of the design. A new design is added, highlighting the combination of "square" and "round" surfaces. From the original plane to the current three-dimensional, it extends from 2D to 3D, a new asymmetric element. It also directly breaks the visual inertia, brings new impact and dynamic beauty, and enhances the vitality of the design.
Concept | Open | 2024.07.22 | [0722] Please elaborate on the rationale behind selecting green and blue for the color variations. | "Color Plan: Olive green is a natural color, mature and calm. By imitating nature, hope becomes the center of attention. Mineral blue is a color like the deep sea. It gives people a high-end and calm feeling, through the contrast between light and dark To create a sense of light, you can have a cool technological style."
ME | Open | 2024.07.22 | [0722] What is the dimensions for the device label area? | It depends on what content will be showed on the label. And the label size also can be decided by ALT or SKB. Our ID is just for your reference.
HW | Open | 2024.07.22 | [0724] Fii will use the Knowles digital mic. If Fii will update the location of mic., then ALT will check it. [0722] What potential issues might arise with this design? | 1. The SPK design must be locked down ASAP, because it impacts ME design, especially MIC board. 2. The distance between two microphones does not meet Android TV OS's requirement.(66-71 mm)
HW | Open | 2024.07.22 | [0722] How is thermal management addressed in this design? | The thermal simulation was passed in 25 degC and 50 degC of environment temperature.
HW | Open | 2024.07.22 | [0722] Where is the FFV mic. located? | Will add MIC hole in next version.
HW | Open | 2024.07.22 | [0722] Please place the FFV mic. | Will add MIC hole in next version.
HW | Open | 2024.07.22 | [0722] Please move the LED to the front part. | Will follow and update in next version.
HW | Open | 2024.07.22 | [0722] Please move the IR receiver to the front part. | The IR receiver is to the front part already.
HW | Open | 2024.07.22 | [0722] Please place the button according to the provided sequence | Will follow and update in next version.
HW | Open | 2024.07.22 | [0722] Please change the BT paring button to nomal button type. It's not button like Reset. | Will follow and update in next version.
HW | Open | 2024.07.22 | [0724] Please provide the dimention and location for the I/O interface. [0722] Please align the I/O ports on the rear side. | If ALT want to align the I/O with the bottom line, the HDMI connector should be customized part. Will cost up.
HW | Open | 2024.07.22 | [0724] Please provide schematic design after closing the SWAN NRE discussion. [0722] Please provide Sub PCB location and major components on it. | There are BT, speaker AMP, MEMS, tact swich on Sub board.
Etc | Open | 2024.07.22 | [0722] Please apply "B tv" logo instead of "BRAND". | Will follow and update in next version.
Etc | Open | 2024.07.22 | [0722] Please change the USB image for USB 3.0 image. | Will follow and update in next version.
Etc | Open | 2024.07.22 | [0722] Please mark the On/Off symbol on the main power switch. | The switch itself has the On/Off symbol as picture.
Etc | Open | 2024.7.22 | [0722] Please provide thermal simulation data. | The thermal simulation report will be provided once the ID is settle down.

## 3. POC Milestone
0910 ver
0820 ver

## 4. Updated POC Milestone
4