## Box
|  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December
Major Milestone by ALT/SKB | Conditions before the event | WK5/10 | WK5/17 | WK5/24 | WK5/31 | WK6/7 | WK6/14 | WK6/21 | WK6/28 | WK7/5 | WK7/12 | WK7/19 | WK7/26 | WK8/2 | WK8/9 | WK8/16 | WK8/23 | WK8/30 | WK9/6 | WK9/13 | WK9/20 | WK9/27 | WK10/4 | WK10/11 | WK10/18 | WK10/25 | WK11/1 | WK11/8 | WK11/15 | WK11/22 | WK11/29 | WK12/6 | WK12/13 | WK12/20 | WK12/27
Kick off (5/17) | ID design lock down and check sample qty' | bar: May WK5/17
SKB QA(3 weeks) | leverage EVT sample | bar: August WK8/23 to September WK9/6
BMT(7 weeks) | bar: September WK9/13 to October WK10/25
HW Milestone
EVT Schematic Design | bar: May WK5/17 to May WK5/24
EVT PCB Layout | Stacking ready | bar: May WK5/24 to May WK5/31
EVT PCB FAB | bar: June WK6/7 to June WK6/14
EVT Build | bar: June WK6/21 to June WK6/28
EVT Test | bar: July WK7/5 to July WK7/19
DVT Schematic Modify | Stacking ready | bar: July WK7/26 to August WK8/2
DVT PCB Layout Modify | bar: August WK8/2 to August WK8/9
DVT PCB FAB | bar: August WK8/16 to August WK8/23
DVT Build | Inkel housings should arrive VN | bar: August WK8/30 to September WK9/6
DVT Test + certification pre-test | bar: September WK9/13 to September WK9/27
Certification(BQB&HDMI&KC) | bar: October WK10/4 to October WK10/25
Reliability Test | bar: September WK9/13 to October WK10/11
Approve to MP | bar: October WK10/11
pilot run | bar: October WK10/18
MP delivery | bar: October WK10/25
ME Milestone
ME design | ID lock down on day 1 | bar: May WK5/17 to May WK5/31
EVT mock up | assume 20pcs | bar: June WK6/7 to June WK6/14
mock up review & DFM | bar: June WK6/21 to June WK6/28
Hard Tooling T0 | bar: July WK7/5 to August WK8/2
Hard Tooling T1 | bar: August WK8/9 to August WK8/23
SW milestone
Board Bringup | bar: June WK6/28 to July WK7/5
I/O Interface checking and verification | bar: July WK7/12 to August WK8/2
BTF HAL Development(Display, LED, Mic, Button) | bar: June WK6/21 to August WK8/9
BTF HAL Development(A/V related) | bar: June WK6/21 to August WK8/9
BTF testsuite verification | bar: August WK8/16
M/W integration test and bug fixes | bar: August WK8/23 to September WK9/27
CTS cert. | bar: August WK8/30 to October WK10/11
NTS cert. | bar: September WK9/13 to October WK10/18

## Dongle
|  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December
Major Milestone by ALT/SKB | Conditions before the event | WK5/10 | WK5/17 | WK5/24 | WK5/31 | WK6/7 | WK6/14 | WK6/21 | WK6/28 | WK7/5 | WK7/12 | WK7/19 | WK7/26 | WK8/2 | WK8/9 | WK8/16 | WK8/23 | WK8/30 | WK9/6 | WK9/13 | WK9/20 | WK9/27 | WK10/4 | WK10/11 | WK10/18 | WK10/25 | WK11/1 | WK11/8 | WK11/15 | WK11/22 | WK11/29 | WK12/6 | WK12/13 | WK12/20 | WK12/27
Kick off (5/17) | ID design lock down and check sample qty' | bar: May WK5/17
SKB QA(3 weeks) | leverage EVT sample | bar: August WK8/9 to August WK8/23
BMT(7 weeks) | bar: August WK8/30 to October WK10/11
HW Milestone
EVT Schematic Design | bar: May WK5/17
EVT PCB Layout | Stacking ready | bar: May WK5/24
EVT PCB FAB | bar: May WK5/31 to June WK6/7
EVT Build | bar: June WK6/14 to June WK6/21
EVT Test | bar: June WK6/28 to July WK7/12
DVT Schematic Modify | Stacking ready | bar: July WK7/19
DVT PCB Layout Modify | bar: July WK7/26
DVT PCB FAB | bar: August WK8/2 to August WK8/9
DVT Build | Inkel housings should arrive VN | bar: August WK8/16 to August WK8/23
DVT Test + certification pre-test | bar: August WK8/30 to September WK9/13
Certification(BQB&HDMI&KC) | bar: September WK9/20 to October WK10/11
Reliability Test | bar: August WK8/30 to September WK9/27
Approve to MP | bar: September WK9/27
pilot run | bar: October WK10/4
MP delivery | bar: October WK10/11
ME Milestone
ME design | ID lock down on day 1 | bar: May WK5/17 to May WK5/31
EVT mock up | assume 20pcs | bar: June WK6/7 to June WK6/14
mock up review & DFM | bar: June WK6/21 to June WK6/28
Hard Tooling | bar: July WK7/5 to August WK8/2
SW milestone
Board Bringup | bar: June WK6/21 to June WK6/28
I/O Interface checking and verification | bar: July WK7/5 to July WK7/26
BTF HAL Development(Display, LED, Mic, Button) | bar: June WK6/14 to August WK8/2
BTF HAL Development(A/V related) | bar: June WK6/14 to August WK8/2
BTF testsuite verification | bar: August WK8/9
M/W integration test and bug fixes | bar: August WK8/16 to September WK9/20
CTS cert. | bar: August WK8/23 to October WK10/4
NTS cert. | bar: September WK9/6 to October WK10/11