## Reliability test plan
SWAN Reliability Test Plan Rev: 2.0 Document NO: RAD-HCP-202004002
No | Foxconn Test Items | Test Condition | Test Criteria | Q'ty | L/T | Test Location | Cost | Ref. Doc | Remark
A. MTBF Prediction
1 | MTBF Prediction | 1. Ambinet temperature: 25℃/50℃ 2. Telecordia SR-332 Issue 3 | >65,000hour (@25°C condition) | 0 | 2 | HC | 500 | Telecordia
B. Thermal Measurement
2 | Thermal Test - Operation | 1. Temperature: 25℃/50℃ 2. Duration: 8 hours for each condition 3. External heat rise: No surface point of the product chassis | 1. Meet thermal specifications of each IC. 2. Housing Top < △20℃ 3. Housing Bottom < △30℃ | 1 | 5 | HC | 1200 | IEC 60068-2-2
C. Climatic Test
3 | Cold Start Test | Power off, Storage, Ta = -20℃ Storage 48 hours then ramp the temperature to 0℃, power on operation test Power on/off 15 times | 1. No functional failures both before and after the test. 2. No performance degradation during the functional test 3. No visual damage to the products during inspection, such as warpage, peeling, missing pixels, discoloration, etc. | 2 | 3 | HC | 190 | IEC 60068-2-01
4 | Hot Start Test | Power off, Storage, Ta = 70℃ Storage 48 hours then ramp the temperature to 50℃, power on operation test Power on/off 15 times |  |  | 3 | HC | 190 | IEC 60068-2-02
5 | High temperature & High humidity test - storage | 1. Temperature 70℃ 2. Humidity 90%RH 3. Test period 72 hours |  |  | 4 | HC | 380 | IEC 60068-2-30
6 | High Temperature & Humidity Test (Op) | Power on, Operation, Ta = 50℃, Humi.= 95%R.H. for 72 hours | 1. No functional failures both before and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 2 | 4 | HC | 380 | IEC 60068-2-30
7 | Operational Temperature cycle test | Power on 1. 25℃ for 1 hr 2. 25℃ to -5℃ for 2 hrs 3. -5℃ for 13 hrs 4. -5℃ to 25℃ for 2 hrs 5. 25℃/65% for 1 hr 6. 25℃/65% to 50℃/95% for 2 hrs 7. 50℃/95% for 13 hrs 8. 50℃/95% to 25℃ for 2 hrs Repeat 1~8 for 2 cycles 9. 25℃/60% for 48 hrs Total for 120 hrs | 1. No functional failures both during and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 2 | 6 | HC | 570 | IEC 60068-2-30
8 | Thermal shock (PCB only) | Power off , non-operation Ta= -20℃ (30min) ~ 70℃(30min) 60 cycles Transfer time: 5 min | 1. No functional failures both before and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 3 | 2 | HC | 920 | MIL –STD-810F
9 | Power On/Off with Temperature | 1. Power on: 50 sec. (follow product characteristic) 2. Power off: 10 sec. (follow product characteristic) 3. Temperature: -5°C and 50°C 4. Vin: follow customer's spec or MRS 5. Cycle: 2500 cycles per test condition 6. Total 5000 cycles | 1. No functional failures both before and after the test. 2. No performance degradation after the functional test. 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 2 | 5 | HC | 475 | IEC 60068-2-1
10 | Highly Accelerated Life Test (HALT) | 1. Thermal step stress (Cold) 2. Thermal step stress (Hot) 3. Fast thermal transition 4. Vibration step stress 5. Combined thermal cycling | To find the product limit | 5 | 5 | TMC | 3000 | Product Spec.
11 | EDVT | Verify the hardware design by exposure of the product to wider temperature, voltage and frequency margining. Test Temp. at -5/50 °C | No functional failures both during and after the test | 2 | 5 | HC | 1200 | NA
12 | MTBF Demonstration Test | 1. System temperature (Tn): 25°C 2. Test environment (Ta) Temp.: 50°C 3. Activation Energy(EA): 0.7 4. Number of units in test: 20 5. Confidence level: 90% 6. Test day: 26 days 7. MTBF:43800 Hours ( 5 years) | 1. No functional failures of the test 2. No performance degradation during the functional test 3. No visual damage to the products during inspection, such as shrinkage, peeling, or discoloration, etc. | 20 | 26 | HC | 9100 | MIL-STD-781
13 | Acoustic Noise Test (Normal operation mode & Standby mode) | To ensure the DUT does not exceed the product specifications (With Fan) for acoustic noise levels (Sound Pressure Level). Defines the allowable acoustic noise as four types, “Type I, Type II, Type III and Type IV, we can follow Type III or Type IV. | The noise value shuld be less than 23dB(A). | 1 | 1 | TMC | 200 | ISO-7779
D. Mechanical test
14 | Free Fall Drop Test (Single unit test) | 1. Height for fall test: 75 cm 2. Fall plate: Wood Floor 3. Drop 6 faces | 1. No functional failures before and after the test. 2. No performance degradation during the functional test. 3. No visual damage to the products during inspection. | 2 | 1 | HC | 75 | IEC-68-2-31
15 | Free Fall Drop Test (Gift Box packaging test) | 1. Height for fall test: 1.5m, 2. Fall plate: steel floor 3. 1 corner, 3 edges, 6 faces each one time | 1. No function failures both during and after the test 2. No performance degradation during the function test 3. No visual damage to the products after inspection, such aspeeling, discoloration, etc. | 2 | 1 | HC | 75 | IEC-68-2-31
16 | Salt Spray Test | 1. Salt: 5% , Temp.: 35°C and Humidity: 85% 2. Sprayed amount: 0.6~30 ml/hr 3. Test duration: 48 hours | No physical defect, corrosion and function failure after this test. | 2 | 3 | HC | 350 | IEC 60068-2-11
17 | Connector Insertion/Removal Test (Power Jack, HDMI, USB*2, MIC, AUX & RJ-45) | 1. Power Jack Connector: 5,000 times 2. HDMI Connector: 5,000 times 3. USB Connector: 5,000 times 4. MIC Connector: 5,000 times 5. AUX Connector: 2,000 times 6. RJ-45 Connector: 2,000 times 7. Test Speed: 10 cycles/min | 1. No functional failures before and after the test. 2. No performance degradation during the functional test. 3. No visual damage to the products during inspection. | 2 | 4 | HC | 840 | NA
18 | Button Life test | Test cycles: 5,000 cycles Test Speed: 10 cycles/min | Buttons must withstand mechanical cycling | 2 | 4 | HC | 175 | NA
19 | Power Switch Lift test | Test cycles: 5,000 cycles Test Speed: 10 cycles/min | Power Switch must withstand mechanical cycling | 2 | 2 | HC | 90 | NA
20 | Operational Random Vibration | 1. Acceleration: 10mm /4.4G/2.5G, 2. Sweep range: 5~15Hz/10mm P-P, 16~30Hz/4.4G, 30~300Hz/2.5G 3. Sweep rate: 0.25 octave/min 4. Duration: 60 min/ axis | 1. No function failures both during and after the test 2. No performance degradation during the function test 3. No visual damage to the products after inspection, such aspeeling, discoloration, etc. | 2 | 2 | HC | 200 | IEC 60068-2-64
21 | Operational Shock Test | 1. Acceleration: 30G, 2. Test wave: Square Wave 3. Duration: 11 ms 4. Direction: 6 faces 5. 3cycles/direction | No functional failures both during and after the test | 2 | 1 | HC | 250 | IEC-60068-2-27
22 | Chassis Static Load | 1. Applied position: TOP on the enclosure 2. Weight and time: 5Kg/ diameter 9mm area/apply 30 seconds | There is no damage of Mechanical material (for examples Cover's crack, breakdown | 2 | 1 | HC | 100 | NA
23 | Surface Coating Abrasion | Test loading: 250g Test cycles: 50cycles by No.74 the eraser | No visually damage of the enclose surface | 2 | 1 | HC | 150 | UL60950
24 | Abrasion Resistance of Label Test | 1. Loading force: 1000g 2. Cycles: 800 cycles | There in no abrasion of printing character and number | 2 | 1 | HC | 150 | CSA C22.2 NO.0.15-95
25 | Logo/Printing Abrasion Test | Loading force: 1000g Test cycles: 2000cycles for the abrasion by the 95% alcohol solvent | There in no abrasion of case printing and no changible color | 2 | 1 | HC | 150 | NA
E. Packaged test Plan Rev.: 1.0
26 | Temperature and Humidity Test | Test Temlpearture: 38℃ Test humidity: 85%R.H. Dwell time: 72hours | No obvious visible damage on boxes after temperature and humidity test. | 1 carton | 4 | NN | 367 | ISTA-2A
27 | Static Compression Test | Units are packaged Compression load=Wt x (S - 1) x F Wt:Total weitht of the packaged-procuct S:Total number of packaged-products in a stack 1:Represents the bottom container in a Stack Compression Test duration:1hour | No obvious visible damage on boxes after static compression test. | 1 carton | 3 | NN | 83 | ISTA-2A
28 | Random Vibration Test | The following breakpoints shall be programmed into the vibration controller to produce the acceleration versus frequency profile (spectrum) below with an overall Grm s level of 1.15 | No obvious visible damage on boxes after random vibration test. | 1 carton | 2 | NN | 117 | ISTA-2A
29 | Package drop test | The test drop height varies with the weight of the packaged-product. Find the weight of the packaged-product in the following chart to determine a drop height or an equivalent impact velocity to be used for a substituted drop: | No obvious visible damage on boxes after packaged drop test. | 1 carton | 1 | NN | 33 | ISTA-2A
30 | Fix displacement Test | Displacement:25mm Duration:14200times | No obvious visible damage on boxes after fixed displacement test. | 1 carton | 2 | NN | 117 | ISTA-2A

## Test schedule
SWAN LED Driver Reliability Test Schedule Rev: 2.0
Climatic Test
No | Test Items | Q'ty | L/T | DVT | Test Location | Status | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18
1 | Cold Start Test | 2 | 3 | V | HC | bar: D1 to D2
2 | Hot Start Test | re-use item 1 | 3 | V | HC | bar: D3 to D4
3 | High Temperature & Humidity Test (Op) | re-use item 2 | 4 | V | HC | bar: D5 to D8
4 | Thermal shock (PCB only) | re-use item 3 | 2 | V | HC | bar: D9 to D10
5 | Power On/Off with Temperature | re-use item 4 | 5 | V | HC | bar: D11 to D15

## Allocation
LED Driver Test Sample Allocation
Dept. | Location | Items | Sample | Total L/T (Day) | Test Engineer | Ext.
HMQA | HC | 5 | 2 units | 15 | Jackson | 550-6712
| Total | 5 | 2 units | 15