## ALT owned DFM
No. | Status | What | Enclosed Picture | PCB 設計規範條例 | Recommendation | ALT Remark | image | Fii Remark 0202 | ALT Remark 0204 | Fii/ALT discussion 2/19 | ALT Remark 0318 | ALT Remark 0726 | Fii Remark 0928 | ALT Remark 0929 | Fii Remark 1014 | ALT Remark 1124 | INKEL Remark 1124 | Remark
1 | Closed | Add glue issue: When add glue, Glue may be dropped into inside port of HDMI |  |  | Can skip the glue on both side of HDMI connector? | ALT : instade glue, can use SMT Glue on HDMI |  | Cannot accept. Once there are issues with boards the rework be be a big problem. | Fii decide choose one of solution | ALT agreed to add the glue from later half of the connector for DVT2 and check
2 | Closed | Add glue issue: Add glue may be make PCBA become dirty, and impact to visual of parts if glue is over on sufrace of component |  |  | Need check and help to solve issue: Modify layout/ change requirement to add glue, etc… | ALT : instade glue, can use SMT Glue on Ethernet / DC JACK |  | Still the same issue no matter when the glue is added. | Fii decide choose one of solution
3 | Closed | Assembly issue: Bracket side led need to be stick more gasket 484.00429.005 & 484.00430.005 |  |  | Need to ask vendor to stick gasket | ALT : Next production, vender will be subassembled |  | OK |  | ok |  | check with vender, I will update it. | ALT commented that will apply from 1st MP (2K).
4 | Closed | Speaker cable issue: 1. Length of wire at midragne & Tweeter speaker is short --> sponge is easily broken 2. Length of wire at woofer speaker is long alittle |  |  | Need check and update spec | ALT : review DVT sample first, will update before next production |  | OK | ALT FII suggest each cable length. ALT will update as your suggestion | ok | Check cable drawing and please feedback. https://mantis.cnsbg.foxconn.com/vaas/view.php?id=1131#c6428
5 | Closed | Speaker cable issue: Rubber of speaker cable is so tight. Need a lot of strength to put in |  |  | Need check and improve | ALT : 'Not accpectable, due to air leackage |  | Will discuss with factory |  | ok
6 | Closed | Speaker cable issue: 1. Lock of cable to connect with speaker is very tight 2. Small lock is remove so hard |  |  | 1. Need vendor to modify size of pin on speaker or lock of cable 2. Modify design of small lock as big lock | ALT : will check with vender (Dreamus), let you know |  | ok |  | ok |  | ALT is dicussed with vender and Inkel. Woofer SPK is the beginning of vibration. So, Need to more tight. Because It must not unlock during operation. Please see the image that the SOP update for insert way fix our suggestion to more easy unlock. |  | ALT already guided how operator can pull out the cable.
7 | Closed | Assembly issue: When assembly speaker, speaker cable has confliction with housing because of the black tube is too hard to bend |  |  | Need check and improve | ALT : will check with vender (Dreamus), let you know |  | ok |  | ok | changed SPK design. ALT/Inkel expect this issue clear
8 | Closed | Assembly issue: Speaker has not Fix-boss --> Need to use hand fix speaker to drive svrew |  |  | Modify housing to add fix-boss or a sink area to locate speaker better for locking the screws | INKEL : It can be assembled using conditions "a" and "b" ALT : first Screw tightening "a" area, next "b" area. It will be fixed in screw hole place. |  | The suggesting is for the positioning and make it easy to drive the screw while the speaker is fixed in a location and doesn't slide. |  | ALT will have Inkel revise after DVT2 | changed SPK design. ALT/Inkel expect this issue clear
9 | Closed | Assembly issue: Distance from surface of speaker to surface of inside housing is only 7.2mm but BOM reuqest to use screw M3x10mm |  |  | Need Check and confirm | ALT : it can use M3x10mm screw' INKEL : If the outer diameter("a") of the thread on the opposite side of the screw is small, a problem may occur in the tightening force. (The possibility of occurrence of defects was blocked in advance. It is applied to sound products with high output.) |  | ok |  | ok | changed SPK design. ALT/Inkel expect this issue clear
10 | Closed | Assembly issue: Port 476.00295.005 & 476.00296.005 is similar. They aren't designed to prevent assemble wrong part --> May be assemble wrong |  |  | Need check and improve | ALT : DVT2 housing is update. Top and R/L is engraved |  | ok |  | ok | Removed port for DVT3.
11 | Closed | Assembly issue: RD request to use scre M3x4mm to assemble LED board. It it too short while thread pitch is big --> Easily happened strip thread of housing |  |  | Check and modify design: Length of screw, screw type, size of hole…. | ALT : This is DVT only. Will improved next production INKEL : The screw is designed to apply 3x7mm(Bind Head) |  | ok |  | ok
12 | Monitor | Front cover issue: Hole on Front cover and rubber gril holder cannot match well because the front cover is too long and the tolerance affects the assembly |  |  | Need check and feedback to vendor to improve | ALT : This is DVT only. Will improved next production INKEL : The reason is that the size of the injection part is short. |  | ok |  | ok | Check it out on DVT3 and let me know any issue |  |  |  | In the middle, the grill cover is not pressed completely with holder rubber | when the grill assembly, recmmmended that assemble the center first, then assemble the each side
13 | Open | Design issue: Space between button and switch is only 0.1mm --> Easily happen switch is jammed |  |  | Need check and modify design: Space between button and switch is 0.3-0.5mm | ALT : actually this is not a jammed switch. This is designed gap to reduce vibration noise.. Inkel : Movement(deformation) of the part is impossible due to conditions "a" and "b". And the failure rate is low due to the flexible design of condition "c" |  | ok. But there are jammed buttom issues reported which will need to cut the edge |  | ALT will have Inkel revise after DVT2 | Check it out on DVT3 and let me know any issue | the root cause of button switch jammed is Top case burr, Not to gap the burr is make switch jammed. If you have switch jammed STB, remove the burr, will be clear the issue the vender will make CTQ point as below | The button is still deformed. | We will discuss with INKEL how they can manage Burr, and we will feedback to you. |  | Inkel has mold improvement for injection | before mold design after mold design (to be updated) Inkel suggested that sub-assemble with button PCBA in Inkel VN factory and deliver after button inspection. The factory check that the button PCBA can derlivery to Inkel VN facyory" | Need ALT cowork with INKEL to mold improvement for injection [ALT 1126] ALT will check effective date & update drawing before 12/3 [Fii 1126]Due to the policy and process in Fii, factory cannot ship PCBA to Inkel for assembly. [Fii 1203] Need ALT to push Inkel to modify the mold and provide sample/schedule for control run.
14 | Closed | Add glue issue: After add glue on PCB & bushing. Glue need to spend time to dry. |  |  | The glue Inkel brought to the line also takes a long time. This will be an issue for assembly and testing. For bushing, the glue is damaged easily during assembly. ALT advised vendor cannot trade with any Fii QVL. Possible for buy and sell? | ALT : Please contact to belew vender. This vender is supply FFC to Speaker company (Inkel, Anam) also was supplied Foxconn Also we checked can make Swan side FFC with Bushing Sponge. 업체명: Hwa Sung Elecom Co., Ltd 담당자: Gil-Hwan Jeong(Deputy General Manager) 연락처: 010-2046-6084(h870420@hanmail.net) |  | under checking |  | Fii is checking with vendor | Please share the status, I check with Hwa Sung Elecom, they need to make mold for bushing. And need 14days for tooling mold. I think we don't have much time to prepare DVT3 meterials |  | We can's apply glue on the bottom side, because our employee's fingers will touch the glue during assembly, which will be very dangerous. | 1. What kinds of issue you have ? Could you explain what is the dangerous issue , such as broken bushing or broken FFC cable ? 2. How long does it take to dry glue ? Can you adjust assembly step and give time to dry for Glue ?
15 | Closed | Heat spreader issue: Heat spreader 400.01103.005 is too long but it isn't not drive screw to fix well in housing --> Have risk heat spread deformed and touch pin of DIP part & smt parts at bottom side on PCBA |  |  | 1. Add more one screw to fix heat spreader 2.Use gasket cover on heat spreader to prevent pin of DIP parts touch heat spreader |  |  |  | Contact to Foxconn Thermal team. This thermal solution is designed by Foxconn 1. Need to SoC Bottom plate update by Fii 2. Need to the gasket cover on heat spreader by Fii | Fii ME prepares 3D file for ALT to check with Inkel | Updates, Check 3d modeling data 0001171: [SWAN] 3D modeling data with Inkel and Foxconn - for DVT3 (T0) Please note that, Please note that, for screw with bottom heat spreader, the screw boss height change 6mm to 4mm. But assembly boss (Green) height is not changed. Be careful not to damage when assembling heatspreader / PCBA
16 | Closed | Assembly issue: Wire mount 471.00105.005 is defined to stick on rib of bottom --> It is easily shaked and fixed not well |  |  | Need RD check and modify housing to put wire mount better |  |  |  | ALT Not accpectable Please search more smaller hook Or change the attachment structure | ok | Check it out on DVT3 and let me know any issue
17 | Open | Housing issue: Housing is easily scratched, dirty and adhered sweat. |  |  | Please modify outside of housing to prevent issue. If it cannot be improved, please add the protected film | [6 empty] | ALT is still discuss with vender and customer. Be careful in the factory for scratched, dirty and adhered sweat during assembly | Inkel doesn't deliver the housing with any protected film in preMP. The housing is still easily scratched. | We are reviewing with INKEL on protection film now. |  | ALT is uner review the top side protection film. The other side not planned, so please be careful when housing handeling |  | [Fii 1126]Fii already tried to use protective film but result is not improved. Need INKEL suport to do it. [Fii 1203]Factory will provide suggestions for ALT.
18 | Monitor | Assembly issue: RD/Customer request to use big torque to drive screw -->Threat on screw boss & copper on PCB are damaged |  |  | Need check and confirm | [6 empty] | assembly with PCBA and housing, Please apply FII stanrad torque |  |  | In DVT4 build, RD informed to follow torque as RD& customer defined. We had 4pcs, which screw boss was damaged
19 | Open-->Monitor | Design issue: There is a gap between bottom cover and the side deco --> There is a gap between bottom cover and the side deco after assembly. |  |  | Please modify housing to prevent issue. Populate this gap. | [8 empty] | We already provide assembly guide. Is there any issue to follow assembly guide ? It was commented by INKEL, and we tried to follow their guide and there is no issue. | Deco side may has conflict with knob on screw boss of bottom cover | ALT is request the some of changes to VN factory (21.11.19) to review the long term solution Please check and reply check cavity number of side deco R/L if have big gap | Inkel suggest the short term solution that apply the 1mm EVA cushion to opposite the boss will inform offically after review | [ALT 1126]ALT requests to provide short term solution test data and if any issue found during production, pls take photos and inform ALT to feedback. [Fii 1129] Fii already tried to follow ALT instruction and use the 1mm EVA cushion to opposite the boss, but result is not improved. [Jim 12/2] The gap issues between side deco / bottom has improved a lot in the build, Most gap is less than 0.5mm. We will continue to pay attention to this issue. (mantis #1131)
20 | Closed | Design issue: 3D has positioning pin, and the actual there is no this pin. --> The PCB will easy shift during assembly. |  |  | Please add positioning pin on bottom cover. | [8 empty] | It will apply from MP(2K). |  | applied
21 | Open | Assembly issue: Use 5.5kgf/cm torque to fixed top cover and bottom cover. --> The screw boss is easily damaged. |  |  | Please change the torque. | [8 empty] | We are checking on it. We are waiting for final mold from INKEL. We will updae after review your guide. |  |  | Inkel suggest that apply 4kgf torque with top/bottom assembly. Long term solution is under review
22 | Closed | Assembly issue: The pipe to assemble bottom cover and grill cover is deformed after assembly |  |  | Need RD check and evaluate whether have to modify and improve | [10 empty] | ALT is confirm that grill cover is deformed after assembly
23 | Closed | Assembly issue: The left speaker cable is short |  |  | Need RD check and improve | [10 empty] | if left cable is little short, please un twist the cable. Cable twist has no effect on performance
24 | Open | Assembly issue: Gap between I/O port and bottom cover; bottom cover and top cover/ deco side is over spec |  |  | Need RD help to analyze and improvve | [11 empty] | Inkel suggest the short term solution for assembly sequency guide | [ALT 1126]ALT requests to provide short term solution test data and if any issue found during production, pls take photos and inform ALT to feedback. [Jim 1130] Short term: 100% (5F/5T) gap over spec. on 11/26, waiting ALT give next action – stop production or waive.-->11/30ALT provided inspection spec [Fii 1203] For long term, need Inkel to modify tooling and improve quality.
25 | Closed | Assembly issue: The MIC rubber may be put reverse but testing program can not cover issue |  |  | Need RD check whether modify design to prevent put reverse Please improve testing program to cover issue | [10 empty] | it is alrady applied design to prevent put reverse on the sponge mic silicon. If reverse inserted, it will be not to fit with housing and rubber | OK NG
26 | Closed | Assembly issue: After assemble MIC board, top cover is deformed |  |  | Need RD check whether have to modify any thing | [10 empty] | It is a product characteristic, ALT is confirm that after assemble MIC board, top cover is deformed
27 | Closed | Material issue: Top cover at screw boss of button holder is deformed |  |  | Need RD check and feedback to vendor to improve | [11 empty] | Inkel is defind the CTQ point
28 | Closed | Design issue: The screw boss of top cover is long but has not rib |  |  | Please help to evaluate whether have to add ribs for screw boss | [10 empty] | It is a product characteristic, ALT is confirm that after the screw boss of top cover is long but has not rib
29 | Open | Material issue: Sponge 484.00429.005 484.00422.005 are adhesive into finger gloove when assembly |  |  | Please check whether ask vendor to stick these parts 2. Else, please split or ass broken line to OP easily take and stick these sponges | [10 empty] | ALT is recommend the work with tweezers | Inkel request that how to work at the factory. Please share the examples.
30 | Open | Material issue: Bottom cover has some issues: 1. Screw boss not manufactured completely 2. The Label Frame is not exactly --> impact to stick label | [14 empty] | 1. . Screw boss not manufactured completely : Inkel is defind the CTQ point 2. Label area updated. Please see the drawings in Mantis : 1356
31 | Open | Design issue: Inductor L2 & Button holder has interference --> Has high risk to broken |  |  | Please check and improve | [10 empty] | ALT is uner review the short term solution with Inkel : cutting the rib : change the screw type (Pancake head) Long term solution : PCB update. (Move the inductor)
32 | Closed | Assembly issue: Sponge is loosen after roll around head connector of speaker & ferrit core |  |  | Need to RD check whether can improve issue | [10 empty] | It is a product characteristic, ALT is confirm that Sponge is loosen after roll around head connector of speaker & ferrit core
33 | Open | Assembly issue: Space between connector of the right LED side board and Screw boss of top cover is too small --> lead to connector is broken |  |  | Need RD check and modify design to improve issues | [10 empty] | short term solution : Cutting the rib (Green area). Please refre th the Rib cutting guide : Apply torque 3.5Kgf ~ 4.0Kgf | Long term solution 1. Need to go sign after discuss the cost owner 2. Side LED Rib update cost – Mold modify : $1,500 and 7 ~ 10 working day | [Fii 1126]We must arrange OP to rework(cut the rib) this issue, need sales team and ALT cowork about the cost of fee. We will calculate it soon. Need ALT to check the possibility for Inkel to arrange the rework before ship out. [ALT 1126] ALT will check the housing stock in Inkel and the effective date when Inkel can provide the improved housing. (In the meeting before, ALT feedback 13K already finished in Inkel, pls verify the information.) [Fii 1203] For long term, need Inkel to modify tooling and improve quality. Need ALT to check the tooling modify schedule and discuss.
| Open | Material issue: Top cover was damaged | [13 empty] | ALT was waived Nov production. ALT is under define the pass/fail criteria with Inkel | Root cause : error when burr cutting process Inkel will defind the CTQ point according to the criteria agreed with ALT
a
b
a
b
d
c
a
b
a
TOP
R or L
Note on A15: Factory QA Item 7
Note on A19: Factory QA Item 49
Note on A21: Factory QA Item 29
Note on A24: Factory QA Item 27
Note on A25: Factory QA Item 30
Note on A26: Factory QA Item 31
Note on A27: Factory QA Item 32
Note on A28: Factory QA Item 33
Note on A30: Factory QA Item 36
Note on A35: Factory QA Item 28

## Daily
| ALT File | QA file | Description | Action | Owner | Due Date | Status
1 | 13 | 7 | Space between button and switch is only 0.1mm --> Easily happen switch is jammed | [ALT 1126] ALT will check improved mold effective date & update drawing before 12/3 [ALT 1203] ALT will negotiate with Inkel and check the housing improve effective date by Monday(12/6) afternoon. [ALT 1206] INKEL increased hole size about 0.2 mm after 13K stock. Will provide samples for factory for verification.--> Sample schedule TBC [ALT 1208] ALT is reviewing the sample. If no other issue, ALT will inform Inkel to start preparing sample and target to ship the sample by 12/15. [ALT 1210] The hole size change already applied at Inkel side, will ship modified stock from next batch. (3D drawing not changed) ETA schedule will update later. [Fii 1210] After receiving the batch, will arrange 100pcs control run at factory to verify. | ALT | 12/10>12/15 | Open
2 | 33 | 28 | Space between connector of the right LED side board and Screw boss of top cover is too small --> lead to connector is broken | [ALT 1126] Short term: arrange OP to rework(cut the rib). ALT will check the housing stock in Inkel and the effective date when Inkel can provide the improved housing. [ALT 1203] To improve the issue, Inkel need to change tooling. ALT will check with Inkel about the tooling change schedule and cost and discuss with Fii. [ALT 1206] Inkel provide rough schedule for tooling modification. 1st trial from the decision to change : 14 working days New component delivery and review : 14 working days Approval : It depends on situation. MP preparation from approval : 7 working days MP and deliver the components to Foxconn factory : Not checked yet [Fii 1207] Request ALT to check the detail schedule again with Inkel and expedite the process. If the tooling modify start from now, then we can expect to have modified housing by January 2022. [ALT 1210] Inkel already produced 25Kpcs top housing. ALT is still negotiating with Inkel to support the rework after 13K pcs, will update status next week. [Fii 1210] Factory will do the rework for 13Kpcs. But after 13Kpcs, please request Inkel to rework before shipped out. And need ALT to monitor and make sure Inkel can start tooling modification in time and not to cause gap of supply. Inkel should not produce old housing now. | ALT | 12/10>12/15 | Open
3 | 17 | 49 | Housing is easily scratched, dirty and adhered sweat. | [ALT 11/26] ALT asked factory to help suggest the film spec/suggestion and ALT will discuss with Inkel [An 1203] Factory will provide suggestions before 12/6.--> 12/4 Provided [ALT 1206] Provided suggestions to Inkel and wait for feedback. [ALT 1210] Inkel is still reviewing the solution. ALT will update next week. | ALT | 12/10>12/15 | Open
4 | 19 | 29 | There is a gap between bottom cover and the side deco --> There is a gap between bottom cover and the side deco after assembly. | [ALT 1126] ALT requests to provide short term solution test data and if any issue found during production, pls take photos and inform ALT to feedback. [Jim 1202] The gap issues between side deco / bottom had improved a lot in this build, Most gap is less than 0.5mm. We will continue to pay attention to this issue. (mantis #1131) [ALT 1206] INKEL is reivewing the design change side effect. Target to fix this week. [ALT 1210] ALT will check the schedule about when will Inkel apply the short term solution(add EVA gasket) and feedback next week. | PM An/ Chenglun/ ME RD Jim | 2021-12-03 | Monitor
5 | 24 | 31 | Gap between I/O port and bottom cover; bottom cover and top cover/ deco side is over spec | [ALT 11/26] ALT requests to provide short term solution(assembly sequency guide) test data and if any issue found during production, pls take photos and inform ALT to feedback. [Jim 11/30] Short term: 100% (5F/5T) gap over spec. on 11/26, waiting ALT give next action – stop production or waive.-->ALT provided inspection spec | ALT | 2021-12-03 | Closed
6 | 22 | 27 | The pipe to assemble bottom cover and grill cover is deformed after assembly | [ALT 11/24]ALT confirms that grill cover is deformed after assembly | ALT | 2021-11-26 | Closed
7 | 23 | 30 | The left speaker cable is short | [ALT 11/24] If left cable is little short, please un twist the cable. Cable twist has no effect on performance | ALT | 2021-11-26 | Closed
8 | 25 | 32 | The MIC rubber may be put reverse but testing program can not cover issue | [ALT 11/24] It is alrady applied design to prevent put reverse on the sponge mic silicon. If reverse inserted, it will be not to fit with housing and rubber | ALT | 2021-11-26 | Closed
9 | 26 | 33 | After assemble MIC board, top cover is deformed | [ALT 11/24] It is a product characteristic, ALT confirms that after assemble MIC board, top cover is deformed | ALT | 2021-11-26 | Closed
10 | 28 | 36 | The screw boss of top cover is long but has not rib | [ALT 11/24] It is a product characteristic, ALT confirms that after the screw boss of top cover is long but has not rib | ALT | 2021-11-26 | Closed
11 | NA | 12 | Contact between screw & boss is short--> easily damage thread of screw boss | [Jim 11/26] Factory ME checked and feedback no issue. | Jim | 2021-11-26 | Closed

## MOH cost down DFM
No. | Status | What | Enclosed Picture | Recommendation | Comment from ALT(9/29) | Comment from ALT(10/15)
1 | Open | Assembly issue on top cover: 1. Sponge MIC (MPN:4050-21732-500-0V) shall be pre-assembled with double-sided tape 2. Sponge MIC (MPN:4050-21732-500-0V) shall be pre-assembled on top cover |  | 1. Need to ask vendor to stick double-sided tape on Sponge MIC 2. Need to ask vendor to stick Sponge MIC on top cover | 1. Double sided-tape cannot attach Sponge MIC due to material characteristics of Sponge MIC. We are trying to find alternative solution now. We will update it next week. 2. It is difficult to accept your guide. The reasons are -. Again above issue. Sponge MIC cannot be attached to Double sided-tape. Spong MIC has some oil itself, so it is impossible to keep attaching. -. Even though we find a way to keep Sponge MIC to double sided tape, you should pull out "Sponge MIC + double sided-tape" ass'y from the top cover due to remove protection film of double sided-tape. -. If we attached "Sponge MIC + double sided-tape" ass'y to top cover, we have big trouble to repair it because Spong MIC cannot detach for rework. You mean you should change Top cover Ass'y. And these method to attach between Top cover, Sponge MIc and double sided-tape needs design change and we need check MIC sealing performance. So currently we cannot accept your suggestion. | same as 9/29
2 | Open | Assembly issue on top cover: Top cover shall be pre-assembled with Gasket_case_top (MPN:4050-21730-500-0V) |  | Need to ask vendor to stick gaskets | It already discussed before. It will not detach gasket during delivery. This detachment makes some quality issue. If your factory assembe with defected gasket, then it can make air leakage issue after assembly. We keep asking to assemble in Foxconn factory. So we cannot accept
3 | Open | Screw issue on heat spreader: 2 type screw: M2.5x5mm, M3x7mm were required on the same heat spreader. --> Need 2 Ops to control different screw machine |  | Need to use 1 screw type only. ->suggest to use M2.5x5 mm because this screw type also be used on other assembly part. | 1. If we change screws from M3x7mm to M2.4x5mm, then it need to change Tooling, and we may use "insert nut" type for it. It makes cost increase. So we cannot accept. 2. We will check we can assemble M3x7mm screw when other M3x7mm assembly step. | will update after review FII mechnical SOP
4 | Open | Screw issue on bottom cover: 4 kinds of screw with different torque: M3x7(torque 3-3.5kgf*cm)*2pcs, M3x12(torque 5.5-6kgf*cm)*2pcs, M3x10(torque 5.5-6kgf*cm)*18pcs, M3x10(torque 3-3.5kgf*cm)*2pcs were required on the bottom cover. --> Need 4 OPs to control different screw machine |  | Suggesto to keep M3x7 on L/R side, M3x10mm on bottom site. (remove M3x12), and keep the torque consistent. | 1. If we remove M3x12mm screws, then it make assembly fault. The top cover area of those screws will bulge up. So we cannot accept. 2. We will check to use same screw for M3x10 2pcs and M3x7 2pcs (Torque 3~3.5kgf*cm). | M3x7(torque 3-3.5kgf*cm)*2pcs, M3x10(torque 3-3.5kgf*cm)*2pcs were required on the bottom cover. : can be change M3x7(torque 3-3.5kgf*cm)*2pcs on the bottom cover so Now M3x7(torque 3-3.5kgf*cm)*4pcs, : 2pcs on the bottom. 2pcs for side M3x12(torque 5.5-6kgf*cm)*2pcs, M3x10(torque 5.5-6kgf*cm)*18pcs, --> Need 3 OPs to control different screw machine for review the marge the M3X12 and M3X10, need to more time
5 | Closed | Hole dimension issue on bottom cover: ALT requirement: no need to paste rubber cover on the screw hole which is under rubber foot. Hover, the dimension of the screw hole is the same with others. It will make OP confused. |  | The dimension of screw hole which is under rubber foot shall be different from others (Fool-proofing). | You need to change tooling to accept your suggestion. We cannot accept your suggestion. So we think that you should make a process to avoid it. | first of all, ALT is don't care rubber cover under foot rubber. ALT will be not judge it as defect. But the screw cover material management should be done.
6 | Open | Assembly issue on LED board: LED board shall be pre-assembled with sponge |  | Need to ask vendor to stick sponge on front cover | There is no area to attach sponge on front cover. Even though vendor attach it, it will be detach easily. And it may cover LED LENS during assembly. So we cannot accept. | If attach sponge on front cover, need to more review for mold design side. Will update it
7 | Closed | Screw issue on main board 2 type screw: M3x7mm, M3x8mm were required on the main board. --> Need 2 Ops to control different screw machine |  | Need to use 1 screw type only. ->suggest to use M3x8 mm only. | We already asked to change it. So it will provide changed Parts after 2K delivery. | Clear. Next housing is fixed.
8 | Closed | Housing issue: Housing is easily scratched, dirty and adhered fingerprint. |  | Need to ask vendor to modify the outside of housing to prevent issue. Otherwise, please ask vendor to add PE bag or tray. If there is no any countermeasure, Fii has to buy the tray to prevent issues and increase MOH. | We will discuss with INKEL about it. After discussion, we will update you. | Apply PE bag packing

## top gap최소화 조립순서
관리번호 :
|  |  | 기 안 | 검 토 | 승 인
SKBB TOP COVER 고정시 좌,우 BKT부 밀착 先고정건
|  |  | / / | / / | / /
보
기
작업주의 |  | 1. 좌우 BKT 반드시 밀착 형합된 상태에서 스크류 고정 할것
2. 그외 나머지 ALL 스크류 고정 한다(GAP 확인)
결재완
2. 그외 스크류 ALL 고정 한다
2. The ohter screw assembly
1. 좌,우 사이드 BKT 부분 先 고정 한다
★ 반드시 밀착 눌러서 형합된 상태 고정 할것
1. R/L side bracket should be assembly frist.
. Press by hand to make it tight, then fix it with a screw