## Slide 1
50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
12/6 | 12/13 | 12/20 | 12/27 | 1/3’22 | 1/10 | 1/17 | 1/24 | 1/31 | 2/7 | 2/14 | 2/21 | 2/28 | 3/7 | 3/14 | 3/21 | 3/28 | 4/4 | 4/11 | 4/18 | 4/25 | 5/2 | 5/9 | 5/16 | 5/23 | 5/30 | 6/6 | 6/13
Milestone Swan
Milestone
2nd source
Non-P2P
SW
Certification
ALT design
2nd source
P2P (normal)
1st
sample build
ETA
TW
HW validation
SI testing
Synaptics fine tune SW
circuit
layout
Gerber out
PCB fab
2nd
sample build
ETA
TW
Control run
ECR
Approval
ETA
KR
Pre-test
(EMI/EMC)
8pcs sample
ETA
KR
Pre-test
(EMI/EMC)
Pre-test
(EMI/EMC)
Pre-test
(EMI/EMC)
KC
BMT
LED tuning
HW validation/SI testing
Climate Reliability @HC
2/11->2/22
Confirm if
PCBA fixed

## Slide 2
50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
12/6 | 12/13 | 12/20 | 12/27 | 1/3’22 | 1/10 | 1/17 | 1/24 | 1/31 | 2/7 | 2/14 | 2/21 | 2/28 | 3/7 | 3/14 | 3/21 | 3/28 | 4/4 | 4/11 | 4/18 | 4/25 | 5/2 | 5/9 | 5/16 | 5/23 | 5/30 | 6/6 | 6/13
2nd source part (pin to pin)
2nd source part (non pin to pin)
PIN to PIN Part (ALT request 41pcs sample)
Main source: Eth PHY Realtek RTL8211F-CG  2nd source: Motorcomm YT8531C
 ALT request to ship 3pcs sample from sample build, rest can be shipped after control run
Non PIN to PIN Part (ALT request 44pcs sample)
Main source:
BT CYPRESS CYW20704
2nd source: AMPAK W511
HWQA
Reliability
Test
Factory control run
HW RD
verify
SW change
Circuit design+
Layout change
PCB Fabrication
1st
Sample
Build
HW&SW RD verify
HWQA Reliability Test
RD
Receive 10pcs
sample
Ship
To
TW
SW change
2nd source part (non pin to pin)
Certification
Pre-test (EMI/EMC/RF)
Apply BQB/KC
Provide
BQB
report
to ALT
Factory control run
Circuit design+
Layout change
PCB Fabrication
2nd
Sample
Build
Ship
To
TW
Pre-test (EMI/EMC/RF)
CNY
Milestone Eagle
Target Risk Buy
(Motorcomm)
BMT
BMT
Milestone
RD release EC
RD release EC
Ship
To
KR
Ship
To
KR
Vendor only provide 15pcs free sample
Ship 3pcs
sample
To ALT
Buy
Motor
Comm
Sample
For
control
run