## Test schedule
K18X001 2nd Source Reliability Test Schedule Rev: 2.0
Climatic Test
No | Test Items | Q'ty | L/T | Test Location | Status | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01
1 | Cold Start Test | 2 | 3 | HC | bar: 2022-04-20 to 2022-04-22
2 | Hot Start Test |  | 3 | bar: 2022-04-23 to 2022-04-25
3 | High temperature & High humidity test - storage |  | 4 | bar: 2022-04-18 to 2022-04-21
4 | High Temperature & Humidity Test (Op) |  | 4 | bar: 2022-04-22 to 2022-04-25
5 | Operational Temperature cycle test |  | 6 | bar: 2022-04-26 to 2022-05-01
6 | Thermal shock (PCB only) | 3 | 3 | bar: 2022-04-27 to 2022-04-29
7 | Power On/Off with Temperature | 2 | 5 | bar: 2022-04-18 to 2022-04-22
8 | EDVT | 2 | 5 | bar: 2022-04-25 to 2022-04-29
9 | Abnormal power on/off (100 times) | 20 | 2 | bar: 2022-04-16 to 2022-04-17

## Reliability test plan
SWAN 2nd Source Reliability Test Plan Rev: 2.0 Document NO: RAD-HCP-202004002
No | Foxconn Test Items | Test Condition | Test Criteria | Q'ty | L/T | Test Location | Ref. Doc | Remark
1 | Cold Start Test | Power off, Storage, Ta = -20℃ Storage 48 hours then ramp the temperature to 0℃, power on operation test Power on/off 15 times | 1. No functional failures both before and after the test. 2. No performance degradation during the functional test 3. No visual damage to the products during inspection, such as warpage, peeling, missing pixels, discoloration, etc. | 2 | 3 | HC | IEC 60068-2-01
2 | Hot Start Test | Power off, Storage, Ta = 70℃ Storage 48 hours then ramp the temperature to 50℃, power on operation test Power on/off 15 times |  |  | 3 | HC | IEC 60068-2-02
3 | High temperature & High humidity test - storage | 1. Temperature 70℃ 2. Humidity 90%RH 3. Test period 72 hours |  |  | 4 | HC | IEC 60068-2-30
4 | High Temperature & Humidity Test (Op) | Power on, Operation, Ta = 50℃, Humi.= 95%R.H. for 72 hours | 1. No functional failures both before and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 2 | 4 | HC | IEC 60068-2-30
5 | Operational Temperature cycle test | Power on 1. 25℃ for 1 hr 2. 25℃ to -5℃ for 2 hrs 3. -5℃ for 13 hrs 4. -5℃ to 25℃ for 2 hrs 5. 25℃/65% for 1 hr 6. 25℃/65% to 50℃/95% for 2 hrs 7. 50℃/95% for 13 hrs 8. 50℃/95% to 25℃ for 2 hrs Repeat 1~8 for 2 cycles 9. 25℃/60% for 48 hrs Total for 120 hrs | 1. No functional failures both during and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 2 | 6 | HC | IEC 60068-2-30
6 | Thermal shock (PCB only) | Power off , non-operation Ta= -20℃ (30min) ~ 70℃(30min) 60 cycles Transfer time: 5 min | 1. No functional failures both before and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 3 | 3 | HC | MIL –STD-810F
7 | Power On/Off with Temperature | 1. Power on: 50 sec. (follow product characteristic) 2. Power off: 10 sec. (follow product characteristic) 3. Temperature: -5°C and 50°C 4. Vin: follow customer's spec or MRS 5. Cycle: 2500 cycles per test condition 6. Total 5000 cycles | 1. No functional failures both before and after the test. 2. No performance degradation after the functional test. 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 2 | 5 | HC | IEC 60068-2-1
8 | EDVT | Verify the hardware design by exposure of the product to wider temperature, voltage and frequency margining. Test Temp. at -5/50 °C | No functional failures both during and after the test | 2 | 5 | HC | NA
9 | Abnormal power on/off (100 times) | 1. Power on: 50 sec. (follow product characteristic) 2. Power off: 2 sec. (follow product characteristic) 3. Vin: follow customer's spec or MRS 4. Cycle: 100 times | 1. No functional failures both before and after the test. 2. No performance degradation after the functional test. 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 20 | 2 | HC | NA

## Allocation
Test Sample Allocation
Dept. | Location | Items | Sample | Total L/T (Day) | Test Engineer | Ext.
HMQA | HC | 9 | 20 units | 16 | Jackson | 550-6712
| Total | 9 | 20 units | 16