## ALT owned DFM
No. | Status | What | Enclosed Picture | PCB 設計規範條例 | Recommendation | ALT Remark | image | Fii Remark 0202 | ALT Remark 0204 | Fii/ALT discussion 2/19 | ALT Remark 0318 | ALT Remark 0726 | Fii Remark 0928 | ALT Remark 0929
1 | Monitor | Add glue issue: When add glue, Glue may be dropped into inside port of HDMI |  |  | Can skip the glue on both side of HDMI connector? | ALT : instade glue, can use SMT Glue on HDMI |  | Cannot accept. Once there are issues with boards the rework be be a big problem. | Fii decide choose one of solution | ALT agreed to add the glue from later half of the connector for DVT2 and check
2 | Closed | Add glue issue: Add glue may be make PCBA become dirty, and impact to visual of parts if glue is over on sufrace of component |  |  | Need check and help to solve issue: Modify layout/ change requirement to add glue, etc… | ALT : instade glue, can use SMT Glue on Ethernet / DC JACK |  | Still the same issue no matter when the glue is added. | Fii decide choose one of solution
3 | Monitor | Assembly issue: Bracket side led need to be stick more gasket 484.00429.005 & 484.00430.005 |  |  | Need to ask vendor to stick gasket | ALT : Next production, vender will be subassembled |  | OK |  | ok |  | check with vender, I will update it. | ALT commented that will apply from 1st MP (2K).
4 | Monitor | Speaker cable issue: 1. Length of wire at midragne & Tweeter speaker is short --> sponge is easily broken 2. Length of wire at woofer speaker is long alittle |  |  | Need check and update spec | ALT : review DVT sample first, will update before next production |  | OK | ALT FII suggest each cable length. ALT will update as your suggestion | ok | Check cable drawing and please feedback. https://mantis.cnsbg.foxconn.com/vaas/view.php?id=1131#c6428
5 | Monitor | Speaker cable issue: Rubber of speaker cable is so tight. Need a lot of strength to put in |  |  | Need check and improve | ALT : 'Not accpectable, due to air leackage |  | Will discuss with factory |  | ok
6 | Open | Speaker cable issue: 1. Lock of cable to connect with speaker is very tight 2. Small lock is remove so hard |  |  | 1. Need vendor to modify size of pin on speaker or lock of cable 2. Modify design of small lock as big lock | ALT : will check with vender (Dreamus), let you know |  | ok |  | ok |  | ALT is dicussed with vender and Inkel. Woofer SPK is the beginning of vibration. So, Need to more tight. Because It must not unlock during operation. Please see the image that the SOP update for insert way fix our suggestion to more easy unlock. |  | ALT already guided how operator can pull out the cable.
7 | Monitor | Assembly issue: When assembly speaker, speaker cable has confliction with housing because of the black tube is too hard to bend |  |  | Need check and improve | ALT : will check with vender (Dreamus), let you know |  | ok |  | ok | changed SPK design. ALT/Inkel expect this issue clear
8 | Monitor | Assembly issue: Speaker has not Fix-boss --> Need to use hand fix speaker to drive svrew |  |  | Modify housing to add fix-boss or a sink area to locate speaker better for locking the screws | INKEL : It can be assembled using conditions "a" and "b" ALT : first Screw tightening "a" area, next "b" area. It will be fixed in screw hole place. |  | The suggesting is for the positioning and make it easy to drive the screw while the speaker is fixed in a location and doesn't slide. |  | ALT will have Inkel revise after DVT2 | changed SPK design. ALT/Inkel expect this issue clear
9 | Monitor | Assembly issue: Distance from surface of speaker to surface of inside housing is only 7.2mm but BOM reuqest to use screw M3x10mm |  |  | Need Check and confirm | ALT : it can use M3x10mm screw' INKEL : If the outer diameter("a") of the thread on the opposite side of the screw is small, a problem may occur in the tightening force. (The possibility of occurrence of defects was blocked in advance. It is applied to sound products with high output.) |  | ok |  | ok
10 | Closed | Assembly issue: Port 476.00295.005 & 476.00296.005 is similar. They aren't designed to prevent assemble wrong part --> May be assemble wrong |  |  | Need check and improve | ALT : DVT2 housing is update. Top and R/L is engraved |  | ok |  | ok | Removed port for DVT3.
11 | Monitor | Assembly issue: RD request to use scre M3x4mm to assemble LED board. It it too short while thread pitch is big --> Easily happened strip thread of housing |  |  | Check and modify design: Length of screw, screw type, size of hole…. | ALT : This is DVT only. Will improved next production INKEL : The screw is designed to apply 3x7mm(Bind Head) |  | ok |  | ok
12 | Monitor | Front cover issue: Hole on Front cover and rubber gril holder cannot match well because the front cover is too long and the tolerance affects the assembly |  |  | Need check and feedback to vendor to improve | ALT : This is DVT only. Will improved next production INKEL : The reason is that the size of the injection part is short. |  | ok |  | ok | Check it out on DVT3 and let me know any issue
13 | Open | Design issue: Space between button and switch is only 0.1mm --> Easily happen switch is jammed |  |  | Need check and modify design: Space between button and switch is 0.3-0.5mm | ALT : actually this is not a jammed switch. This is designed gap to reduce vibration noise.. Inkel : Movement(deformation) of the part is impossible due to conditions "a" and "b". And the failure rate is low due to the flexible design of condition "c" |  | ok. But there are jammed buttom issues reported which will need to cut the edge |  | ALT will have Inkel revise after DVT2 | Check it out on DVT3 and let me know any issue | the root cause of button switch jammed is Top case burr, Not to gap the burr is make switch jammed. If you have switch jammed STB, remove the burr, will be clear the issue the vender will make CTQ point as below | The button is still deformed. | We will discuss with INKEL how they can manage Burr, and we will feedback to you.
14 | Open | Add glue issue: After add glue on PCB & bushing. Glue need to spend time to dry. |  |  | The glue Inkel brought to the line also takes a long time. This will be an issue for assembly and testing. For bushing, the glue is damaged easily during assembly. ALT advised vendor cannot trade with any Fii QVL. Possible for buy and sell? | ALT : Please contact to belew vender. This vender is supply FFC to Speaker company (Inkel, Anam) also was supplied Foxconn Also we checked can make Swan side FFC with Bushing Sponge. 업체명: Hwa Sung Elecom Co., Ltd 담당자: Gil-Hwan Jeong(Deputy General Manager) 연락처: 010-2046-6084(h870420@hanmail.net) |  | under checking |  | Fii is checking with vendor | Please share the status, I check with Hwa Sung Elecom, they need to make mold for bushing. And need 14days for tooling mold. I think we don't have much time to prepare DVT3 meterials |  | We can's apply glue on the bottom side, because our employee's fingers will touch the glue during assembly, which will be very dangerous. | 1. What kinds of issue you have ? Could you explain what is the dangerous issue , such as broken bushing or broken FFC cable ? 2. How long does it take to dry glue ? Can you adjust assembly step and give time to dry for Glue ?
15 | Closed | Heat spreader issue: Heat spreader 400.01103.005 is too long but it isn't not drive screw to fix well in housing --> Have risk heat spread deformed and touch pin of DIP part & smt parts at bottom side on PCBA |  |  | 1. Add more one screw to fix heat spreader 2.Use gasket cover on heat spreader to prevent pin of DIP parts touch heat spreader |  |  |  | Contact to Foxconn Thermal team. This thermal solution is designed by Foxconn 1. Need to SoC Bottom plate update by Fii 2. Need to the gasket cover on heat spreader by Fii | Fii ME prepares 3D file for ALT to check with Inkel | Updates, Check 3d modeling data 0001171: [SWAN] 3D modeling data with Inkel and Foxconn - for DVT3 (T0) Please note that, Please note that, for screw with bottom heat spreader, the screw boss height change 6mm to 4mm. But assembly boss (Green) height is not changed. Be careful not to damage when assembling heatspreader / PCBA
16 | Closed | Assembly issue: Wire mount 471.00105.005 is defined to stick on rib of bottom --> It is easily shaked and fixed not well |  |  | Need RD check and modify housing to put wire mount better |  |  |  | ALT Not accpectable Please search more smaller hook Or change the attachment structure | ok | Check it out on DVT3 and let me know any issue
17 | Open | Housing issue: Housing is easily scratched, dirty and adhered sweat. |  |  | Please modify outside of housing to prevent issue. If it cannot be improved, please add the protected film | [6 empty] | ALT is still discuss with vender and customer. Be careful in the factory for scratched, dirty and adhered sweat during assembly | Inkel doesn't deliver the housing with any protected film in preMP. The housing is still easily scratched. | We are reviewing with INKEL on protection film now.
18 | Monitor | Assembly issue: RD/Customer request to use big torque to drive screw -->Threat on screw boss & copper on PCB are damaged |  |  | Need check and confirm | [6 empty] | assembly with PCBA and housing, Please apply FII stanrad torque
19 | Open | Design issue: There is a gap between bottom cover and the side deco --> There is a gap between bottom cover and the side deco after assembly. |  |  | Please modify housing to prevent issue. Populate this gap. | [8 empty] | We already provide assembly guide. Is there any issue to follow assembly guide ? It was commented by INKEL, and we tried to follow their guide and there is no issue.
20 | Open | Design issue: 3D has positioning pin, and the actual there is no this pin. --> The PCB will easy shift during assembly. |  |  | Please add positioning pin on bottom cover. | [8 empty] | It will apply from MP(2K).
21 | Open | Assembly issue: Use 5.5kgf/cm torque to fixed top cover and bottom cover. --> The screw boss is easily damaged. |  |  | Please change the torque. | [8 empty] | We are checking on it. We are waiting for final mold from INKEL. We will updae after review your guide.
a
b
a
b
d
c
a
b
a
TOP
R or L

## MOH cost down DFM
No. | Status | What | Enclosed Picture | Recommendation | Comment from ALT(9/29)
1 | Open | Assembly issue on top cover: 1. Sponge MIC (MPN:4050-21732-500-0V) shall be pre-assembled with double-sided tape 2. Sponge MIC (MPN:4050-21732-500-0V) shall be pre-assembled on top cover |  | 1. Need to ask vendor to stick double-sided tape on Sponge MIC 2. Need to ask vendor to stick Sponge MIC on top cover | 1. Double sided-tape cannot attach Sponge MIC due to material characteristics of Sponge MIC. We are trying to find alternative solution now. We will update it next week. 2. It is difficult to accept your guide. The reasons are -. Again above issue. Sponge MIC cannot be attached to Double sided-tape. Spong MIC has some oil itself, so it is impossible to keep attaching. -. Even though we find a way to keep Sponge MIC to double sided tape, you should pull out "Sponge MIC + double sided-tape" ass'y from the top cover due to remove protection film of double sided-tape. -. If we attached "Sponge MIC + double sided-tape" ass'y to top cover, we have big trouble to repair it because Spong MIC cannot detach for rework. You mean you should change Top cover Ass'y. And these method to attach between Top cover, Sponge MIc and double sided-tape needs design change and we need check MIC sealing performance. So currently we cannot accept your suggestion.
2 | Open | Assembly issue on top cover: Top cover shall be pre-assembled with Gasket_case_top (MPN:4050-21730-500-0V) |  | Need to ask vendor to stick gaskets | It already discussed before. It will not detach gasket during delivery. This detachment makes some quality issue. If your factory assembe with defected gasket, then it can make air leakage issue after assembly. We keep asking to assemble in Foxconn factory. So we cannot accept
3 | Open | Screw issue on heat spreader: 2 type screw: M2.5x5mm, M3x7mm were required on the same heat spreader. --> Need 2 Ops to control different screw machine |  | Need to use 1 screw type only. ->suggest to use M2.5x5 mm because this screw type also be used on other assembly part. | 1. If we change screws from M3x7mm to M2.4x5mm, then it need to change Tooling, and we may use "insert nut" type for it. It makes cost increase. So we cannot accept. 2. We will check we can assemble M3x7mm screw when other M3x7mm assembly step.
4 | Open | Screw issue on bottom cover: 4 kinds of screw with different torque: M3x7(torque 3-3.5kgf*cm)*2pcs, M3x12(torque 5.5-6kgf*cm)*2pcs, M3x10(torque 5.5-6kgf*cm)*18pcs, M3x10(torque 3-3.5kgf*cm)*2pcs were required on the bottom cover. --> Need 4 OPs to control different screw machine |  | Suggesto to keep M3x7 on L/R side, M3x10mm on bottom site. (remove M3x12), and keep the torque consistent. | 1. If we remove M3x12mm screws, then it make assembly fault. The top cover area of those screws will bulge up. So we cannot accept. 2. We will check to use same screw for M3x10 2pcs and M3x7 2pcs (Torque 3~3.5kgf*cm).
5 | Open | Hole dimension issue on bottom cover: ALT requirement: no need to paste rubber cover on the screw hole which is under rubber foot. Hover, the dimension of the screw hole is the same with others. It will make OP confused. |  | The dimension of screw hole which is under rubber foot shall be different from others (Fool-proofing). | You need to change tooling to accept your suggestion. We cannot accept your suggestion. So we think that you should make a process to avoid it.
6 | Open | Assembly issue on LED board: LED board shall be pre-assembled with sponge |  | Need to ask vendor to stick sponge on front cover | There is no area to attach sponge on front cover. Even though vendor attach it, it will be detach easily. And it may cover LED LENS during assembly. So we cannot accept.
7 | Open | Screw issue on main board 2 type screw: M3x7mm, M3x8mm were required on the main board. --> Need 2 Ops to control different screw machine |  | Need to use 1 screw type only. ->suggest to use M3x8 mm only. | We already asked to change it. So it will provide changed Parts after 2K delivery.
8 | Open | Housing issue: Housing is easily scratched, dirty and adhered fingerprint. |  | Need to ask vendor to modify the outside of housing to prevent issue. Otherwise, please ask vendor to add PE bag or tray. If there is no any countermeasure, Fii has to buy the tray to prevent issues and increase MOH. | We will discuss with INKEL about it. After discussion, we will update you.