## Project DFM Record
|  | Project | K18X001.00 | DFM
|  | From | SMT | NPI Report | REV:01
Rev | Author | PCB Ver. | DFM Update | Updated Reason |  | Released Date
01 | Khiem Tran | 115 | Pilot run | The first time assembly |  | 2020-01-26
02
03
04
05
06
07
08
09
10

## V001
No. | Status | What | Enclosed Picture | PCB 設計規範條例 | Recommendation | Remark | image | notation 2/1
1 | Open | Add glue issue: When add glue, Glue may be dropped into inside port of HDMI |  |  | Can skip the glue on both side of HDMI connector? | ALT : instade glue, please use SMT Glue on HDMI
2 | Open | Add glue issue: Add glue may be make PCBA become dirty, and impact to visual of parts if glue is over on sufrace of component |  |  | Need check and help to solve issue: Modify layout/ change requirement to add glue, etc… | ALT : instade glue, SMT Glue on Ethernet / DC JACK
3 | Open | Assembly issue: Bracket side led need to be stick more gasket 484.00429.005 & 484.00430.005 |  |  | Need to ask vendor to stick gasket | ALT : Next production, vender will be subassembled
4 | Open | Speaker cable issue: 1. Length of wire at midragne & Tweeter speaker is short --> sponge is easily broken 2. Length of wire at woofer speaker is long alittle |  |  | Need check and update spec | ALT : review DVT sample first, will update before next production
5 | Open | Speaker cable issue: Rubber of speaker cable is so tight. Need a lot of strength to put in |  |  | Need check and improve | ALT : 'Not accpectable, due to air leackage
6 | Open | Speaker cable issue: 1. Lock of cable to connect with speaker is very tight 2. Small lock is remove so hard |  |  | 1. Need vendor to modify size of pin on speaker or lock of cable 2. Modify design of small lock as big lock | ALT : check with vender (Dreamus)
7 | Open | Assembly issue: When assembly speaker, speaker cable has confliction with housing because of the black tube is too hard to bend |  |  | Need check and improve | ALT : check with vender (Dreamus)
8 | Open | Assembly issue: Speaker has not Fix-boss --> Need to use hand fix speaker to drive svrew |  |  | Modify housing to add fix-boss or a sink area to locate speaker better for locking the screws | INKEL : It can be assembled using conditions "a" and "b"
9 | Open | Assembly issue: Distance from surface of speaker to surface of inside housing is only 7.2mm but BOM reuqest to use screw M3x10mm |  |  | Need Check and confirm | ALT : it can use M3x10mm screw' INKEL : If the outer diameter("a") of the thread on the opposite side of the screw is small, a problem may occur in the tightening force. (The possibility of occurrence of defects was blocked in advance. It is applied to sound products with high output.)
10 | Open | Assembly issue: Port 476.00295.005 & 476.00296.005 is similar. They aren't designed to prevent assemble wrong part --> May be assemble wrong |  |  | Need check and improve | DVT2 housing is update. Top and R/L is engraved
11 | Open | Assembly issue: RD request to use scre M3x4mm to assemble LED board. It it too short while thread pitch is big --> Easily happened strip thread of housing |  |  | Check and modify design: Length of screw, screw type, size of hole…. | ALT : This is DVT only. Will improved next production INKEL : The screw is designed to apply 3x7mm(Bind Head)
12 | Open | Front cover issue: Hole on Front cover and rubber gril holder cannot match well because the front cover is too long and the tolerance affects the assembly |  |  | Need check and feedback to vendor to improve | ALT : This is DVT only. Will improved next production INKEL : The reason is that the size of the injection part is short.
13 | Open | Assembly issue: Top cover need to stick gasket 484.00422.005 & 484.00423.005 |  |  | Need to ask vendor to stick gaskets | ALT : Not accpectable. If sub assembly in vender, this gasket must be damaged durnig transportation.
14 | Open | Front cover issue: Have to stick a rubber before shipping to factory |  |  | Need to ask vendor to stick this rubber by adhesive tape | ALT : 1. Not accpectable. This is reladed FFV MIC performance. 2. cost impacked. need to pay FXN
15 | Open | Design issue: Space between button and switch is only 0.1mm --> Easily happen switch is jammed |  |  | Need RD check and modify design: Space between button and switch is 0.3-0.5mm | ALT : actually this is not a jammed switch. This is designed gap to reduce vibration noise.. Inkel : Movement(deformation) of the part is impossible due to conditions "a" and "b". And the failure rate isl ow due to the flexible design of condition "c"
16 | Open | Add glue issue: After add glue on PCB & bushing. Glue need to spend time to dry. |  |  | The glue Inkel brought to the line also takes a long time. This will be an issue for assembly and testing. For bushing, the glue is damaged easily during assembly. ALT advised vendor cannot trade with any Fii QVL. Possible for buy and sell? | ALT : Please contact to belew vender. This vender is supply FFC to Speaker company (Inkel, Anam) also was supplied Foxconn Also we checked can make Swan side FFC with Bushing Sponge. 업체명: Hwa Sung Elecom Co., Ltd 담당자: Gil-Hwan Jeong(Deputy General Manager) 연락처: 010-2046-6084(h870420@hanmail.net)
a
b
a
b
d
c
a
b
a
TOP
R or L