## All DFM Issues
Project DFM List : |  |  |  | K18X001.00 | DFM Status
PCB Version: |  |  |  | 115 | open | 49
Gerber Review Date: |  |  |  | 2020-12-01 | Monitor | 0
Pilot Run Date: |  |  |  | 2021-12-28 | Close | 0
No. | Status | Severity | What | Enclosed Picture | Recommendation | Suggested Picture | discussion 1/29 | Temp solution
01 | Open | P2 | Layout issue: Space between J809 & R2994 is small --> Hard to add glue for power J809 part |  | 1. Modify layout: Space between J809 & R2994 over 10mm 2. Need RD check whether have to add glue full around part or not |  | revise into next build | NA
02 | Open | P1 | Add glue issue: Customer requests to add white glue for Power jack, RJ45 port, HDMI port, Power port --> It makes difficult for repair if PCBA has defect. |  | 1. Layout small part far away these part to prevent glue overlap them 2. Need to Test function of these group before add white glue |  | already moved the ehternet and HDMi related testing items to PT. After testing PT OK then adding the glue | Re-arrange ethernet, HDMI related test stations before assembly
03 | Open | P1 | Add glue issue: When add glue, Glue may be dropped into inside port of HDMI |  | Need RD check and find improverment |  | ALT owned | Remove the extra glue in the connector
04 | Open | P1 | Add glue issue: Space between RJ 45 HDMI & Power port is small --> Difficult to add glue |  | Need RD check and help to solve issue: Modify layout/ change requirement to add glue, etc… |  | checks the spec for the injection point with glue vendor | NA
05 | Open | P1 | Add glue issue: Add glue may be make PCBA become dirty, and impact to visual of parts if glue is over on sufrace of component |  | Need RD check and help to solve issue: Modify layout/ change requirement to add glue, etc… |  | ME RD checks the spec for the injection point with glue vendor | NA
06 | Open | P2 | Layout issue: PCB isn't marked limit area to add glue |  | Need to add marking on PCB |  | revised in next build for areas without components | NA
07 | Open | P1 | Housing issue: Housing has not fix-boss to locate heat spreader during assembly |  | Add Fix-boss to locate Heat spreader well |  | could add the fix-boss but the locations need to re-evaluate by ME RD. Plz prepare the propsoal to inform ALT. | NA
08 | Open | P1 | Heat spreader issue: Heat spreader 400.01103.005 is too long but it isn't not drive screw to fix well in housing --> Have risk heat spread deformed and touch pin of DIP part & smt parts at bottom side on PCBA |  | 1. Add more one screw to fix heat spreader 2.Use gasket cover on heat spreader to prevent pin of DIP parts touch heat spreader |  | could add the fix-boss but the locations need to re-evaluate by ME RD. Plz prepare the propsoal to inform ALT. | NA
09 | Open | P1 | Assembly issue: Our factory need to stick 5pcs thermal pad (480.01930.005& 480.01931.005) --> Add more operation -->Have to add more OP and layout area for this step |  | Suggest to vendor of heat spreader 400.01103.005 to stick these thermal pad before export for use |  | check with sourcer | NA
10 | Open | P2 | Assembly issue: Switch power cable issue: 1. Cable has confliction with housing 2. Cable isn't designed to prevent assemble cable reverse into housing |  | Need RD check and modify design |  | RD checks with vendor if smaller power switch. Mifght need Inkel to modify the tooling Check if possible to bend the conneting area to prevent the wrong assembly. | NA
11 | Open | P2 | ANT issue: BT Antenna 361.01405.005 is so long |  | Need RD check and modify the length of wire |  | ME RD evaluates the length again | NA
12 | Open | P2 | Layout issue: When buckle ANT, tooling may press to small part near ANT |  | Please help to check and move small part far away ANT header |  | need to check | NA
13 | Open | P1 | Assembly issue: Our factory need to stick 5pcs thermal pad (480.01929.005& 480.01931.005) --> Add more Operation -->Have to add more OP and layout area for this step |  | Suggest to vendor of heat spreader 400.01108.005 to stick these thermal pad before export for use |  | check with sourcer | NA
14 | Open | P1 | Layout issue: To fix heat spreader 400.01108.005 need to use 2 type screw : M2.5x5mm (401.00634.005) & M3x7mm (401.01460.005) --> Have to split to 2 step ( 2 person & 2 drive screw machine) |  | Please check and modify design to use 1 screw type to fix this heat spreader |  | check with ALT if the housing could be modified to apply the same screw. Need ME to provide the proposal. Onlt the yellow pieces) | NA
15 | Open | P1 | Assembly issue: Bracket side led need to be stick more gasket 484.00429.005 & 484.00430.005 |  | Need to ask vendor to stick gasket |  | will inform ALT | NA
16 | Open | P1 | Assembly issue: Buckle FPC cable into connector on LED side board is difficultly. Special with the right led side board |  | Need RD check and improve |  | Need to add the acetate tape*2 for side LED boards, but need to check if enough materials…Total usage is 16pcs=>PM Bi CFM enough The already assembled 6pcs need to rework. | NA
17 | Open | P1 | Assembly issue: Wire mount 471.00105.005 is defined to stick on rib of bottom --> It is easily shaked and fixed not well |  | Need RD check and modify housing to put wire mount better |  | Total usage is 3pcs. Need RD to provide the drawing to illustrate to ALT | only use 1 wire mount to fix speaker cable but still use acatate tape for FFC cable
18 | Open | P1 | Speaker cable issue: 1. Length of wire at midragne & Tweeter speaker is short --> sponge is easily broken 2. Length of wire at woofer speaker is long alittle |  | Need RD check and update spec |  | The advised length is to be evaluated | NA
19 | Open | P2 | Speaker cable issue: Rubber of speaker cable is so tight |  | Need RD check and improve |  | will inform ALT | NA
20 | Open | P1 | Speaker cable issue: 1. Lock of cable to connect with speaker is very tight 2. Small lock is remove so hard |  | 1. Need RD check and feedback to vendor to modify size of pin on speaker or lock of cable 2. Modify design of small lock as big lock |  | will inform ALT | NA
21 | Open | P2 | Assembly issue: When assembly speaker, speaker cable has confliction with housing because of the black tube. |  | Need RD check and improve |  | will inform ALT | NA
22 | Open | P1 | Assembly issue: Speaker has not Fix-boss --> Need to use hand fix speaker to drive svrew |  | Modify housing to add fix-boss to locate speaker better |  | Need a positioning area .Will inform ALT. | NA
23 | Open | P2 | Assembly issue: Distance from surface of speaker to surface of inside housing is only 7.2mm but BOM reuqest to use screw M3x10mm |  | Need RD Check and confirm |  | Need ME proposal to inform ALT | NA
24 | Open | P1 | Assembly issue: Port 476.00295.005 & 476.00296.005 is similar. They aren't designed to prevent assemble wrong part --> May be assemble wrong |  | Need RD check and improve |  | will inform ALT | NA
25 | Open | P1 | Speaker cable issue: 1. Left woofer cable (377.00301.005LT) is put over board to assemble with connector on PCB --> Assembly is more complex 2. The length of wire is not enough to assemble as design |  | 1. Please check whether can modify layout to move connector the left 2. Modify length of wire |  | HWRD feedback not possible to change | remove wire sandle-1 and put wire over AMP heat spreader top
26 | Open | P1 | FPC cable issue: OP confirm difficultly that FPC cable is put into connector OK or not |  | Add more a marking line to OP can confirm put FPC OK or not |  | Will check with the vendor | NA
27 | Open | P2 | FPC cable issue: During assemble FPC cable, we need to spend more time to confirm what is FPC cable is true |  | Suggest to print name of FPC cable on the wire |  | Need to check with vendor if possible to change the blue color for each cable. | NA
28 | Open | P1 | FPC cable issue: The left&right led side FPC cable have not marking to OP know how to set FPC cable into housing is enough long to assemble led side board |  | Add marking on FPC cable |  | check with vendor how to do the positioning mark | NA
29 | Open | P2 | FPC cable issue: Led side FPC cable has conflict with screw boss on housing |  | 1.Please check and modify design to prevent conflict 2.Please check whether need to vendor help to fold fpc cable to prevent confliction |  | Cables for DVT2 will not have such issues | NA
30 | Open | P2 | FPC cable issue: When assembly, FPC cable need to be fixed and folded |  | Please update spec to vendor help us fold FPC cable |  | Cables for DVT2 will not have such issues | NA
31 | Open | P2 | Assembly issue: We have to stick thermal pad 480.01932.005 &480.01979.005 on heat spreader AMP top |  | Suggest to vendor stick these thermal pads on heat spreader 400.01109.005 |  | check with sourcer | NA
32 | Open | P1 | Design issue: Thermal pad on heat spreader AMP bottom is over lap on FPC cable and adhesive tape |  | Need RD check and improve design |  | revise for next build | NA
33 | Open | P1 | Design issue: Thermal pad on heat spreader AMP bottom is not touch on IC location |  | Need RD check and improve design |  | revise for next build | NA
34 | Open | P1 | Layout issue: PCB has not any marking to OP stick adhesive tape exactly |  | Add marking on AMP PCB to mark area to put FPC cable and stick adhesive tape |  | revise for next build | NA
35 | Open | P1 | Layout issue: FPC cable is overlap on pin of Ecap --> Risk FPC cable will be damaged |  | Need RD check and modify layout of AMP board to improve |  | Will need to modify the routing after DVT2 | 2021/01/27: Temporary, we cut off pin of E-cap and stick a sponge over on pin of E-cap
36 | Open | P1 | Assembly issue: Because we need to fix FPC cable by 2 tape --> Button FPC cable is short a little |  | Need RD check and modify length of cabel |  | will change the length of button FPC cable in next build | NA
37 | Open | P1 | Assembly issue: RD request to use scre M3x4mm to assemble LED board. It it too short while thread pitch is big --> Easily happened strip thread of housing |  | Check and modify design: Length of screw, screw type, size of hole…. |  | will inform ALT | NA
38 | Open | P2 | Layout issue: Label of Led board is on top side but we can't see label after assemble board into front cover |  | Modify layout: put label on bottom side and modify panel drawing: reverse led board |  | revise into next build | NA
39 | Open | P1 | Front cover issue: Hole on Front cover and rubber gril holder is skew too much because the front cover is too long and the tolerance affects. |  | Need RD check and feedback to vendor to improve |  | will inform ALT | NA
40 | Open | P1 | Assembly issue: Top cover need to stick gasket 484.00422.005 & 484.00423.005 |  | Need to ask vendor to stick gaskets |  | will inform ALT | NA
41 | Open | P2 | Front cover issue: Have to stick a rubber before shipping to factory |  | Need to ask vendor to stick this rubber by adhesive tape |  | will inform ALT | NA
42 | Open | P1 | Design issue: Space between button and switch is only 0.1mm --> Easily happen switch is jammed |  | Need RD check and modify design: Space between button and switch is 0.3-0.5mm |  | will inform ALT | 2021/01/27: We detected 2/6pcs "+" button is jammed
43 | Open | P1 | Thermal pad issue: Thermal pad 480.01929.005 (15x15x0.25mm) is too slight --> Take thermal pad so hard, and thermal pad is easily broken |  | Need RD check and improve issue |  | will check with vendor | NA
44 | Open | P1 | PMD issue: PMD is still not clearly and not exactly |  | Need RD check and update PMD document as newest changing |  | will revise PMD | NA
45 | Open | P1 | BOM issue: Q'ty of material is not same with BOM |  | Need RD check and update q'ty of material again |  | will revise BOM | NA
46 | Open | P1 | Add glue issue: After add glue on PCB & housing. Glue need to spend time to dry. |  | Need RD check whether have to wait glue dry before test or not |  | To be discussed pn 1/29 after 文謙checking | NA
47 | Open | P1 | Material issue: Glue 593.00152.005 as Inkel suggest is so watery --> It is unavailable to use adding glue machine (air gun) |  | Please give for us method to use this glue better |  | check with vendor | NA
48 | Open | P1 | Material issue: Package of Glue 593.00152.005 is tube and the the nozzle of tube is short and big --> stick glue into housing hard and may make dirty |  | Please help to ask vendor to change package of glue or whether they can support for us the nozzle longer and smaller to stick glue better |  | check with vendor | NA
49 | Open |  | No fix-boss for heatsink under main board |  |  |  | Will check how to modify may affect layout | NA
Note on F3: the open issue should has a risk of the yield rate or reliability or efficiency etc..for the projrct
Note on F4: when the open DFM issue has the improved solution, but the solution is still not be verified, the open DFM issue should change the "open" to "monitor". But once this solution is verified "fail", the status also change "monitor" to "open".
Note on F5: the improved solution of the open issue had been verified this is valid, only just so, the staus can change "open" or "monitor" to "close"

## ALT owned
No. | Status | What | Enclosed Picture | PCB 設計規範條例 | Recommendation | ALT Remark | image | Fii Remark 0202 | ALT Remark 0204
1 | Open | Add glue issue: When add glue, Glue may be dropped into inside port of HDMI |  |  | Can skip the glue on both side of HDMI connector? | ALT : instade glue, can use SMT Glue on HDMI |  | Cannot accept. Once there are issues with boards the rework be be a big problem. | Fii decide choose one of solution
2 | Open | Add glue issue: Add glue may be make PCBA become dirty, and impact to visual of parts if glue is over on sufrace of component |  |  | Need check and help to solve issue: Modify layout/ change requirement to add glue, etc… | ALT : instade glue, can use SMT Glue on Ethernet / DC JACK |  | Still the same issue no matter when the glue is added. | Fii decide choose one of solution
3 | Open | Assembly issue: Bracket side led need to be stick more gasket 484.00429.005 & 484.00430.005 |  |  | Need to ask vendor to stick gasket | ALT : Next production, vender will be subassembled |  | OK
4 | Open | Speaker cable issue: 1. Length of wire at midragne & Tweeter speaker is short --> sponge is easily broken 2. Length of wire at woofer speaker is long alittle |  |  | Need check and update spec | ALT : review DVT sample first, will update before next production |  | OK | ALT FII suggest each cable length. ALT will update as your suggestion
5 | Open | Speaker cable issue: Rubber of speaker cable is so tight. Need a lot of strength to put in |  |  | Need check and improve | ALT : 'Not accpectable, due to air leackage |  | Will discuss with factory
6 | Open | Speaker cable issue: 1. Lock of cable to connect with speaker is very tight 2. Small lock is remove so hard |  |  | 1. Need vendor to modify size of pin on speaker or lock of cable 2. Modify design of small lock as big lock | ALT : will check with vender (Dreamus), let you know |  | ok
7 | Open | Assembly issue: When assembly speaker, speaker cable has confliction with housing because of the black tube is too hard to bend |  |  | Need check and improve | ALT : will check with vender (Dreamus), let you know |  | ok
8 | Open | Assembly issue: Speaker has not Fix-boss --> Need to use hand fix speaker to drive svrew |  |  | Modify housing to add fix-boss or a sink area to locate speaker better for locking the screws | INKEL : It can be assembled using conditions "a" and "b" ALT : first Screw tightening "a" area, next "b" area. It will be fixed in screw hole place. |  | The suggesting is for the positioning and make it easy to drive the screw while the speaker is fixed in a location and doesn't slide.
9 | Open | Assembly issue: Distance from surface of speaker to surface of inside housing is only 7.2mm but BOM reuqest to use screw M3x10mm |  |  | Need Check and confirm | ALT : it can use M3x10mm screw' INKEL : If the outer diameter("a") of the thread on the opposite side of the screw is small, a problem may occur in the tightening force. (The possibility of occurrence of defects was blocked in advance. It is applied to sound products with high output.) |  | ok
10 | Open | Assembly issue: Port 476.00295.005 & 476.00296.005 is similar. They aren't designed to prevent assemble wrong part --> May be assemble wrong |  |  | Need check and improve | ALT : DVT2 housing is update. Top and R/L is engraved |  | ok
11 | Open | Assembly issue: RD request to use scre M3x4mm to assemble LED board. It it too short while thread pitch is big --> Easily happened strip thread of housing |  |  | Check and modify design: Length of screw, screw type, size of hole…. | ALT : This is DVT only. Will improved next production INKEL : The screw is designed to apply 3x7mm(Bind Head) |  | ok
12 | Open | Front cover issue: Hole on Front cover and rubber gril holder cannot match well because the front cover is too long and the tolerance affects the assembly |  |  | Need check and feedback to vendor to improve | ALT : This is DVT only. Will improved next production INKEL : The reason is that the size of the injection part is short. |  | ok
13 | Open | Assembly issue: Top cover need to stick gasket 484.00422.005 & 484.00423.005 |  |  | Need to ask vendor to stick gaskets | ALT : Not accpectable. If sub assembly in vender, this gasket must be damaged durnig transportation. |  | Could you explain how the gasket will be damaged? How does Inkel stack and ship to us? Not quite understand the concern.
14 | Open | Front cover issue: Have to stick a rubber before shipping to factory |  |  | Need to ask vendor to stick this rubber by adhesive tape | ALT : 1. Not accpectable. This is reladed FFV MIC performance. 2. cost impacked. need to pay FXN |  | Plz kindly explain how the advised action affects the MIC performance and the cost impact. Not quite understand
15 | Open | Design issue: Space between button and switch is only 0.1mm --> Easily happen switch is jammed |  |  | Need RD check and modify design: Space between button and switch is 0.3-0.5mm | ALT : actually this is not a jammed switch. This is designed gap to reduce vibration noise.. Inkel : Movement(deformation) of the part is impossible due to conditions "a" and "b". And the failure rate is low due to the flexible design of condition "c" |  | ok. But there are jammed buttom issues reported which will need to cut the edge
16 | Open | Add glue issue: After add glue on PCB & bushing. Glue need to spend time to dry. |  |  | The glue Inkel brought to the line also takes a long time. This will be an issue for assembly and testing. For bushing, the glue is damaged easily during assembly. ALT advised vendor cannot trade with any Fii QVL. Possible for buy and sell? | ALT : Please contact to belew vender. This vender is supply FFC to Speaker company (Inkel, Anam) also was supplied Foxconn Also we checked can make Swan side FFC with Bushing Sponge. 업체명: Hwa Sung Elecom Co., Ltd 담당자: Gil-Hwan Jeong(Deputy General Manager) 연락처: 010-2046-6084(h870420@hanmail.net) |  | under checking
07 | Open | Housing issue: Housing has not fix-boss to locate heat spreader during assembly |  |  | Add Fix-boss to locate Heat spreader well |  |  |  | ALT Please send modeling data as you modified. Below fix-boss will be add next build
08 | Open | Heat spreader issue: Heat spreader 400.01103.005 is too long but it isn't not drive screw to fix well in housing --> Have risk heat spread deformed and touch pin of DIP part & smt parts at bottom side on PCBA |  |  | 1. Add more one screw to fix heat spreader 2.Use gasket cover on heat spreader to prevent pin of DIP parts touch heat spreader |  |  |  | Contact to Foxconn Thermal team. This thermal solution is designed by Foxconn 1. Need to SoC Bottom plate update by Fii 2. Need to the gasket cover on heat spreader by Fii
14 | Open | Layout issue: To fix heat spreader 400.01108.005 need to use 2 type screw : M2.5x5mm (401.00634.005) & M3x7mm (401.01460.005) --> Have to split to 2 step ( 2 person & 2 drive screw machine) |  |  | Please check and modify design to use 1 screw type to fix this heat spreader |  |  |  | ALT I think it's not good idea in terms of total cost. need to modify bottom housing mold design. - Tooling cost - Meterial cost : we will update cost increase. need to discuss cost impact due to Fii requested
17 | Open | Assembly issue: Wire mount 471.00105.005 is defined to stick on rib of bottom --> It is easily shaked and fixed not well |  |  | Need RD check and modify housing to put wire mount better |  |  |  | ALT Not accpectable Please search more smaller hook Or change the attachment structure
a
b
a
b
d
c
a
b
a
TOP
R or L