## ALT owned
No. | Status | What | Enclosed Picture | PCB 設計規範條例 | Recommendation | ALT Remark | image | Fii Remark 0202 | ALT Remark 0204 | Fii/ALT discussion 2/19
1 | Open | Add glue issue: When add glue, Glue may be dropped into inside port of HDMI |  |  | Can skip the glue on both side of HDMI connector? | ALT : instade glue, can use SMT Glue on HDMI |  | Cannot accept. Once there are issues with boards the rework be be a big problem. | Fii decide choose one of solution | ALT agreed to add the glue from later half of the connector for DVT2 and check
2 | Open | Add glue issue: Add glue may be make PCBA become dirty, and impact to visual of parts if glue is over on sufrace of component |  |  | Need check and help to solve issue: Modify layout/ change requirement to add glue, etc… | ALT : instade glue, can use SMT Glue on Ethernet / DC JACK |  | Still the same issue no matter when the glue is added. | Fii decide choose one of solution
3 | Open | Assembly issue: Bracket side led need to be stick more gasket 484.00429.005 & 484.00430.005 |  |  | Need to ask vendor to stick gasket | ALT : Next production, vender will be subassembled |  | OK |  | ok
4 | Open | Speaker cable issue: 1. Length of wire at midragne & Tweeter speaker is short --> sponge is easily broken 2. Length of wire at woofer speaker is long alittle |  |  | Need check and update spec | ALT : review DVT sample first, will update before next production |  | OK | ALT FII suggest each cable length. ALT will update as your suggestion | ok
5 | Open | Speaker cable issue: Rubber of speaker cable is so tight. Need a lot of strength to put in |  |  | Need check and improve | ALT : 'Not accpectable, due to air leackage |  | Will discuss with factory |  | ok
6 | Open | Speaker cable issue: 1. Lock of cable to connect with speaker is very tight 2. Small lock is remove so hard |  |  | 1. Need vendor to modify size of pin on speaker or lock of cable 2. Modify design of small lock as big lock | ALT : will check with vender (Dreamus), let you know |  | ok |  | ok
7 | Open | Assembly issue: When assembly speaker, speaker cable has confliction with housing because of the black tube is too hard to bend |  |  | Need check and improve | ALT : will check with vender (Dreamus), let you know |  | ok |  | ok
8 | Open | Assembly issue: Speaker has not Fix-boss --> Need to use hand fix speaker to drive svrew |  |  | Modify housing to add fix-boss or a sink area to locate speaker better for locking the screws | INKEL : It can be assembled using conditions "a" and "b" ALT : first Screw tightening "a" area, next "b" area. It will be fixed in screw hole place. |  | The suggesting is for the positioning and make it easy to drive the screw while the speaker is fixed in a location and doesn't slide. |  | ALT will have Inkel revise after DVT2
9 | Open | Assembly issue: Distance from surface of speaker to surface of inside housing is only 7.2mm but BOM reuqest to use screw M3x10mm |  |  | Need Check and confirm | ALT : it can use M3x10mm screw' INKEL : If the outer diameter("a") of the thread on the opposite side of the screw is small, a problem may occur in the tightening force. (The possibility of occurrence of defects was blocked in advance. It is applied to sound products with high output.) |  | ok |  | ok
10 | Open | Assembly issue: Port 476.00295.005 & 476.00296.005 is similar. They aren't designed to prevent assemble wrong part --> May be assemble wrong |  |  | Need check and improve | ALT : DVT2 housing is update. Top and R/L is engraved |  | ok |  | ok
11 | Open | Assembly issue: RD request to use scre M3x4mm to assemble LED board. It it too short while thread pitch is big --> Easily happened strip thread of housing |  |  | Check and modify design: Length of screw, screw type, size of hole…. | ALT : This is DVT only. Will improved next production INKEL : The screw is designed to apply 3x7mm(Bind Head) |  | ok |  | ok
12 | Open | Front cover issue: Hole on Front cover and rubber gril holder cannot match well because the front cover is too long and the tolerance affects the assembly |  |  | Need check and feedback to vendor to improve | ALT : This is DVT only. Will improved next production INKEL : The reason is that the size of the injection part is short. |  | ok |  | ok
13 | Open | Assembly issue: Top cover need to stick gasket 484.00422.005 & 484.00423.005 |  |  | Need to ask vendor to stick gaskets | ALT : Not accpectable. If sub assembly in vender, this gasket must be damaged durnig transportation. |  | Could you explain how the gasket will be damaged? How does Inkel stack and ship to us? Not quite understand the concern. |  | The glue area is too thin so cannot assemble before shipment. Will check with Inkel about the issue of the integral number of gaskets assembled on top case. (5.5 for now)
14 | Open | Front cover issue: Have to stick a rubber before shipping to factory |  |  | Need to ask vendor to stick this rubber by adhesive tape | ALT : 1. Not accpectable. This is reladed FFV MIC performance. 2. cost impacked. need to pay FXN |  | Plz kindly explain how the advised action affects the MIC performance and the cost impact. Not quite understand |  | The impact comes from the thickness of the glue or the tape so cannot stick before shipment
15 | Open | Design issue: Space between button and switch is only 0.1mm --> Easily happen switch is jammed |  |  | Need RD check and modify design: Space between button and switch is 0.3-0.5mm | ALT : actually this is not a jammed switch. This is designed gap to reduce vibration noise.. Inkel : Movement(deformation) of the part is impossible due to conditions "a" and "b". And the failure rate is low due to the flexible design of condition "c" |  | ok. But there are jammed buttom issues reported which will need to cut the edge |  | ALT will have Inkel revise after DVT2
16 | Open | Add glue issue: After add glue on PCB & bushing. Glue need to spend time to dry. |  |  | The glue Inkel brought to the line also takes a long time. This will be an issue for assembly and testing. For bushing, the glue is damaged easily during assembly. ALT advised vendor cannot trade with any Fii QVL. Possible for buy and sell? | ALT : Please contact to belew vender. This vender is supply FFC to Speaker company (Inkel, Anam) also was supplied Foxconn Also we checked can make Swan side FFC with Bushing Sponge. 업체명: Hwa Sung Elecom Co., Ltd 담당자: Gil-Hwan Jeong(Deputy General Manager) 연락처: 010-2046-6084(h870420@hanmail.net) |  | under checking |  | Fii is checking with vendor
07 | Open | Housing issue: Housing has not fix-boss to locate heat spreader during assembly |  |  | Add Fix-boss to locate Heat spreader well |  |  |  | ALT Please send modeling data as you modified. Below fix-boss will be add next build | Fii ME prepares 3D file for ALT to check with Inkel
08 | Open | Heat spreader issue: Heat spreader 400.01103.005 is too long but it isn't not drive screw to fix well in housing --> Have risk heat spread deformed and touch pin of DIP part & smt parts at bottom side on PCBA |  |  | 1. Add more one screw to fix heat spreader 2.Use gasket cover on heat spreader to prevent pin of DIP parts touch heat spreader |  |  |  | Contact to Foxconn Thermal team. This thermal solution is designed by Foxconn 1. Need to SoC Bottom plate update by Fii 2. Need to the gasket cover on heat spreader by Fii | Fii ME prepares 3D file for ALT to check with Inkel
14 | Open | Layout issue: To fix heat spreader 400.01108.005 need to use 2 type screw : M2.5x5mm (401.00634.005) & M3x7mm (401.01460.005) --> Have to split to 2 step ( 2 person & 2 drive screw machine) |  |  | Please check and modify design to use 1 screw type to fix this heat spreader |  |  |  | ALT I think it's not good idea in terms of total cost. need to modify bottom housing mold design. - Tooling cost - Meterial cost : we will update cost increase. need to discuss cost impact due to Fii requested | ALT will check with Inkel by 2/26
17 | Open | Assembly issue: Wire mount 471.00105.005 is defined to stick on rib of bottom --> It is easily shaked and fixed not well |  |  | Need RD check and modify housing to put wire mount better |  |  |  | ALT Not accpectable Please search more smaller hook Or change the attachment structure | ok
a
b
a
b
d
c
a
b
a
TOP
R or L