## 工作表1
K18X001.00 2nd source introduction table
| Main Source |  |  | 2nd Source
Item | Manufacture | MPN | L/T (day) | Manufacture | MPN | Pin to Pin | L/T (day) | SW impaction | R&D Validation items | RD Test Result | Reliability | Test Report | Notes
1 | TI | TPS51206DSQR | 504 | 3PEAK | TPL51206-DFFR | P2P | 140 | - | a. Voltage accuracy(Vin) b. Voltage accuracy(Vout) c. AC ripple d. Power Efficiency e. Power on sequence f. Short test g. Power Consumption h. EMI test | 1. Fail. No voltage output. 2. Since 3PEAK fail the test, so we will only introduce GMT G2986K21U as 2nd source for TI TPS51206DSQR | NA | NA
|  |  |  | GMT | G2986K21U | P2P | Under Confrim | - | a. Voltage accuracy(Vin) b. Voltage accuracy(Vout) c. AC ripple d. Power Efficiency e. Power on sequence f. Short test g. Power Consumption h. EMI test | Item a~g: pass Item h: will test on 11/18. The test report will be provided on 11/19 | 1. Will test on K18X001.01 (new version of PCBA) 2. Estimated schedule: 1/28 ~ 2/18
2 | TI | TLV75525PDBVR | 504 | 3PEAK | TPL740F25-5TR | P2P | 140 | - | a. Voltage accuracy(Vin) b. Voltage accuracy(Vout) c. AC ripple d. Power Efficiency e. Power on sequence f. Short test g. Power Consumption h. EMI test | Item a~g: pass Item h: will test on 11/18 The test report will be provided on 11/19 | Ongoing. The test will be finished on 11/29
3 | DIODES | AP7366-18W5-7-76 | 588 | 3PEAK | TPL740F18-5TR | P2P | Under Confrim | - | a. Voltage accuracy(Vin) b. Voltage accuracy(Vout) c. AC ripple d. Power Efficiency e. Power on sequence f. Short test g. Power Consumption h. EMI test | Item a~g: pass Item h: will test on 11/18 The test report will be provided on 11/19 | Ongoing. The test will be finished on 11/29
4 | MPS | MP1605GTF-Z | 532 | GMT | G2262TR1U | P2P | Under Confrim | - | a. Voltage accuracy(Vin) b. Voltage accuracy(Vout) c. AC ripple d. Power Efficiency e. Power on sequence f. Short test g. Power Consumption h. EMI test | Item a~g: pass Item h: will test on 11/18 The test report will be provided on 11/19 | 1. Will test on K18X001.01 (new version of PCBA) 2. Estimated schedule: 1/28 ~ 2/18
5 | SILERGY | SY8120IABC | 224 | FITI | FR9811S6 FR9850S6 | P2P | 252 | - | a. Voltage accuracy(Vin) b. Voltage accuracy(Vout) c. AC ripple d. Power Efficiency e. Power on sequence f. Short test g. Power Consumption h. EMI test | 1. FITI recommend to use FR9850S6, because FR9850S6 have better efficiency and more popular than FR9811S6. 2. Fail, 0~1 A transient ripple > 5% 3. We will continue to survey other alternative parts and update to ALT if any. | N/A | NA
6 | NEXPERIA | 74LVC125APW | 203 | TOSHIBA | 74LCX125FT | P2P | 203 | - | a. I2S timing test b. EMI test | TOSHIBA doesn't has available sample to provide to Fii for testing. | NA
|  |  |  | DIODES | 74LVC125AT14-13 | P2P |  | - | a. I2S timing test b. EMI test | Fii is requesting samples now. | 1. Will test on K18X001.01 (new version of PCBA) 2. Estimated schedule: 1/28 ~ 2/18
7 | MPS | MP2338GTL-Z | 532 | SILERGY TMI | SY8263AIC TMI3343B | non P2P | 252 | - | a. Voltage accuracy(Vin) b. Voltage accuracy(Vout) c. AC ripple d. Power Efficiency e. Power on sequence f. Short test g. Power Consumption h. EMI test | 1. Will test on K18X001.01(new version of PCBA). 2. The estimated schedule of sample build : 11/26-12/1 | 1. Will test on K18X001.01 (new version of PCBA) 2. Estimated schedule: 1/28 ~ 2/18
8 | REALTEK | RTL8211F-CG | 224 | Motorcomm | YT8531C | P2P | Under Confrim | Y | a. RGMII timing test b. Throughput test c. Ethernet complaince test d. Aging test e. EMI test |  |  |  | non-QVL. Will need ALT's help to designate this component.
9 | TI | LP5024RSMR | 392 | Awinic | AW21024QNR | P2P | Under Confrim | Y | a. I2C timing test b. LED tuning test c. EMI test d. Aging test |  |  |  | non-QVL. Will need ALT's help to designate this component.
10 | TI | LP5036RJVR | 392 | Awinic | AW21036QNR | non P2P | Under Confrim | Y | Same as above item |  |  |  | 1. thermal pad size different. 2. non-QVL. Will need ALT's help to designate this component.
11 | SILERGY | SY8824CAIC | 224 | Halo Microelectronics | HL7593 | non P2P | Under Confrim | Under Confirm | a. Voltage accuracy(Vin) b. Voltage accuracy(Vout) c. AC ripple d. Power Efficiency e. Power on sequence f. Short test g. Power Consumption h. EMI test i. I2C timing test |  |  |  | 1. Synaptics recommand us to use this as alternative part. 2. non-QVL. Will need ALT's help to designate this component.