## Sheet1
Fii bring up status |  |  |  | Synaptics bring up status
Main Board |  |  | Due date
I/O interface | Function | Remark | Done
DDR4 memory 3GB configuration | Pass | DDR4 3G configuration OK | Done
DC 24V power | Pass | System can be power up normally, and enter to Android OS | Done
Gbit Ethernet | Pass | Iperf TX: 873Mbit/s, RX:895Mbit/s | Done
HDMI2.0 | Pass | Display 1080p60, 4KP60 normally | Done
AUX IN | On-going |  | 2020-09-03
MICs IN | On-going | S/W to implement test app for MIC recording and playing audio to speaker | 2020-09-03
USB2.0 | Pass | Can read the USB2.0 flash data normally | Done
USB3.0 | Pass | Can read the USB2.0 flash data normally | Done
mono-audio AMP (woofer) | Pass | Audio output normally | Done
Stereo-audio AMP (twitter/mid. range) | Pass | Audio output normally. Need following rework: 1. PIN 3: /PLL : Need to connect a 1K pulled-low RES to GND 2. PIN 6: CLK_OUT: Need to connect a 10K pulled-high RES to PWR_3V3 3. PIN 32: /PD : Need to connect it to a normal GPIO instead of SM_GPIO9 | Done
Bluetooth | On-going | S/W to debug BT driver init fail on EVT1 board | 2020-09-04
Sub board
Key board | On-going | S/W to implement GPIO key button driver | 2020-09-03
All LED RGB funtion | Pass | All RGB LED can light up normally | Done
IR receiver | Pass | 38KHz, NEC key code OK | Done
MICs array | On-going | Can record 2 channel of AMIC sound, S/W still working with Synaptics for how to config I2S TDM mode for 4 channel of AMIC | 2020-09-03