## Sheet1
Fii bring up status |  |  |  | Synaptics bring up status
Main Board |  |  | Due date
I/O interface | Function | Remark | Done
DDR4 memory 3GB configuration | Pass | DDR4 3G configuration OK | Done
DC 24V power | Pass | System can be power up normally, and enter to Android OS | Done
Gbit Ethernet | Pass | Iperf TX: 873Mbit/s, RX:895Mbit/s | Done
HDMI2.0 | Pass | Display 1080p60, 4KP60 normally | Done
AUX IN | Pass | AUX voice can be recorded normally * MIC 3.5mm phone jack pin3/4 & pin1/2 need to be reworked (swapped) | Done
MICs IN | Pass | MICs voice can be recorded normally * MIC 3.5mm phone jack pin3/4 & pin1/2 need to be reworked (swapped) | Done
USB2.0 | Pass | Can read the USB2.0 flash data normally | Done
USB3.0 | Pass | Can read the USB2.0 flash data normally | Done
mono-audio AMP (woofer) | Pass | Audio output normally | Done
Stereo-audio AMP (twitter/mid. range) | Pass | Audio output normally. Need following rework: 1. PIN 3: /PLL : Need to connect a 1K pulled-low RES to GND 2. PIN 6: CLK_OUT: Need to connect a 10K pulled-high RES to PWR_3V3 3. PIN 32: /PD : Need to connect it to a normal GPIO instead of SM_GPIO9 | Done
Bluetooth | On-going | S/W to debug BT driver init fail on EVT1 board | 2020-09-09
Sub board
Key board | On-going | MICs mute, volume up, Power on/off is under checking, the other keys function are OK | 2020-09-04
All LED RGB funtion | Pass | All RGB LED can light up normally | Done
IR receiver | Pass | 38KHz, NEC key code OK | Done
MICs array | Pass | 4 channels of AMIC voice can be recorded normally | Done