## Sheet1
Request item no. | Item | document | remark (for example)
5. HW specificaiton | block diagram | block diagram | [SB 0402] the power block in this diagram is Eagle's. SWAN will be used 24V adatper. So please change the power block or remove them?
5.4 DRAM | Memory name | Vender Part No. | Need to confirm with Synaptics. Will update the P/N next week.
| DDR STRESS TEST | Test setup diagram | [SB0402] If this picture is size up, the caracter is broken. Please update a picture which has a higher quality (or it is good to update origianl picture) the Adapter picture is Eagle's. Please change the Eagle adapter to general adapter picture or below picture the DUT picture is also Eagle. please change the Eagle board to general DUT or below picture
| DDR SI simulation | Simulation condition | [SB 0402] please change the conroller model name and vender name. If ddr memorys are also chagned, please modify the DDR model / vender name. and could you update test picture?
| Aging test | Test setup diagram
5.5 Flash Memory | Memory name | Vender Part No. | Need to confirm with Synaptics. Will update the P/N next week.
| emmc STRESS TEST | Test setup diagram | [SB 0402] the Adapter picture is Eagle's. Please change the Eagle adapter to general adapter picture or below picture. the DUT picture is also Eagle. please change the Eagle board to general DUT or below picture
| timing test | Test setup diagram | [SB 0402] the Adapter picture is Eagle's. Please change the Eagle adapter to general adapter picture or below picture. the DUT picture is also Eagle. please change the Eagle board to general DUT or below picture
5.6 power | Power tree | Power tree document
5.7.2 FFV | I2S | Test setup diagram | [SB 0402] Please update both i2s timing test setup picture and far field voice test picture
5.7.3 Audio HW | mic/speaker | Test setup diagram chamber photo
5.8 HDMI | Material Name | Vender Part No. | Use the same Part No. as Eagle
| Compliance test | test setup diagram
5.9 AUX in (3.5 PI) | Material Name | Vender Part No. | Will provide the new Part No. next week
| AUX in | test setup diagram | [SB 0402] the Adapter picture is Eagle's. Please change the Eagle adapter to general adapter picture or below picture. the DUT picture is also Eagle. please change the Eagle board to general DUT or below picture
5.10 MIC input (3.5pi) | Material Name | Vender Part No. | Will provide the new Part No. next week
| test | test setup diagram | [SB 0402] the Adapter picture is Eagle's. Please change the Eagle adapter to general adapter picture or below picture. the DUT picture is also Eagle. please change the Eagle board to general DUT or below picture
5.11 RCU input | IR sensor | Vender Part No. | Use the same Part No. as Eagle
| IR test | test setup diagram
| BT test | test setup diagram
5.13 USB | USB 2.0 | Compliance TEST setup | [SB0402] If this picture is size up, the caracter is broken. Please update a picture which has a higher quality (or it is good to update origianl picture) the DUT picture is also Eagle. please change the Eagle board to general DUT or below picture
| USB 3.0 | Compliance TEST setup | [SB0402] If this picture is size up, the caracter is broken. Please update a picture which has a higher quality (or it is good to update origianl picture) the DUT picture is also Eagle. please change the Eagle board to general DUT or below picture
|  | drop/overload test setup | [SB0402] If this picture is size up, the caracter is broken. Please update a picture which has a higher quality (or it is good to update origianl picture) the DUT picture is also Eagle. please change the Eagle board to general DUT or below picture
5.15 Ethernet | Material Name | Vender Part No. | Use the same Part No. as Eagle
| 10/100/1000 | Compliance TEST setup | [SB0402] If this picture is size up, the caracter is broken. Please update a picture which has a higher quality (or it is good to update origianl picture) the DUT picture is also Eagle. please change the Eagle board to general DUT or below picture
5.17 LED | Material Name | Vender Part No. | To be confirm.
5.20 Power | power consumption | test setup | [SB 0402] the Adapter picture is Eagle's. Please change the Eagle adapter to general adapter picture or below picture. the DUT picture is also Eagle. please change the Eagle board to general DUT or below picture
5.21 noise | Acoustic noise | test setup
5.22 thermal | test | test setup for IR image
7. Reliability test | test criteria | reliability test plan | please modify the reliability test plan of Eagle to Swan especially, add and modify the below SKB's criteria
Transducer Test
Anechoic Chamber