## Question list
| Questions | Remark
PM | ALT's planned schedule and actions for the design change. | [ALT] See the attchement milestone So far, we are on schedule.
PM | If the EMC and thermal are taken into consideration on the schedule? Will there be mock ups for the verification? | [ALT] 1. about thermal ALT and Amp IC vender did prevalidation according to the block diagram configuration. Same as current configuration (ESMT IC)
PM | If all the design change content including the ID/ME/speaker will be fixed within this week | [ALT] No. Each item is being reviewed in parallel. See the milestone schedule our plan. Speaker is still under reviewing with B&O / SKB / Inkel ID(design look) is fixed. But horizontal size may be changed due to SPK unit design ME is start the design change
PM | Clarify the R&R of SW and HW during the development of AMP design. We will prepare the list. | [ALT] the R&R will be upate next week. (3/2~)
SW | Is it a standalone system and will be run with an embedded Linux OS ? | [ALT] Yes, will linux standalone system
SW | We knew I2S interface will be used as sending audio data and how to control and communicate between VS550 and A113X ex: volume control, EQ enable/disable? Will it be controlled by VS550 or A113X via I2C interface ? | [ALT] VS550 is Main SoC and will control - Volume - A113x via I2C or UART A113x (DSP) will control - EQ enable/disable?
SW | Which SoC(OS) do initialize AMP device via I2C bus? | [ALT] A113x (Linux) will initialize AMP device WA20-6829B (wellang)
SW | How to update F/W in NAND flash of AMP board through VS550 ? | [ALT] as we plan is 1. A113x will mount using OTG mode. VS-550 is host mode and A113X is slave mode. 2. VS-550 will copy F/W to A113x F/W update folder. 3. A113x will detect F/W update file, and update automatcally
SW | How to integrate the SWon A113X into Android system on Syanptics and what would be the architecture (ALT will complete the SW development on A113X) | [ALT] will update by SY,Yoon

## R&R draft
|  | Item | ALT | Fii | Remark
Verification build | HW | schematic design and layout | v |  | Fii will review schematic and BOM list then advise to ALT the alternative parts if any based on QVL pool
|  | material prep and sample build | v
|  | performance verification | v
|  | audio tuning | v
| SW | A113X SW development | v
|  | integrate with Android system |  | v
DVT3 | HW | schematic and layout modification | v | V | [ALT] Verification build is follow the SoC reference design. DVT3 will need to be supported by Foxconn to the mass production design.
|  | data transformation for production |  | v
|  | Sample build |  | v
| PM | procurement of ALT designated materials | v