## HW Test Schedule
Test Item |  | EVT |  |  | DVT
|  | Start Date | End Date | Report release date | Start Date | End Date | Report release date | Remark
Thermal Test |  | 2020-09-28 | 2020-10-09 | 2020-10-09
Power consumption | Active Standby | 2020-09-28 | 2020-10-09 | 2020-10-09
| Operation mode | 2020-09-28 | 2020-10-09 | 2020-10-09
| Passive Standby(Deep sleep) | 2020-09-28 | 2020-10-09 | 2020-10-09
Audio performace | Speaker | [6 empty] | Mock-up should be tuned before delivery. EQ should be tuned and provide the FW for integration and provide the testing report. When are these done?
| MIC | [6 empty] | When does SKT decide the array? Fii should reserve 2pcs curve typed boards.
Memory verification | eMMC | 2020-09-14 | 2020-09-25 | 2020-09-25
| DRAM | 2020-09-14 | 2020-10-09 | 2020-10-09
Extraction force | HDMI | 2020-09-28 | 2020-10-09 | 2020-10-09
| DC Jack | 2020-09-28 | 2020-10-09 | 2020-10-09
USB | USB2.0 | 2020-09-21 | 2020-10-02 | 2020-10-02
| USB 3.0 | 2020-09-21 | 2020-10-02 | 2020-10-02
HDMI | HDMI SI | 2020-09-21 | 2020-10-02 | 2020-10-02
Ethernet |  | 2020-09-21 | 2020-10-02 | 2020-10-02
Bluetooth HW Verification
HW Verification | EMC | 2020-09-21 | 2020-10-09 | 2020-10-09
| I2C | 2020-09-14 | 2020-09-18 | 2020-09-18
| Clock | 2020-09-10 | 2020-09-25 | 2020-09-25
| Power | 2020-09-21 | 2020-10-02 | 2020-10-02
| BT RF Test | 2020-09-14 | 2020-09-25 | 2020-09-25
| Acoustic | 2020-09-28 | 2020-10-09 | 2020-10-09
| Button | 2020-09-28 | 2020-10-02 | 2020-10-02
| LED | 2020-10-05 | 2020-10-09 | 2020-10-09
| MIC for Karaoke | 2020-10-05 | 2020-10-09 | 2020-10-09
| AUX IN | 2020-10-05 | 2020-10-09 | 2020-10-09
RCU | Bluetooth performance | 2020-09-28 | 2020-10-02 | 2020-10-02
| IR Performance | 2020-09-28 | 2020-10-02 | 2020-10-02
Bluetooth Certification | Test
Certification
DOLBY- MS11 | Test
Certification
RoHS | [7 empty] | Plz check if self-declaration as Eagle is OK
Add your HW Test items for SWAN

## Reliability Test Schedule
Test Item | EVT |  |  | DVT
| Start Date | End Date | Report release date | Start Date | End Date | Report release date
Vibration Test
Shock Test
Drop test
Abrasion resistance of Label Test
Add your test items for SWAN

## SW development schedule
SW Items that Foxconn develop |  |  | Start Date | End Date | Comment
BTF HAL | AV output | Display | 2020-08-06 | 2020-08-27
|  | Video compositor | 2020-08-27 | 2020-09-10
| Peripheral porting | LED | 2020-09-10 | 2020-09-24
|  | MIC | 2020-09-24 | 2020-10-07
|  | USB |  |  | not related to BTF HAL but will be verified by FXN
|  | Ethernet |  |  | not related to BTF HAL but will be verified by FXN
|  | Button |  |  | not related to BTF HAL but will be verified by FXN
|  | IR |  |  | not related to BTF HAL but will be verified by FXN
Formulas:
End Date = [Start Date]+14
Start Date = [End Date, row above]