## HW Test Schedule
Test Item |  | EVT |  |  | DVT |  |  | Remark
|  | Start Date | End Date | Report release date | Start Date | End Date | Report release date
Thermal Test |  | 2020-09-28 | 2020-10-09 | 2020-10-09
Power consumption | Active Standby | 2020-09-28 | 2020-10-09 | 2020-10-09
| Operation mode | 2020-09-28 | 2020-10-09 | 2020-10-09
| Passive Standby(Deep sleep) | 2020-09-28 | 2020-10-09 | 2020-10-09
Audio performace | Speaker | [6 empty] | Mock-up should be tuned before delivery. EQ should be tuned and provide the FW for integration and provide the testing report. When are these done?
| MIC | [6 empty] | When does SKT decide the array? Fii should reserve 2pcs curve typed boards.
Memory verification | eMMC | 2020-09-14 | 2020-09-25 | 2020-09-25
| DRAM | 2020-09-14 | 2020-10-09 | 2020-10-09
Extraction force | HDMI | 2020-09-28 | 2020-10-09 | 2020-10-09 |  |  |  | All I/O connectors shall have life time over 1000 times insertion and extraction
| DC Jack | 2020-09-28 | 2020-10-09 | 2020-10-09
USB | USB2.0 | 2020-09-21 | 2020-10-02 | 2020-10-02
| USB 3.0 | 2020-09-21 | 2020-10-02 | 2020-10-02
HDMI | HDMI SI | 2020-09-21 | 2020-10-02 | 2020-10-02
Ethernet |  | 2020-09-21 | 2020-10-02 | 2020-10-02
Bluetooth HW Verification
HW Verification | EMC | 2020-09-21 | 2020-10-09 | 2020-10-09
| I2C | 2020-09-14 | 2020-09-18 | 2020-09-18
| Clock | 2020-09-10 | 2020-09-25 | 2020-09-25 |  |  |  | Do your test included X-tal test(matching with SoC) ?
| Power | 2020-09-21 | 2020-10-02 | 2020-10-02 |  |  |  | Do your test included Power sequence/Ripple & Noise/POR test ?
| BT RF Test | 2020-09-14 | 2020-09-25 | 2020-09-25
| Acoustic | 2020-09-28 | 2020-10-09 | 2020-10-09
| Button | 2020-09-28 | 2020-10-02 | 2020-10-02
| LED | 2020-10-05 | 2020-10-09 | 2020-10-09
| MIC for Karaoke | 2020-10-05 | 2020-10-09 | 2020-10-09
| AUX IN | 2020-10-05 | 2020-10-09 | 2020-10-09
RCU | Bluetooth performance | 2020-09-28 | 2020-10-02 | 2020-10-02
| IR Performance | 2020-09-28 | 2020-10-02 | 2020-10-02
HDMI Certification
Bluetooth Certification | Test
Certification
DOLBY- MS11 | Test
Certification
RoHS | [7 empty] | Plz check if self-declaration as Eagle is OK
Add your HW Test items for SWAN
I2S Timing(I2S0/1/2) | [7 empty] | Please add I2S audio bus timing test.
USB(Drop/Droop) | [7 empty] | Please add USB drop/droop test.
RGMII Timing | [7 empty] | Please add RGMII bus timing test.
Pop noise | [7 empty] | Please add pop-up test.

## Reliability Test Schedule
Test Item | EVT |  |  | DVT |  |  | Remark
| Start Date | End Date | Report release date | Start Date | End Date | Report release date
Vibration Test
Shock Test
Drop test
Abrasion resistance of Label Test
Add your test items for SWAN
ESD Test
Surge Test
Environmental Test | [6 empty] | From Ethernet & From BT

## SW development schedule
SW Items that Foxconn develop |  |  | Owner | Start Date | End Date | Comment
BTF HAL | AV output | Display | Jim | 2020-08-06 | 2020-08-27
|  | Video compositor | Jim | 2020-08-27 | 2020-09-10
| Peripheral porting | LED | Sam | 2020-09-10 | 2020-09-24
|  | MIC | River | 2020-09-24 | 2020-10-07
|  | USB |  |  |  | not related to BTF HAL but will be verified by FXN
|  | Ethernet |  |  |  | not related to BTF HAL but will be verified by FXN
|  | Button |  |  |  | not related to BTF HAL but will be verified by FXN
|  | IR |  |  |  | not related to BTF HAL but will be verified by FXN
Formulas:
End Date = [Start Date]+14
Start Date = [End Date, row above]