## PM&Sales
Category | Item | owner | status | due date | Reply
PM | DVT3 sample qty for ALT/SKB | ALT | close | 2021-03-15 | [Fii] Nominally ALT has 176pcs left for DVT3 (320-36-108) but will need to calculate the actual qty left with increased BOM cost after design change. [Fii 0317] If the qty is not informed by 3/18 the schedule will be delayed for another week because the factoy load the demand once a week. [ALT] Will provide on 3/17
PM | R&R discussion | Fii/ALT | close | 3/23=>3/26=>4/9 | [Fii] Fii will update the R&R list and ALT needs to check if additional items needed. [ALT 0319] Will provide the detailed items about HW development for discussion. [Fii 0326] Fii will review and reply by 3/29 [ALT 0329] We add some feedback on your comment in "AMP Board R&R" Tab. [ALT 0401] R&R for AMP board PCB artwork for MP still needs to be discussed. [Fii 0408] Fii willdo the EMC test and provide the solutions for EMC issue. [ALT 0408] MP artwork will be owned by ALT.
Sales | pre-MP+MP PO for 1K | ALT | open | 3/26=>4/8 | [Fii] will evaluate the BOM bassed on final ME design by 3/19 first. The final PO should be provided by 3/26. [Fii 0319] Before 3/24 Fii will evaluate the BOM cost based on the design as of 3/19. If there are design changes after then the price will be updated again. Also the E&O will be handled by ALT. [Fii 0325] ALT needs to provide the UP for amplifier [ALT 0326] will provide it today for Fii to update the quote. [Fii 0401] Will provide the quotation within this week. [Fii 0412] Those LT greater than 90 days are not prepared. Need ALT to provide the PO ASAP to lead the demand based on current design.
PM | E&O amount for DVT and 1K (pre MP+MP) after design change | Fii/ALT | open | 4/7=>4/16 | [Fii] Will evaluate when receiving the final ME drawing together with HW design [ALT] Final ME Design will be derivered by 3/19. We can deliver Speaker cable data by 3/19 Speaker data will be ready by 4/9 [Fii 0325] HW Tom will isse EC by 3/26 and the list will be updated later. [Fii 04009] Will provide the 1st version but will update again before MP due to possible design change after the verification of DVT3.
PM | Fii will scrap all the ALT provided parts such as hosuing sub-assembly, speakers and speaker cables after DVT2 | Fii | close | 2021-04-09 | [ALT 0317] Fii provide the list for ALT to review first. [Fii 0325] List provided to ALT [Fii 0326] Received the reply from ALT and will scrap based on the confirmation column.
PM | DVT3 material preparation | Fii/ALT | open | 2021-04-19 | [Fii] Fii will finalize the AMP BOM for production and place order for DVT3 by 3/17.(Sean) [Fii 0317] -A113X LT*32WK. Will need ALT to have AML Demian book the materials for DVT3 and MP. Fii will also check with vendor. [Fii 0319] -A113X was kicked off by ALT with AML and ALT has the power to push AML BD Demian to book MP 1K demand. Fii will place the order to AML when receiving the PO from ALT later. -ALT helps to check the Wellang amplifier LT and start the preparation of DVT3 first. [Fii 0324] Fii will prepare materials for AMP board for DVT3 and MP based on ALT provided BOM on 3/19 on Mantis 1143. The 1st EC will be released by 3/26 by HW Tom. [ALT 0326] ALT talked to AML and will check with AML BD for the preparation of A113X. [ALT 0401] Already talked to AML Korea BD and got the reply in need of PO. [Fii 0406] Need the PO to place the order for extra parts from the design change for DVT3 ASAP. [Fii 0409] Fii QVL don't have stock ready for ECAP with spec requested by ALT and need ALT to check the originally designated vendor for DVT3 sample build demand. Fii will change to QVL part for MP. Mantis #0001143~0006640 [Fii 0412] Need check ALT provided parts schedule. Need amplifier & ECAP ETA factory 4/21. ME parts & speaker sets ETA factory 4/23.
PM | VI specification | ALT | open | 2021-04-19 | [ALT] OK
PM | New speaker sets data sheet for application of new PNs | ALT | open | 4/7=>4/12 | [ALT 0401] will reply by 4/5 if the data sheet could be released as planned. [Fii 0406] Need apply for PN immediately. Plz provide it no later than 4/12. [Fii 0412] Got the data sheet for cables. Need the speaker's ASAP.
PM | Philips business trip visa documents | Fii-Dennis | open | 2021-04-12 | [Fii 0325] 1. 外國法人指派文件Travel Order_ALT_revised更新上傳法務系統。(3/24,done) 2. 待孫律師核簽 (3/25,done) [0326] 1. 用印簽核。(3/29,done)=> 目前核簽到鄭總 2. 3/25 和人事怡廷及Call Philips 查詢, 簽證申請以韓國辦事處規定為準 , 簽證需有邀請函及工作許可才核發簽證。 [0330] 1. 3/29送虎躍廠用印。 2. 3/30 文件送勞動部開案審查。 [0331] 已送勞動局 , 編號: 1100565962 ( 勞動局回覆,申請需要12個工作天) [0401] 1. 詢問勞動局加急需求 ,勞動局回覆,目前沒有這項申請管道,也沒有加費用申請加急的作法。 2. 可到網站:http://www.wda.gov.tw , 查詢申請進度,已經提供 ALT Philip 了解目前進度及查詢訊息。 [0406-0408] 查詢勞動局網站:http://www.wda.gov.tw , 進度為審查中。 [0409] 所附的合約是新加坡的公司和韓國ALT Co,.Ltd兩家外國公司簽約，不符合規定。需要補件。 note : 需提供買賣訂單或合約 , 是新加坡公司台灣分公司和 ALT 之間有關的文件。 [0412] ALT 提供訂單 , 先用原用印申請單,將ALT 訂單送虎躍廠用印。
PM | Wellang AMP designation letter & vendor contact to register vendor code and PN | ALT | open | 2021-06-30 | [Fii 0317] Need to apply for PN with B&S mode and direct trading mode at the same time. Need ALT to provide the needed documents and reply email. [Fii 0325] Documents are submitted in the system for DVT3 PN application and will finish by 4/9. [Fii 0326] Vendor code registration is in process and expected to complete by end of June. Will notify ALT once the process is done and before then will need ALT to support buy and sell.
PM | AMP eMMC 4G changed to NAND flash | ALT/Fii | close | 2021-04-07 | [ALT 0402] Could you check NAND Flash that Mr. Lonnie KIM informed in e-mail ? [Fii 0406] Fii buyer is checking the supply and will reply by 4/7 [Fii 0409] Will change to NAND flash starting from DVT3.
PM | Package final artwork for MP version | ALT | open | 2021-04-30 | [Fii 0406] ALT approves to use up old stock for DVT3. Need ALT to provide the updated artwork for MP version and check the sample qty. [Fii 0409] Need to check with vendor for the sample qty and schedule by 4/13. [Fii 0412] sample ETD no later than 4/23.
PM | ALT advised FFC cable + bushing vendor HWASUNG | Fii | open |  | [Fii 0406] Notified the vendor to prepare the sample for verification.

## HW&ME
Category | Item | owner | status | due date | Reply
HW | AMP board layout review by EMC engineer & H/W RD | Fii | close | 2021-03-15
ME | Final ME 3D drawing. For ME/ Package/ HW review | ALT | close | 3/16=>3/19 | [ALT] We will provide it by 3/19 [Fii 0317] When does tooling start? We'd like to review before then. Is the T0 tooling schedule impacted? [ALT 0317] Tooling will start in WK3/22 and no impact on the schedule. [ALT 0319] Will push for the final drawing today.
ME | Part List of housing & speaker and updated designation letter for new parts | ALT | close | 3/19=>3/22=>3/31 | [Fii] Need to register PN and issue EC [ALT] We will check it with INKEL when they can prepare. [Fii 0319] Need the data no later than 3/22 or the schedule will be impacted. [ALT 0401] Inkel is preparing it and will check it with Inkel today. [Fii 0401] Plz provide the data on 4/6. The time left to Fii internal process is less and less. [ALT_0402] INKEL will provide it by 4/5. INKEL said that there is no additional parts, but some parts should be removed. [Fii 0406] Receive and ME is reviewing the parts that need the designation letter.
HW | AMP board DFM review by MFG ME | Fii/ALT | close | 2021-03-17 | [Fii] will send out the file for ALT to review and modify for factory review DFM again.
ME | Final 2D drawings for all parts for IQC inspection and the defined critical dimension | ALT | close | 3/19=>3/31 | [Fii] Need update in the system when applying for PN [ALT] We will check it with INKEL when they can prepare. [ALT 0326] Inkel is preparing it and will check it with Inkel today. [ALT 0401] provided already.
ME | INKEL needs to review the ME design to reduce the assembly process | ALT/Fii | close | 3/23=>3/26=>4/7 | [ALT] If you have any idea, please let me know. Do you have any idea to reduce to assembly for B'd side ? [Fii 0318] The factory will provide the DFx on 3/18. Fii will internally review with ME from 3/19. The advice will be provided by 3/23. [Fii 0323] the factory will update DFM based on ALT updated 3D drawing and internal review by 3/26. [ALT 0402] 3/26 DFM Feedback : not acceptable due to tooling started center(PCBA) area. this is too late. Don't change LED board connector direction (3/30 replied on mantis).
HW | Acoustic testing equipment needs to improve the isolation effect | Fii | close | 2021-03-19 | [Fii] Vendor provided the new pressing material to verify again after DVT2. [ALT 0318] Could you explain what problems you have.
HW | FIT RJ45 connector for Wired Network Authentication | Fii | close | 2021-03-19 | [Fii 0323] informed FIT to proceed with certification
HW | Thermal simulation with new AMP board | Fii | open | 3/19=>3/25=>4/12 | [Fii 0325] ALT provided amplifier power consumption data changed and thus need to redo the thermal sim [Fii 0326] The report and the summary will be provided on 3/26. Need ALT to talk to SKB to change the thermal spec. [ALT 0326] Will review the report first. [Fii 0401] - Top and bottom case over 5-7degC and some key components are over spec. at 50degC ambient. - VS550 107℃(over 7.6℃), 8GB eMMC 98.9℃(over 6.2℃), DDR4 103.3℃ (over 8.3℃), A113X 110.9℃ (over 5.9℃), 4GB eMMC 109.2℃(over 24.2℃), DDR3L 109.1℃ (over 24.1℃), housing top 71.2℃ (over 6.2℃), housing Bot. 79.4℃ (over 5.4℃) - Need ALT to discuss the spec with SKB, to keep the speaker power to 42W or reduce ambient temperature to 40℃ - Will discuss with ALT off-line in terms of the speaker wattage spec. [ALT_0402] When FII will start to discuss ? [Fii 0406] Need the concall for discussion. Checking the time slot on 4/8. [Fii 0407] Have provided an explanation of the power dissipation difference between EVT and the new AMP board for ALT reference. Need further discussion with ALT for the thermal issue. [ALT 0408] Need Fii to do the simulation with ALT proposed solution first then consider Fii proposed solutions to reduce the ambient temp., reduce the watt, enlarged vent holes. [Fii 0409] Will start the simulation on 4/9 and expect to provide the report by 4/12.
HW | new design AMP board samples & speaker *13 sets for HW EMC/Thermal & SW | ALT | open | AMP:3/19=>3/31 SPK:3/19=>4/23 | [ALT] AMP board ETD KR 3/31 and the material status is under checking. On speaker, Dreamus will provide it by the end of April. So we will use current Speakers for test for HW, not acoustic feature. [Fii 0317] Need the speaker together to do the EMC and thermal. If ALT decides not to do any EMC/ thermal test before DVT3, plz send a formal email to confirm. [ALT 0317] 1st lot of speaker is 60cs pn 4/23. Fii may provide the risk statement for ALT to confirm. [ALT 0319] AMP board ETD KR still 3/31 [ALT 0401] No any verifications done before shipment. =>ALT shipped on 4/1. [Fii 0406] Speaker needs to pull in to 4/23
HW | Microphone sealing test fail. | ALT | open | 4/2=>4/16 | [Fii] 1. Fii have provided the test report and suggestion to on mantis 0000952. Need ALT to work with Inkel to review the rubber pad design and make a new rubber sample for further testing. 2. ALT has to impelemnt the rubber pad solution, which can solve sealing issue in new T0 ME design [ALT 0317] Will test MIC on 3/22 and check if need to make new rubber pad on 3/23. Will check with Inkel and notify the ETA TW for new rubber pad. (normally 1 week) [ALT 0318] How many mockup for rubber pad for your test ? [Fii 0319] 3sets is acceptable. [Fii 0325] ALT sent 3pcs new Mic silicon on 3/23, and will be ETA on 3/25. Will verify new Mic silicon on 3/26 in HsinChu acoustic Lab. [Fii 0329] The sealing performance can reach 25dB after applying rubber (t=0.9mm) and adhesive to increase the pressure on the MIC hole. Need ALT to verify the solution again in Korea side to see if ALT is agreed with the solutions. [ALT 0401] ALT will provide our test result by today under similar environment various cases. [Fii 0406] Will ship out the top case with solution by 4/8 after ALT confirms the FEDEX account. [Fii 0408] Have provided the test environment and setup on 4/7 to ALT SH review. [Fii 0409] 1. Need ALT to check if possible to provide the sample of silicon rubber within 4/9. 2. Need ALT to check if tooling modification for inteference issue is still possible. =>ALT will help verify the impact of the interference.
HW | AMP board verification test done before DVT3 gerber out | Fii/ALT | close | 2021-04-06 | [Fii]The verification before gerber out is necessary [ALT] We will provide AMP b'd gerber data by 4/6. [Fii 0317] Remind again the verifications mentioned in the email must be done before 4/6. The gerber must be provided on 4/5 morning. We have internal process for gerber out. [Fii 0325] Will proceed if ALT confirms the risk.
ME | T0 samples*2 for ME in China and factory ME in VN with assembly SOP | ALT | open | 4/7=>4/23 | [ALT] T0 Sample will be prepare the end of April. If you need these ME parts, then you should prepare with 3D data [Fii 0317] With Inkel provided SOP we need to 1. review with real housing and try assembling then evaluate assembly issues 2. transform into our SOP before DVT3. We need to reduce the time to do the trouble shooting when the production starts. [ALT 0318] We asked INKEL about it. But currently they provide T0 sample when they [ALT 0319] Will request Inkel to provide T0 sample and need Fii to provide the recipient info. [Fii 0325] Plz help check the delivery date -ME RD in China Recipient: Jim CHEN Cell: 18376747022 Address: Foxconn Technology Park, No.51, Tongle Road, Jiangnan District, Nanning City, Guangxi Province, China. -ME in VN factory Recipient: Nguyen Thi Thu Thuy Mobile: +84 0912872792 Company : FUNING PRECISION COMPONENT CO., LTD. Address : Lot B, Que Vo Industrial Zone, Nam Son Ward, Bac Ninh City, Bac Ninh Province, Vietnam [Fii 0326] Plz provide as early as possible. This will impact the production going smoothly. Also need Inkel on-site support. [ALT 0326] Likely to be 4/23 or 1 week before. Will check again. Also will check with Inkel or on site support
HW | Need power dissipation of all key components in AMP board for thermal simulation | ALT | close | 2021-03-16
HW | IQC for THD & FR of DREAMUS new speaker Fii Q team will on-site check the testing result. Need the updated spec to audit. | ALT | open | 2021-04-22 | [Fii] Dreamus cannot provide the testing equipment and Fii will send the Q team to Dreamus factory to check the testing result before shipment. [ALT 0318] We will check it when Dreamus start to produce Speaker. [Fii 0330] Because Dreamus cannot provide the testing equipment to Fii, if any suspect of speaker unit issue, Fii will need to return to Dreamus for analysis.=>[ALT 0409] well noted. [Fii 0401] Before Dreamus ship out on 4/23, Fii IQC must be done in Dreamus factory. [ALT 0401] Will check with Dreamus if THD&FR are tested. [ALT_0402] ALT sent e-mail that OQC schedule and test items on 4/2. [Fii 0406] Plz check the testing items of THD and FR. Besides the speaker schedule needs pull-in.
HW | What would be the new spec for the soundbar on THD and FR as B&O requested? | ALT | close | 2021-04-12 | [ALT] We will check it to B&O [ALT 0318] B&O didn't have any requirement about THD and FR. They listen sound from speaker and evaluate. They focus on SNR(> 95dB) and Noise level(< 200uV). [ALT 0319] System test spec remains the same as RFP specifies.
ME | T0 housing ETA factory | ALT | open | 2021-04-24 | [Fii] Plz confirm the sample qty for DVT3 [ALT] We asked to INKEL, but they will finish tooling by 4/23. So they need a week more. [Fii 0317] We need the materials ready no later than 4/24. Besides, is the shipment from China again? If so how do we start SMT on 4/26 considering the delivery period from DVT1? [ALT 0318] We asked to provide T0 housing by 4/24 at your factory. But they don't have enough time, so they are discussing with their factory in china. [ALT 0319] Will request Inkel to provide the housings as specified and is aware any delay will cause the production start date delay. [ALT 0401] Still checking with Inkel if ETA factory 4/23.
HW | ECAP lifetime | Fii | open | 2021-05-20 | [Fii]Will verify with the final design
HW | A113X OTA architecture |  | close |  | [ALT 0317] Design both option 1 and option 2. But option 2 no need to do SMT, just reserve on layout. If needed after, ALT will rework. Fii no need to prepare for the materials.
HW | EMI pre-test and debugging | Fii | close | 2021-04-01 | [Fii 0325] 1. P-two make the new FFC cable and estimated ETD on 3/26. 2. Book 3/30~4/1 3rd party Lab. and debugging [Fii 0326] Target to complete by 4/1 but still need to check the lab time slot [Fii 0329] The new FFC cable ETA is 3/30. Have booked the 3rd party Lab. on 4/1.
HW | DVT heatspreader sample thermal test and improvement | Fii | Open | 2021-04-23 | [Fii 0325] Current test result is bottom case 52.8degC @ 25degC ambient (spec.=50degC) 1. Make the new heat spreader top/bottom of AMP board, and estimated ETD on 3/28 2. Make the new heat spreader bottom of main board, and ETD is to be confirmed with vendor NWE [Fii 0329] The new bottom heat spreader is estimated complete and shipped by 4/15. Expect to complete the test by 4/23.
HW | Acoustic testing equipment may need to modify due to new speaker location | Fii | Open | 2021-04-26 | [Fii 0325] Will contact the vendor to evaluate the impact and cost based on 3D drawing. [ALT 0326] The 3D drawing provided can be used to evaluate the impact on chamber HW. [Fii 0326] Will provide the evaluation by 3/30 [Fii 0330] Need ATBU to evaluate the adjustment of the testing environment. [ALT 0402] How will you test bottom side Woofer speaker ? [Fii 0406] Updated on Mantis for the workaround since the time needed for making the formal fixture is long. The proposal of the fixture and the quotation will be updated by 4/7 morning. [Fii 0412] Need ALT to check the quotation and provide PO by 4/14. Fii needs to get the PO to have the vendor modify the SW for DVT3.
HW | ESD risk from the vent hole design for DVT3 housing. | Fii | open | 2021-05-10 | [Fii] Suggest ALT to seal the venting hole to avoid ESD issue [ALT 0401] If any ESD issues, will seal the hole in T1 housings. The detailed plan will be discussed later.
HW | DVT2 Speaker test result | FII | Open | 2021-04-02 | [ALT] Please provide Speaker Test result in your test chamber for DVT2 samples
HW | EMC test with new AMP board, new speaker sets, old housings | Fii | open | 2021-05-05 | [Fii 0409] Need the speaker ETA TW 4/23 for assembly with new AMP board in the old housing.
HW | LED chip color shift issue | Fii | open | 2021-04-13 | [Fii 0412] Everlight will update the FA with short term solution and the DOE for reproducibility. The final solution schedule will also be updated for fast introduction.

## SW
Category | Item | owner | status | due date | Reply
SW | AMP EVK*2 ETA TW for SW development | Fii | close | 2021-03-25 | [ALT] We will receive EVK b’d by 3/19. We should check it first and then we will send it. So we can send it 3/22 [Fii 0323] Need the circuit diagram and the user manual [Fii 0325] HW help to rework AMP EVK to connect to our VS-550 board (for i2c)
SW | For normal OTA of A113x, which function do we need to implement? Do we only need to implment USB switch API? Please provide detail SW R&R. => OTA server readiness | ALT | close Use other item to track | 2021-04-12 | [ALT] We should prepare OTA function. So OTA app will be installed in VS550. We think that 2 part of SW we need. OTA App in VS 550 : Implement by FII. It should connect OTA server and download new firmware and send image data to DSP. SW for DSP : It will implemented by ALT. But I think that it is more efficient to develop all OTA related function developped by one party. Can you support it ? [Fii 0317] Who will provide OTA server ? Because we don't know S/W detail and how to upgrade S/W in A113x side so we think the OTA function shall be implemented by ALT. [ALT 0317] OTA server is not decided. [Fii 0319] Need ALT to check the OTA server owner with SKB by 4/12 [ALT 0326] The OTA server owner will be decided by SKB but not yet decided. Probably will be SKB or ALT.
SW | Please also consider if A113x crashes in developing and OTA can not be used, which interface will you used for update image of A113x? | ALT | close |  | [ALT] We think that we can use USB for update But if A113x crashed, then it can be updated by serial port and USB.
SW | [Source code management - AMP control function] | Fii | Open | 2021-04-16 | [Fii 0329] Wha'ts AMP control function? EQ or DRC ? AMP(WA20-6829B) registers would be controlled by driver in VS-550 [Fii 0331] We have some questions about how to config registers for EQ/DRC to enable/disable. Would you help to forward these questions to Wellang or provide us the contact information? [ALT 0401] Will provide the engineer contact and Fii needs to copy ALT members in the loop. [ALT_0402] We already sent e-mail to Wellang and introduced both FII and Wellang engineers. [Fii 0407] We now can use sample code to initalize EVK board(one AMP IC) successfully from VS550. We now are add a psedudo code to check BCLK ready from A113x and check the impact of delay of BCLK. [Fii 0408] Delay of initalize AMP driver will cause NUGU open device fail. We are now working on it. We also recevied Wellang reply about our questions and will check the answer. [Fii 0413] Pending the NUGU can not open issue. Test with A113X AMP board and change driver registers for PBTL mono mode.
SW | [I2C comm - Implement I2C Master at VS-550 -- -Check A113x BLCK readiness status] We think you should integrate the AMP drivers in A113x side and provide an interface between VS550 and A113x to control AMP EQ/DRC. Because the initial timeing sequenc of AMP needs to make sure the power and I2C BLCK to be ready(as the picture at the right side). And the delay of initialization of AMP on VS550 will also impact FFV MIC access in VS550 at system booting. | ALT | Open | 2021-04-16 | [ALT]We suggested to control I2C of AMP by VS550.So if there is any issue to control AMP b’d. We will provide AMP B’d first, and we will provide SW as soon as it ready. [Fii 0317] As we mentioned, there is initial timing issue happened if WA20-6829B drvier implemented in VS-550 side after checking timing sequence in WA20-6829B datasheet. Until now, there is no mechanism to know if the power(PVDO) and BCLK is ready(A113X would produce BCLK signal to 6829B, not from VS-550). Please refer to picture at right side. So we think the right solution is to implement 6829B driver in A113x side. [ALT 0318] Could you provide timing sequence of VS-550(BCLK, RESET, I2C) when it boot. [Fii 0319] Fii will do the AMP initialization from VS550. Will explain more in the email and if needed will do concall for explanation. [Fii 0325] ALT to provide a way to check I2S output signal from A113X is ready or not. Fii suggest to implement some i2c commands at A113X side. [ALT 0402] ALT will send A113X is ready via I2C after boot. [Fii 0407] Please also notify us when ALT has implemented i2c API command of A113X BCLK ready.
SW | AMP board bring-up | ALT | Open | 2021-04-12 | [Fii 0409] At least I2S interface should be ready by 4/12. ALT should check when the 1st version of image will be ready within 4/9. [Fii 0413] Found I2S outrput signal has a lot of gaps and cause noise (Mantis1197). Please fix it and give the schedule when you will fix it.
SW | Provide the procedure about updating A113X AMP board | ALT | Close | 2021-04-12 | [Fii 0407] Please provide the procedure for how to update F/W in A113X AMP boards https://mantis.cnsbg.foxconn.com/vaas/view.php?id=1185
SW | [OTA - Develop OTA download APP for DSP B'd at VS-550 side] | Fii | Open | 2021-04-30 | [Fii 0329] Need to check if USB storage device at A113X side can be generated and access by VS-550 ? [Fii 0331] API: get_current_fw_version, start_ota, get_update_progress, get_update_status(idle/updating/completed), get_amp_state(running, updating, ...); OTA App development depends on these APIs. Please provide these APIs by 4/12. [Fii 0407] Based on current schedule, please provide OTA server and related API for testing and verification by 4/12, otherwise, the finished date of OTA implementation will be delayed [Fii 0408] We proposed a file base api of Amp board. Details are described in note 6601 of Mantis 1175.
SW | [OTA - USB devic class at A113X side] What kind of USB device class will be used for option-1 OTA file trasfer ? We suggest you to use USB storage class to ease OTA implemetnation. | ALT | open | 2021-04-14 | [ALT 0319] Will do OTA via USB but the exact how-to is not decided. [Fii 0319] Will share with ALT the implementation scenario. [Fii 0325] Already provided A113X OTA flow and mechanism to mantis (https://172.18.223.170/vaas/view.php?id=1175) and need ALT to reply any comments for our proposal [ALT 0326] Will check it aftere verification. [Fii 0407] Do you have any update on our proposed flow?
SW | [OTA - Develop Image Transfer(to A113X)] Framework modification for OTA | Fii | Open | 2021-04-16 | [Fii 0407] It depends on above item [OTA - USB devic class at A113X side]
SW | [I2C comm - Implement I2C Master at VS-550 -- -Check comm. Status -- - Implement command list ] | Fii | Close | 2021-04-12 | [Fii 0407] We are trying to access I2C from app. [Fii 0408] We can now access I2C from app.
SW | [OTA - build OTA server] | ALT | Open | 2021-04-12 | [Fii 0319] Need ALT to check the OTA server owner with SKB by 4/12 [ALT 0326] The OTA server owner will be decided by SKB but not yet decided. Probably will be SKB or ALT. [Fii 0331] OTA App development depends on OTA Server. Please provide OTA server and related API by 4/12. [Fii 0407] Based on current schedule, please provide OTA server and related API for testing and verification by 4/12, otherwise, the finished date of OTA implementation will be delayed
SW | [I2C Comm - Function for Mass production -- A113 Status Check/ Firmware release for MP] What is your plan to burn image of A113x in factory manufacturing? Copy IC or Use other iterface like usb burning tool? You also need to implement some functions for fatory manufacturing test command to test DSP and AMPs. | ALT | open | 2021-04-12 | [ALT] We would like to use Gang writing for eMMC of AMP B'd. We don't have any idea to test during production. So could you help to what kind of test fuction should be prepared for MP ? [Fii 0317] Relist the API commmands list in 0407. [ALT 0318] We will check it and come back to you soon. [Fii 0325] Already replied in mantis #1174 (https://172.18.223.170/vaas/view.php?id=1174) [Fii 0326] We can use Copy IC to write A113X image for eMMC of AMP B'd in factroy. [Fii 0331] Command 7 will be implemented by Fii. [Fii 0407] List the final APIs which are required to be implemented by ALT: 1. Provide a command to check if A113x is running normally (For example, you can check if the running A113x fw version is loaded successfully and running without any failure). 2. Provide a command to show the A113x Firmware version. 3. Provide a command to check the size of DDR and eMMC of A113x. 4. USB is accessable for option-1 HW design. We assume in this case, A113X acts as a storage. We will check if A113X is connected and access USB storage of A113x. Please make sure USB is accessible by default. 5. USB switch design for option-2 HW design. ALT need to provide a command to test A113X can access external USB storage.
SW | Copy IC image of A113X image for manufacturing test | ALT | Open | 2021-04-16 | [Fii 0407] Provide manufacture A113x COPY IC image before 4/16. We need to test COPY IC image before 4/26 DVT run.

## AMP board R&R
AMP board (AML A113X & Wellang) R&R
Items |  | ALT | FII | Comments
SW | Source code management
| -Source management System | O |  | Git : http://altserver01.iptime.org:8282/
| -Build Development environment | O | O | What support is needed from Fii?? [ALT] FII make develop environment in FII side
| -Develop Bootloader | O
| -Develop Main SW in DSP include Audio weaver porting | O
| -AMP control function |  | O
DSP B’d Bring up
| -I/O Port set (I2S, I2C, USB etc) | O
OTA
| -Build OTA server | O |  | Should be discussed with SKB
| -Develop OTA download APP for DSP B’d – VS-550 side |  | O | Same way to RCU Firmware update method
| -Develop Image Transfer(to A113X) | O | O
| -Develop Image update (bootloader) | O |  | Download certain area of NAND and it will be updated when DSP b’d reboot
Audio I/O Implementation
| - Develop I2S path : I2S input port -> DSP -> I2S ouput port | O
I2C comm
Implement I2C Slave – DSP
| -Check comm. status | O
| - Implement command list | O |  | check if all A113 command list is implemented by ALT; what is the difference between the command list for DSP and VS550
| -status check | O |  | [ALT] For example, we need below functions to run reboot.
| - Reboot | O |  | VS-550 asked DSP to reboot, then the command function should be implemented VS-550.
And the commands for receiving command and reboot in DSP should be implemented in DSP side
| Implement I2C Master – VS-550 |  |  | So, FII implement SW in VS-550, and ALT implement SW in DSP.
| -Check comm. status |  | O
| - Implement command list |  | O
Function for Mass production
| - A113 Status Check | O
| - Firmware release for MP | O |  | We should discuss which format FII need for MP.
| Share Data |  |  | Is this A113X source code? What's the purpose of this item [ALT] source code share is more efficient to understand each others. It is an language for SW development side.
- Source code
- Development environment
HW | Circuit design | O
| PCB Artwork – for DVT3 | O
| For MP | O |  | [ALT] We would like to devide R&R for development(ALT) and MP(FII) of AMP B'd. But if you want to provide Artwork for MP from us, then please share the cost of PCB for MP.
| Bring up | O
HW Test
AMP Performance test
| -Max. Power | O
| -THD+N vs. Freq.(1W) | O
| -THD+N vs. Freq.(Max. Po) | O
| -Max. Hum noise(Output Noise) | O
| -Min. Hum noise(Output Noise) | O
| -SNR@ Max. Power | O
| -Frequency Response | O
| -Cross talk | O
Etc
| - Thermal |  | O
| - EMC |  | O
| Share Data |  |  | What about this column? It means the data will be provided by ALT? [ALT] We can provide it if you want. I think it is for time saving.
Circuit diagram
Gerber data(DVT3+MP)
AMP performance test report
Components datasheet
Data for production