## PM&Sales
Category | Item | owner | status | due date | Reply
PM | DVT3 sample qty for ALT/SKB | ALT | close | 2021-03-15 | [Fii] Nominally ALT has 176pcs left for DVT3 (320-36-108) but will need to calculate the actual qty left with increased BOM cost after design change. [Fii 0317] If the qty is not informed by 3/18 the schedule will be delayed for another week because the factoy load the demand once a week. [ALT] Will provide on 3/17
PM | R&R discussion | Fii/ALT | close | 3/23=>3/26=>4/9 | [Fii] Fii will update the R&R list and ALT needs to check if additional items needed. [ALT 0319] Will provide the detailed items about HW development for discussion. [Fii 0326] Fii will review and reply by 3/29 [ALT 0329] We add some feedback on your comment in "AMP Board R&R" Tab. [ALT 0401] R&R for AMP board PCB artwork for MP still needs to be discussed. [Fii 0408] Fii willdo the EMC test and provide the solutions for EMC issue. [ALT 0408] MP artwork will be owned by ALT.
Sales | pre-MP+MP PO for 1K | ALT | close | 3/26=>4/8 | [Fii] will evaluate the BOM bassed on final ME design by 3/19 first. The final PO should be provided by 3/26. [Fii 0319] Before 3/24 Fii will evaluate the BOM cost based on the design as of 3/19. If there are design changes after then the price will be updated again. Also the E&O will be handled by ALT. [Fii 0325] ALT needs to provide the UP for amplifier [ALT 0326] will provide it today for Fii to update the quote. [Fii 0401] Will provide the quotation within this week. [Fii 0412] Those LT greater than 90 days are not prepared. Need ALT to provide the PO ASAP to lead the demand based on current design.
PM | E&O amount for DVT and 1K (pre MP+MP) after design change | Fii/ALT | open | 4/7=>4/29 | [Fii] Will evaluate when receiving the final ME drawing together with HW design [ALT] Final ME Design will be derivered by 3/19. We can deliver Speaker cable data by 3/19 Speaker data will be ready by 4/9 [Fii 0325] HW Tom will isse EC by 3/26 and the list will be updated later. [Fii 04009] Will provide the 1st version but will update again before MP due to possible design change after the verification of DVT3. [Fii 0415] ALT updated BOM again on 4/13 and the EC process is still ongoing.
PM | Fii will scrap all the ALT provided parts such as hosuing sub-assembly, speakers and speaker cables after DVT2 | Fii | close | 2021-04-09 | [ALT 0317] Fii provide the list for ALT to review first. [Fii 0325] List provided to ALT [Fii 0326] Received the reply from ALT and will scrap based on the confirmation column.
PM | DVT3 material preparation | Fii/ALT | open | 4/29=>5/7 | [Fii] Fii will finalize the AMP BOM for production and place order for DVT3 by 3/17.(Sean) [Fii 0317] -A113X LT*32WK. Will need ALT to have AML Demian book the materials for DVT3 and MP. Fii will also check with vendor. [Fii 0319] -A113X was kicked off by ALT with AML and ALT has the power to push AML BD Demian to book MP 1K demand. Fii will place the order to AML when receiving the PO from ALT later. -ALT helps to check the Wellang amplifier LT and start the preparation of DVT3 first. [Fii 0324] Fii will prepare materials for AMP board for DVT3 and MP based on ALT provided BOM on 3/19 on Mantis 1143. The 1st EC will be released by 3/26 by HW Tom. [ALT 0326] ALT talked to AML and will check with AML BD for the preparation of A113X. [ALT 0401] Already talked to AML Korea BD and got the reply in need of PO. [Fii 0406] Need the PO to place the order for extra parts from the design change for DVT3 ASAP. [Fii 0409] Fii QVL don't have stock ready for ECAP with spec requested by ALT and need ALT to check the originally designated vendor for DVT3 sample build demand. Fii will change to QVL part for MP. Mantis #0001143~0006640 [Fii 0412] Need check ALT provided parts schedule. Need amplifier & ECAP ETA factory 4/21. ME parts & speaker sets ETA factory 4/23. [ALT 0413] We will send AMP and ECAP by this Friday. We are checking on Mechanical part delivery schedule. We will inform Mechanical part delivery schedule when we get feedback from INKEL. [Fii 0416] Plz prepare the documents needed for ECAP PN application. Need the PO for DVT3 ASAP. The schedule will be delayed if not provided by 4/19. [Fii 0420] The shortage will be updated on 4/21.=>4/26 [ALT 0423] Inkel finished T0 tooling. DVT3 ETD 4/28. SOP should be provided no later than 4/27 to keep the DVT3 schedule. [Fii 0428] The most gatng is Inkel housing. Fii controlled parts will be ready by 5/4.
PM | VI specification | ALT /Fii | open | 2021-05-31 | [ALT] OK [Fii 0423] received the VI spec and will review with factory and reply by 4/27. [Fii 0428] factory will compare to the real production status and feedback.
PM | New speaker sets data sheet for application of new PNs | ALT | close | 4/7=>4/13 | [ALT 0401] will reply by 4/5 if the data sheet could be released as planned. [Fii 0406] Need apply for PN immediately. Plz provide it no later than 4/12. [Fii 0412] Got the data sheet for cables. Need the speaker's ASAP. [ALT 0413] Dreamus answered that they will send their datasheet by tomorrow morning.
PM | Philips business trip visa documents | Fii-Dennis | close | 2021/4/12=>4/28 | [Fii 0325] 1. 外國法人指派文件Travel Order_ALT_revised更新上傳法務系統。(3/24,done) 2. 待孫律師核簽 (3/25,done) [0326] 1. 用印簽核。(3/29,done)=> 目前核簽到鄭總 2. 3/25 和人事怡廷及Call Philips 查詢, 簽證申請以韓國辦事處規定為準 , 簽證需有邀請函及工作許可才核發簽證。 [0330] 1. 3/29送虎躍廠用印。 2. 3/30 文件送勞動部開案審查。 [0331] 已送勞動局 , 編號: 1100565962 ( 勞動局回覆,申請需要12個工作天) [0401] 1. 詢問勞動局加急需求 ,勞動局回覆,目前沒有這項申請管道,也沒有加費用申請加急的作法。 2. 可到網站:http://www.wda.gov.tw , 查詢申請進度,已經提供 ALT Philip 了解目前進度及查詢訊息。 [0406-0408] 查詢勞動局網站:http://www.wda.gov.tw , 進度為審查中。 [0409] 所附的合約是新加坡的公司和韓國ALT Co,.Ltd兩家外國公司簽約，不符合規定。需要補件。 note : 需提供買賣訂單或合約 , 是新加坡公司台灣分公司和 ALT 之間有關的文件。 [0412] ALT 提供訂單 , 先用原用印申請單,將ALT 訂單送虎躍廠用印。 [0415] 1. ALT 訂單用印已重新送勞動局審核,依辦理周小姐回覆依3/31收件, 4/1開始計算12個工作天為 (4/20完成) 。 note : 1. 4/20 勞動局核可後會將公文郵寄出 , 4/23可收到公文。 2. ALT 再依公文申請簽證,韓國台灣辦事處回覆需5個工作天 , 預計4/28完成。 [0421] 1. 4/16 下午收到勞動局核可公文 , 4/17郵寄到韓國。 2. 4/21 Tracking number : EE940708313TW , ALT Philips 已經收到文件。 [防疫規定 : 人事周怡廷 ) 1. 依據國內防疫規定 , 客戶來台之後 => 先隔離 14天 => 再自主健康管理 7天 2. 鴻海公司內部規定 , 再自主健康管理 7天期間 , 如果要進公司開會...等等 , 需持有核酸檢驗核格報告才可到公司。 3. 完成自主健康管理 7天者 , 鴻海公司內部規定不需提供核酸檢驗核格報告。
PM | Wellang AMP designation letter & vendor contact to register vendor code and PN =>changed to B&S | ALT | open | 2021-06-30 | [Fii 0317] Need to apply for PN with B&S mode and direct trading mode at the same time. Need ALT to provide the needed documents and reply email. [Fii 0325] Documents are submitted in the system for DVT3 PN application and will finish by 4/9. [Fii 0326] Vendor code registration is in process and expected to complete by end of June. Will notify ALT once the process is done and before then will need ALT to support buy and sell. [Fii 0428] Sales Tiffanie is checking with ALT the buy and sell part list.
PM | AMP eMMC 4G changed to NAND flash | ALT/Fii | close | 2021-04-07 | [ALT 0402] Could you check NAND Flash that Mr. Lonnie KIM informed in e-mail ? [Fii 0406] Fii buyer is checking the supply and will reply by 4/7 [Fii 0409] Will change to NAND flash starting from DVT3.
PM | Package final artwork for MP version | ALT | open | 2021-04-30 | [Fii 0406] ALT approves to use up old stock for DVT3. Need ALT to provide the updated artwork for MP version and check the sample qty. [Fii 0409] Need to check with vendor for the sample qty and schedule by 4/13. [Fii 0412] sample ETD no later than 4/23. [Fii 0423] The vendor feedback they can support samples but the delivery cost needs to be born by customer. Plz advise [Fii 0428] The vendor agreed to ship out 5pcs to Korea(shipped on 4/27) and need ALT to advise FEDEX account for the rest samples.
PM | ALT advised FFC cable + bushing vendor HWASUNG | Fii | close |  | [Fii 0406] Notified the vendor to prepare the sample for verification. EMI performance is worse than P Two
PM | Sub-boards PCB hold production as ALT requested | ALT/Fii | close | 2021-04-14 | [Fii 0413] ALT notifed to hold production on 4/13 and update the gerber of AMP board. The gerber out date from Fii to PCB vendor will be on 4/14. Total delay of 5 days will impact the DVT3 build schedule. [Fii 0414] There will be cost for PCB as the old one cannot be used and need to scrap. The DVT3 start date changed to 5/3.
Sales | PO for acoustic chamber modification | ALT/Fii | close | 2021-04-16 | [Fii 0415] Will provide the breakdown list for SW within 4/15 and need the PO by 4/16 as the SW modification is still needed for DVT3. [Fii 0416] The PO should be provided by 4/19.
PM | 2nd source list to be introduced after MP | Fii | open | 2021-07-09 | [Fii 0421] Including ECAP from NICHICON [Fii 0423] The introduction process follows Eagle.
PM | LS communication inductor OPO cancel(Mantis 0001131~0006674) | ALT | open | 2021-05-07 | [Fii 0428] Plz check if will continue to use the inductor SPH10040-100M for MP and onward. This will impact the 100pcs material preparation and the heatspreader design.
PM | 30pcs heatspreader allocated to ALT for urgent request to BMT | Fii | open | 2021-05-14 | [Fii 0428] N.W.E shipped out 30pcs AMP heatspreader top and bottom to ALT on 4/27 from 195sets demand for DVT3. Need to push to re-make 30 sets for DVT3
PM | ALT designation letter for BQB lab | ALT | open | 2021-05-04 | [ALT 0430] Will reply by 5/4.
PM | DREAMUS REACH (SVHC 211 items) Compliance Declaration | ALT | open | 2021-05-07 | [Fii 0430] Plz check with INKEL for the declaration with general format for REACH.

## HW &ME
Category |  | owner | status | due date | Reply
HW | AMP board layout review by EMC engineer & H/W RD | Fii | close | 2021-03-15
ME | Final ME 3D drawing. For ME/ Package/ HW review | ALT | close | 3/16=>3/19 | [ALT] We will provide it by 3/19 [Fii 0317] When does tooling start? We'd like to review before then. Is the T0 tooling schedule impacted? [ALT 0317] Tooling will start in WK3/22 and no impact on the schedule. [ALT 0319] Will push for the final drawing today.
ME | Part List of housing & speaker and updated designation letter for new parts | ALT | close | 3/19=>3/22=>3/31 | [Fii] Need to register PN and issue EC [ALT] We will check it with INKEL when they can prepare. [Fii 0319] Need the data no later than 3/22 or the schedule will be impacted. [ALT 0401] Inkel is preparing it and will check it with Inkel today. [Fii 0401] Plz provide the data on 4/6. The time left to Fii internal process is less and less. [ALT_0402] INKEL will provide it by 4/5. INKEL said that there is no additional parts, but some parts should be removed. [Fii 0406] Receive and ME is reviewing the parts that need the designation letter.
HW | AMP board DFM review by MFG ME | Fii/ALT | close | 2021-03-17 | [Fii] will send out the file for ALT to review and modify for factory review DFM again.
ME | Final 2D drawings for all parts for IQC inspection and the defined critical dimension | ALT | close | 3/19=>3/31 | [Fii] Need update in the system when applying for PN [ALT] We will check it with INKEL when they can prepare. [ALT 0326] Inkel is preparing it and will check it with Inkel today. [ALT 0401] provided already.
ME | INKEL needs to review the ME design to reduce the assembly process | ALT/Fii | close | 3/23=>3/26=>4/7 | [ALT] If you have any idea, please let me know. Do you have any idea to reduce to assembly for B'd side ? [Fii 0318] The factory will provide the DFx on 3/18. Fii will internally review with ME from 3/19. The advice will be provided by 3/23. [Fii 0323] the factory will update DFM based on ALT updated 3D drawing and internal review by 3/26. [ALT 0402] 3/26 DFM Feedback : not acceptable due to tooling started center(PCBA) area. this is too late. Don't change LED board connector direction (3/30 replied on mantis).
HW | Acoustic testing equipment needs to improve the isolation effect | Fii | close | 2021-03-19 | [Fii] Vendor provided the new pressing material to verify again after DVT2. [ALT 0318] Could you explain what problems you have.
HW | FIT RJ45 connector for Wired Network Authentication | Fii | close | 2021-03-19 | [Fii 0323] informed FIT to proceed with certification
HW | Thermal simulation with new AMP board | Fii | open | 3/19=>3/25=>4/16 | [Fii 0325] ALT provided amplifier power consumption data changed and thus need to redo the thermal sim [Fii 0326] The report and the summary will be provided on 3/26. Need ALT to talk to SKB to change the thermal spec. [ALT 0326] Will review the report first. [Fii 0401] - Top and bottom case over 5-7degC and some key components are over spec. at 50degC ambient. - VS550 107℃(over 7.6℃), 8GB eMMC 98.9℃(over 6.2℃), DDR4 103.3℃ (over 8.3℃), A113X 110.9℃ (over 5.9℃), 4GB eMMC 109.2℃(over 24.2℃), DDR3L 109.1℃ (over 24.1℃), housing top 71.2℃ (over 6.2℃), housing Bot. 79.4℃ (over 5.4℃) - Need ALT to discuss the spec with SKB, to keep the speaker power to 42W or reduce ambient temperature to 40℃ - Will discuss with ALT off-line in terms of the speaker wattage spec. [ALT_0402] When FII will start to discuss ? [Fii 0406] Need the concall for discussion. Checking the time slot on 4/8. [Fii 0407] Have provided an explanation of the power dissipation difference between EVT and the new AMP board for ALT reference. Need further discussion with ALT for the thermal issue. [ALT 0408] Need Fii to do the simulation with ALT proposed solution first then consider Fii proposed solutions to reduce the ambient temp., reduce the watt, enlarged vent holes. [Fii 0409] Will start the simulation on 4/9 and expect to provide the report by 4/12. [Fii 0412] Have provided the update simulation result to ALT. The key components are still fail @ 50degC ambient but the temperaure of the parts on AMP board is indeed lower than the previous results. [Fii 0413] To evaluate chaning of the material of heat spreader/ die-casting from Aluminum to Copper, and consider the VC (Vapor Chamber) cooling method to see if there is any improvement. Will provide the updated simulation report to ALT by 4/15. [Fii 0416] The simulation report was provided and need ALT to advise. [Fii 0423] Fii will do the simulation based on ALT proposal again. [Fii 0426] Reduce 50% speaker volume, the total AMP power changes from 7.7W to 4W, no additional venting hole, both AL & VC HSR @ 25degC & 50degC ambient can pass criteria of all components but the housing surface are still marginal fail. [Fii 0428] Will simulate again based on the same condition with additional venting hole, and see if housing surface temperaure is improved or not. [ALT 0430] The housing*2 and speaker will be shipped out on 4/30. ALT will also reply the thermal solution on 5/3. [Fii 0430] Will perform thermal test once receive the samples and need ALT to fix the thermal solution within WK 5/3. Otherwise the heatspreader tooling schedule will impact MP
HW | new design AMP board samples & speaker *13 sets for HW EMC/Thermal & SW | ALT | open | AMP:3/19=>3/31 SPK:3/19=>4/23=>4/26=>4/29 | [ALT] AMP board ETD KR 3/31 and the material status is under checking. On speaker, Dreamus will provide it by the end of April. So we will use current Speakers for test for HW, not acoustic feature. [Fii 0317] Need the speaker together to do the EMC and thermal. If ALT decides not to do any EMC/ thermal test before DVT3, plz send a formal email to confirm. [ALT 0317] 1st lot of speaker is 60cs pn 4/23. Fii may provide the risk statement for ALT to confirm. [ALT 0319] AMP board ETD KR still 3/31 [ALT 0401] No any verifications done before shipment. =>ALT shipped on 4/1. [Fii 0406] Speaker needs to pull in to 4/23 [ALT 0423] Speaker sample ETD 4/26 and the samples are not final. Will check the difference with final one. [Fii 0428] After checking with Sophie the ETD is delayed to 4/29. [ALT 0430] Will ship out the speaker samples on 4/30.
HW | Microphone sealing test fail. | ALT | open | 4/2=>4/16=>5/7 | [Fii] 1. Fii have provided the test report and suggestion to on mantis 0000952. Need ALT to work with Inkel to review the rubber pad design and make a new rubber sample for further testing. 2. ALT has to impelemnt the rubber pad solution, which can solve sealing issue in new T0 ME design [ALT 0317] Will test MIC on 3/22 and check if need to make new rubber pad on 3/23. Will check with Inkel and notify the ETA TW for new rubber pad. (normally 1 week) [ALT 0318] How many mockup for rubber pad for your test ? [Fii 0319] 3sets is acceptable. [Fii 0325] ALT sent 3pcs new Mic silicon on 3/23, and will be ETA on 3/25. Will verify new Mic silicon on 3/26 in HsinChu acoustic Lab. [Fii 0329] The sealing performance can reach 25dB after applying rubber (t=0.9mm) and adhesive to increase the pressure on the MIC hole. Need ALT to verify the solution again in Korea side to see if ALT is agreed with the solutions. [ALT 0401] ALT will provide our test result by today under similar environment various cases. [Fii 0406] Will ship out the top case with solution by 4/8 after ALT confirms the FEDEX account. [Fii 0408] Have provided the test environment and setup on 4/7 to ALT SH review. [Fii 0409] 1. Need ALT to check if possible to provide the sample of silicon rubber within 4/9. 2. Need ALT to check if tooling modification for inteference issue is still possible. =>ALT will help verify the impact of the interference. [Fii 0413] According to SH, the sponge silicon mic can ship to TW office (1.1t, housing side with O-ring, PCB side is plat.). Can ALT provide us 3pcs samples for testing? Please inform us when ALT can ship out the samples. [Fii 0420] ALT SH has shipped 3 sets of new rubber pad to Fii by 4/19. DHL tracking: 9167971131 [Fii 0428] Arrange sealing test at HC acoustic chamber on 4/29
HW | AMP board verification test done before DVT3 gerber out | Fii/ALT | close | 2021-04-06 | [Fii]The verification before gerber out is necessary [ALT] We will provide AMP b'd gerber data by 4/6. [Fii 0317] Remind again the verifications mentioned in the email must be done before 4/6. The gerber must be provided on 4/5 morning. We have internal process for gerber out. [Fii 0325] Will proceed if ALT confirms the risk.
ME | T0 samples*2 for ME in China and factory ME in VN with assembly SOP | ALT | open | 4/7=>4/23=>4/30 | [ALT] T0 Sample will be prepare the end of April. If you need these ME parts, then you should prepare with 3D data [Fii 0317] With Inkel provided SOP we need to 1. review with real housing and try assembling then evaluate assembly issues 2. transform into our SOP before DVT3. We need to reduce the time to do the trouble shooting when the production starts. [ALT 0318] We asked INKEL about it. But currently they provide T0 sample when they [ALT 0319] Will request Inkel to provide T0 sample and need Fii to provide the recipient info. [Fii 0325] Plz help check the delivery date -ME RD in China Recipient: Jim CHEN Cell: 18376747022 Address: Foxconn Technology Park, No.51, Tongle Road, Jiangnan District, Nanning City, Guangxi Province, China. -ME in VN factory Recipient: Nguyen Thi Thu Thuy Mobile: +84 0912872792 Company : FUNING PRECISION COMPONENT CO., LTD. Address : Lot B, Que Vo Industrial Zone, Nam Son Ward, Bac Ninh City, Bac Ninh Province, Vietnam [Fii 0326] Plz provide as early as possible. This will impact the production going smoothly. Also need Inkel on-site support. [ALT 0326] Likely to be 4/23 or 1 week before. Will check again. Also will check with Inkel or on site support [Fii 0420] Need extra 2 sets of samples to do the thermal test. Need to be as much assembled as possible. [Fii 0423] INKEL needs to provide the SOP ASAP. The date 4/30 is not acceptable. Plz check again if possible to provide no later than 4/27 to keep the schedule. [ALT 0423] Will check with INKEL for the SOP schedule. [Fii 0428] Where are the samples for ME review? Received the SOP and Fii ME is reviewing. [ALT 0430] Housing samples are shipping out with speaker samples on 4/30
HW | Need power dissipation of all key components in AMP board for thermal simulation | ALT | close | 2021-03-16
HW | IQC for THD & FR of DREAMUS new speaker Fii Q team will on-site check the testing result. Need the updated spec to audit. | ALT | open | 4/22=>4/29 | [Fii] Dreamus cannot provide the testing equipment and Fii will send the Q team to Dreamus factory to check the testing result before shipment. [ALT 0318] We will check it when Dreamus start to produce Speaker. [Fii 0330] Because Dreamus cannot provide the testing equipment to Fii, if any suspect of speaker unit issue, Fii will need to return to Dreamus for analysis.=>[ALT 0409] well noted. [Fii 0401] Before Dreamus ship out on 4/23, Fii IQC must be done in Dreamus factory. [ALT 0401] Will check with Dreamus if THD&FR are tested. [ALT_0402] ALT sent e-mail that OQC schedule and test items on 4/2. [Fii 0406] Plz check the testing items of THD and FR. Besides the speaker schedule needs pull-in. [Fii 0416] Received the proposal from Dreamus and will check internally and reply by 4/20. [ALT 0423] DVT3 speakers are not final. Performance related testing items for speaker could be waived. Will check the updated schedule with Dreamus on 4/23. Will provide the difference report for Fii to evaluate the impact on the following testing and MP. [Fii 0428] When the difference report will be provided? Need ALT to push DREAMUS to add the FR test in production and OQC report. [Fii 0430] If Dreamus only does FR in OQC and not during production, once Fii discovers FR test fail and does the the SWAP analysis, the rework cost will be transferred to Dreamus. (send email to ALT)
HW | What would be the new spec for the soundbar on THD and FR as B&O requested? | ALT | close | 2021-04-12 | [ALT] We will check it to B&O [ALT 0318] B&O didn't have any requirement about THD and FR. They listen sound from speaker and evaluate. They focus on SNR(> 95dB) and Noise level(< 200uV). [ALT 0319] System test spec remains the same as RFP specifies.
ME | DVT3 housing ETA factory | ALT | open | 4/24=>5/4=>5/7 | [Fii] Plz confirm the sample qty for DVT3 [ALT] We asked to INKEL, but they will finish tooling by 4/23. So they need a week more. [Fii 0317] We need the materials ready no later than 4/24. Besides, is the shipment from China again? If so how do we start SMT on 4/26 considering the delivery period from DVT1? [ALT 0318] We asked to provide T0 housing by 4/24 at your factory. But they don't have enough time, so they are discussing with their factory in china. [ALT 0319] Will request Inkel to provide the housings as specified and is aware any delay will cause the production start date delay. [ALT 0401] Still checking with Inkel if ETA factory 4/23. [Fii 0416] The schedule was delayed to 5/4. plz continue to pull in to 4/29. Fii will check the production plan starting from 5/4. [Fii 0428] further delayed to 5/7 and the production schedule provided based on the date.
HW | ECAP lifetime | Fii | open | 2021-05-20 | [Fii]Will verify with the final design [Fii 0415] DVT3 applies ALT provided ECAP, need ALT help check if KC certification will be impacted if the ECAP is changed for MP. [ALT 0416] Confirmed no need to do EMC/ KC for change of ECAP. [Fii 0419] The substitute for ECAP from Fii QVL will not be able to make it to MP. Plz check if possible to go buy and sell for this part [Fii 0423] Fiki will check if any agent could buy the part. If not, will need ALT to help buy and parts for first couple shipment of MP. Will update the progress by 4/26 to ALT first. [Fii 0428] The vendor is surveying how to trade with Fii for MP demand as SAMYOUNG rejected to trade with Fii AVL agent. requested SAMYOUNG to reply by 4/30 [Fii 0430] Will check with factory if the stock is enough to support pre-MP 100pcs.
HW | A113X OTA architecture |  | close |  | [ALT 0317] Design both option 1 and option 2. But option 2 no need to do SMT, just reserve on layout. If needed after, ALT will rework. Fii no need to prepare for the materials.
HW | EMI pre-test and debugging | Fii | close | 2021-04-01 | [Fii 0325] 1. P-two make the new FFC cable and estimated ETD on 3/26. 2. Book 3/30~4/1 3rd party Lab. and debugging [Fii 0326] Target to complete by 4/1 but still need to check the lab time slot [Fii 0329] The new FFC cable ETA is 3/30. Have booked the 3rd party Lab. on 4/1.
HW | DVT heatspreader sample thermal test and improvement | Fii | close | 2021-04-23 | [Fii 0325] Current test result is bottom case 52.8degC @ 25degC ambient (spec.=50degC) 1. Make the new heat spreader top/bottom of AMP board, and estimated ETD on 3/28 2. Make the new heat spreader bottom of main board, and ETD is to be confirmed with vendor NWE [Fii 0329] The new bottom heat spreader is estimated complete and shipped by 4/15. Expect to complete the test by 4/23. [Fii 0419] The new bottom heat spreader was shipped by 4/17, and ETA on 4/23. Need rebook the schedule of HCQA thermal chamber. [Fii 0428] The test result of top and bottom surface are passed @ 25degC & 50degC ambient. (48.6degC & 37.9degC @ 25degC ambient and 70.5degC & 61degC @ 50degC ambient)
HW | Acoustic testing equipment may need to modify due to new speaker location | Fii | Open | 2021-05-30 | [Fii 0325] Will contact the vendor to evaluate the impact and cost based on 3D drawing. [ALT 0326] The 3D drawing provided can be used to evaluate the impact on chamber HW. [Fii 0326] Will provide the evaluation by 3/30 [Fii 0330] Need ATBU to evaluate the adjustment of the testing environment. [ALT 0402] How will you test bottom side Woofer speaker ? [Fii 0406] Updated on Mantis for the workaround since the time needed for making the formal fixture is long. The proposal of the fixture and the quotation will be updated by 4/7 morning. [Fii 0412] Need ALT to check the quotation and provide PO by 4/14. Fii needs to get the PO to have the vendor modify the SW for DVT3. [Fii 0416] The schedule will be further delayed if the PO is not provided by 4/19. [Fii 0423] Because the speaker for DVT3 is not final. ALT agree to waive the speaker perfornance test. [Fii 0430] Received the testing items advised by ALT and will discuss with vendor and reply by 5/5.
HW | ESD risk from the vent hole design for DVT3 housing. | Fii | open | 2021-05-10 | [Fii] Suggest ALT to seal the venting hole to avoid ESD issue [ALT 0401] If any ESD issues, will seal the hole in T1 housings. The detailed plan will be discussed later.
HW | DVT2 Speaker test result | FII | Open | 2021-04-02 | [ALT] Please provide Speaker Test result in your test chamber for DVT2 samples
HW | EMC test with new AMP board, new speaker sets, old housings | Fii | open | 2021-04-30 | [Fii 0409] Need the speaker ETA TW 4/23 for assembly with new AMP board in the old housing. [Fii 0415] If ALT can provide the complete S/W by 4/16, the function of new AMP board is expected to be verified completed by 4/23. Then Fii wiFll book the 3rd party chamber on week 4/26 ~ 4/30 for EMC testing. [Fii 0416] If the SW for all functions ready by 4/21 then the EMC will start on 4/22. Also the NRE PO for EMC test should be provided ASAP.
HW | LED chip color shift issue | Fii | open | 2021-06-10 | [Fii 0412] Everlight will update the FA with short term solution and the DOE for reproducibility. The final solution schedule will also be updated for fast introduction. [Fii 0413] The vendor proposed the short term solution which should be able to keep the defects from flowing out to Fii and will verify by 4/23. [Fii 0419] Fii will also survey the alternative part for LED. Will provide the update information on 4/23=> by 4/30 [Fii 0423] The verification of validity of solutions will be done within WK 4/26. The proposal to handle the defects return will need to discuss with vendor and feedback within the same week.

## SW
Category | Item | owner | status | due date | Reply
SW | AMP EVK*2 ETA TW for SW development | Fii | close | 2021-03-25 | [ALT] We will receive EVK b’d by 3/19. We should check it first and then we will send it. So we can send it 3/22 [Fii 0323] Need the circuit diagram and the user manual [Fii 0325] HW help to rework AMP EVK to connect to our VS-550 board (for i2c)
SW | For normal OTA of A113x, which function do we need to implement? Do we only need to implment USB switch API? Please provide detail SW R&R. => OTA server readiness | ALT | close Use other item to track | 2021-04-12 | [ALT] We should prepare OTA function. So OTA app will be installed in VS550. We think that 2 part of SW we need. OTA App in VS 550 : Implement by FII. It should connect OTA server and download new firmware and send image data to DSP. SW for DSP : It will implemented by ALT. But I think that it is more efficient to develop all OTA related function developped by one party. Can you support it ? [Fii 0317] Who will provide OTA server ? Because we don't know S/W detail and how to upgrade S/W in A113x side so we think the OTA function shall be implemented by ALT. [ALT 0317] OTA server is not decided. [Fii 0319] Need ALT to check the OTA server owner with SKB by 4/12 [ALT 0326] The OTA server owner will be decided by SKB but not yet decided. Probably will be SKB or ALT.
SW | Please also consider if A113x crashes in developing and OTA can not be used, which interface will you used for update image of A113x? | ALT | close |  | [ALT] We think that we can use USB for update But if A113x crashed, then it can be updated by serial port and USB.
SW | [Source code management - AMP control function] | Fii | Close | 4/13=>4/16 | [Fii 0329] Wha'ts AMP control function? EQ or DRC ? AMP(WA20-6829B) registers would be controlled by driver in VS-550 [Fii 0331] We have some questions about how to config registers for EQ/DRC to enable/disable. Would you help to forward these questions to Wellang or provide us the contact information? [ALT 0401] Will provide the engineer contact and Fii needs to copy ALT members in the loop. [ALT_0402] We already sent e-mail to Wellang and introduced both FII and Wellang engineers. [Fii 0407] We now can use sample code to initalize EVK board(one AMP IC) successfully from VS550. We now are add a psedudo code to check BCLK ready from A113x and check the impact of delay of BCLK. [Fii 0408] Delay of initalize AMP driver will cause NUGU open device fail. We are now working on it. We also recevied Wellang reply about our questions and will check the answer. [Fii 0413] Pending the NUGU can not open issue. Test with A113X AMP board and change driver registers for PBTL mono mode. [Fii 0414] 1.Trying to find a way to fix "NUGU can not open issue". 2.Modifing AMP driver for new AMP reset pin and change LED i2c address which conflicts with Wellang AMP i2c address. [Fii 0415] 1.Still working on trying to find a way to fix "NUGU can not open issue". 2.Modifing AMP driver for new AMP reset pin and change LED i2c address which conflicts with Wellang AMP i2c address.(Done) [Fii 0419] 1.Find a way to fix "NUGU can not open issue.(Done) AMP driver porting is almost done and need ALT to provide the BLCK check I2C command. Before ALT provide us the BCLK I2C command, we will temporarily use a fixed delay to initialize AMP driver. Please add /usr/bin/speaker_process to init.d and give us a test image for measuring BCLK ready time for the fixed delay.
SW | [I2C comm - Implement I2C Master at VS-550 -- -Check A113x BLCK readiness status] We think you should integrate the AMP drivers in A113x side and provide an interface between VS550 and A113x to control AMP EQ/DRC. Because the initial timeing sequenc of AMP needs to make sure the power and I2C BLCK to be ready(as the picture at the right side). And the delay of initialization of AMP on VS550 will also impact FFV MIC access in VS550 at system booting. | ALT | Close | 4/16=>4/23 | [ALT]We suggested to control I2C of AMP by VS550.So if there is any issue to control AMP b’d. We will provide AMP B’d first, and we will provide SW as soon as it ready. [Fii 0317] As we mentioned, there is initial timing issue happened if WA20-6829B drvier implemented in VS-550 side after checking timing sequence in WA20-6829B datasheet. Until now, there is no mechanism to know if the power(PVDO) and BCLK is ready(A113X would produce BCLK signal to 6829B, not from VS-550). Please refer to picture at right side. So we think the right solution is to implement 6829B driver in A113x side. [ALT 0318] Could you provide timing sequence of VS-550(BCLK, RESET, I2C) when it boot. [Fii 0319] Fii will do the AMP initialization from VS550. Will explain more in the email and if needed will do concall for explanation. [Fii 0325] ALT to provide a way to check I2S output signal from A113X is ready or not. Fii suggest to implement some i2c commands at A113X side. [ALT 0402] ALT will send A113X is ready via I2C after boot. [Fii 0407] Please also notify us when ALT has implemented i2c API command of A113X BCLK ready. [Fii 0421] We got a test image which support I2C command to check BCLK ready. We will test it with AMP driver. The boottime of A113X is too long, please release test image that shortens the boottime. [Fii 0423] Still working on integrating I2C BCLK ready to AMP driver. [Fii 0423] AMP driver integrated the BCLK ready. (Done)
SW | A113X I2S output has gaps issue | ALT | Close | 4/12=>4/23 | [Fii 0409] At least I2S interface should be ready by 4/12. ALT should check when the 1st version of image will be ready within 4/9. [Fii 0413] Found I2S outrput signal has a lot of gaps and cause noise (Mantis1197). Please fix it and give the schedule when you will fix it. [Fii 0414] Please fix it before 4/16. Please also include run /usr/bin/speaker_process while A113x boots. DVT3 manufacture will need this fix to test audio. [Fii 0423] We found if we unplug FFV board, the I2S gap issue disappears. We think it is related to I2S BCLK signal quality. We are still doing more tests with HW. [Fii 0426] The audio gap issue is releated to I2S signal. HW reworked a board to add some buffer IC in I2S bus and this issue is gone. DVT3 design already included the buffice IC. (Done)
SW | Provide the procedure about updating A113X AMP board | ALT | Close | 2021-04-12 | [Fii 0407] Please provide the procedure for how to update F/W in A113X AMP boards https://mantis.cnsbg.foxconn.com/vaas/view.php?id=1185
SW | [OTA - USB devic class at A113X side] What kind of USB device class will be used for option-1 OTA file trasfer ? We suggest you to use USB storage class to ease OTA implemetnation. | ALT | Close | 4/16 => 4/22 | [ALT 0319] Will do OTA via USB but the exact how-to is not decided. [Fii 0319] Will share with ALT the implementation scenario. [Fii 0325] Already provided A113X OTA flow and mechanism to mantis (https://172.18.223.170/vaas/view.php?id=1175) and need ALT to reply any comments for our proposal [ALT 0326] Will check it aftere verification. [Fii 0407] Do you have any update on our proposed flow? [Fii 0413] Response from ALT: They need more time for OTA server and APIs. (Mantis 1175) [Fii 0421] Instead of taking the USB device as a storage device, ALT takes it as an android usb device and operates it through adb tool.
SW | [OTA - Develop Image Transfer(to A113X)] Framework modification for OTA | Fii | Close | 4/16 => 4/22 | [Fii 0407] It depends on above item [OTA - USB devic class at A113X side] [Fii 0413] Todo: 1. Prevent Amp storage from being converted to android internal storage. 2. Prevent Amp storage (external storage) from being used by apps those should not access it. [Fii 0415] 1. Prevent Amp storage from being converted to android internal storage. => Done, still need some modification for Amp storage 2. Prevent Amp storage (external storage) from being used by apps those should not access it. => Todo [Fii 0421] According to ALT's implementation, we don't need the above modification of framework.
SW | [OTA - build OTA server] | ALT | Close | 4/12=>4/22 | [Fii 0319] Need ALT to check the OTA server owner with SKB by 4/12 [ALT 0326] The OTA server owner will be decided by SKB but not yet decided. Probably will be SKB or ALT. [Fii 0331] OTA App development depends on OTA Server. Please provide OTA server and related API by 4/12. [Fii 0407] Based on current schedule, please provide OTA server and related API for testing and verification by 4/12, otherwise, the finished date of OTA implementation will be delayed [Fii 0413] Response from ALT: They need more time for OTA server and APIs. (Mantis 1175) [Fii 0421] According to ALT's implementation, we don't need OTA server.
SW | SW compatible for old EVT/DVT1/DVT2 and new DVT3 board. | Fii | Open | 2021-05-03 | [Fii 0423] Find a way to make one SWAN image can run on both old EVT2/DVT1/DVT2 and new DVT3. [Fii 0428] Still working on onr SWAN image can run on both old EVT2/DVT1/DVT2 and new DVT3. [Fii 0429] AMP compatible is ready and still working on LED subboard compatible issue.
SW | [OTA - Develop OTA download APP for DSP B'd at VS-550 side] | Fii | Open | 4/30=>5/14 | [Fii 0329] Need to check if USB storage device at A113X side can be generated and access by VS-550 ? [Fii 0331] API: get_current_fw_version, start_ota, get_update_progress, get_update_status(idle/updating/completed), get_amp_state(running, updating, ...); OTA App development depends on these APIs. Please provide these APIs by 4/12. [Fii 0407] Based on current schedule, please provide OTA server and related API for testing and verification by 4/12, otherwise, the finished date of OTA implementation will be delayed [Fii 0408] We proposed a file base api of Amp board. Details are described in note 6601 of Mantis 1175. [Fii 0413] Response from ALT: They need more time for OTA server and APIs. (Mantis 1175) [Fii 0421] Wait for ALT's image and binary for testing [Fii 0422] Test OTA flow with ALT's binary: 4K2 button needs to be reworked, otherwise the OTA flow of A113X will be blocked. [Fii 0423] 1. Integration of adbsub and Android App. (Mantis 1175) a. There are sepolicy issues. (some are neverallow) b. Modifying adbsub is also needed.(ALT) c. This may take extra 1~2 weeks. 2. There are several features we need. (Mantis 1175) FW version, OTA progress/status, A113X state, Detection of OTA failure [Fii 0428] Integration of adbsub and Android App. (Mantis 1175) a. ALT is checking the problem of adbsub. [0123456789ABCDEF device] is not detected. b. /vendor/bin and /data/vendor are used for adbsub related files. Need to modify sepolicy and file permission.
SW | [I2C comm - Implement I2C Master at VS-550 -- -Check comm. Status -- - Implement command list ] | Fii | Close | 2021-04-12 | [Fii 0407] We are trying to access I2C from app. [Fii 0408] We can now access I2C from app.
SW | Copy IC image of A113X image for manufacturing test | ALT | Close | 2021-04-16 | [Fii 0407] Provide manufacture A113x COPY IC image before 4/16. We need to test COPY IC image before 4/26 DVT run. [Fii 0420] AML say A113x can not use COPY IC for nand flash. So we need to use USB Burning tool to upgrade fw. Please provide us image for USB Burning tool.
SW | [I2C related APIs --- OTA, Manufacturing, Amp driver development] | Fii | Open | 2021-05-14 | [Fii 0428] I2C slave mode is not supported in recovery mode currently. (Mantis 1209) 1. FW version (done, i2cget 0 -y 0x20 1) 2. Bclk Ready (done, i2cget 0 -y 0x20 0) 3. A113x reboot (done, i2cset 0 -y 0x20 0 0x99 b) 4. Get the progress of OTA => While updating, we'd like to show progress (0~100) of A113X OTA on UI for user. (Due date: 5/14) 5. Get the state of A113X state: booting -> A113X is booting. (Due date: 5/7) running -> A113X is running. (Due date: 5/7) updating -> A113X is updating. (Due date: 5/14) error_update -> Udpating fails and A113X is blocked in some error state. Details are described below. (Due date: 5/14) standby -> A113X is standby. (Due date: 5/14) And any other state you think it is necessary. (Due date: 5/14) [Fii 0429] Without supporting I2C command in recovery mode, end users need to power cycle SWAN if A113x OTA failed. (Mantis 1209)
SW | [A113X firmware for DVT3] | ALT | Open | 2021-05-04 | [Fii 0414] Need functions being ready for DVT3 1. I2S audio output [Fii 0427] I2S audio output is related to HW issue. DVT3 add a buffer IC to fix it. [Fii 0428] Please provide a final A113x image that we can use adbsub to detect usb. We want to use this final A113X image for DVT3 manufacturing testing. [Fii 0429] For DVT3 manufacturing, please provide A113x image which include usb ota function even when adbusb root isuuse is not fixed. Then it will avoid to remove housing when DVT3 boxes needs to change A113X image at RD and 3party development stage.
SW | [I2C Comm - Function for Mass production -- A113 Status Check/ Firmware release for MP] What is your plan to burn image of A113x in factory manufacturing? Copy IC or Use other iterface like usb burning tool? You also need to implement some functions for fatory manufacturing test command to test DSP and AMPs. | ALT | Close | 4/12=>4/27 | [Fii 0331] Command 7 will be implemented by Fii. [Fii 0407] List the final APIs which are required to be implemented by ALT: 1. Provide a command to check if A113x is running normally (For example, you can check if the running A113x fw version is loaded successfully and running without any failure). 2. Provide a command to show the A113x Firmware version. 3. Provide a command to check the size of DDR and eMMC of A113x. 4. USB is accessable for option-1 HW design. We assume in this case, A113X acts as a storage. We will check if A113X is connected and access USB storage of A113x. Please make sure USB is accessible by default. 5. USB switch design for option-2 HW design. ALT need to provide a command to test A113X can access external USB storage. [Fii 0428] 1. update command list in mantis #1209 (https://172.18.223.170/vaas/view.php?id=1209)
SW | AudioWeaver DSP - acoustic fine tuning | ALT | open | 2021-05-14 | [Fii 0423] Please provide FW schedule for AudioWeaver DSP fine tune

## Pre-MP issues
Open issues for 100pcs pre MP=>check if possible to pull in to ETD 6/25?
1. Thermal issue -
1.1 ALT request to reduce 50% speaker volume, the total AMP power changes from 7.7W to 4W, no additional venting hole, both AL & VC HSR @ 25degC & 50degC ambient can pass criteria of all components but the housing surface are still marginal fail.
1.2 The thermal solution of VC is the maximum limit for the current design. The temperature of all components can be passed based on VC solution with maximum AMP power but the surface temperature are still marginal fail.
1.3 Fii will arrange the real case thermal test based on DVT3 sample but that mean Fii don't have enough time to implement any solutions if we need to shipped 1st 100pcs sample by June.
1.4 Thermal solution should be fixed within this week for MP demand. The heatspreader sample price is very expensive and the capacity will not be able to meet 4.9K demand later.
2. DREAMUS Speaker
2.1 100pcs will use the same speaker as DVT3?=>not yet finalized
2.2 Need the comparison of old and new speakers to evaluate the impact.
3. Test
3.1 Reliability will not be able to complete before shipment
3.2 BQB and HDMI pre test doesn't have enough time to go through completely
4. Material
4.1 MP PO was provided late on 4/19. Fii only prepared the materials with long LT(greater than 90days) excluding AMP boards with new design. Will need to check with vendor if possible to meet the target. If not, will need to buy from spot market. The same for MP order later. | WK5/3給出那些物料需要採買現貨，提供清單給ALT
4.2 ALT controlled parts such as DREAMUS speaker, INKEL housing, Wellang amplifier (also need ECAP) should ETA VN 6/9 =>need to check with factory for the ECAP qty , if enough for 100pcs??
5. SW
5.1 OTA function on A113X should be ready by 5/14
6. Selling price related to payment
6.1 The final quotation is not fixed yet.
7. EMC
7.1 The system RE/RS/CE is being tested and debugged with new AMP board. Even if we use the latest speakers and enhanced FFC cables for testing, but the housing is not the final one, which means that the cable routing will not be the final setup. and this may bring some risks when using DVT3 sample for certification.=>need ALT to send out the DVT3 housing sample ASAP
7.2 There are some venting holes in the DVT3 housing, which may cause the risk of ESD failure.

## AMP board R&R
AMP board (AML A113X & Wellang) R&R
Items |  | ALT | FII | Comments
SW | Source code management
| -Source management System | O |  | Git : http://altserver01.iptime.org:8282/
| -Build Development environment | O | O | What support is needed from Fii?? [ALT] FII make develop environment in FII side
| -Develop Bootloader | O
| -Develop Main SW in DSP include Audio weaver porting | O
| -AMP control function |  | O
DSP B’d Bring up
| -I/O Port set (I2S, I2C, USB etc) | O
OTA
| -Build OTA server | O |  | Should be discussed with SKB
| -Develop OTA download APP for DSP B’d – VS-550 side |  | O | Same way to RCU Firmware update method
| -Develop Image Transfer(to A113X) | O | O
| -Develop Image update (bootloader) | O |  | Download certain area of NAND and it will be updated when DSP b’d reboot
Audio I/O Implementation
| - Develop I2S path : I2S input port -> DSP -> I2S ouput port | O
I2C comm
Implement I2C Slave – DSP
| -Check comm. status | O
| - Implement command list | O |  | check if all A113 command list is implemented by ALT; what is the difference between the command list for DSP and VS550
| -status check | O |  | [ALT] For example, we need below functions to run reboot.
| - Reboot | O |  | VS-550 asked DSP to reboot, then the command function should be implemented VS-550.
And the commands for receiving command and reboot in DSP should be implemented in DSP side
| Implement I2C Master – VS-550 |  |  | So, FII implement SW in VS-550, and ALT implement SW in DSP.
| -Check comm. status |  | O
| - Implement command list |  | O
Function for Mass production
| - A113 Status Check | O
| - Firmware release for MP | O |  | We should discuss which format FII need for MP.
| Share Data |  |  | Is this A113X source code? What's the purpose of this item [ALT] source code share is more efficient to understand each others. It is an language for SW development side.
- Source code
- Development environment
HW | Circuit design | O
| PCB Artwork – for DVT3 | O
| For MP | O |  | [ALT] We would like to devide R&R for development(ALT) and MP(FII) of AMP B'd. But if you want to provide Artwork for MP from us, then please share the cost of PCB for MP.
| Bring up | O
HW Test
AMP Performance test
| -Max. Power | O
| -THD+N vs. Freq.(1W) | O
| -THD+N vs. Freq.(Max. Po) | O
| -Max. Hum noise(Output Noise) | O
| -Min. Hum noise(Output Noise) | O
| -SNR@ Max. Power | O
| -Frequency Response | O
| -Cross talk | O
Etc
| - Thermal |  | O
| - EMC |  | O
| Share Data |  |  | What about this column? It means the data will be provided by ALT? [ALT] We can provide it if you want. I think it is for time saving.
Circuit diagram
Gerber data(DVT3+MP)
AMP performance test report
Components datasheet
Data for production