## Foxconn agenda
ID | Project | Reporter | Assigned To | Priority | Severity | Reproducibility | Product Version | Category | Date Submitted | View Status | Updated | Summary | Status | Resolution | agenda
573 | SKB Eagle (T99X171) | (ALTech) SB Park | (PM) Sheila Tu | immediate | s1-catastrophic | sometimes |  | HW Issue | 2019-03-22 | public | 2019-04-04 | [USB] happen to reboot when the ext HDD is connected to USB port | assigned | open | Do you test? | going test but not reproduce
458 | SKB Eagle (T99X171) | (ALTech) SB Park | (RD) Fu-chiang Young | immediate | s1-catastrophic | always |  | HW | 2019-02-22 | public | 2019-04-09 | SKB's test criteria of power consumption during normal operating state | assigned | open | Do check the wake up time of active standby mode | update schedule
541 | SKB Eagle (T99X171) | (ALTech) SB Park | (HW) Sean Chiang | immediate | s1-catastrophic | have not tried |  | HW | 2019-03-08 | public | 2019-04-09 | [DDR, EMMC] aging test | assigned | open | please update replacement of DDR and EMMC readwrite, aging test | 1. update aging test report next week 2. update mantis read / write test schedule
542 | SKB Eagle (T99X171) | (ALTech) SY Yoon | (ALTech) SB Park | high | s2-severe | have not tried |  | HW | 2019-03-11 | public | 2019-04-09 | Bright ness of LED | acknowledged | open | skip. But see the mantis update
527 | SKB Eagle (T99X171) | (ALTech) SB Park | (PM) Sheila Tu | immediate | s2-severe | N/A |  | HW | 2019-02-28 | public | 2019-04-09 | [Accessory] HDMI, LAN Cable | assigned | open | price information and I will discuss with SKB again | re discuss with SKB 0.08
531 | SKB Eagle (T99X171) | (ALTech) SB Park | (RD) Fu-chiang Young | immediate | s1-catastrophic | N/A |  | HW | 2019-03-04 | public | 2019-04-09 | [EAGLE] Extraction test between adapter and DC jack | acknowledged | open | You said to me second test is also fail. Do you have any solution and when do you retest? | still fail.
612 | SKB Eagle (T99X171) | (ALTech) SB Park | (HW) Sean Chiang | immediate | s1-catastrophic | N/A |  | HW | 2019-04-09 | public | 2019-04-09 | [BT] RF output level and modulation method | assigned | open | according to datasheet. GFSK, pi/4 – DQPSK, and 8 – DPSK RF TX power is about 16mW
543 | SKB Eagle (T99X171) | (ALTech) SB Park | (HW) Sean Chiang | immediate | s1-catastrophic | N/A |  | HW | 2019-03-11 | public | 2019-04-09 | [HW] update HW validation test report | assigned | open
603 | SKB Eagle (T99X171) | (ALTech) SB Park | (HW) Sean Chiang | immediate | s1-catastrophic | N/A |  | HW | 2019-04-04 | public | 2019-04-09 | [KC certification] Schedule of KC | assigned | open | I want to 2pcs of Sample first | 2pcs Together DVT
456 | SKB Eagle (T99X171) | (ALTech) SB Park | (HW) Jim Liang | immediate | s3-moderate | N/A |  | HW | 2019-02-19 | public | 2019-04-08 | DDR SI Simulation report | assigned | open | skip
500 | SKB Eagle (T99X171) | (SW) Jacky Chiang | (HW) Sean Chiang | normal | s2-severe | have not tried |  | HW | 2019-02-22 | public | 2019-04-04 | Eagle B'd can run without power adaptor. It just connected console Board or HDMI or USB. | assigned | open | skip
586 | SKB Eagle (T99X171) | (HW) Sean Chiang | (ALTech) SB Park | normal | s3-moderate | N/A |  | HW | 2019-03-27 | public | 2019-03-27 | Update power adapter CE test result | assigned | open | skip
463 | SKB Eagle (T99X171) | (ALTech) SY Yoon | (PM) Sheila Tu | normal | s2-severe | have not tried |  | HW | 2019-02-22 | public | 2019-03-14 | Weld line on Rear side | assigned | open | ??

## HW Validation test
Item Name | Large category | Detail test | Spec | Result | TEST REPORT | Start Date | Due Date | Note
eMMC waveform measurement | eMMC | Timing | FXN | Finished |  | 2019-02-14 | 2019-02-19
|  | Data read, write, erase test | FXN | ?? |  |  |  | Replace to other test
|  | Aging test | FXN |  |  | Not Yet | Not Yet | replace to reliability test
I2C waveform measurement | I2C | Timing | FXN | Finished | Finished | 2019-02-13 | 2019-02-19
Power | On/Off sequence | ON sequence | FXN | Finished | Finished | 2019-02-13 | 2019-02-22
|  | OFF sequence | FXN | Finished | Finished
| Accuracy/Ripple | Power Level (0, 25, 50) | FXN | Finished |  | 2019-02-14 | 2019-02-22
|  | Power ripple (0, 25, 50) | FXN | Finished |  |  |  | powr ripple conditional pass | update report Friday
| Power consumption | Normal mode | SKB | Finished |  | 2019-02-18 | 2019-02-26 | test again at DVT
|  | Active standby | SKB | Finished |  |  |  | test again at DVT
|  | Passive standby | SKB | Finished |  |  |  | test again at DVT
|  | Full load (with USB) | SKB | Finished |  |  |  | test again at DVT
Clock | Crystal Frequency | Amlogic | FXN |  |  | 2019-02-12 | 2019-02-27
|  | ethernet PHY | FXN
|  | BT | FXN
RF | RF TEST | BT | FXN | Finished |  | 2019-02-12 | 2019-02-27
DDR related measurement | DDR | SSQ test | FXN | Not Yet |  | 2019-02-12 | 2019-03-07 | SS not schedule. Replace to other test
|  | Data read, write, verify test | FXN | Not Yet |  |  |  | Replace to other test
|  | SI simulation | FXN | Finished
|  | Aging test | FXN | Not Yet |  | Not Yet | Not Yet | replace to reliability test
DCDC Power verification | DCDC | Power effciency (25℃) | FXN | Finished |  | 2019-02-12 | 2019-03-07 | wrong test. Re test at DVT
|  | Power loss (25℃) | FXN | Finished
|  | Load Regulation (25℃) | FXN | Finished
|  | Bode plot (Phase, Margin) | FXN | Finished
BT RCU sensitivity test | BT | BT RCU test | FXN | Finished |  | 2019-03-04 | 2019-03-07 | This test can be replace to RF test
EMI/EMS | EMI | Radiated Emission | FXN | Finished |  | 2019-02-14 | 2019-03-07
|  | Conducted Emission | FXN | Finished
| EMS | Radiated Immunity | FXN | Finished
|  | Conducted Immunity | FXN | Finished
|  | ESD | FXN | Finished
|  | Surge | FXN | Finished
HDMI/USB/Ethernet SI test | USB | USB2.0 (Low speed) | FXN | Finished |  | 2019-02-18 | 2019-03-07 | conditional pass
|  | USB2.0 (Full speed) | FXN | Finished
|  | USB2.0 (High speed) | FXN | Finished
|  | USB3.0 (RX) | FXN | Not Yet |  |  |  | amlogic's support
|  | USB3.0 (TX) | FXN | Finished
|  | Drop test | FXN | Finished
|  | Port overload test | FXN | Finished
| HDMI | 720p, 1080i, 1080p, 4K | FXN | Not Yet |  |  |  | replace to 3rd report
|  | HDMI electrical | FXN | Not Yet |  |  |  | replace to 3rd report
| HDCP | HDCP | FXN | Not Yet |  |  |  | replace to 3rd report
| Ethernet | Ethernet 10 | FXN | Not Yet |  |  |  | amlogic's support
|  | Ethernet 100 | FXN | Finished
|  | Ethernet 1000 | FXN | Finished
Microphone | Mic test | Mic test | FXN | Not Yet |  | 2019-02-18 | 2019-03-07
Thermal pre-test | Thermal | Simulation | SKB | Finished |  | 2019-02-18 | 2019-03-07
|  | Surface | SKB | Finished
|  | Derating (Main Ics) | SKB | Finished |  |  |  | some ic 스펙이 없음
Noise | acoustic | Normal operation | SKB | Not Yet |  | Not Yet | Not Yet | DVT with T1
|  | Standby mode | SKB | Not Yet |  | Not Yet | Not Yet | DVT with T1
DC Jack | DC Jack | extraction test | SKB | Not Yet |  | Not Yet | Not Yet
IR | IR TEST | Angle, Distance | SKB |  |  |  | 2019-02-22
|  | 3 wavelength | SKB |  | see the Angle, Distance report |  | 2019-02-22
|  | reponse speed | SKB |  |  | Not Yet | Not Yet
Button | Button Test | Value up/down Switch | FXN | Not Yet |  |  |  | DVT with T1
LED | LED Test | LED Leakage | FXN | Not Yet |  |  |  | DVT with T1