## ALT
| Main Source |  |  |  | 2nd Source
Priority | PN |  | Manufacturer | MPN | Manufacturer | MPN | Compatibility | LT | Remark | ALT request RD verification items
1 | 039.00272.005 | IC | Fiti | FP6809-29CS3GTR | 3Peak | TPV809S-3TR | P2P | 126days | RD verification: Pass Target Reliability test: 11/24-12/8 Target control run: 12/13-12/17 | a. Reset timing test b. Power On/Off test
1 | 002.02152.005 | Eth PHY | Realtek | RTL8211F-CG | Motorcomm | YT8531C | P2P | 16wks (Actual schedule depends on PO release time) | (Need SW change) RD verification: Undergoing, target to finish by 11/19 Target Reliability test: 11/24-12/8 Target control run: 12/13-12/17 | a. RGMII timing test b. Throughput test c. Ethernet complaince test d. Aging test e. EMI test
2 | 001.01313.005 | BT | CYPRESS | CYW20704UA2KFFB1G | AMPAK | W511 | non P2P | 20-22wks | (SW/HW change-->BQB/KC certification renew /SKB BMT & QA) Biz issue not yet finalized, need ALT to decide Ampak or Movon | a. BT performance test b. BT RF test c. BT remocon test d. Aging test e. SW test f. BQB certification g. KC certification
[5 empty] | Movon | MD-BRC101 | non P2P | 36wks | non QVL Fii RD/sourcer under checking ALT suggested BT Chipset: RTL8761BTV SKB application: Smart3(Intek Digital) BT SIG Certification(Module level): RF completed Biz issue not yet finalized, need ALT to decide Ampak or Movon
3 | 033.00402.005 | E-fuse | TI | TPS25200DRVR | Toshiba | TCKE712BNL | non P2P |  | No sample, LT too long (HW change-->Certification change KC need ALT to check) | a. OVP/OCP test b. Voltage accuracy(Vout) c. ESD test d. Surge test e. Aging test
[5 empty] | GMT | G5288BQE1U | non P2P | 210days | Buyer suggest to keep main source TI
[5 empty] | Maxim | MAX17561AUD+T |  |  | Buyer suggest to keep main source TI
[5 empty] | Microsemi | LX8233 |  |  | non QVL
[5 empty] | Awinic | AQ32919 |  |  | non QVL
[5 empty] | Onsemi | NIS6150MT2TXG |  |  | Buyer suggest to keep main source TI