## Slide 1
50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
12/6 | 12/13 | 12/20 | 12/27 | 1/3’22 | 1/10 | 1/17 | 1/24 | 1/31 | 2/7 | 2/14 | 2/21 | 2/28 | 3/7 | 3/14 | 3/21 | 3/28 | 4/4 | 4/11 | 4/18 | 4/25 | 5/2 | 5/9 | 5/16 | 5/23 | 5/30 | 6/6 | 6/13
2nd source part (pin to pin)
2nd source part (non pin to pin)
PIN to PIN Part (ALT request 42pcs sample)
Main source: Eth PHY Realtek RTL8211F-CG  2nd source: Motorcomm YT8531C
Non PIN to PIN Part (ALT request 43pcs sample)
Main source:
BT CYPRESS CYW20704
2nd source: AMPAK W511
HWQA Reliability
Test
Factory control run
HW RD
verify
SW change
Circuit design+
Layout change
PCB Fabrication
1st
Sample
Build
HW RD verify
HWQA Reliability Test
RD
Receive 10pcs
sample
Ship
To
TW
SW change
2nd source part (non pin to pin)
Certification
Pre-test (EMI/EMC/RF)
Apply BQB/KC
Provide
BQB
report
to ALT
Factory control run
Circuit design+
Layout change
PCB Fabrication
2nd
Sample
Build
Ship
To
TW
Pre-test (EMI/EMC/RF)
CNY
Milestone Eagle
Target Risk Buy
BMT
BMT
Reset IC
RD release EC
RD release EC
Sample
Ship
To
KR
Sample
Ship
To
KR
Factory control run
PIN to PIN Part (ALT to check sample Qty to Korea??)
Main source: Fiti FFP6809-29CS3GTR 2nd source: 3Peak TPV809S-3TR