## Slide 1
44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
10/25 | 11/1 | 11/8 | 11/15 | 11/22 | 11/29 | 12/6 | 12/13 | 12/20 | 12/27 | 1/3’22 | 1/10 | 1/17 | 1/24 | 1/31 | 2/7 | 2/14 | 2/21 | 2/28 | 3/7 | 3/14 | 3/21 | 3/28 | 4/4 | 4/11 | 4/18 | 4/25 | 5/2
2nd source part (pin to pin)
2nd source part (non pin to pin)
PIN to PIN Part
Main source: Eth PHY Realtek RTL8211F-CG  2nd source: Motorcomm YT8531C
Non PIN to PIN Part
Main source:
E-FUSE TI TPS25200DRVR
2nd source: Toshiba TCKE712BNL
BT CYPRESS CYW20704
 2nd source: AMPAK W511A
HWQA Reliability
Test
Factory control run
HW RD
verify
SW change
Circuit design+
Layout change
PCB Fabrication
1st
Sample
Build
HW RD verify
HWQA Test
TBD
ALT not yet approve
RD
Receive 10pcs
sample
Ship
To
TW
SW change
2nd source part (non pin to pin)
Certification
Pre-test (EMI/EMC/RF)
Apply BQB
Provide
BQB
report
to ALT
Factory control run
Circuit design+
Layout change
PCB Fabrication
2nd
Sample
Build
Ship
To
TW
Pre-test (EMI/EMC/RF)
CNY
Milestone Eagle
Target Risk Buy
Send samples to ALT
for KC certification??
TBD
ALT not yet approve
BMT
BMT?
KC?