## HW
HW/SW | Item Name | Large category | Detail test | Spec | Result | TEST REPORT | Note | Start Date | Due Date
HW | eMMC waveform measurement | eMMC | Timing | FXN |  |  | Waive in DVT build since there is no layout changes in DVT build
|  |  | Data read, write, erase test | FXN |  |  |  | 2019-05-13 | 2019-05-22
|  |  | Aging test | FXN |  |  | Replace by HWQA report | 2019-05-08 | 2019-06-05
HW | I2C waveform measurement | I2C | Timing | FXN |  |  | Waive in DVT build since there is no layout changes in DVT build
HW | Power | On/Off sequence | ON sequence | FXN |  |  |  | 2019-05-13 | 2019-05-17
|  |  | OFF sequence | FXN |  |  |  | 2019-05-13 | 2019-05-17
HW |  | Accuracy/Ripple | Power Level (0, 25, 50) | FXN |  |  |  | 2019-05-13 | 2019-05-17
|  |  | Power ripple (0, 25, 50) | FXN |  |  |  | 2019-05-13 | 2019-05-17
HW |  | Power consumption | Normal mode | SKB |  |  | Will be re test using DVT | 2019-05-13 | 2019-05-17
|  |  | Active standby | SKB |  |  | Will be re test using DVT | 2019-05-13 | 2019-05-17
|  |  | Passive standby | SKB |  |  | Will be re test using DVT | 2019-05-13 | 2019-05-17
|  |  | Full load (with USB) | SKB |  |  | Will be re test using DVT | 2019-05-13 | 2019-05-17
HW | Clock | Crystal Frequency | Amlogic | FXN |  |  |  | 2019-05-07 | 2019-05-17
|  |  | ethernet PHY | FXN |  |  |  | 2019-05-07 | 2019-05-17
|  |  | BT | FXN |  |  |  | 2019-05-07 | 2019-05-17
HW | RF | RF TEST | BT | FXN |  |  |  | 2019-05-08 | 2019-05-15
HW | DDR related measurement | DDR | SSQ test | FXN |  |  | Will be test at DVT Validation period | TBC | TBC
|  |  | Data read, write, verify test | FXN |  |  |  | 2019-05-13 | 2019-05-17
|  |  | SI simulation | FXN |  |  | Waive in DVT build
|  |  | Aging test | FXN |  |  | Replace by HWQA report | 2019-05-08 | 2019-06-05
HW | DCDC Power verification | DCDC | Power effciency (25℃) | FXN |  |  | wrong test at EVT. Will be test using DVT | 2019-05-07 | 2019-05-15
|  |  | Power loss (25℃) | FXN |  |  | wrong test at EVT. Will be test using DVT | 2019-05-07 | 2019-05-15
|  |  | Load Regulation (25℃) | FXN |  |  | wrong test at EVT. Will be test using DVT | 2019-05-07 | 2019-05-15
|  |  | Bode plot (Phase, Margin) | FXN |  |  | wrong test at EVT. Will be test using DVT | 2019-05-07 | 2019-05-15
HW | BT RCU sensitivity test | BT | BT RCU test | FXN |  |  | this report can be replaced RF TEST | 2019-05-13 | 2019-05-17
HW | EMI/EMS | EMI | Radiated Emission | FXN |  |  | Replace to KC certification | 2019-05-08 | 2019-06-14
|  |  | Conducted Emission | FXN |  |  | Replace to KC certification | 2019-05-08 | 2019-06-14
|  | EMS | Radiated Immunity | FXN |  |  | Replace to KC certification | 2019-05-08 | 2019-06-14
|  |  | Conducted Immunity | FXN |  |  | Replace to KC certification | 2019-05-08 | 2019-06-14
|  |  | ESD | FXN |  |  | Replace to KC certification | 2019-05-08 | 2019-06-14
|  |  | Surge | FXN |  |  | Replace to KC certification | 2019-05-08 | 2019-06-14
HW | HDMI/USB/Ethernet SI test | USB | USB2.0 (Low speed) | FXN |  |  |  | 2019-05-13 | 2019-05-24
|  |  | USB2.0 (Full speed) | FXN |  |  |  | 2019-05-13 | 2019-05-24
|  |  | USB2.0 (High speed) | FXN |  |  |  | 2019-05-13 | 2019-05-24
|  |  | USB3.0 (RX) | FXN |  |  | Verified in AML SH Lab. | 2019-05-20 | 2019-05-24
|  |  | USB3.0 (TX) | FXN |  |  | Verified in AML SH Lab. | 2019-05-20 | 2019-05-24
|  |  | Drop test | FXN |  |  | Waive in DVT build since there is no layout changes in DVT build
|  |  | Port overload test | FXN |  |  | Waive in DVT build since there is no layout changes in DVT build
|  | HDMI | 720p, 1080i, 1080p, 4K | FXN |  |  | 3RD TEST using DVT | 2019-05-13 | 2019-05-24
|  |  | HDMI electrical | FXN |  |  | 3RD TEST using DVT | TBC | TBC
|  | HDCP | HDCP | FXN |  |  | 3RD TEST using DVT | TBC | TBC
|  | Ethernet | Ethernet 10 | FXN |  |  | No need test, AML don't support this test
|  |  | Ethernet 100 | FXN |  |  |  | 2019-05-13 | 2019-05-24
|  |  | Ethernet 1000 | FXN |  |  |  | 2019-05-13 | 2019-05-24
|  |  | RGMII | FXN |  |  | Waive in DVT build since there is no layout changes in DVT build
|  |  | LED status (Link Activity) | FXN |  |  | Waive in DVT build since there is no layout changes in DVT build
|  |  | Auto Negotiation test | FXN |  |  | Waive in DVT build since there is no layout changes in DVT build
|  |  | CRC Error | FXN |  |  |  | 2019-05-07 | 2019-05-15
HW | Microphone | Mic test | Mic test | FXN |  |  |  | 2019-05-13 | 2019-05-24
HW | Thermal pre-test | Thermal | Simulation | SKB |  |  | Waive in DVT build
|  |  | Surface | SKB |  |  | Replace by HWQA report | 2019-05-08 | 2019-06-05
|  |  | Derating (Main Ics) | SKB |  |  | Replace by HWQA report | 2019-05-08 | 2019-06-05
| Noise | acoustic | Normal operation | SKB |  |  | DVT with T1 housing | 2019-05-13 | 2019-05-17
|  |  | Standby mode | SKB |  |  | DVT with T1 housing | 2019-05-13 | 2019-05-17
| DC Jack | DC Jack | extraction test | SKB |  |  | will be test and update | 2019-05-23 | 2019-05-29
| IR | IR TEST | Angle, Distance | SKB | PASS |  |  | 2019-05-09 | 2019-05-13
|  |  | 3 wavelength | SKB |  |  |  | 2019-05-09 | 2019-05-13
|  |  | response speed | SKB |  |  |  | 2019-05-09 | 2019-05-13
| Button | Button Test | ch up/down Switch | FXN |  |  | DVT with T1 | 2019-05-13 | 2019-05-17
| LED | LED Test | LED Leakage | FXN |  |  | DVT with T1 | 2019-05-20 | 2019-05-24
v

## reliability
NO | Test Item | SKB SPEC | Comment
1 | Vibration | Acceleration: 10mm /4.4G/2.5G, 진동폭 : 10mm | 1) 5~125Hz/0.25mm : X/Y/Z each 30 minutes
|  | Sweep range: 5~15Hz/10mm P-P,16~30Hz/4.4G, 30~300Hz/2.5G | 2) 5~33Hz/1G : X/Y/Z each 30 minutes
3) 67~133Hz/3G : X/Y/Z each 30 minutes
|  | Sweep rate: 0.25 octave/min, test time :X,Y,Z each 1 hour | 4) Sweep rate: 0.5 octave/min
|  | 1. No functional failures both during and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such aspeeling, discoloration, etc. | 5) Un-Packing state (SET only)
2 | drop | Height for fall test :1.5m, fall plate : steel floor or concrete floor (with Gift box packaging) | -
|  | drop : 1 corner ,3 edges ,6 faces each one time | -
|  | 1. No functional failures both during and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such aspeeling, discoloration, etc. | -
3 | Chassis Static Load | 1. Applied position : TOP on the enclosure 2) Weight and time : 5Kg/ diameter 9mm area/apply 30 seconds, 3) There is no damage of Mechanical material (for examples Cover's crack, breakdown | -
4 | salt fog | salt : 5%(PH 6.6~7.2), test time: 48 hr | -
|  | sprayed amount : 0.6~.30 ml/hr, temperature: 35℃ | -
|  | No physical defect, corrosion and functional failure after this test. | -
5 | AbrasionResistance ofLabel Test | 800times using abrasion machine. There in no abrasion of printing character and number
criteria : Load 1 kgf, alcohol.
6 | Logo/PrintingAbrasion Test | 2000times using abrasion machine. There is no abrasion of case printing and no changible color/
criteria : Load 1 kgf, alcohol.

## SW
HW/SW | Item Name | Start Date | Due Date | Remark
SW | SetupWizard |  | 2019-03-15 | New requirement
SW | Front Panel Keypad(CH+/CH-) |  | 2019-02-22
SW | HAL library for Controlling Front LED |  | 2019-02-22 | New requirement
SW | HAL library for Controlling Mic. |  | 2019-02-27
SW | HDCP on/off and version setup (for debug) |  | 2019-02-22 | New requirement
SW | Auto Reset Guide |  | 2019-02-22 | New requirement
SW | Console Enable |  | 2019-02-22 | New requirement
SW | Support Start Recover Mode by Front Panel Key (uboot) |  | 2019-02-22 | New requirement
SW | RCU Info Key |  | 2019-02-22 | New requirement
SW | BT RCU Key Mapping |  | 2019-02-22
SW | BT RCU Voice Transmission |  | 2 weeks after UEI release SDK
SW | Factory Test APP |  | 2019-03-15
SW | Aging Test Tool |  | TBD | New requirement