## HW
HW/SW | Item Name | Large category | Detail test | Spec | Result | TEST REPORT | Start Date | Due Date | Note
HW | eMMC waveform measurement | eMMC | Timing | FXN | PASS | Will Upload on the Mantis | 2019-02-14 | 2019-02-19
|  |  | Data read, write, erase test | FXN | PASS
|  |  | Aging test | FXN | - |  | DVT Stage |  | replace to reliability test
HW | I2C waveform measurement | I2C | Timing | FXN | PASS |  | 2019-02-13 | 2019-02-19
HW | Power | On/Off sequence | ON sequence | FXN | PASS |  | 2019-02-13 | 2019-02-22
|  |  | OFF sequence | FXN | PASS
HW |  | Accuracy/Ripple | Power Level (0, 25, 50) | FXN | PASS(25℃ ) |  | 2019-02-14 | 2019-02-22 | Have finished 25deg. Condition
|  |  | Power ripple (0, 25, 50) | FXN | PASS(25℃ ) |  |  |  | 0, 50 Temp will be by 3/13
HW |  | Power consumption | Normal mode | SKB | PASS |  | 2019-02-18 | 2019-03-02
|  |  | Active standby | SKB | PASS
|  |  | Passive standby | SKB | PASS
|  |  | Full load (with USB) | SKB | PASS
HW | Clock | Crystal Frequency | Amlogic | FXN | PASS |  | 2019-02-12 | 2019-02-27 | Amlogic 24M
|  |  | ethernet PHY | FXN | PASS |  |  |  | PHY 25M
|  |  | BT | FXN | PASS |  |  |  | BT 20M
HW | RF | RF TEST | BT | FXN | PASS |  | 2019-02-12 | 2019-03-08
HW | DDR related measurement | DDR | SSQ test | FXN | TBD |  | 2019-02-12 | 2019-03-08 | not confirm schedule yet by samsung
|  |  | Data read, write, verify test | FXN | TBD
|  |  | SI simulation | FXN | TBD
|  |  | Aging test | FXN | - |  | DVT Stage |  | replace to reliability test
HW | DCDC Power verification | DCDC | Power effciency (25℃) | FXN | Fail |  | 2019-02-12 | 2019-03-07 | Apply Test point on DVT PCBA
|  |  | Power loss (25℃) | FXN | Fail
|  |  | Load Regulation (25℃) | FXN | PASS
|  |  | Bode plot (Phase, Margin) | FXN | PASS
HW | BT RCU sensitivity test | BT | BT RCU test | FXN | PASS |  | 2019-03-04 | 2019-03-08
HW | EMI/EMS | EMI | Radiated Emission | FXN | PASS |  | 2019-02-14 | 2019-03-22 | Pre-test @ 3rd party open site 10M chamber
|  |  | Conducted Emission | FXN | PASS
|  | EMS | Radiated Immunity | FXN | TBD |  |  |  | Need more Adaptor sample to pull in test schedule
|  |  | Conducted Immunity | FXN | TBD
|  |  | ESD | FXN | TBD
|  |  | Surge | FXN | TBD
HW | HDMI/USB/Ethernet SI test | USB | USB2.0 (Low speed) | FXN | TBD |  | 2019-02-18 | 2019-03-15 | Need Test command (SOC)
|  |  | USB2.0 (Full speed) | FXN | PASS |  | 2019-02-18 | 2019-03-07 | FXN internal report
|  |  | USB2.0 (High speed) | FXN | PASS |  | 2019-02-18 | 2019-03-07 | FXN internal report
|  |  | USB3.0 (RX) | FXN | PASS |  | 2019-02-18 | 2019-03-07
|  |  | USB3.0 (TX) | FXN | PASS |  | 2019-02-18 | 2019-03-07 | Amlogic test report
|  |  | Drop test | FXN | TBD |  | 2019-02-18 | 2019-03-13
|  |  | Port overload test | FXN | TBD |  | 2019-02-18 | 2019-03-13
|  | HDMI | 720p, 1080i, 1080p, 4K | FXN | PASS |  | 2019-02-18 | 2019-03-07 | FXN internal report
|  |  | HDMI electrical | FXN | - |  | DVT Stage |  | Replace to 3rd party report
|  | HDCP | HDCP | FXN | - |  | DVT Stage |  | Replace to 3rd party report
|  | Ethernet | Ethernet 10 | FXN | TBD |  | 2019-02-18 | 2019-03-15 | Amlogic S905X2 can't generate test pattern (~ 3/15)
|  |  | Ethernet 100 | FXN | PASS |  | 2019-02-18 | 2019-03-07 | FXN internal report
|  |  | Ethernet 1000 | FXN | PASS |  | 2019-02-18 | 2019-03-07 | FXN internal report
HW | Microphone | Mic test | Mic test | FXN | PASS |  | 2019-02-18 | 2019-03-08
HW | Thermal pre-test | Thermal | Simulation | SKB | PASS |  | 2019-02-18 | 2019-03-07
|  |  | Surface | SKB | Fail
|  |  | Derating (Main Ics) | FXN | PASS
| Noise | acoustic | Normal operation | SKB | - |  | DVT Stage
|  |  | Standby mode | SKB | - |  | DVT Stage
| DC Jack | DC Jack | extraction test | SKB | TBD |  |  | 2019-03-13 | ME test
| IR | IR TEST | Angle, Distance | SKB | PASS |  |  | 2019-02-22
|  |  | 3 wavelength | SKB | PASS |  |  | 2019-02-22
|  |  | reponse speed | SKB | TBD |  |  | 2019-03-15
| Button | Button Test | Value up/down Switch | FXN | - |  | DVT Stage |  | DVT with T1
| LED | LED Test | LED Leakage | FXN | - |  | DVT Stage |  | DVT with T1