## HW
HW/SW | Item Name | Large category | Detail test | Spec | Result | TEST REPORT | Note | Start Date | Due Date
HW | POWER | Accuracy/Ripple | Power Level (0, 25, 50) | FXN | PASS | update
|  |  | Power ripple (0, 25, 50) | FXN | PASS | update
HW |  | Power consumption | Normal mode | SKB | PASS | update | Plz provide the spec Passive standby puts "TBD" is it required?
|  |  | Active standby | SKB | PASS | update
|  |  | Passive standby | SKB | TBD | update
|  |  | Full load (with USB) | SKB | PASS | update
| DC Jack | DC Jack | extraction test | SKB | PASS | update
v

## reliability
HW/SW | Item Name | Large category | Detail test | Spec | Result | TEST REPORT | Note | Start Date | Due Date
HW | FII | climate | Cold start | FII | pass | update
|  |  | Hot start | FII | pass | update
HW |  |  | Continuation of temperature cycle | FII | pass | update
|  |  | Temperature and humidity cycles test | FII | pass | update
|  |  | High Temperature & Humidity Test (Op) | FII | pass | update
|  |  | Operational Temperature Range | SKB | pass | update | Plz provide the spec
HW |  |  | Thermal Shock | FII | pass | update
|  |  | Power on /off Test with Temperature | FII | pass | update
|  |  | Quicky Power on/off Test | FII | pass | update
HW |  | Mechanical test | Vibration test random (Op) | FII | pass | update | Spec follows FII or SKB (below table also lists this item)
|  |  | Shock test (Op) | FII | pass | update
|  |  | Power jack plug test | FII | pass | update
|  | Package test (1 carton) | Temperature and humidity test | FII | pass | update | I didn't receive the carton but the tiny box of ADP
|  |  | Static Compression test | FII | pass | update
|  |  | Random Vibration test | FII | pass | update
|  |  | Package drop test | FII | pass | update
HW |  |  | Fix displacement test | FII | pass | update
|  | SKB's criteria | Below items should all be included as well?
v