## HW
HW/SW | Item Name | Large category | Detail test | Spec | Result | TEST REPORT | Note
HW | eMMC waveform measurement | eMMC | Timing | FXN | PASS | Complete
|  |  | Data read, write, erase test | FXN | Not Yet |  | will be test and update until 3W ARP
|  |  | Aging test | FXN | Not Yet |  | will be test and update until 3W ARP
HW | I2C waveform measurement | I2C | Timing | FXN | PASS | Complete
HW | Power | On/Off sequence | ON sequence | FXN | PASS | Complete
|  |  | OFF sequence | FXN | PASS | Complete
HW |  | Accuracy/Ripple | Power Level (0, 25, 50) | FXN | PASS | Complete
|  |  | Power ripple (0, 25, 50) | FXN | PASS | Complete
HW |  | Power consumption | Normal mode | SKB | FAIL | Complete | Will be re test using DVT
|  |  | Active standby | SKB | PASS | Complete | Will be re test using DVT
|  |  | Passive standby | SKB | PASS | Complete | Will be re test using DVT
|  |  | Full load (with USB) | SKB | PASS | Complete | Will be re test using DVT
HW | Clock | Crystal Frequency | Amlogic | FXN | PASS | Complete
|  |  | ethernet PHY | FXN | PASS | Complete
|  |  | BT | FXN | PASS | Complete
HW | RF | RF TEST | BT | FXN | PASS | Complete
HW | DDR related measurement | DDR | SSQ test | FXN | Not Yet |  | Will be Replace to other test. Report
|  |  | Data read, write, verify test | FXN | Not Yet |  | will be test and update until 3W ARP
|  |  | SI simulation | FXN | PASS | Complete
|  |  | Aging test | FXN | Not Yet |  | will be test and update until 3W ARP
HW | DCDC Power verification | DCDC | Power effciency (25℃) | FXN | Fail |  | wrong test at EVT. Will be test using DVT
|  |  | Power loss (25℃) | FXN | Fail |  | wrong test at EVT. Will be test using DVT
|  |  | Load Regulation (25℃) | FXN | Fail |  | wrong test at EVT. Will be test using DVT
|  |  | Bode plot (Phase, Margin) | FXN | Fail |  | wrong test at EVT. Will be test using DVT
HW | BT RCU sensitivity test | BT | BT RCU test | FXN | PASS | Complete | this report can be replaced RF TEST
HW | EMI/EMS | EMI | Radiated Emission | FXN | PASS | Complete
|  |  | Conducted Emission | FXN | PASS | Complete
|  | EMS | Radiated Immunity | FXN | PASS | Complete
|  |  | Conducted Immunity | FXN | PASS | Complete
|  |  | ESD | FXN | PASS | Complete
|  |  | Surge | FXN | PASS | Complete
HW | HDMI/USB/Ethernet SI test | USB | USB2.0 (Low speed) | FXN | FAIL |  | conditional pass. Cannot debugging because of No Amlogic support
|  |  | USB2.0 (Full speed) | FXN | PASS
|  |  | USB2.0 (High speed) | FXN | PASS
|  |  | USB3.0 (RX) | FXN | Not Yet |  | cannot test because of No amlogic support
|  |  | USB3.0 (TX) | FXN | PASS | Complete
|  |  | Drop test | FXN | PASS | Complete
|  |  | Port overload test | FXN | PASS | Complete
|  | HDMI | 720p, 1080i, 1080p, 4K | FXN | PASS | not complete | 1080i will be test at 3W APR. 3RD TEST using DVT
|  |  | HDMI electrical | FXN | Not Yet |  | 3RD TEST using DVT
|  | HDCP | HDCP | FXN | Not Yet |  | 3RD TEST using DVT
|  | Ethernet | Ethernet 10 | FXN | FAIL |  | Cannot debugging because of No Amlogic support
|  |  | Ethernet 100 | FXN | PASS | Complete
|  |  | Ethernet 1000 | FXN | PASS | Complete
HW | Microphone | Mic test | Mic test | FXN | PASS | Complete
HW | Thermal pre-test | Thermal | Simulation | SKB | PASS | Complete
|  |  | Surface | SKB | PASS | Complete
|  |  | Derating (Main Ics) | SKB | PASS | Complete
| Noise | acoustic | Normal operation | SKB | Not Yet |  | DVT with T1
|  |  | Standby mode | SKB | Not Yet |  | DVT with T1
| DC Jack | DC Jack | extraction test | SKB | FAIL |  | will be test and update until 3W ARP
| IR | IR TEST | Angle, Distance | SKB | PASS | Complete
|  |  | 3 wavelength | SKB | PASS | Complete
|  |  | response speed | SKB | PASS | Complete
| Button | Button Test | ch up/down Switch | FXN | Not Yet |  | DVT with T1
| LED | LED Test | LED Leakage | FXN | Not Yet |  | DVT with T1

## SW
HW/SW | Item Name | Start Date | Due Date | Remark
SW | SetupWizard |  | 2019-03-15 | New requirement
SW | Front Panel Keypad(CH+/CH-) |  | 2019-02-22
SW | HAL library for Controlling Front LED |  | 2019-02-22 | New requirement
SW | HAL library for Controlling Mic. |  | 2019-02-27
SW | HDCP on/off and version setup (for debug) |  | 2019-02-22 | New requirement
SW | Auto Reset Guide |  | 2019-02-22 | New requirement
SW | Console Enable |  | 2019-02-22 | New requirement
SW | Support Start Recover Mode by Front Panel Key (uboot) |  | 2019-02-22 | New requirement
SW | RCU Info Key |  | 2019-02-22 | New requirement
SW | BT RCU Key Mapping |  | 2019-02-22
SW | BT RCU Voice Transmission |  | 2 weeks after UEI release SDK
SW | Factory Test APP |  | 2019-03-15
SW | Aging Test Tool |  | TBD | New requirement