## HW
HW/SW | Item Name | Large category | Detail test | Spec | Result | TEST REPORT | Note
HW | eMMC waveform measurement | eMMC | Timing | FXN | PASS | Complete
|  |  | Data read, write, erase test | FXN | PASS | Complete | will be test and update until 4W APR.
|  |  | Aging test | FXN | PASS | Complete
HW | I2C waveform measurement | I2C | Timing | FXN | PASS | Complete
HW | Power | On/Off sequence | ON sequence | FXN | PASS | Complete
|  |  | OFF sequence | FXN | PASS | Complete
HW |  | Accuracy/Ripple | Power Level (0, 25, 50) | FXN | PASS | Complete
|  |  | Power ripple (0, 25, 50) | FXN | PASS | Complete
HW |  | Power consumption | Normal mode | SKB | FAIL | Complete | Will be re test using DVT
|  |  | Active standby | SKB | PASS | Complete | Will be re test using DVT
|  |  | Passive standby | SKB | PASS | Complete | Will be re test using DVT
|  |  | Full load (with USB) | SKB | PASS | Complete | Will be re test using DVT
HW | Clock | Crystal Frequency | Amlogic | FXN | PASS | Complete
|  |  | ethernet PHY | FXN | PASS | Complete
|  |  | BT | FXN | PASS | Complete
HW | RF | RF TEST | BT | FXN | PASS | Complete
HW | DDR related measurement | DDR | SSQ test | FXN | Not Yet |  | Will be test at DVT Validation period
|  |  | Data read, write, verify test | FXN | PASS | Complete
|  |  | SI simulation | FXN | PASS | Complete
|  |  | Aging test | FXN | PASS | Complete
HW | DCDC Power verification | DCDC | Power effciency (25℃) | FXN | Fail |  | wrong test at EVT. Will be test using DVT
|  |  | Power loss (25℃) | FXN | Fail |  | wrong test at EVT. Will be test using DVT
|  |  | Load Regulation (25℃) | FXN | Fail |  | wrong test at EVT. Will be test using DVT
|  |  | Bode plot (Phase, Margin) | FXN | Fail |  | wrong test at EVT. Will be test using DVT
HW | BT RCU sensitivity test | BT | BT RCU test | FXN | PASS | Complete | this report can be replaced RF TEST
HW | EMI/EMS | EMI | Radiated Emission | FXN | PASS | Complete
|  |  | Conducted Emission | FXN | PASS | Complete
|  | EMS | Radiated Immunity | FXN | PASS | Complete
|  |  | Conducted Immunity | FXN | PASS | Complete
|  |  | ESD | FXN | PASS | Complete
|  |  | Surge | FXN | PASS | Complete
HW | HDMI/USB/Ethernet SI test | USB | USB2.0 (Low speed) | FXN | PASS | Complete | some test case is conditional pass. But USB lab confirm that conditional pass also pass.
|  |  | USB2.0 (Full speed) | FXN | PASS
|  |  | USB2.0 (High speed) | FXN | PASS
|  |  | USB3.0 (RX) | FXN | Not Yet |  | Amlogic have provided test method to us. We will arrange the test at HC SI team and will update status to you once there is any progress.
|  |  | USB3.0 (TX) | FXN | PASS | Complete
|  |  | Drop test | FXN | PASS | Complete
|  |  | Port overload test | FXN | PASS | Complete
|  | HDMI | 720p, 1080i, 1080p, 4K | FXN | PASS | Complete | 3RD TEST using DVT
|  |  | HDMI electrical | FXN | Not Yet |  | 3RD TEST using DVT
|  | HDCP | HDCP | FXN | Not Yet |  | 3RD TEST using DVT
|  | Ethernet | Ethernet 10 | FXN | Not Yet | Skip | Cannot debugging because of No Amlogic support
|  |  | Ethernet 100 | FXN | PASS | Complete
|  |  | Ethernet 1000 | FXN | PASS | Complete
|  |  | RGMII | FXN | PASS | Complete
|  |  | LED status (Link Activity) | FXN | PASS | Complete
|  |  | Auto Negotiation test | FXN | PASS | Complete
|  |  | CRC Error | FXN | PASS | Complete
HW | Microphone | Mic test | Mic test | FXN | PASS | Complete
HW | Thermal pre-test | Thermal | Simulation | SKB | PASS | Complete
|  |  | Surface | SKB | PASS | Complete
|  |  | Derating (Main Ics) | SKB | PASS | Complete
| Noise | acoustic | Normal operation | SKB | Not Yet |  | DVT with T1
|  |  | Standby mode | SKB | Not Yet |  | DVT with T1
| DC Jack | DC Jack | extraction test | SKB | FAIL |  | will be test and update
| IR | IR TEST | Angle, Distance | SKB | PASS | Complete
|  |  | 3 wavelength | SKB | PASS | Complete
|  |  | response speed | SKB | PASS | Complete
| Button | Button Test | ch up/down Switch | FXN | Not Yet |  | DVT with T1
| LED | LED Test | LED Leakage | FXN | Not Yet |  | DVT with T1

## reliability
NO | Test Item | SKB SPEC | Comment
1 | Vibration | Acceleration: 10mm /4.4G/2.5G, 진동폭 : 10mm | 1) 5~125Hz/0.25mm : X/Y/Z each 30 minutes
|  | Sweep range: 5~15Hz/10mm P-P,16~30Hz/4.4G, 30~300Hz/2.5G | 2) 5~33Hz/1G : X/Y/Z each 30 minutes
3) 67~133Hz/3G : X/Y/Z each 30 minutes
|  | Sweep rate: 0.25 octave/min, test time :X,Y,Z each 1 hour | 4) Sweep rate: 0.5 octave/min
|  | 1. No functional failures both during and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such aspeeling, discoloration, etc. | 5) Un-Packing state (SET only)
2 | drop | Height for fall test :1.5m, fall plate : steel floor or concrete floor (with Gift box packaging) | -
|  | drop : 1 corner ,3 edges ,6 faces each one time | -
|  | 1. No functional failures both during and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such aspeeling, discoloration, etc. | -
3 | Chassis Static Load | 1. Applied position : TOP on the enclosure 2) Weight and time : 5Kg/ diameter 9mm area/apply 30 seconds, 3) There is no damage of Mechanical material (for examples Cover's crack, breakdown | -
4 | salt fog | salt : 5%(PH 6.6~7.2), test time: 48 hr | -
|  | sprayed amount : 0.6~.30 ml/hr, temperature: 35℃ | -
|  | No physical defect, corrosion and functional failure after this test. | -
5 | AbrasionResistance ofLabel Test | 800times using abrasion machine. There in no abrasion of printing character and number
criteria : Load 1 kgf, alcohol.
6 | Logo/PrintingAbrasion Test | 2000times using abrasion machine. There is no abrasion of case printing and no changible color/
criteria : Load 1 kgf, alcohol.

## SW
HW/SW | Item Name | Start Date | Due Date | Remark
SW | SetupWizard |  | 2019-03-15 | New requirement
SW | Front Panel Keypad(CH+/CH-) |  | 2019-02-22
SW | HAL library for Controlling Front LED |  | 2019-02-22 | New requirement
SW | HAL library for Controlling Mic. |  | 2019-02-27
SW | HDCP on/off and version setup (for debug) |  | 2019-02-22 | New requirement
SW | Auto Reset Guide |  | 2019-02-22 | New requirement
SW | Console Enable |  | 2019-02-22 | New requirement
SW | Support Start Recover Mode by Front Panel Key (uboot) |  | 2019-02-22 | New requirement
SW | RCU Info Key |  | 2019-02-22 | New requirement
SW | BT RCU Key Mapping |  | 2019-02-22
SW | BT RCU Voice Transmission |  | 2 weeks after UEI release SDK
SW | Factory Test APP |  | 2019-03-15
SW | Aging Test Tool |  | TBD | New requirement