## Eth PHY
Eth PHY Motorcomm | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11
| WK41 | WK42 | WK43 | WK44 | WK45(Nov) | WK46 | WK47 | WK48 | WK49(Dec) | WK50 | WK51
HW | Production | Ship to TW | Receive rest 130pcs sample |  |  | RD Verify | HWQA Test | HWQA Test | HWQA Test | Factory Control Run | RD issue EC
SW | WK3: SW Change; WK4: SW Change; WK5: SW Change; WK6: ALT Run BMT; WK7: ALT Run BMT; WK8: ALT Run BMT
Note on B3: Sample Ship to VN before 10/1 *skip board level test
Note on D4: Vendor not yet provide driver; will try our best to pull in if possible

## EFUSE
E-Fuse Toshiba | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13
HW | Layout change (Circuit Design) | Layout change | PCB Fabrication | PCB Fabrication | PCB Fabrication | Factory Production | Ship to TW | RD Verify | HWQA Test | HWQA Test | HWQA Test | Factory Control Run | RD issue EC