## Schedule
T99X171.00 Test Schedule
No | Test Items | Qty' | Location | L/T | Sataus | 2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | 2019-05-17 | 2019-05-18 | 2019-05-19 | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | 2019-06-01 | 2019-06-02 | 2019-06-03 | 2019-06-04 | 2019-06-05 | 2019-06-06 | 2019-06-07 | 2019-06-08 | 2019-06-09 | 2019-06-10 | 2019-06-11
1 | Thermal Measurement Test | 1 | HC | 3 | PASS
2 | Cold start | 2 | HC | 2 | PASS | bar: 2019-05-13 to 2019-05-14
3 | Hot start | re-use item 2 | HC | 2 | PASS | bar: 2019-05-15 to 2019-05-16
4 | Continuation of temp. cycle | re-use item 3 | HC | 3 | ON-GOING | bar: 2019-05-17 to 2019-05-19
5 | Temp. and humidity cycles test | 2 | HC | 3 | bar: 2019-05-20 to 2019-05-22
6 | High Temp. & Humidity Test (Op) | re-use item 5 | HC | 3 | bar: 2019-05-23 to 2019-05-25
7 | Operational Temp. Range | 2 | HC | 6 | bar: 2019-05-19 to 2019-05-24
8 | Thermal Shock | re-use item 5 | HC | 1 | ON-GOING | bar: 2019-05-16 to 2019-05-17
9 | EDVT test | re-use item 1 | HC | 5 | bar: 2019-05-25 to 2019-05-29
10 | Power on /off Test with Temp. | re-use item 8 | HC | 5 | bar: 2019-05-26 to 2019-05-30
11 | Quicky Power on/off Test | 20 | HC | 4 | PASS | bar: 2019-05-13 to 2019-05-16
12 | Highly Accelerated Life Test (HALT) | 5 | TMC | 5 | bar: 2019-05-19 to 2019-05-23
13 | MTBF Prediction | 0 | HC | 3 | bar: 2019-05-21 to 2019-05-23
14 | MTBF Demonstration | re-use item 11 | HC | 26 | ON-GOING | bar: 2019-05-17 to 2019-06-11
No | Test Items | Qty' | Location | L/T | Sataus | 2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | 2019-05-17 | 2019-05-18 | 2019-05-19 | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | 2019-06-01 | 2019-06-02 | 2019-06-03 | 2019-06-04 | 2019-06-05 | 2019-06-06 | 2019-06-07 | 2019-06-08 | 2019-06-09 | 2019-06-10 | 2019-06-11
15 | Vibration Test Random (Op) | 2 | HC | 1 | PASS | bar: 2019-05-14
16 | Shock test (Op) | re-use item 15 | HC | 1 | bar: 2019-05-15
17 | Drop test | re-use item 18 | HC | 1 | bar: 2019-05-24
18 | Remote Control Display Angle | 2 | HC | 1 | bar: 2019-05-20
19 | Abrasion Resistance of Label Test | 2 housing | HC | 2 | bar: 2019-05-24 to 2019-05-25
20 | Logo/Printing Abrasion Test | 2 housing | HC | 1 | bar: 2019-05-26
21 | Mirco USB Plug Test | 2 | HC | 3 | ON-GOING | bar: 2019-05-17 to 2019-05-19
22 | HDMI Plug Test | re-use item 21 | HC | 3 | bar: 2019-05-20 to 2019-05-22
23 | RJ-45 Plug Test | re-use item 22 | HC | 3 | bar: 2019-05-23 to 2019-05-25
24 | Power Jack Plug Test | re-use item 23 | HC | 3 | bar: 2019-05-26 to 2019-05-28
25 | Salt Fog | 2 | HC | 4 | ON-GOING | bar: 2019-05-17 to 2019-05-20

## Reliability Test
T99X171.00 Reliability Test Plan v1.0
Climatic test plan
No. | Item | Test Condition | Pass Criteria | Q'ty | Day | Reference Standard | Test cost (US) | Test Location
1 | Thermal Measurement Test | Power on, Operation 8 hours at 25℃/50℃ and thermal record | 1. Tj < Spec. 2. Housing top < △t15 ℃ 3. Housing bottom < △t15 ℃ 4. Cap's MTBF > 43,800 hrs | 1 | 3 | IEC 60068-2-1 IEC 60068-2-2 | 1500 | HC
2 | Cold start | 1. Power off, and store at -5℃ for 24 hours then power on to check function. 2. Repeat test 15 times | 1. No functional failures both during and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 2 | 2 | IEC 60068-2-1 | 300 | HC
3 | Hot start | 1. Power off, and store at 50℃ for 24 hours then power on to check function. 2. Repeat test 15 times |  | 2 | 2 | IEC 60068-2-2 | 300 | HC
4 | Continuation of temperature cycle | 1. Operating in high and low temperature environment at 50/-5℃ 2. 50°C with 1°C/min, Dwell 3 hrs ; -5°C with 1°C/min, Dwell 3 Hrs, total 72 hrs | 1. No functional failures both during and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 2 | 3 | IEC 60068-2-30 | 350 | HC
5 | Temperature and humidity cycles test | Power off, storage in temperature and humidity environment at 70 / -20℃( Dwell 12 hrs )and 90 %R.H. Total: 72 hrs | 1. No functional failures both before and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 2 | 3 | IEC 60068-2-30 | 350 | HC
6 | High Temperature & Humidity Test (Op) | Power on, Operation, Ta = 50℃ ,Humi.= 90%R.H. for 72 hours | 1. No functional failures both during and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 2 | 3 | IEC 60068-2-78 | 350 | HC
7 | Operational Temperature Range | Power on 1. 25℃ for 1 hr 2. 25℃ to -5℃ for 2 hrs 3. -5℃ for 13 hrs 4. -5℃ to 25℃ for 2 hrs 5. 25℃/65% for 1 hr 6. 25℃/65% to 50℃/65% for 2 hrs 7. 50℃/90% for 13 hrs 8. 50℃/90% to 25℃ for 2 hrs Repeat 1~8 for 2 cycles 9. 25℃/60% for 48 hrs Total for 120 hrs Note: 1. Input condition 1) voltage : 220v 2) Source : SKB's Live channel in their network 2. Test sample quantity : 6ea 1) DUT1, 2 : MultiView 2) DUT3, 4 : VOD 3) DUT5, 6 : UHD (Umax) | 1. No functional failures both before and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 6 | 6 | Customer's Spec. | 700 | HC
8 | Thermal Shock | Power off , non-OP, Ta= -20C (30min) ~ 70C (30min) 15 cycles, Transfer time : 5 min | 1. No functional failures both before and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 2 | 1 | MIL-810 | 200 | HC
9 | EDVT test | Verify the hardware design by exposure of the product to wider temperature, voltage and frequency margining. Test Temp. at -5/50 °C | 1. No functional failures both during and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 1 | 5 | Foxconn's Spec. | 600 | HC
10 | Power on /off Test with Temperature | 1.Power on: 50 sec; off 10 sec. (follow product characteristic) 2..Vin: follow customer's spec or MRS, 2,500 cycle, total 5,000 3. Test Temp at -5/50 ℃ |  | 2 | 5 | Foxconn's Spec. | 600 | HC
11 | Quicky Power on/off Test | 1.Power on: 120 sec; off 3 sec. (follow product characteristic) 2..Vin: follow customer's spec or MRS, for 100 cycles 3. Test Temp at 25 ℃ (Room Temp.) | No functional failures both during and after the test | 20 | 4 | Foxconn's Spec. | 300 | HC
12 | Highly Accelerated Life Test（HALT） | 1. Thermal step stress (Cold) 2. Thermal step stress (Hot) 3. Fast thermal transition 4. Vibration step stress 5. Combined thermal cycling | To find the product limit | 5 | 5 | Foxconn's Spec. | 3500 | TMC
13 | MTBF Prediction | Based on Telecordia SR-332 Issue-III Prediction software: Relax program | NA | 0 | 3 | Telecordia SR-332 Issue-III | 500 | HC
14 | MTBF Demonstration | Target: 43,800 hours Test Temperature: 50°C Sample size: 20 units Refer to Mil-Std 781D , LCL 90% RDT Completion Milestone: @ 90% confidence level | 1. Life Time> 5 years. No functional failures of the test 2. No performance degradation during the functional test 3. No visual damage to the products during inspection, such as shrinkage, peeling, or discoloration, etc. | 20 | 26 | Mil-Std 781D | 9300 | HC
18850
Mechanical test plan
No. | Item | Test Condition | Pass Criteria | Q'ty | Day | Reference Standard | Test cost (US) | Test Location
1 | Vibration Test Random (Op) | 1. 0.002G^2/Hz 2. 5 to 500HZ 3. Direction: 3 mutually perpendicular axis 4. Duration:30 min/ axis | 1. No functional failures both during and after the test 2. No performance degradation during the functional test 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 2 | 1 | IEC 60068-2-64 | 350 | HC
2 | Shock test (Op) | 1. Shock spectrum: Half sine, Duration: 11 ms, 2. Acceleration: 30 m/s2, Direction of shocks: 6 3. Test duration: 6 faces x 3 shocks |  | 2 | 1 | IEC 60068-2-27 | 350 | HC
3 | Drop test | 1. Height for fall test: 750 mm 2. Steel floor 3. Drop 6 faces | 1. No functional failures both before and after the test 2. No performance degradation before the functional test 3. No visual damage to the products after inspection, such as peeling, discoloration, etc. | 2 | 1 | IEC-60950-01 | 50 | HC
4 | Remote Control Display Angle | The operating range of the IR Remote shall be 10 m at an angle +/- 0deg & +/-30deg from axial, Remote shall be 7 m at an angle of +/-45 degrees from axial when tested in accordance with standard test procedures. | 1. No functional failures both during and after the test 2. No performance degradation during the functional test | 2 | 1 | Foxconn's Spec. | 0 | HC
5 | Abrasion Resistance of Label Test | 1. Storage the label at 50℃ for 12 hours . 2. Start the test at 50℃. 3. 95% alcohol. 4. Load: 3N. 5. Total 5 times. | 1. Any paints required by this standard shall be durable and legible. 2. No any exposed original surface. 3. After this test, the product should not be deformed or disfigured in any way. | 2 | 2 | Foxconn's Spec. | 200 | HC
6 | Logo/Printing Abrasion Test | Alcohol Abrasion Test Alcohol concentration: > 95%, load: 200gf, cycle: 150 cycles (one cycle= forward + backward), | No physical defect and functional failure after this test. | 2 | 1 | Foxconn's Spec. | 150 | HC
7 | USB Plug Test | Test Cycles: 5,000 Cycles Test Speed: 10 times/min Functional check every 1,000 cycles. | No physical defect and functional failure after this test. | 2 | 3 | Foxconn's Spec. | 400 | HC
8 | HDMI Plug Test | Test Cycles: 5,000 Cycles Test Speed: 10 times/min Functional check every 1,000 cycles. |  | 2 | 3 | Foxconn's Spec. | 400 | HC
9 | RJ-45 Plug Test | Test Cycles: 5,000 Cycles Test Speed: 10 times/min Functional check every 1,000 cycles. |  | 2 | 3 | Foxconn's Spec. | 400 | HC
10 | Power Jack Plug Test | Test Cycles: 5,000 Cycles Test Speed: 10 times/min Functional check every 1,000 cycles. |  | 2 | 3 | Foxconn's Spec. | 400 | HC
11 | Salt Fog | 1. Salt: 5% , Temp. : 35C and Humidity: 85% 2. Test duration: 8 hours salt fog exposure then 8 hours drying conditions 3. Total test time: 16 hours | No physical defect and functional failure after this test. | 2 | 4 | MIL-810F section 509.4 | 700 | HC
3400
Packaged test plan
No. | Item | Test Condition | Pass Criteria | Q'ty | Day | Reference Standard | Test cost (US) | Test Location
1 | Temperature and Humidity Test | Power off, Storage, Ta =38℃, Humi.= 85%R.H. for 72 hrs | No obvious visible damage on boxes after temperature and humidity test. | 1 carton | 3 | ISTA-2A | 350 | NN
2 | Static Compression Test | 1. Apply a static load “Wt x (S - 1) x F” for 1 hour. 2. Wt: Total weight of the packaged-product. 3. S: Total number of packaged-products in a stack. 4. F: Compensating factor=5 | No obvious visible damage on boxes after drop test | 1 carton | 1 | ISTA-2A | 150 | NN
3 | Random Vibration Test | 1. Face 3 rests on the platform for 30 mins 2. Face 1 rests on the platform for 10 mins 3. Face 2 or 4 rests on the platform for 10 mins 4. Face 5 or 6 resets on the platform for 10 mins 5. Frequency : 1…4…100…200 6. PSD : 0.0001…0.01…0.01…0.0001 | No obvious visible damage on boxes after vibration test. | 1 carton | 1 | ISTA-2A | 350 | NN
4 | Package drop test | < 10 Kg, drop 97 cm, 10 ~ 19 Kg, drop 81 cm, 19 ~ 28 Kg, drop 66 cm, one corner, three edge, six faces, total ten drop. | No obvious visible damage on boxes after vibration test. | 1 carton | 1 | ISTA-2A | 50 | NN
5 | Fix displacement Test | Displacement: 25 mm Duration: 14200 times | No obvious visible damage on boxes after drop test. | 1 carton | 1 | ISTA-2A | 350 | NN
1250
[9 empty] | Total | 23500

## Allocation
T99X171.00 Reliability Test Sample Allocation
Dept. | Location | Items | Sample | Total L/T | Test Engineer | Ext.
HMQA | HC | 15 | 40 pcs + 22 RCU + 4 pcs housing | 30 days | Leif Lin 林益民 | 550-6592
| NN | 14 | 1 carton + 2 RCU | 7 days | Moon Xie 謝光慶 | 581-30440
| Total | 29 | 40 pcs + 4 pcs housing + 1 carton + 24 RCU | 30 days

## Bug list
Test Bug List
No | Test Item | Test condition | Issue Description | Action | Owner | Due Date | Status | Remark