## Sheet1
No | Model | Agenda | ALT | Foxconn | Remark
1 | EAGLE | Product plan | 9K, 51K product schedule is not clear 1. the original schedule 2. the final version (from FXN) 1) 9K : 08/01_08/06 (if continuous serial no., the end date will be delayed) 2) 20K : 08/31 3) 31K : 09/16
2 | EAGLE | Product plan | please let me know the detail schedule of 9K's product
3 | EAGLE | Material status | Some materials are not provided on schedule How do you pull in these materials? 1. The final version 2. If you pull in these materials, the product schedule can be moved up?
4 | EAGLE | package | 1. Continuous matching Of Serial no. How?
5 | EAGLE | package | 1. Pallet
6 | EAGLE | test spec | How do you test the below test items (see the red box)
7 | EAGLE | mechanical | Top housing protection
8 | EAGLE | approval process | ALT should check the gate, If this gate is not passed, the next stage cannot start
9 | EAGLE | Production report | OBA inspection report and SN report
10 | AOSP | Product plan | 255 pcs product schedule is not clear
11 | EAGLE | Product plan | 15 pcs (VIP) SAMPLE product schedule is not clear