## 工作表1
Item Name | Start Date | Due Date | Status
Front Panel Keypad(CH+/CH-) |  | 2019-02-22 | Done(Will be included in next FW)
HAL library for Controlling Front LED (SKB change LED color) |  | 2019-02-22 | Done(Will be included in next FW)
HDCP on/off and version setup (for debug) |  | 2019-02-22 | Done(Included in FW r3)
Auto Reset Guide |  | 2019-02-22 | Done(Included in FW r3)
Console Enable |  | 2019-02-22 | Done(Included in FW r3)
Support Start Recover Mode by Front Panel Key (uboot) |  | 2019-02-22 | Done(Included in FW r3a)
BT RCU Key Mapping |  | 2019-02-22 | Done(Included in FW r3a)
HAL library for Controlling Mic. |  | 2019-03-05 | Done(Will be included in next FW)
RamOops(for debug) | 2019-03-05 | 2019-03-07 | Done(Will be included in next FW)
Audio HAL implementation to support Mic input |  | 2019-03-15 | 1. Need to work with TVS to integrate and test
SetupWizard |  | 2019-03-15 | New requirement
BT RCU Voice Transmission(HID driver by FXN, Audio HAL by AML) |  | 2019-03-15 | We propose 1st version of NUGU support will be provided by 3/8
Factory Test APP |  | 2019-03-15
Official FW release #2 |  | 2019-04-09
IO compatbility test & bug fixes (BT/HDMI/Ethernet/USB) | 2019-03-11 | 2019-04-12
Official FW release #3 |  | 2019-05-06
Integrate additional RCU |  | 2019-05-10 | Done(Included in FW r5)
Official FW release #4 |  | 2019-05-30
CTS/GTS/CTS Verifier/VTS/Smoke test/BTS pre-testing & bug fixes | 2019-02-25 | 2019-05-31
Official CTS certfication(by Google/3PL) | 2019-06-01 | 2019-06-14
BMT compatbility test & bug fixes | 2019-05-13 | 2019-06-14
Official FW release #5 (MP FW) |  | 2019-06-14
RCU Info Key |  | TBD | New requirement (pending)
Power management(power consumption in active standby or passive standby mode) |  | TBD
Aging Test Tool | 2019-03-11 | TBD | New requirement 1. Need TVS to provide API document